#### STRATEGIC PLAN

FOR

##### MOUNT RUSHMORE NATIONAL MEMORIAL

#### OCTOBER 1, 2000 – SEPTEMBER 30, 2005

#### Fiscal Years 2001-2005

###### Strategic Plan

for

Mount Rushmore National Memorial

"...[to] conserve the scenery and the natural and historic objects and the wildlife therein and to provide for the enjoyment of the same in such manner and by such means as will leave them unimpaired for the enjoyment of future generations."

Approved:

Daniel N. Wenk, Superintendent

July 27, 2000

# TABLE OF CONTENTS

Approval page ……………………………………………………………………………………	iii

Table of Contents…………………………………………………………………………………	iv

Preface…………………………………………………………………………………………….	vi

Government Performance and Results Act of 1993 (GPRA)……………………………	vi

About this plan…………………………………………………………………………..	viii

Introduction……………………………………………………………………………………….	1

About Mount Rushmore National Memorial.….…………………………………………	1

I. Mission..………………………………………………………………………………………	2

Legislative Intent………………………………………………………………………..	2

Purpose………………………………………………………………………………….	2

Significance……………………………………………………………………………..	2

Mission Goals…………………………………………………………………………..	3

Goal Category   I: Preserve Park Resources..…………………………………	3

Mission Goal Ia ………………………………………….. 	3

Mission Goal Ib……………………………………………	3

Goal Category  II: Provide for Public Enjoyment and Visitor Experience…...	3

Mission Goal IIa…………………………………………..	3

Mission Goal IIb…………………………………………..	3

Goal Category III: Legislated Partnerships...…………………………………	3

Goal Category IV: Ensure Organizational Effectiveness……………………..	3

Mission Goal IVa…………………………………………	3

Mission Goal IVb…………………………………………	3

II. Long-term Goals……………………………………………………….………………………	4

Goal Explanations……………………………………………….……………………...	4

Ia1A	- Disturbed Lands………………………………………………………..	4

Ia1B	- Exotic Plant Species...…………………………………………………	5

Ia5	- Historic Structures……………………………………………………..	5

Ia6	- Museum Collections...…………………………………………………	6

Ib2C	- Historic Structures Baseline……………………………………………	6

Ib2D	- Cataloguing Museum Objects…………………………………………	6

Ib3	- Vital Signs……………………………………………………………..	7

IIa1	- Visitor Satisfaction…………………………………………….………	8

IIa2	- Visitor Safety………………………………………………….……… 	8

IIb1	- Visitor Understanding and Appreciation.……………………………. 	9

IVa3A	- Employee Performance Agreements…………………………………	10

IVa4A	- Workforce Diversity – Permanent Women/Minorities………………	10

IVa4B	- Workforce Diversity – Temporary/Seasonal Women/Minorities……	10

IVa4C	- Workforce Diversity – Permanent Employees with Disabilities…….	10

IVa4D	- Workforce Diversity – Seasonal Employees with Disabilties……….	10

IVa5	- Employee Housing…………………………………………………...	10

IVa6A	- Employee Safety (Lost-time Accidents)…………………………….	10

IVa6B	- Employee Safety (Continuation of Pay)…………………………….. 	10

IVa7	- Line Item Construction………………………………………………	10

IVb1	- Volunteer Hours……………………………………………………..	11

IVb2A	- Cash Donations and Grants………………………………………….	11

IVb2B	- Friends Groups and Other Organizations……………………………	11

IVb2C	- Cooperating Associations..………………………………………….	11

III. How Goals Will Be Accomplished…………………………………………………………….	12

IV. Key External Factors……………………………………………………………………….. …	13

V. Program Evaluation Methodology and Schedule for Future Evaluations………………………	13

VI. Consultation……………………………………………………………………………………	13

VII. Strategic Plan Preparers………………………………………………………………………	14

Appendix A – Long-term Goals Displayed in Five-Year Annual Increments……………..………	15

PREFACE

This Strategic Plan was written to fulfill the requirements of the Government Performance and Results Act.  Following is a brief overview of that law, passed by the U.S. Congress in 1993.

## Government Performance and Results Act of 1993  (GPRA)

GPRA is one of the most recent and comprehensive of a number of laws and executive orders directing federal agencies to join the “performance management revolution” already embraced by private industry and many local, state, and national governments.

In a nutshell, performance management ensures that daily actions and expenditures of resources are guided by long- and short-term goal setting in pursuit of accomplishing an organization’s primary mission, followed by performance measurement and evaluation.  Importantly, the goals are quantifiable and measurable results or outcomes, rather than efforts or outputs (activities, services, products).  The established and proven performance management approach is to establish goals – allocate resources to accomplish those goals – take action/do the work – measure results – evaluate and report performance – use evaluation to adjust goals and reallocate resources – and continue the loop.  This process sharpens our focus on accomplishing our mission in the most efficient and effective ways, and holds managers and employees accountable on a clear and measurable basis.

The approach seems so elegantly simple and logical that one is compelled to ask, “Isn’t that what everyone is already doing.”  In fact, most federal agencies have not traditionally done business this way.  They have been funded and conducted their business by activities rather than by goals.  Too often they have conducted business year after year based on what they have always routinely done, rather than in pursuit of mission-oriented goals.  Too often they have not measured their performance in terms of results achieved, but rather in level of activities conducted, products produced, or services provided – if they have measured performance at all.  And too often managers and employees have not been held accountable for their performance in achieving concrete, results-oriented goals, and have not communicated the outcomes of their work to their important constituencies – the American people, the Congress, even the President.  So performance management, as embodied in GPRA, is new, revolutionary, and vitally important to a more effective, efficient, and credible federal government.

GRPA requires federal agencies to develop and use three primary documents in conducting their business.  These documents are also to be submitted to the Congress and the Office of Management and Budget (OMB):

- Strategic Plan of no less than five years duration, reviewed and revised every three years, and containing:

- mission statement based in law, executive order, etc.;

- long-term goals, which are objective, quantified, and measurable, to accomplish mission;

- how goals will be accomplished, an adequate explanation including “…operational processes, skills and technology, and the human, capital, information and other resources required to meet those goals…”;

- relationship of annual goals to long term goals, a description of how long term goals are carried out in annual goal increments;

- key external factors which could positively or negatively affect goal accomplishment; and

- program evaluation methodology, a description of how mission and goals were arrived at and a schedule for future program evaluations.

- GPRA also requires consultation with affected and interested parties in the development of the Strategic Plan, and it requires that the plan be

- developed by federal employees (versus contractors, etc.).

- Annual Performance Plan tiered off the Strategic Plan each year, showing how long term goals will be accomplished in annual increments, and containing:

- annual goals to incrementally achieve long-term goals in Strategic Plan;

- annual work plan, i.e. explanation of how annual goals will be accomplished – “briefly describe the operational processes, skills and technology, and the human, capital, information and other resources required to meet the performance goals….”;                and

- basis for measuring results – “…provide a basis for comparing actual program results with the established performance goals….” and “…describe the means to be used to verify and validate measured values.”

- Annual Performance Report reviewing each year’s successes and failures and identifying areas where activities or goals need to be revised in the future, addressing:

- what annual goals were met or exceeded;

- what annual goals were not met;

- why annual goals were not met; and

- what remedial action will be taken for goals not met.

Importantly, GPRA mandates that long-term and annual goals be results or outcomes rather than outputs (activities, products, or services) and that they be “objective, quantifiable, and measurable” so that performance can be adequately measured and reported, progress on mission accomplishment assessed, and managers and employees held accountable.

While the National Park Service has long been a mission-oriented organization, it has also had a long tradition of planning, managing, and budgeting by activity, problem solving and issue resolution.  Its response to GPRA requirements will help it focus on accomplishing mission through establishing long-term and annual goals, allocating resources to those goals, and measuring and reporting results.

About This Plan

In consultation with Congress, OMB and other interested parties, the National Park Service (NPS) developed its own unique GPRA implementation process.  Using this process, the NPS methodically developed its first “servicewide” Strategic Plan and submitted it on September 30, 1997.  That plan was revised and published electronically on January 15, 2000.  A copy of revised plan is available for review at park headquarters.  It is also available on the Internet at http://www.nps.gov.

The NPS manages the National Park System, which consists of over 375 units located in nearly every state and territory of the nation.  Thus the NPS is fundamentally a field-based, resource preservation and visitor service organization, where results or outcomes actually occur in the parks rather than Washington headquarters.  In addition, the NPS has legislated partnership responsibilities, carried out by central offices throughout the country, to provide technical assistance and grant funding to other non-federal preservation entities.  Therefore, as part of its GPRA implementation process, NPS decided that each of its component parks, programs, and offices would develop and submit their own  Strategic Plans, Annual Performance Plans, and Annual Performance Reports.  The National Park Management Omnibus Act of 1998 codified into law that all field units of the National Park System would write Strategic Plans and Annual Performance Plans consistent with the Government Performance and Results Act.

The local plans address the long-term goals in the “servicewide” plan that are appropriate to the individual units as parts of the overall National Park System, NPS, and its mission.  Then they add goals specific to their own legislative mandates, missions, resources, visitor services, and issues needs.  The local plans, then, are a blend of national and local missions and goals.

This Strategic Plan for Mount Rushmore National Memorial follows this pattern.  It is a five-year plan covering fiscal years 2001through 2005.  It consists of a mission statement born out of the NPS organic act as well as the specific legislation establishing this park.  It contains mission goals, closely paralleling the “servicewide” mission goals, that illustrate in broad brushstroke what we do far beyond just five years – “in perpetuity” - to accomplish our stated mission.  It then contains long-term goals, which target in quantified, measurable ways what we will accomplish in the next five years toward achieving our overall mission goals and mission.  The long-term goals address both appropriate “servicewide” goals as well as park-specific outcomes.  The goal numbering protocol follows that of the “servicewide” plan with park-specific suffixes.  Since not all servicewide goals apply to Mount Rushmore National Memorial, some numbers are skipped.  In addition, there are numbers containing 0’s which are not in the servicewide plan and indicate park-specific goals.

Following the simple goal listing, each long-term goal is repeated with one or more explanatory paragraphs that give background, detail, and other information useful to help the reader understand the goal as well as to sketch in how the goal will be accomplished.

After these goal explanations, the plan contains a general section on “How Goals will be Accomplished” which briefly sketches the park’s organization, staffing, fiscal, infrastructure, and other resources available to achieve the plan’s long-term goals.  This is followed in turn by brief discussion of “Key External” factors over which park staff may have influence but not control, and  which could positively or negatively affect goal achievement.

Finally, there is a brief discussion of how the contents of the plan were arrived at, and a listing of those who were consulted in the development of the plan.

It should be noted that the goals in this plan are generally predicated on “flat budgets” for the next five years.  Other than increases for inflation, we assumed no major increases in funding.  Where increases in appropriations were known or are likely, they were taken into account.  Where other funding sources (donations, fee revenues, etc.) were “reasonably assured”, they too were taken into consideration when setting performance targets.  Obviously, limits on  funding constrain what can be accomplished toward our

goals and mission.  GPRA, however, is distinctly not about discussing budget shortfalls or requesting or justifying additional funding.  Rather it is about planning, managing, and communicating what we can accomplish with what we already have.  Performance target numbers speak for themselves about how well funded we are to accomplish our mission, and where targets are low, additional budget discussions might be generated.  But this is not the primary purpose of the plan.

We would, however, be remiss in our duties as stewards of and storytellers about the priceless natural and cultural resources - defining America’s heritage - which are in our care if we did not duly note that we sincerely believe we are under-funded and under-staffed to fully achieve our important mission and goals.  On the other hand, we also recognize that we are but one of many worthwhile federal enterprises which compete for scarce and precious tax dollars, and we are pursuing a wide variety of alternative management,

funding, and staffing scenarios to supplement our appropriations.  In the meantime, we welcome the opportunity to respond to the requirements of GPRA with this Strategic Plan and its companion documents to better plan, manage, and communicate how - and how well - we are achieving our mission through performance goals supported by existing, and largely flat, levels of funding.

Each year that the Strategic Plan is in effect, beginning with fiscal year 2001 (October, 2000) there will be a companion Annual Performance Plan which shows in annual goals, that year’s targeted incremental achievement of each long-term goal, and a work plan for accomplishing that increment.  Each year there will also be an Annual Performance Report discussing actual achievement of the prior year’s annual goals and progress on long-term goals.

Questions, comments, and requests for additional copies are welcome and encouraged and can be addressed to the Superintendent at P.O. Box 268, Keystone, SD 57751.  As they are written and approved, copies of the current year’s Annual Performance Plan and Annual Performance Report will also be available on request, with questions and comments equally welcome.

INTRODUCTION

About the Park

This five-year Strategic Plan has been written for Mount Rushmore National Memorial, one of over 375 units of the greater National Park System administered by the National Park Service, U.S. Department of the Interior.

The National Park System preserves outstanding representatives of  the best of America’s natural, cultural, and recreational resources of national significance.  These resources constitute a significant part of America’s heritage, character, and future.  Along with similar resources of local, state, tribal, and national significance administered by other public and private organizations and supported by National Park Service technical assistance and grant funding support, Mount Rushmore is a vital part of America’s national system of parks and other preserved resources.  The National Park Service not only directly and indirectly preserves these myriad national treasures, it also makes them available to millions of visitors from throughout the country and the world every year.

The bust of four presidents – George Washington, Thomas Jefferson, Abraham Lincoln, and Theodore Roosevelt – were sculpted in the southeastern granite face of Mount Rushmore as “…a memorial…commemorative of our national history and progress…” (Act of March 3, 1925).  This basic legislation authorized the carving and established the purpose of what was to become Mount Rushmore National Memorial.

Subsequent legislation established the Mount Rushmore National Memorial Commission with the responsibility of completing the memorial “…to be constructed according to designs and models by Gutzon Borglum.”  Included were charges to “…administer, protect, and develop…” the memorial and specifics such as “…reconstruction of the studio for the preservation of the models, landscaping the contiguous grounds, and construct the entrance to the Memorial.” (Acts of February 25, 1929: June 26, 1934; and June 15, 1938.)

By Executive Order, on June 10, 1933, President Franklin Delano Roosevelt placed Mount Rushmore under the jurisdiction of the National Park Service.  However, there were no immediate administrative changes and the Mount Rushmore Memorial Commission played the major role in administering the memorial.

The Act of July 3, 1941, by providing “that the Mount Rushmore National Memorial Commission shall cease to exist or function on June 30, 1943,” in effect transferred all responsibilities to the National Park Service with the first superintendent being appointed October 1, 1941.

I. MISSION of the National Park Service at Mount Rushmore National Memorial

It is the mission of the National Park Service at Mount Rushmore National Memorial to preserve and protect Mount Rushmore National Memorial while providing for the education and enjoyment of the public.

The mission of the National Park Service at Mount Rushmore National Memorial is rooted in and grows from the Executive Order of June 10, 1933 and supplemented by the Organic Act of August 25, 1916.  Our mission statement is a synthesis of this mandated purpose, plus the park’s primary significance as itemized below.

## Legislative Intent

Mount Rushmore National Memorial is administered under the spirit and intent of the Act of August 25, 1916, which established the National Park Service and which states the purpose of the service to be, “…to conserve the scenery and the natural and historic objects and the wildlife therein and to provide for the enjoyment of the same in such manner and by such means as will leave them unimpaired for the enjoyment of future generations.”  This act, those previously mentioned, and subsequent legislation provide direction for the National Park Service to preserve and protect the memorial sculpture and the natural setting, and to provide for the access of the public and for the inspirational and educational appreciation of the cultural and natural resources of the memorial..

## Purpose

Therefore, the purpose of Mount Rushmore National Memorial is to:

(	Commemorate our national history and progress through the visages of George Washington, Thomas Jefferson, Abraham Lincoln, and Theodore Roosevelt.

(	Provide the opportunity for a contemplative visitor experience as related to the sculpture and its setting.

(	Provide recreational opportunities.

## Significance

Mount Rushmore National Memorial significance is the sculpture and historic structures and artifacts associated with the carving. The major resource at Mount Rushmore is the sculpture itself; carved during the period from 1927 to 1941 from the southeastern face of a granite upthrust.  The sculpted busts of presidents George Washington, Thomas Jefferson, Theodore Roosevelt, and Abraham Lincoln were described as the “Shrine of Democracy” by President Franklin Delano Roosevelt in a speech on the site in 1936.  Also the sculpture is significant as a unique creative endeavor.  Important to the sculpture is the natural scene surrounding and framing it.  A stand of ponderosa pine on the adjacent steep slopes provides a setting that complements the carving and contributes eloquently to its full aesthetic appreciation.  These naturally occurring evergreens add color and life

## Mission Goals

Mount Rushmore National Memorial’s mission is accomplished through pursuit of the following broad, “in perpetuity” mission goals:

### Goal Category I     Preserve Mount Rushmore National Memorial Resources

Ia The Mount Rushmore Sculpture and associated cultural and natural resources will be protected, restored, and maintained in good condition and managed within the broader ecosystem and cultural context.

Ib Mount Rushmore National Memorial contributes to knowledge about natural and cultural resources and associated values; management decisions about resources and visitors are based on adequate scholarly and scientific information.

### Goal Category II     Provide for the Public Use and Enjoyment and Visitor Experience of

### Mount Rushmore National Memorial

IIa   Visitors to Mount Rushmore National Memorial safely enjoy and are satisfied with the availability, accessibility, diversity, and quality of park facilities, services, and appropriate recreational opportunities.

IIb    Park visitors and the general public understand and appreciate the preservation of Mount Rushmore National Memorial and its resources for this and future generations.

# Goal Category IV     Ensure Organizational Effectiveness of Mount Rushmore National Memorial

IVa     The National Park Service at Mount Rushmore National Memorial uses current management practices, systems, and technologies to accomplish its mission.

IVb     The National Park Service at Mount Rushmore National Memorial increases its managerial capabilities through initiatives and support from other agencies, organizations, and individuals.

Goal Explanations

## Goal Category I: Preserve Park Resources

The mission goals and long-term goals in goal category I are inclusive of the mandates in Mount Rushmore National Memorial’s authorizing legislation to protect Mount Rushmore from commercial exploitation; and the NPS Organic Act “to conserve the scenery and the natural and historic objects and the wild life therein….”  Subsequent legislation reinforced and expanded these mandates.  All goals that pertain to resource preservation and the acquisition of knowledge from and about the resources to meet this mandate are appropriate to this category.

Mission Goal Ia: The Mount Rushmore Sculpture and associated cultural and natural resources will be protected, restored, and maintained in good condition and managed within the broader ecosystem and cultural context.

Long-term goals related to the mission goal include the protection, restoration, or maintenance of ecosystems, rare plant and animal populations, archeological and ethnographic resources, historic structures and objects, research collections, cultural traditions, and subsistence activities, relevant to the purpose and/or significance of the memorial. Long-term goals deal with threats to natural and cultural resource values and seeks cooperation with neighboring land managers and that promote the ecosystem management,

Mount Rushmore National Memorial preserves and protects a unique artistic sculpture representing the principles of our present form of government and carved into a massive granite mountain. The memorial contains 1240 acres of which approximately 40 acres are developed.  Within the boundaries of the memorial are old-growth forests, riparian streams, various wildlife and outstanding geological resources.  The forest is managed to provide the unique setting surrounding the sculpture.  Historic structures and artifacts are protected to reveal for current and future visitors the significance of this carving. Security systems are incorporated into the management of the park to insure the safety of employees and visitors.

## Long-term Goals Addressing Mission Goal Ia

Ia1A	By September 30, 2005, 4 acres (4%) of Mount Rushmore’s 100 acres of disturbed lands targeted in the 1999 Resource Management Plan are restored.

Since 1925, various levels of developmental activities within Mount Rushmore National Memorial have occurred to provide for visitor access and services.  These have included road and trail construction, visitor use structures, and administrative facilities.  Some of the construction has resulted in the disturbance of the natural vegetative cover.   A few areas have been allowed to revegetate through natural plant succession processes.  Some disturbed sites have been reseeded with a combination of native and exotic grasses and forbs to provide immediate ground cover and reduce the incidence of erosion.

A major road construction on South Dakota Highway 244 was finished in 1990.  This straightened the existing highway along with adding one uphill traffic lane from the intersection of Highway 244 and US 16A to the parking facility.  Several areas of erosion exist along the highway.

Major construction of visitor use and parking facilities completed in 1998 has created additional areas of disturbance.  Facilities created include: a 3-tiered parking facility, a larger amphitheater and visitor center, access road to the rear of the amphitheater, a concession complex, and South Dakota Highway 244 was rerouted adjacent to the new facilities.  There was some rehabilitation work accomplished by the construction contractors, but major site restoration is still needed.  Examples of  work that needs to be done include erosion control and planting native vegetation such as grasses and ponderosa pine trees.

A rehabilitation plan will be developed and implemented to include the following:

- Inventory and map disturbed sites

- Replacing lost top soil in areas worn to bedrock

- Revegetation with native plants

1a1B	By September 30, 2005, exotic vegetation on 8 acres (4.4%) of 180 acres  is contained.

Mount Rushmore has approximately 180 acres of exotic plant species within the boundary of the memorial.   Recognized exotic plants of concern at Mount Rushmore include Canada thistle, field bindweed, musk thistle and sweet clover. Exotic vegetation are invasive, nonnative plant species that pose a serious threat to the survival of native species.  Most exotic species were introduced at Mount Rushmore over the last 100 years.  More recently, with the redevelopment of visitor facilities, many disturbed areas saw a large rise in non-native or exotic species.

The intention of Mount Rushmore is to manage the surrounding vegetation community as a natural setting for the sculpture.  It is NPS policy to control or remove nonnative species whenever possible and feasible.

Efforts to control and/or eliminate nonnative or exotic plant species include:

- Identification and mapping of exotic species in the field.

- Survey roadsides, disturbed areas, developed areas, and trailside areas.

- Maps of general areas will be developed.

- Prioritize species and areas of control.

- Separate plots will be identified to apply chemical and non-chemical methods such as mowing, clipping, and hand pulling.

- Main attempts at controlling exotic species will be in the spring and fall months.

Ia5	Historic Structures – By September 30, 2005, 88% (7 of 8) of Mount Rushmore’s historic structures are maintained in good condition.

Mount Rushmore has 8 historic structures identified on the List of Classified Structures report.  These structures include the Mount Rushmore Sculpture itself that requires annual inspection and resealing of any cracks where the existing sealant has failed.  This structure requires waterproofing membrane material, which is placed in small areas on the top of the Sculpture, be replaced on a cyclic schedule.  Crack and movement monitoring of the Sculpture will be completed through a complex electronic monitoring system installed in 1999.  This monitoring system is maintained and results evaluated by a contracting firm who specializes in rock formations.

The Historic Borglum Studio and Residence #2 buildings will receive a historic structure report (HSR).  This HSR will dictate the rehabilitation methods and future preservation maintenance techniques to be used to maintain the buildings in good condition.  Once completed, work to rehabilitate the structures can begin.  These buildings will be used to conduct interpretive programs in for the education of park visitors.

Other historic structures include the Borglum Memorial View Terrace and the Lift Platform, which are concrete and native rock viewing terraces.  These structures require routine inspections for any cracking or deterioration of these masonry structures. Repairs are made as necessary to maintain good condition of these structures. The parks 2 million annual recreational visitors use these platforms to view the Mount Rushmore Sculpture.  The historic air compressor that was used to supply air pressure to the many air tools used to carve the Mount Rushmore Sculpture is on display for visitors viewing.  Routine cleaning to prevent dirt build-up and to keep rust from forming is performed by park maintenance personnel.

Ia6	By September 30, 2005, 73.4% of preservation and protection standards for park museum collections are met.

Mount Rushmore National Memorial currently has met 156 (69.3%) of the 225 applicable automated checklist standards.  The remaining 69 deficiencies are spread out over several museum spaces that include the Archives, Studio, Storage Repository, and Visitor Center Exhibit Hall.  Each space has ACP deficiencies peculiar to each site and the percentage of checklist items met varies.

The park will target each specific space to be at the service wide goal of 73.4% by September 30, 2005.   Attaining this long-term goal insures the continued survival of collections here at the memorial.  However, corrected preservation and protection standards are easily reversed due to negligence and lack of park resources.  Therefore, maintenance of the collections is equally addressed to maintain the current Automated Checklist Program percentage level.

External funding is not a reliable method for correction of high cost deficiencies, and the park will have to commit some of it’s base funding to address some of the problems.  However, Mount Rushmore National Memorial will initially focus on low cost fire, safety, and procedural deficiencies to meet this long-term goal.

Mission Goal Ib: Mount Rushmore National Memorial contributes to knowledge about natural and cultural resources and associated values; management decisions about resources and visitors are based on adequate scholarly and scientific information.

The National Park Service conducts scholarly and scientific research regarding the sculpture, water quality, air quality and historic artifacts and structures to assure methods for long-term preservation and protection can be met. The memorial protects the sculpture through monitoring techniques, and patching cracks inherent to the mountain for long term preservation.  Museum objects are cataloged and preserved using methods that will assure future generations will have access to them.  Through studies no known archeological sites exist within the memorial but the area has a rich cultural history which has tremendous potential for research.

## Long-term Goals Addressing Mission Goal Ib

Ib2C	By September 30, 2005, 100% of the historic structures will have updated information.  (FY 1999 baseline 7 of 8 are updated)

The list of classified structures (LCS) is the primary computerized database containing information (including condition) of the items listed.  Structures in the LCS are either on or eligible for the National Register of Historic Places or are treated as cultural resources.

Current LCS data indicate that 7 of the 8 inventoried structures are up-to-date in the computerized database.  The goal will be to update the database to include all the historic structures and then to maintain the database in the following years.

Ib2D	By September 30, 2005, the number of museum objects cataloged is increased from 55,618 in FY1999 to 55,894 (0.5% increase).

Mount Rushmore National Memorial has a current collection of 55,618 individually catalogued items.  Over 2,454 artifacts were catalogued in 1999 and consequently eliminated much of the documented backlog.  The current long-term goal is increasing the number of Mount Rushmore museum objects cataloged into the National Park Service’s Automated National Catalog System (ANCS+) from 55618 in FY1999 to 55894  (0.5% increase) by September 30, 2005.  Collection totals will change from year to year and work plans will be adjusted accordingly.

The overall five-year goal of Mount Rushmore National Memorial is to catalogue objects at a pace that matches yearly accessions and be 99% catalogued by the target date.

Ib3	By September 30, 2005, Mount Rushmore National Memorial will have identified its vital signs for natural resource monitoring.

There has never been a Resource Management Specialist or similar position allocated to Mount Rushmore National Memorial.  The duties have always been collateral and usually assigned to an employee in the Resource Management and Visitor Protection Division.  A priority within the next 5 years is to establish a resource management coordinator/specialist position.

The only previous inventory of resources completed was for vascular plants.  In 1986 a vegetation baseline study was begun and in 1993, a vegetation-mapping survey was done.  Additional work needed includes the survey and mapping of threatened and endangered species, and of noxious weeds.

Inventories need to be completed for other natural resources to establish baseline data.  Significant research needs to be completed on herpetological species, mammals, and birds.  A limited survey inventory on fish also needs to be done.  Vital signs for natural resource monitoring also must be identified.

Mount Rushmore is one of 14 National Park units within the Northern Great Plains Inventory and Monitoring Network.  A proposal for fiscal year 2000 has taken initial steps to begin conducting inventories of vertebrates and vascular plants.  Initial steps include: 1) doing an inventory of existing data sources and organizing and compiling existing data; 2) identifying data gaps and determining priorities and the level of detail required for additional field samplings; and 3) development of full study plan that describes the spatial sampling strategy and methodology for collecting additional information as well as listing the products to be generated by the inventories.

Once comprehensive baseline inventories are complete, an ongoing resource condition and vital signs monitoring program must be established.

Goal Category II: Provide for the Public Enjoyment and Visitor Experience of Mount Rushmore National Memorial

The mission goals and long-term goals in Goal Category II embrace the mandate in the NPS Organic Act:

"...to provide for the enjoyment of the [resources] in such manner

and by such means as will leave them unimpaired for the

enjoyment of future generations."

Subsequent legislation reinforced and expanded this mission. All effort for visitor satisfaction, enjoyment, safety, appreciation, and understanding of Mount Rushmore’s resources and facilities is appropriate to this category.

Mission Goal IIa: Visitors safely enjoy and are satisfied with the availability, accessibility, diversity, and quality of park facilities, services, and appropriate recreational opportunities at Mount Rushmore National Memorial.

The "Organic Act" of August 25, 1916 which established the National Park Service outlines the purpose of the Service to conserve the nations natural and cultural resources and to provide for the enjoyment of these resources. The category IIa goals in this Strategic Plan measures how effective Mount Rushmore National Memorial is at accomplishing the enjoyment aspect of the National Park Service Mission statement by measuring visitor’s level of enjoyment and satisfaction. Goal IIa1 uses random visitor surveys as an instrument to measure the level of satisfaction visitors have with the facilities and services provided at Mount Rushmore National Memorial. Goal IIa2 measures levels of visitor accident and incident rates. The achievement both category IIa goals is essential to ensure that that visitors enjoy Mount Rushmore National Memorial.

Long-term Goals Addressing Mission Goal IIa

IIa1	By September 30, 2005, 99% of park visitors to Mount Rushmore are satisfied with appropriate park facilities, services and recreational opportunities.

Mount Rushmore receives 2 million recreational visitors to the park each year and an additional 700,000  visitors who are other than recreational visitors.  Visitors come to Mount Rushmore to experience the deep patriotic feeling one gets from viewing the 60-foot high faces of four presidents carved in the natural granite stone of the Black Hills of South Dakota.  They are able to visit the Historic Borglum Studio which houses the 1:12 scale model that Gutzon Borglum used as the guiding model for carving Mount Rushmore.  Interpretive programs are given in the studio each day during summer months. Park visitors may also walk the .6-mile Presidential Trail to get within 600 feet below the Sculpture.  A portion of this trail is handicap accessible.  Over the past 10 years Mount Rushmore facilities have undergone major redevelopment.  All of the previous visitor use facilities have been replaced with granite structures designed to compliment the surrounding Ponderosa Pine trees and granite hills.  The new visitor center includes two state-of-the-art theaters and a museum containing over 5,000 objects.  The park concessionaire operates a dining room, snack bar and gift shop to fulfill the needs of the park visitors.

The 1998 and 1999 Visitor Survey Card results showed that visitors were satisfied 98% and 99% of the time respectively.  The visitors indicated they appreciated the clean restroom facilities, the clean and well-kept visitor center and information center, and the food and gift facilities.  Visitors also indicated they were well satisfied with the uniformed personnel at the park as well as with the exhibits in the park.  It is our long-range goal to maintain this satisfaction rate with the park visitors.  Mount Rushmore is currently involved in a program to install wayfinding signs throughout the park.  This project will better allow visitors to experience all the opportunities the park has to offer.  Mount Rushmore is a pilot park in this nation-wide “Message Project” which is meant to better identify all National Parks.

IIa2	By September 30, 2005, the number of Mount Rushmore National Memorial visitor accidents / incidents results in a rate no higher than the Servicewide FY 1992 – FY 1996 five year annual average rate of 8.1 per 100,000 visitor days.

Mount Rushmore National Memorial had an average annual visitation of 2.65 million visitors during FY 1992 – FY 1996, equaling 233,735 visitor days.  The records for this baseline period are inaccurate due to massive reconstruction of all facilities at the Memorial.  All old facilities were demolished and removed and new facilities built from 1991 through 1998.  The Park did not close during this time, but many temporary structures, walkways, and facilities were used during this period.

This construction of facilities caused our baseline rates to fluctuate widely.  This is due in part to the construction itself, and also to the increased amount of time visitors are now spending at the Memorial.  The new facilities have increased average visitation timed from 1½ hours to 2 ½ hours per visitor.  This increase in time therefore increases the potential for visitor accidents/incidents.

Due to these facts, Mount Rushmore National Memorial will adopt the servicewide goal of 8.1 visitor accidents / incidents per 100,000 visitor days.

When facilities are completed, visitor safety will be enhanced by the reconstruction of visitor use areas.  Improvements such as steps being replaced by ramps, irregular stone walkways being replaced by smooth surface pavers, and reducing grades on trails, have already been accomplished.

Frequent inspections of all visitor use areas by NPS employees, cooperating association members, concessioners, volunteers, SCA’s, and VIP’s will identify any safety hazards before accidents/incidents can occur.  Correction of these hazards will be immediate if possible; if not, the areas will be restricted from visitor use until the corrections are made and the area declared safe.

Mission Goal IIb: Mount Rushmore National Memorial visitors and the general public understand and appreciate the preservation of the memorial and its resources for this and future generations.

The National Park Service offers numerous programs and services both on-site and off-site to provide information about the memorial and its resources.  The memorial seeks to provide a quality experience by imparting its meaning and significance through interpretive and educational programs.  By showing the value of the memorial visitors will become supporters not only of the memorial but also of national parks in general.

Long-term Goals Addressing Mission Goal IIb

IIb1	By September 30, 2005, 70% of Mount Rushmore National Memorial visitors understand the significance of the memorial.

This goal measures visitors' grasp of the memorial's significance, defined as "the set of the themes describing a park's unique contribution to the national park system."  Visitors' understanding and appreciation for Mount Rushmore increase as they learn why the memorial was established and about the natural and cultural resources the Memorial protects.  Park efforts to provide visitors with information, orientation, interpretation and education all help visitors discover the meaning the park holds for them, and make connections between tangible natural and cultural resources and the site's intangible values.  At Mount Rushmore these efforts include interpretive talks and walks, education programs, exhibits, videos and printed materials.

This goal is measured through the NPS Visitor Survey Card project.  Visitors are asked to identify what is significant about the memorial.  These are matched to a list of themes that describe the site's unique place in the park system.  Based on FY1999 Visitor Survey Card data, 66% of the over 2 million visitors to Mount Rushmore understand the significance of the memorial.

By 2005, the NPS will increase visitor understanding of the significance of the memorial to 70%.  This will be achieved through maintaining current interpretive efforts while adding new wayside exhibits, new Information Center exhibits, and a new audiovisual production for the evening lighting program.

Goal Category IV: Ensure Organizational Effectiveness at Mount Rushmore National Memorial

The goals in Goal Category IV support the National Park Service mission.  This category generally relates to efficient and effective governmental processes rather than to the results of those processes. These goals measure workplace standards including diversity and competency levels, as well as program efficiencies such as accuracy of construction cost estimates.

Goals in Category IV are the ways that the National Park Service has chosen to better accomplish its mission of protecting park resources, providing for visitor understanding and enjoyment, and assisting others in preserving their resources and the enjoyment of those resources by their constituents.

# Mission Goal IVa: Mount Rushmore National Memorial uses current management practices, systems, and technologies to accomplish its mission.

To become more responsive, efficient, and accountable, the National Park Service must integrate its planning, management, accounting, reporting, and other information resource systems.  Integrating or interfacing these systems will provide better cross-communication during daily operations and help the National Park Service develop required annual performance plans in compliance with the Government Performance and Results Act.  Modern electronic technology makes it possible to integrate/interface these systems among the park units, central offices, and program centers.  Improvements in the areas of workforce diversity, employee safety, employee housing, and employee performance standards will help the National Park Service accomplish its mission.  Long-term goals pertaining to organizational responsiveness, efficiency, and accountability are related to this mission goal.

Long-term Goals Addressing Mission Goal IVa

IVa3A	By September 30, 2005, 100% of Mount Rushmore National Memorial employee performance agreements are linked to appropriate strategic and annual performance goals and position competencies.

IVa4A	By September 30, 2005, the number of Mount Rushmore National Memorial permanent positions in targeted occupational series filled by employees from underrepresented groups is increased from the fiscal year 1999 level of zero to one (out of three targeted positions).

IVa4B	By September 30, 2005, the total number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by women and minorities is increased from 22 in fiscal year 1999  to 29 (32% increase).

IVa4C	By September 30, 2005, the number of Mount Rushmore National Memorial permanent positions filled by employees with targeted disabilities is increased from 1 in fiscal year 1999 to 4 (10% of permanent staff).

IVa4D	By September 30, 2005, the number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by employees with targeted disabilities is increased from 0 in fiscal year 1999 to 3 (5% of seasonal staff).

IVa6A	Employee Safety-Lost time Injury Rate: By September 30, 2005 the annual number of Mount Rushmore National Memorial lost-time injuries is 3 or less (higher than the FY1992-FY1996 five year annual average of 1.2 injuries).

The National Park Service has the worst safety record in the Department of Interior and one of the worst in the Federal Government.  Each year, the National Park Service temporarily loses approximately 6% of its employees due to work-related injuries and illnesses that take them off the job for more than one day (the lost-time injury rate).  During the five-year baseline period, Mount Rushmore had an average of only 1.2 lost-time injuries per year.  Since that time, the size of the Memorial’s staff has increased greatly.  Because of this, our goal is to keep the number of lost-time injuries at 3 or fewer per year.  We recognize that unsafe work practices account for approximately 90% of NPS employee accidents (National Safety Council & NPS analysis, 1995) and will make every effort to ensure that safety is our first priority.

IVa6B	Employee Safety-Continuation of Pay: By September 30, 2005, the number of Mount Rushmore National Memorial hours of Continuation of Pay (COP) will be at or below 55.

Closely related to the goal for lost-time injuries is that for continuation of pay (COP) hours.  The staff at Mount Rushmore National Memorial understands that virtually all accidents are avoidable, our goal to keep the annual number of COP hours at 55 or less.  We recognize that unsafe work practices account for approximately 90% of NPS employee accidents (National Safety Council & NPS analysis, 1995) and will make every effort to ensure that safety is our first priority.

IVa7	By September 30, 2005, 100% (1of 1) of Mount Rushmore’s line-item projects funded by September 30, 1998, and each successive fiscal year, meet 90% of cost, schedule, and construction parameters.

Construction of a Wastewater Treatment Plant at Mount Rushmore will be completed in FY 2001.  This construction project will be completed within 90% ($4.112 of the $4.568 million) of the funding that has been approved for this project (includes net construction, contingency and contract administration) and will be finished within 90% (18 of the 20 months) of time that has been allotted for the construction.  This facility replaces a wastewater treatment plant which has been determined to have exceeded its useful life cycle.  The new plant was designed to treat a maximum of 75,000 gallons per day (6.7 million gallons per year), and will produce an effluent that meets or exceeds the requirements of the South Dakota Department of Environment and Natural Resources for the next 30 years.

Mission Goal IVb: The National Park Service at Mount Rushmore National Memorial increases its managerial capabilities through initiatives and support from other agencies, organizations, and individuals.

The National Park Service will pursue maximum public benefit through contracts, cooperative agreements, contributions, and other alternative approaches to support park operations and partnership programs. Partners include non-government organizations such as friends groups, foundations, cooperating associations, and concessionaires, as well as federal, state, tribal, and local government organizations which already assist NPS managerial ability through partnerships and cooperative agreements. Long-term goals that deal with park management strategies and funding sources carried out in cooperation with other government and non-government organizations and private donors relate to this mission goal.

Long-term Goals Addressing Mission Goal IVb

IVb1	By September 30, 2005, the number of Mount Rushmore National Memorial volunteer hours is increased from 1500 hours in FY 1998 to 2000 hours (33% increase).

Volunteers, through the NPS Volunteer-in-Parks (VIP) program, annually provide thousands of hours of assistance to Mount Rushmore National Memorial.  The VIP program, authorized in 1970, permits the NPS to accept and use voluntary help in ways mutually beneficial to the parks and the volunteers.  Park volunteers at Mount Rushmore assist in areas as diverse as maintenance, interpretation, natural resource management and museum management.

This goal measures the total number of hours contributed to the Mount Rushmore volunteer program.  We have cited a baseline of 1500 hours from FY 1998 because a very large, non-recurring work group carried out major maintenance projects during the designated baseline year of FY 1997.

From our baseline of 1500 hours, we propose increasing volunteer hours to 2000 (33%) by 2005.  This will be accomplished through greater efforts to recruit and place park volunteers in all areas of park operations.  Efforts will include press releases and other media publicity as well as community programs to encourage volunteerism.  The volunteer coordinator will also work with park divisions to identify potential volunteer projects.

IVb2A	By September 30, 2005, cash donations to Mount Rushmore National Memorial are maintained at the 1998 level of $5,280.

IVb2B	By September 30, 2005, the cash value of in-kind donations, grants, and services provided Mount Rushmore National Memorial by the Mount Rushmore National Memorial Society and other organizations is increased for $82,824 in FY 1998 to $120,000 (45% increase).

Ivb2C	By September 30, 2005, the annual value of donations, grants and services from the Mount Rushmore History Association is increased by 10% (from $90,000 to $100,000).

Mount Rushmore has a partnership with the Mount Rushmore History Association, a non-profit cooperating association, to sell interpretive and educational materials to the visitors at the Memorial. The goal is to increase the amount contributed to the National Park Service by 10%.

III. HOW GOALS WILL BE ACCOMPLISHED

Mount Rushmore National Memorial’s long-term goals will be accomplished in five annual increments detailed each year in an Annual Performance Plan.  The Annual Performance Plan will contain annual goal increments of the long-term goals.  It will also contain a work plan for each annual goal, which will lay out the activities and products, along with their personnel and fiscal costs that will be carried out to achieve the annual goal.

The five-year summary forms in Appendix A illustrate how annual goals and work efforts will accomplish each long-term goal.

The estimated human and fiscal resources available to achieve the park’s FY 2001 annual goals and beyond include a base operating budget of approximately $2,482,000, a permanent work force of 39 permanent positions, and approximately 59 seasonal positions.

The park’s base (appropriated ONPS) budget is supplemented each fiscal year by non-appropriated fund sources and by competing for additional appropriated funds for projects.  In FY2000 these additional funds included approximately $10,500 of donated funds (or value), $31,000 of park housing funds, $477,000 repair and rehabilitation funds, and $150,000 cyclic maintenance funds.

Additional specific assistance in achieving the park’s annual goals will be provided by the National Park Service’s Midwest Regional Office, by the Western Archeological and Conservation Center, the Harper’s Ferry Center, and the Denver Service Center.  The Black Hills Parks and Forests Association in addition to directly helping accomplishing education and visitor service goals through literature sales and donating approximately $15,000 for interpretive and educational purposes, will provide sales clerks at the visitor center and will operate the books store at no cost to the NPS.  Details of all these supplementary and/or alternative activities, services, products, funds and staffing are shown, where applicable, on the annual work plan worksheets which follow.

A superintendent leads park staff.  The staff is organized into four operating divisions: Interpretation, Resource Management and Visitor Protection, Maintenance, and Administration.  Staff expertise and specialties include 9 permanent park rangers and 1 museum curator working in Interpretation and 8 permanent rangers working in resource management and visitor protection; 10 permanent employees working in facility management and maintenance.  There are approximately 29 seasonal (temporary) park rangers with 16 in interpretation, and 13 in visitor protection.  There are approximately 11 seasonal maintenance workers and 2 seasonal museum technicians.  The Black Hills Administrative Group provides administrative support services.  Mount Rushmore, Wind Cave, and Jewel Cave share the administrative staff of the Black Hills Administrative Group.  This recurring staff will be supplemented and/or supported this year using special project funds, contracts, and/or the assistance or expertise of various NPS and other organizations as available.

IV. KEY EXTERNAL FACTORS

Legislative and political challenges to the mission and management of the National Park Service (NPS) required that NPS personnel have the capability to reasonably and factually respond privately or publicly if necessary.

Changing demographics of park visitors and the general public challenge us to find new and relevant means of providing interpretive/educational services.

Economically and environmentally re-emerging cities will continue to demand increasing NPS resources.

Citizen Action and Land Rights groups will require us to develop effective means of communicating NPS goals and policies to such groups and the public with methods that incorporate tactful resolve.

V.   PROGRAM EVALUATION METHODOLOGY AND SCHEDULE FOR FUTURE

EVALUATIONS

In order to comply with the National Park Service process and policy pertaining to GPRA, the management team and several other key staff members have successfully progressed through a number of processes.  All members of the park management team received training, assemble a GPRA planning team, and appointed a park GPRA Coordinator to facilitate planning team efforts.   This group reviewed park legislation, the NPS servicewide Strategic Plan, and existing planning documents in developing the park mission statement and mission goals.  In addition the team reviewed the current status of resources and visitor services, current fiscal and human resources, and provided interested parties with the opportunity to participate in determining the most important needs in developing long-term goals for the park.  The team then laid each long-term goal out in five annual increments to determine necessary annual outcomes, funding, and staffing needed to reach the five-year performance targets.  A draft of the final plan was then developed and written which was review by the Superintendent and park staff.  The final document was approved by the Superintendent and copies submitted to the Midwest Regional Office.

The Mount Rushmore National Memorial Strategic Plan will be reviewed annually and potential minor adjustments made based on annual performance achievements from the prior year.  The plan will undergo a more substantive review and revision at least every three years as required by GPRA.  All substantive reviews and revisions will follow the same pattern as outlined above.

# VI. CONSULTATION

GPRA requires that Congress, OMB, and other interested and affected parties be consulted in the development of Strategic Plans.  Congress and OMB, as well as the Department of the Interior, were extensively consulted in the development of the NPS servicewide plan.  In the development of Mount Rushmore National Memorial’s local Strategic Plan, the opportunity for public review and comment on the draft Strategic Plan was announced through the media.  In addition copies of the draft were provided to those listed below.

Interested members of the public

South Dakota Division of Game Fish and Parks

South Dakota Department of Tourism

Custer State Park

South Dakota Department of Environment an Natural Resources

Black Hill National Forest

Mount Rushmore National Memorial Society

Mount Rushmore History Association

Black Hills, Badlands and Lakes Association

Keystone, Chamber of Commerce

Hill City, Chamber of Commerce

Custer, Chamber of Commerce

Rapid City, Chamber of Commerce

Rapid City Convention and Visitors Bureau

Rapid City Hospitality Association

VII.  STRATEGIC PLAN PREPARERS

The following park staff members were intimately and extensively involved in preparing this strategic plan:

Dan Wenk, Superintendent

Mark Davison, Park Ranger

Don Hart, Park Ranger

Jill Hart, Administrative Officer/Budget Analyst

Paul Menard, Chief, Black Hills Administrative Group  (GPRA Coordinator)

Ben O’Dell, Chief of Maintenance

Mike Pflaum, Chief of Resource Management and Visitor Protection

Jim Popovich, Chief of Interpretation

Meg Schwartz, Management Assistant

Rick Wallner, Assistant Chief of Interpretation

Bruce Weisman, Museum Curator

# APPENDIX A

## Five-year Annual Goal Charts

The following charts illustrate how each of this plan’s long-term goals will be accomplished incrementally through annual goals and work plans over the next five years.

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name: Mount Rushmore National Memorial

Park/Program Org Code:	1500				                                  Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: Ia1A – Disturbed Lands Park/Program Goal ID Number: Ia1A NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, 10.1% of targeted parklands, disturbed by development or agriculture, as of 1999, (22,500 of 233,000 acres) are restored. |
| --- |
| Long-term Goal Performance Target (Park/Program Long-term Goal text; adjust date for end of current strategic planning period): By September 30, 2005, 4% (4 acres) Of 100 Acres Of Mount Rushmore National Memorial’s lands disturbed by prior development or agricultural use and targeted for restoration, are restored. | Baseline Year: 1999 | Target Year: 2005 |
| Performance Indicator: Acres Restored | Unit Measure: Each | Condition (Desired): Restored | Total # Units in Baseline: 100 | Status in base yr. 0 |
| Projected Performance Target, end of strategic planning period: 4 |
| Annual Performance Plan Detail for FY01 |
| Park/Program Annual Goal text: By September 30, 2001, complete inventory, mapping and written plan for the restoration of disturbed lands. |
| Projected Performance Target, end of this Fiscal Year: 0 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Planning / Inventory / Mapping | RMVP | Written Plan | Pflaum | ONPS Base | 14 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 18 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY02 |
| --- |
| Park/Program Annual Goal text: By September 30, 2002, 1 acre (1%) of 100 acres Of Mount Rushmore National Memorial’s lands disturbed by prior development or agricultural use and targeted for restoration, is restored. |
| Projected Performance Target, end of this Fiscal Year: 1 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Restoration | RMVP | 1 acre restored | Pflaum | ONPS Base | 14 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 18 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY03 |
| --- |
| Park/Program Annual Goal text: By September 30, 2003, 1 additional acre (1%) of 100 acres Of Mount Rushmore National Memorial’s lands disturbed by prior development or agricultural use and targeted for restoration, is restored. |
| Projected Performance Target, end of this Fiscal Year: 2 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Restoration | RMVP | 1 acre restored | Pflaum | ONPS Base | 14 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 18 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, 1 additional acre (1%) of 100 acres of Mount Rushmore National Memorial’s lands disturbed by prior development or agricultural use and targeted for restoration, is restored. |
| Projected Performance Target, end of this Fiscal Year: 3 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Restoration | RMVP | 1 acre restored | Pflaum | ONPS Base | 14 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 18 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY05 |
| --- |
| Park/Program Annual Goal text: By September 30, 2005, 1 additional acre (1%) of 100 acres of Mount Rushmore National Memorial’s lands disturbed by prior development or agricultural use and targeted for restoration, are restored. |
| Projected Performance Target, end of this Fiscal Year: 4 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Restoration | RMVP | 1 acre restored | Pflaum | ONPS Base | 14 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 18 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name: Mount Rushmore National Memorial

Park/Program Org Code:	1500				                                  Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: Ia1B – Exotic Plant Species Park/Program Goal ID Number: Ia1B NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, Exotic vegetation on 6.3% of targeted acres of parkland (167,500 of 2,656,700 acres) is contained. |
| --- |
| Long-term Goal Performance Target (Park/Program Long-term Goal text; adjust date for end of current strategic planning period): By September 30, 2005, 8 acres (4.4%) of 180 acres of Mount Rushmore National Memorial’s lands impacted by exotic vegetation and targeted by September 30, 1999, are contained. | Baseline Year: 1999 | Target Year: 2005 |
| Performance Indicator (what is measured): Acres Contained | Unit Measure: Each | Condition (Desired): Contained | Total # Units in Baseline: 180 | Status in base yr. (# Meeting Condition). 0 |
| Projected Performance Target, end of strategic planning period: 8 |
| Annual Performance Plan Detail for FY01 |
| Park/Program Annual Goal text: By September 30, 2001, complete inventory, map, and develop written plan for containment of exotic vegetation. |
| Projected Performance Target, end of this Fiscal Year: 0 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Planning / Inventory / Mapping | RMVP | Written Plan and Map | Pflaum | ONPS Base | 15 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY02 |
| --- |
| Park/Program Annual Goal text: By September 30, 2002, 2 acres (1.1%) of 180 acres Of Mount Rushmore National Memorial’s lands impacted by exotic vegetation and targeted by September 30, 1999, are contained. |
| Projected Performance Target, end of this Fiscal Year: 2 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Exotic Plant Contained | RMVP | 2 Acres Contained | Pflaum | ONPS Base | 15 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY03 |
| --- |
| Park/Program Annual Goal text: By September 30, 2003, 2 additional acres (1.1%) of 180 acres of Mount Rushmore National Memorial’s lands impacted by exotic vegetation and targeted by September 30, 1999, are contained. |
| Projected Performance Target, end of this Fiscal Year: 4 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Exotic Plant Contained | RMVP | 2 Acres Contained | Pflaum | ONPS Base | 15 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, 2 additional acres (1.1%) of 180 acres of Mount Rushmore National Memorial’s lands impacted by exotic vegetation and targeted by September 30, 1999, are contained. |
| Projected Performance Target, end of this Fiscal Year: 6 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Exotic Plant Contained | RMVP | 2 Acres Contained | Pflaum | ONPS Base | 15 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY05 |
| --- |
| Park/Program Annual Goal text: By September 30, 2005, 2 additional acres (1.1%) of 180 acres of Mount Rushmore National Memorial’s lands impacted by exotic vegetation and targeted by September 30, 1999, are contained. |
| Projected Performance Target, end of this Fiscal Year: 8 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Exotic Plant Contained | RMVP | 2 Acres Contained | Pflaum | ONPS Base | 15 | .32 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name: Mount Rushmore National Memorial

Park/Program Org Code:	1500				Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: 1a5 Park/Program Goal ID Number: 1a5 NPS Servicewide Goal Description: By September 30, 2005, 50% (12,113 of 24,225 structures) of the historic structures on the 1999 List of Classified Structures are in good condition. |
| --- |
| Long-term Goal Performance Target: By September 30, 2005, 88% (7 of 8) of the historic structures on the 1999 List of Classified Structures and Mount Rushmore are in good condition. | Baseline Year: 1999 | Target Year: 2005 |
| Performance Indicator (what is measured): Historic Structures | Unit Measure: Each | Condition (Desired): Good | Total # Units in Baseline: 8 | Status in base yr. (# Meeting Condition). 6 |
| Projected Performance Target, end of strategic planning period: 7 |

| Annual Performance Plan Detail for FY01 |
| --- |
| Park/Program Annual Goal text: By September 30, 2001, maintain 6 listed structures in good condition. Begin Historic Structure Report process for Borglum Studio and Residence 2. |
| Projected Performance Target, end of this Fiscal Year: 6 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Begin Historic Structure Report process for HS-04 & HS-02 phase 1 | Maint | Planning and Maintenance documents | Ben O’Dell | Cultural Resource Pres. Program | 170 | 0 |
| Replace 50% of the water repelling membrane on top of the Mt. Rushmore Sculpture | Maint | Preserve Sculpture | Ben O'Dell | ONPS | 4 | .12 |
| Replace roof HS-04(Studio) | Maint | Preserve Studio | Ben O'Dell | Cyclic | 14 | .06 |
| Monitor rock movement of the Sculpture | Maint | Preserve Sculpture | Ben O'Dell | Re/Rehab | 49 | 0 |
| Preventive Maintenance | Maint | Perform maintenance on buildings and structures | Ben O’Dell | ONPS | 5 | .26 |
| Manage Structure Activities | Maint | Meet requirements and plans | Ben O'Dell | ONPS | 5 | .02 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 251 | .6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY02 |
| --- |
| Park/Program Annual Goal text: By September 30, 2002, maintain 6 listed structures in good condition. Complete Historic Structure Report process for Borglum Studio and Residence 2. |
| Projected Performance Target, end of this Fiscal Year: 6 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Begin Historic Structure Report process for HS-04 & HS-02 phase 2 | Maint | Planning and Maintenance documents | Ben O’Dell | Cultural Resource Pres. Program | 170 | 0 |
| Replace 50% of the water repelling membrane on top of the Mt. Rushmore Sculpture | Maint | Preserve Sculpture | Ben O'Dell | ONPS | 4 | .12 |
| Replace roof HS-02(Res.2) | Maint | Preserve Studio | Ben O'Dell | Cyclic | 5 | .06 |
| Monitor rock movement of the Sculpture | Maint | Preserve Sculpture | Ben O'Dell | Re/Rehab | 49 | 0 |
| Preventive Maintenance | Maint | Perform maintenance on buildings and structures | Ben O’Dell | ONPS | 5 | .26 |
| Manage Structure Activities | Maint | Meet requirements and plans | Ben O'Dell | ONPS | 5 | .02 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 242 | .6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY03 |
| --- |
| Park/Program Annual Goal text: By September 30, 2003, maintain 6 listed structures in good condition, maintain 2 historic structures in fair condition. |
| Projected Performance Target, end of this Fiscal Year: 6 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Preventive Maintenance | Maint | Perform maintenance on buildings and structures | Ben O’Dell | ONPS | 5 | .26 |
| Manage Structure Activities | Maint | Meet requirements and plans | Ben O'Dell | ONPS | 3 | .01 |
| Monitor rock movement of the Sculpture | Maint | Preserve Sculpture | Ben O'Dell | Re/Rehab | 49 | 0 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 61 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, maintain 6 listed structures in good condition, maintain 2 historic structures in fair condition. |
| Projected Performance Target, end of this Fiscal Year: 6 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Preventive Maintenance | Maint | Perform maintenance on buildings and structures | Ben O’Dell | ONPS | 5 | 0.26 |
| Manage Structure Activities | Maint | Meet requirements and plans | Ben O'Dell | ONPS | 3 | .01 |
| Monitor rock movement of the Sculpture | Maint | Preserve Sculpture | Ben O'Dell | Re/Rehab | 49 | 0 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 61 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY05 |
| --- |
| Park/Program Annual Goal text: By September 30, 2005, maintain 7 listed structures in good condition (improving 1 from fair condition) and maintain 1 historic structure in fair condition. |
| Projected Performance Target, end of this Fiscal Year: 7 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Preventive Maintenance | Maint | Perform maintenance on buildings and structures | Ben O’Dell | ONPS | 5 | .26 |
| Manage Structure Activities | Maint | Meet requirements and plans | Ben O'Dell | ONPS | 3 | .01 |
| Monitor rock movement of the Sculpture | Maint | Preserve Sculpture | Ben O'Dell | Re/Rehab | 49 | 0 |
| Overhead & Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 61 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name: Mount Rushmore National Memorial

Park/Program Org Code:1500					Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: Ia6 Park/Program Goal ID Number: Ia6 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, 73.4% of preservation and protection standards for park museum collections are met. |
| --- |
| Long-term Goal Performance Target (Park/Program Long-term Goal text; adjust date for end of current strategic planning period): By September 30, 2005, 171 (75.5%) of 225 applicable preservation and protection standards are met for Mount Rushmore’s museum collections as defined by the ACP. Other preservation and protection museum standards are set and accomplished in through collection research and improving accessibility. | Baseline Year: 2000 | Target Year: 2005 |
| Performance Indicator (what is easured): Percentage of standards met. | Unit Measure: Number of Standards met | Condition (Desired): Meet ACP Standards Maintain park standards | Total # Units in Baseline: 225 | Status in base yr 156 |
| Projected Performance Target, end of strategic planning period: 171 |

| Annual Performance Plan Detail for FY01 |
| --- |
| Park/Program Annual Goal text: By September 30, 2001, increase percentage of preservation and protection standards met to 159 (70.22%). Maintain park standards. |
| Projected Performance Target, end of this Fiscal Year: 159 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Correct ACP Deficiencies | Interp | 3 Deficiencies removed from checklist | Bruce Weisman | ONPS | 14.1 | .27 |
| Maintain and preserve collection | Interp | Collection stored and exhibited to professional standards | Bruce Weisman | ONPS | 25 | .53 |
| Provide research assistance. | Interp | Protection of collections through controlled access | Bruce A. Weisman James G. Popovich | ONPS ONPS | 6.3 4.4 | .13 .09 |
| Overhead & Assessments | Admin |  |  | ONPS | 14 | .2 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 64 | 1.2 |
| Comments: Ongoing collection maintenance and controlled access prevent reinstitution of previously corrected deficiencies. |

| Annual Performance Plan Detail for FY02 |
| --- |
| Park/Program Annual Goal text: By September 30, 2002, , increase percentage of preservation and protection standards met to 162 (71.5%). Maintain park standards |
| Projected Performance Target, end of this Fiscal Year: 162 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Correct ACP Deficiencies | Interpretation | 3 Deficiencies removed from checklist | Bruce Weisman | ONPS | 14.1 | .27 |
| Maintain and preserve collection | Interpretation | Collection stored and exhibited to professional standards | Bruce Weisman | ONPS | 25 | .53 |
| Provide research assistance. | Interpretation | Protection of collections through controlled access | Bruce A. Weisman James G. Popovich | ONPS ONPS | 6.3 4.4 | .13 .09 |
| Overhead & Assessments | Admin |  |  | ONPS | 14 | .2 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 64 | 1.2 |
| Comments: Ongoing collection maintenance and controlled access prevent reinstitution of previously corrected deficiencies. |

| Annual Performance Plan Detail for FY03 |
| --- |
| Park/Program Annual Goal text: By September 30, 2003, , increase percentage of preservation and protection standards met to 165 (72.8%). Maintain park standards. |
| Projected Performance Target, end of this Fiscal Year: 165 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Correct ACP Deficiencies | Interpretation | 3 Deficiencies removed from checklist | Bruce Weisman | ONPS | 14.1 | .27 |
| Maintain and preserve collection | Interpretation | Collection stored and exhibited to professional standards | Bruce Weisman | ONPS | 25 | .53 |
| Provide research assistance. | Interpretation | Protection of collections through controlled access | Bruce A. Weisman James G. Popovich | ONPS ONPS | 6.3 4.4 | .13 .09 |
| Overhead & Assessments | Admin |  |  | ONPS | 14 | .2 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 64 | 1.2 |
| Comments: Ongoing collection maintenance and controlled access prevent reinstitution of previously corrected deficiencies. |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, increase percentage of preservation and protection standards met to 168 (74.2%). Maintain park standards |
| Projected Performance Target, end of this Fiscal Year: 168 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Correct ACP Deficiencies | Interpretation | 3 Deficiencies removed from checklist | Bruce Weisman | ONPS | 14.1 | .27 |
| Maintain and preserve collection | Interpretation | Collection stored and exhibited to professional standards | Bruce Weisman | ONPS | 25 | .53 |
| Provide research assistance. | Interpretation | Protection of collections through controlled access | Bruce A. Weisman James G. Popovich | ONPS ONPS | 6.3 4.4 | .13 .09 |
| Overhead & Assessments | Admin |  |  | ONPS | 14 | .2 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 64 | 1.2 |
| Comments: Ongoing collection maintenance and controlled access prevent reinstitution of previously corrected deficiencies. |

| Annual Performance Plan Detail for FY05 |
| --- |
| Park/Program Annual Goal text: By September 30, 2005, increase percentage of preservation and protection standards met to 171 (75.5%). Maintain park standards |
| Projected Performance Target, end of this Fiscal Year: 171 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Correct ACP Deficiencies | Interpretation | 3 Deficiencies removed from checklist | Bruce Weisman | ONPS | 14.1 | .27 |
| Maintain and preserve collection | Interpretation | Collection stored and exhibited to professional standards | Bruce Weisman | ONPS | 25 | .53 |
| Provide research assistance. | Interpretation | Protection of collections through controlled access | Bruce A. Weisman James G. Popovich | ONPS ONPS | 6.3 4.4 | .13 .09 |
| Overhead & Assessments | Admin |  |  | ONPS | 14 | .2 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 64 | 1.2 |
| Comments: Ongoing collection maintenance and controlled access prevent reinstitution of previously corrected deficiencies. |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name:   Mount Rushmore National Memorial

Park/Program Org Code:	1500				Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: Ib2C Park/Program Goal ID Number: Ib2C NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, 100% of the Historic Structures will have updated information. (FY 1999 baseline 24,225 of 22,225). |
| --- |
| Long-term Goal Performance Target (Park/Program Long-term Goal text; adjust date for end of current strategic planning period): By September 30, 2005, 100% of historic structures will have updated information in the List of Classified Structures. | Baseline Year: 1999 | Target Year: 2005 |
| Performance Indicator (what is measured): LCS Records w/updated information | Unit Measure: Each LCS Record | Condition (Desired): Updated LCS Records | Total # Units in Baseline: 8 | Status in base yr. (# Meeting Condition). 7 |
| Projected Performance Target, end of strategic planning period: 8 |
| Annual Performance Plan Detail for FY01 |
| Park/Program Annual Goal text: By September 30, 2001, 88% (7 of 8) of the historic structures listed in the LCS have updated information. (7 of 8) |
| Projected Performance Target, end of this Fiscal Year: 7 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Verify 7 of the 8 records are updated | Interp | Check PMDS statistics | Jim Popovich | ONPS BASE |  |  |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  |  |  |
| Comments: |

| Annual Performance Plan Detail for FY02 |
| --- |
| Park/Program Annual Goal text: By September 30, 2002, 100% of the historic structures listed in the LCS have updated information (8 of 8). |
| Projected Performance Target, end of this Fiscal Year: 8 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Update all LCS records (8 of 8) | Interp | Update all records | Jim Popovich | ONPS BASE |  |  |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  |  |  |
| Comments: |

| Annual Performance Plan Detail for FY03 |
| --- |
| Park/Program Annual Goal text: By September 30, 2003, 100% of the Historic Structures listed in the LCS have updated information (8 of 8) |
| Projected Performance Target, end of this Fiscal Year: 8 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Maintain all LCS records | Interp |  | Jim Popovich | ONPS BASE |  |  |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  |  |  |
| Comments: |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, 100% of the historic structures listed in the LCS will have updated information ( 8 of 8 ). |
| Projected Performance Target, end of this Fiscal Year: 8 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Maintain all LCS Records | Interp |  | Jim Popovich | ONPS BASE |  |  |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  |  |  |
| Comments: |

| Annual Performance Plan Detail for FY05 |
| --- |
| Park/Program Annual Goal text: By September 30, 2005, 100% of the historic structures listed in the LCS will have updated information ( 8 of 8). |
| Projected Performance Target, end of this Fiscal Year: 8 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Maintain all LCS records | Interp |  | Jim Popovich | ONPS BASE |  |  |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  |  |  |
| Comments: |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name:

Park/Program Org Code:							Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: Ib2D Park/Program Goal ID Number: Ib2D NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, museum objects cataloged are increased by 35.9% (from FY 1999 baseline of 37.3 million to 50.7 million. |
| --- |
| Long-term Goal Performance Target (Park/Program Long-term Goal text; adjust date for end of current strategic planning period): By September 30, 2005, the number of Mount Rushmore museum objects cataloged into the National Park Services Automated National Catalog System (ANCS+) and submitted to the National Catalog is increased from 55618 in FY1999 to 55894 (.5% increase). | Baseline Year: 1999 | Target Year: 2005 |
| Performance Indicator (what is measured): Museum Objects in database. | Unit Measure: Each museum object | Condition (Desired): Objects catalogued | Total # Units in Baseline: 55894 | Status in base yr. (# Meeting Condition). 55618 |
| Projected Performance Target, end of strategic planning period: 55894 |
| Annual Performance Plan Detail for FY01 |
| Park/Program Annual Goal text: By September 30, 2001, the number of Mount Rushmore’s museum object’s cataloged into the National Park Services Automated National Catalog System (ANCS+) and submitted to the National Catalog is increased from 55618 in FY1999 to 55673. |
| Projected Performance Target, end of this Fiscal Year: 55673 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Catalog collection items | Interpretation | Catalog records | Bruce A. Weisman | ONPS | 3.6 | .07 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 4 | .1 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY02 |
| --- |
| Park/Program Annual Goal text: By September 30, 2002, the number of Mount Rushmore’s museum object’s cataloged into the National Park Services Automated National Catalog System (ANCS+) and submitted to the National Catalog is increased from 55618 in FY1999 to 55730. |
| Projected Performance Target, end of this Fiscal Year: 55730 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Catalog collection items | Interpretation | Catalog records | Bruce A. Weisman | ONPS | 3.6 | .07 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 4 | .1 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY03 |
| --- |
| Park/Program Annual Goal text: By September 30, 2003, , the number of Mount Rushmore’s museum object’s cataloged into the National Park Services Automated National Catalog System (ANCS+) and submitted to the National Catalog is increased from 55618 in FY1999 to 55786. |
| Projected Performance Target, end of this Fiscal Year: 55786 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Catalog collection items | Interpretation | Catalog records | Bruce A. Weisman | ONPS | 3.6 | .07 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 4 | .1 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, , the number of Mount Rushmore’s museum object’s cataloged into the National Park Services Automated National Catalog System (ANCS+) and submitted to the National Catalog is increased from 55618 in FY1999 to 55842. |
| Projected Performance Target, end of this Fiscal Year: 55842 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Catalog collection items | Interpretation | Catalog records | Bruce A. Weisman | ONPS | 3.6 | .07 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 4 | .1 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY05 |
| --- |
| Park/Program Annual Goal text: By September 30, 2005, , the number of Mount Rushmore’s museum object’s cataloged into the National Park Services Automated National Catalog System (ANCS+) and submitted to the National Catalog is increased from 55618 in FY1999 to 55898. |
| Projected Performance Target, end of this Fiscal Year: 55898 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Catalog collection items | Interpretation | Catalog records | Bruce A. Weisman | ONPS | 3.6 | .07 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 4 | .1 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name: Mount Rushmore National Memorial

Park/Program Org Code:	1500				                                  Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: Ib3 Park/Program Goal ID Number: Ib3 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, 80% of 265 parks with significant natural resources have identified their vital signs for natural resource monitoring. |
| --- |
| Long-term Goal Performance Target (Park/Program Long-term Goal text; adjust date for end of current strategic planning period): By September 30, 2005, Mount Rushmore National Memorial has identified 40% of it’s vital signs for natural resource monitoring. | Baseline Year: 1999 | Target Year: 2005 |
| Performance Indicator (what is measured): Vital Signs | Unit Measure: Each | Condition (Desired): Identified | Total # Units in Baseline: Unknown | Status in base yr. (# Meeting Condition). 0 |
| Projected Performance Target, end of strategic planning period: 0 |
| Annual Performance Plan Detail for FY01 |
| Park/Program Annual Goal text: By September 30, 2001, there is a complete natural resource inventory and written plan for identifying natural resource vital signs. |
| Projected Performance Target, end of this Fiscal Year: 0 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Inventory | RMVP | Inventory / Written Plan | Pflaum | ONPS Base | 14.5 | .32 |
| Overhead and Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY02 |
| --- |
| Park/Program Annual Goal text: By September 30, 2002, 10% of natural resource vital signs are identified. |
| Projected Performance Target, end of this Fiscal Year: 0 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Identifying Nat. Res. Vital Signs | RMVP | 10% Vital Signs Ident. | Pflaum | ONPS Base | 14.5 | .32 |
| Overhead and Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY03 |
| --- |
| Park/Program Annual Goal text: By September 30, 2003, an additional 10% of natural resource vital signs are identified (20% total). |
| Projected Performance Target, end of this Fiscal Year: 0 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Identifying Nat. Res. Vital Signs | RMVP | 10% Vital Signs Ident. | Pflaum | ONPS Base | 14.5 | .32 |
| Overhead and Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, an additional 10% of natural resource vital signs are identified (30% total). |
| Projected Performance Target, end of this Fiscal Year: 0 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Identifying Nat. Res. Vital Signs | RMVP | 10% Vital Signs Ident. | Pflaum | ONPS Base | 14.5 | .32 |
| Overhead and Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY05 |
| --- |
| Park/Program Annual Goal text: By September 30, 2005, an additional 10% of natural resource vital signs are identified (40% total). |
| Projected Performance Target, end of this Fiscal Year: 0 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Identifying Nat. Res. Vital Signs | RMVP | 10% Vital Signs Ident. | Pflaum | ONPS Base | 14.5 | .32 |
| Overhead and Assessments | Admin |  |  | ONPS | 4 | .1 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 19 | .4 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name: Mount Rushmore National Memorial

Park/Program Org Code:	1500				Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: IIa1 Park/Program Goal ID Number: IIa1 NPS Servicewide Goal Description: By September 30, 2005, 95% of park visitors are satisfied with appropriate park facilities, services, and recreational opportunities. |
| --- |
| Long-term Goal Performance Target: By September 30, 2005, 99% of park visitors to Mount Rushmore are satisfied with appropriate park facilities, services and recreational opportunities. | Baseline Year: 1998 | Target Year: 2005 |
| Performance Indicator (what is measured): Visitor Satisfaction | Unit Measure: Percent of Visitors Satisfied | Condition (Desired): Satisfied Visitors | Total # Units in Baseline: 98 | Status in base yr. (# Meeting Condition). 98 |
| Projected Performance Target, end of strategic planning period: |

| Annual Performance Plan Detail for FY01 |
| --- |
| Park/Program Annual Goal text: By September 30, 2001, 99% of visitors to Mount Rushmore are satisfied with appropriate park facilities, services, and recreational opportunities. |
| Projected Performance Target, end of this Fiscal Year: 99 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Provide Janitorial Services to Park Facilities | Maint | Clean facilities | Ben O'Dell | ONPS | 228 | 7.9 |
| Maintain Walkways/Roads/Trails | Maint | Maintained in safe condition that meets all applicable standards | Ben O’Dell | ONPS | 5 | .1 |
| Utility Systems (water,sewer,electric, HVAC) | Maint | Uninterrupted Service meets Federal, State and Local codes/requirements | Ben O’Dell | ONPS | 313.1 | 5.0 |
| Remove Solid Waste | Cont. | Move waste to landfill | Ben O'Dell | ONPS | 7.5 |  |
| Building and Equipment repair, maintenance, and operational cost | Maint | Perform repair and preventative maintenance | Ben O'Dell | ONPS | 172.1 | 4.9 |
| Provide Elevator Service | Cont. | Safe continued elevator service | Ben O'Dell | ONPS | 5.5 |  |
| Implement Site Signage Plan | Maint | Improve wayfinding | Ben O'Dell | Cyclic-Regular | 11 |  |
| Visitor Services | RMVP | Assist visitors | Pflaum | ONPS Base | 399 | 8.8 |
| Concessions Management | RMVP |  |  | ONPS Base | 22 | .5 |
| Overhead and Assessments | Admin |  |  | ONPS | 316 | 4.4 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 1479 | 31.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY02 |
| --- |
| Park/Program Annual Goal text: By September 30, 2002, 99% of visitors to Mount Rushmore are satisfied with appropriate park facilities, services, and recreational opportunities |
| Projected Performance Target, end of this Fiscal Year: 99 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Provide Janitorial Services to Park Facilities | Maint | Clean facilities | Ben O'Dell | ONPS | 228 | 7.88 |
| Maintain Walkways/Roads/Trails | Maint | Maintained in safe condition that meets all applicable standards | Ben O’Dell | ONPS | 5 | .1 |
| Utility Systems (water,sewer,electric, HVAC) | Maint | Uninterrupted Service meets Federal, State and Local codes/requirements | Ben O’Dell | ONPS…………. Reimbursable Concession…… (Other) | 243.1 70 | 5.0 |
| Remove Solid Waste | Cont. | Move waste to landfill | Ben O'Dell | ONPS | 7.5 |  |
| Building and Equipment repair, maintenance, and operational cost | Maint | Perform repair and preventative maintenance | Ben O'Dell | ONPS | 172.1 | 4.9 |
| Provide Elevator Service | Cont. | Safe continued elevator service | Ben O'Dell | ONPS | 5.5 |  |
| Implement Site Signage Plan | Maint | Improve wayfinding | Ben O'Dell | Cyclic-Regular | 11 |  |
| Visitor Services | RMVP | Assist visitors | Pflaum | ONPS Base | 399 | 8.8 |
| Concessions Management | RMVP |  |  | ONPS Base | 22 | .5 |
| Overhead and Assessments | Admin |  |  | ONPS | 316 | 4.4 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 1479 | 31.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY03 |
| --- |
| Park/Program Annual Goal text: By September 30, 2003, 99% of visitors to Mount Rushmore are satisfied with appropriate park facilities, services, and recreational opportunities |
| Projected Performance Target, end of this Fiscal Year: 99 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Provide Janitorial Services to Park Facilities | Maint | Clean facilities | Ben O'Dell | ONPS | 228 | 7.88 |
| Maintain Walkways/Roads/Trails | Maint | Maintained in safe condition that meets all applicable standards | Ben O’Dell | ONPS | 5 | .1 |
| Utility Systems (water,sewer,electric, HVAC) | Maint | Uninterrupted Service meets Federal, State and Local codes/requirements | Ben O’Dell | ONPS, Reimbursable Concession | 243.1 70 | 5.0 |
| Remove Solid Waste | Cont. | Move waste to landfill | Ben O'Dell | ONPS | 7.5 |  |
| Building and Equipment repair, maintenance, and operational cost | Maint | Perform repair and preventative maintenance | Ben O'Dell | ONPS | 172.1 | 4.9 |
| Provide Elevator Service | Cont. | Safe continued elevator service | Ben O'Dell | ONPS | 5.5 |  |
| Visitor Services | RMVP | Assist visitors | Pflaum | ONPS Base | 399 | 8.8 |
| Concessions Management | RMVP |  |  | ONPS Base | 22 | .5 |
| Overhead and Assessments | Admin |  |  | ONPS | 316 | 4.4 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 1479 | 31.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, , 99% of visitors to Mount Rushmore are satisfied with appropriate park facilities, services, and recreational opportunities |
| Projected Performance Target, end of this Fiscal Year: 99% Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Provide Janitorial Services to Park Facilities | Maint | Clean facilities | Ben O'Dell | ONPS | 228 | 7.88 |
| Maintain Walkways/Roads/Trails | Maint | Maintained in safe condition that meets all applicable standards | Ben O’Dell | ONPS | 5 | .1 |
| Utility Systems (water,sewer,electric, HVAC) | Maint | Uninterrupted Service meets Federal, State and Local codes/requirements | Ben O’Dell | ONPS, Reimbursable Concession | 243.1 70 | 5.0 |
| Remove Solid Waste | Cont. | Move waste to landfill | Ben O'Dell | ONPS | 7.5 |  |
| Building and Equipment repair, maintenance, and operational cost | Maint | Perform repair and preventative maintenance | Ben O'Dell | ONPS | 172.1 | 4.9 |
| Provide Elevator Service | Cont. | Safe continued elevator service | Ben O'Dell | ONPS | 5.5 |  |
| Visitor Services | RMVP | Assist visitors | Pflaum | ONPS Base | 399 | 8.8 |
| Concessions Management | RMVP |  |  | ONPS Base | 22 | .5 |
| Overhead and Assessments | Admin |  |  | ONPS | 316 | 4.4 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 1479 | 31.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY05 |
| --- |
| Park/Program Annual Goal text: By September 30, 2005, 99% of visitors to Mount Rushmore are satisfied with appropriate park facilities, services, and recreational opportunities |
| Projected Performance Target, end of this Fiscal Year: 99 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division |  | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Provide Janitorial Services to Park Facilities | Maint | Clean facilities | Ben O'Dell | ONPS | 228 | 7.88 |
| Maintain Walkways/Roads/Trails | Maint | Maintained in safe condition that meets all applicable standards | Ben O’Dell | ONPS | 5 | .1 |
| Utility Systems (water,sewer,electric, HVAC) | Maint | Uninterrupted Service meets Federal, State and Local codes/requirements | Ben O’Dell | ONPS, Reimbursable Concession | 243.1 70 | 5.0 |
| Remove Solid Waste | Cont. | Move waste to landfill | Ben O'Dell | ONPS | 7.5 |  |
| Building and Equipment repair, maintenance, and operational cost | Maint | Perform repair and preventative maintenance | Ben O'Dell | ONPS | 172.1 | 4.9 |
| Provide Elevator Service | Cont. | Safe continued elevator service | Ben O'Dell | ONPS | 5.5 |  |
| Visitor Services | RMVP | Assist visitors | Pflaum | ONPS Base | 399 | 8.8 |
| Overhead and Assessments | Admin |  |  | ONPS | 316 | 4.4 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 1479 | 31.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name: Mount Rushmore National Memorial

Park/Program Org Code:	1500				                                  Date Prepared:  October 26, 2000

| Servicewide Goal ID Number: IIa2 Park/Program Goal ID Number: IIa2 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, the visitor accident/incident rate will be at or below 8.1 per 100,00 visitor days. |
| --- |
| Long-term Goal Performance Target (Park/Program Long-term Goal text; adjust date for end of current strategic planning period): By September 30, 2005, the number of Mount Rushmore National Memorial visitor accidents/incidents results in a rate that’s no higher than the servicewide rate of 7.96 accidents / incidents per 100,000 visitor days. | Baseline Year: FY’92 – ‘96 | Target Year: 2005 |
| Performance Indicator (what is measured): Visitor Accident/Incidents | Unit Measure: Each Visitor accident | Condition (Desired): Reduced | Total # Units in Baseline: | Status in base yr. (# Meeting Condition). |
| Projected Performance Target, end of strategic planning period: 18 |
| Annual Performance Plan Detail for FY01 |
| Park/Program Annual Goal text: By September 30, 2001, the number of visitor accident/incidents at Mount Rushmore National Memorial results in a rate no higher than the servicewide rate of 8.76 accidents / incidents per 100,000 visitor days. |
| Projected Performance Target, end of this Fiscal Year: 20 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Protection patrols; emergency personnel trained and certified; safety messages communicated to visitors. | RMVP | Visitors are aware of safety issues and are better protected from hazards. | Pflaum | ONPS Base | 217.7 | 4.8 |
| Overhead and Assessments | Admin |  |  | ONPS | 60 | 0.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 278 | 5.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |
| Annual Performance Plan Detail for FY02 |
| Park/Program Annual Goal text: By September 30, 2002, the number of visitor accident/incidents at Mount Rushmore National Memorial results in a rate no higher than the servicewide rate of 8.53 accidents / incidents per 100,000 visitor days. |
| Projected Performance Target, end of this Fiscal Year: 19 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Protection patrols; emergency personnel trained and certified; safety messages communicated to visitors. | RMVP | Visitors are aware of safety issues and are better protected from hazards. | Pflaum | ONPS Base | 217.7 | 4.8 |
| Overhead and Assessments | Admin |  |  | ONPS | 60 | 0.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 278 | 5.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |
| Annual Performance Plan Detail for FY03 |
| Park/Program Annual Goal text: By September 30, 2003, the number of visitor accident/incidents at Mount Rushmore National Memorial results in a rate no higher than the servicewide rate of 8.34 accidents / incidents per 100,000 visitor days. |
| Projected Performance Target, end of this Fiscal Year: 19 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Protection patrols; emergency personnel trained and certified; safety messages communicated to visitors. | RMVP | Visitors are aware of safety issues and are better protected from hazards. | Pflaum | ONPS Base | 217.7 | 4.8 |
| Overhead and Assessments | Admin |  |  | ONPS | 60 | 0.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 278 | 5.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

| Annual Performance Plan Detail for FY04 |
| --- |
| Park/Program Annual Goal text: By September 30, 2004, the number of visitor accident/incidents at Mount Rushmore National Memorial results in a rate no higher than the servicewide rate of 8.15 accidents / incidents per 100,000 visitor days. |
| Projected Performance Target, end of this Fiscal Year: 18 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Protection patrols; emergency personnel trained and certified; safety messages communicated to visitors. | RMVP | Visitors are aware of safety issues and are better protected from hazards. | Pflaum | ONPS Base | 217.7 | 4.8 |
| Overhead and Assessments | Admin |  |  | ONPS | 60 | 0.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 278 | 5.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |
| Annual Performance Plan Detail for FY05 |
| Park/Program Annual Goal text: By September 30, 2005, the number of visitor accident/incidents at Mount Rushmore National Memorial results in a rate no higher than the servicewide rate of 7.96 accidents / incidents per 100,000 visitor days. |
| Projected Performance Target, end of this Fiscal Year: 18 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Protection patrols; emergency personnel trained and certified; safety messages communicated to visitors. | RMVP | Visitors are aware of safety issues and are better protected from hazards. | Pflaum | ONPS Base | 217.7 | 4.8 |
| Overhead and Assessments | Admin |  |  | ONPS | 60 | 0.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX |  | 278 | 5.6 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

Multi-year Worksheet for

Annual Performance Plan

Park/Program Name: MOUNT RUSHMORE NMEM

Park/Program Org Code:	1500				Date Prepared:  April 6, 2000

| Servicewide Goal ID Number: IIb1 Park/Program Goal ID Number: IIb1 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, 86% of park visitors understand and appreciate the significance of the park they are visiting. |
| --- |
| Long-term Goal Performance Target (Park/Program Long-term Goal text; adjust date for end of current strategic planning period): By September 30, 2005, 70% of Mount Rushmore National Memorial visitors understand the significance of the memorial. | Baseline Year: FY 1999 | Target Year: FY 2005 |
| Performance Indicator (what is measured): Visitor understanding | Unit Measure: Percent of visitors that understand significance of the memorial | Condition (Desired): Visitors understand and appreciate the memorial's significance | Total # Units in Baseline: 66 | Status in base yr. (# Meeting Condition). 66 |
| Projected Performance Target, end of strategic planning period: 70 |
| Annual Performance Plan Detail for FY01 |
| Park/Program Annual Goal text: By September 30, 2001, 66% of Mount Rushmore National Memorial visitors understand the significance of the memorial. |
| Projected Performance Target, end of this Fiscal Year: 66 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Personal Interpretive Services | Interp | Provide programs | J.Popovich | ONPS Base | 392 | 11.0 |
| Non-Personal Interp. Services | Interp | Exhibits; A-V programs | J.Popovich | ONPS Base | 30 | .9 |
| Non-Personal Interp. Services | Interp | Brochures; handouts | J.Popovich | Donations | 10 | .2 |
| Non-Personal Interp. Services | Interp | Implement Wayside plan | J.Popovich | Cultural Cyclic Maintenance | 91 | .2 |
| Non-Personal Interp. Services | Interp | Implement Information Center Exhibit plan | J.Popovich | Donations | 25 | .2 |
| Perform natural resource studies | RMVP | Provide information for use in brochures | Pflaum | ONPS Base | 43.6 | .96 |
| Overhead and Assessments | Admin |  |  | ONPS | 128 | 1.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX | XXXXXXXXX | 720 | 15.3 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |
| Annual Performance Plan Detail for FY02 |
| Park/Program Annual Goal text: By September 30, 2002, 68% of Mount Rushmore National Memorial visitors understand the significance of the memorial. |
| Projected Performance Target, end of this Fiscal Year: 68 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Personal Interpretive Services | Interp | Provide programs | J.Popovich | ONPS Base | 392 | 11.5 |
| Non-Personal Interp. Services | Interp | Exhibits; A-V programs | J.Popovich | ONPS Base | 30 | .8 |
| Non-Personal Interp. Services | Interp | Brochures; handouts | J.Popovich | Other sources | 10 | .2 |
| Perform natural resource studies | RMVP | Provide information for use in brochures | Pflaum | ONPS Base | 43.6 | .96 |
| Overhead and Assessments | Admin |  |  | ONPS | 128 | 1.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX | XXXXXXXXX | 720 | 15.3 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |
| Annual Performance Plan Detail for FY03 |
| Park/Program Annual Goal text: By September 30, 2003, 68% of Mount Rushmore National Memorial visitors understand the significance of the memorial. |
| Projected Performance Target, end of this Fiscal Year: 68 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Personal Interpretive Services | Interp | Provide programs | J.Popovich | ONPS Base | 392 | 11.3 |
| Non-Personal Interp. Services | Interp | Exhibits; A-V programs | J.Popovich | ONPS Base | 30 | .8 |
| Non-Personal Interp. Services | Interp | Brochures; handouts | J.Popovich | Other sources | 10 | .2 |
| Non-Personal Interp. Services | Interp. | New Amphitheater A-V Program | J.Popovich | Donations | 200 | .2 |
| Perform natural resource studies | RMVP | Provide information for use in brochures | Pflaum | ONPS Base | 43.6 | .96 |
| Overhead and Assessments | Admin |  |  | ONPS | 128 | 1.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX | XXXXXXXXX | 720 | 15.3 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |
| Annual Performance Plan Detail for FY04 |
| Park/Program Annual Goal text: By September 30, 2004, 70% of Mount Rushmore National Memorial visitors understand the significance of the memorial. |
| Projected Performance Target, end of this Fiscal Year: 70 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Personal Interpretive Services | Interp | Provide programs | J.Popovich | ONPS Base | 392 | 11.3 |
| Non-Personal Interp. Services | Interp | Exhibits; A-V programs | J.Popovich | ONPS Base | 30 | .8 |
| Non-Personal Interp. Services | Interp | Brochures; handouts | J.Popovich | Other sources | 10 | .2 |
| Non-Personal Interp. Services | Interp. | New Amphitheater A-V Program | J.Popovich | Donations | 500 | .2 |
| Perform natural resource studies | RMVP | Provide information for use in brochures | Pflaum | ONPS Base | 43.6 | .96 |
| Overhead and Assessments | Admin |  |  | ONPS | 128 | 1.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX | XXXXXXXXX | 720 | 15.3 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |
| Annual Performance Plan Detail for FY05 |
| Park/Program Annual Goal text: By September 30, 2005, 70% of Mount Rushmore National Memorial visitors understand the significance of the memorial. |
| Projected Performance Target, end of this Fiscal Year: 70 Actual Result: |
| Annual Work Plan |
| Work Plan: Product/Service/Activity | Division | Planned Output | Responsible Person | Funding Category | Dollars ($000) | FTE |
| Personal Interpretive Services | Interp | Provide programs | J.Popovich | ONPS Base | 392 | 11.5 |
| Non-Personal Interp. Services | Interp | Exhibits; A-V programs | J.Popovich | ONPS Base | 30 | .8 |
| Non-Personal Interp. Services | Interp | Brochures; handouts | J.Popovich | Other sources | 10 | .2 |
| Perform natural resource studies | RMVP | Provide information for use in brochures | Pflaum | ONPS Base | 43.6 | .96 |
| Overhead and Assessments | Admin |  |  | ONPS | 128 | 1.8 |
| Total Cost and FTE | XXXXX | XXXXXXXXXXXXXXX | XXXXXXXX | XXXXXXXXX | 720 | 15.3 |
| Comments: Dollars are rounded to whole thousands and FTE are rounded to tenths as required by PMDS. |

Goal Category IV

Multi-year Worksheet

Park/Program Name: Mount Rushmore National Memorial

Park/Program Org Code:	1500				                                        Date Prepared: October 26, 2000

_________________________________________________________________________________________________

Servicewide Goal ID Number: IVa3 Workforce Development and Performance Park/Program Goal ID Number: IVa3 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, IVa3A — 100% of employee performance agreements are linked to appropriate strategic and annual performance goals and position competencies; and IVa3B — 95% of NPS employees demonstrate that they fully meet their competency requirements.

IVa3A Projected Park/Program Performance Target, end of strategic planning period: By September 30, 2005, 100% of Mount Rushmore National Memorial employee performance agreements are linked to appropriate strategic and annual performance goals and position competencies.

Park or Program Baseline: 98 employees

IVa3B (Parks/programs don't report, but must assure data entered in FPPS is correct)

Annual Performance Plan Summary for FY01

IVa3A Projected Park/Program Performance Target, end of this fiscal year: 49 Actual Result: By September 30, 2001, 50% of Mount Rushmore National Memorial employee performance agreements are linked to appropriate strategic and annual performance goals and position competencies.

Park or Program Baseline: 98 employees

Comments:

Annual Performance Plan Summary for FY02

IVa3A Projected Park/Program Performance Target, end of this fiscal year: 98 Actual Result: By September 30, 2002, 100% of Mount Rushmore National Memorial employee performance agreements are linked to appropriate strategic and annual performance goals and position competencies.

Park or Program Baseline: 98 employees

Comments:

Annual Performance Plan Summary for FY03

IVa3A Projected Park/Program Performance Target, end of this fiscal year: 98 Actual Result: 100% of Mount Rushmore National Memorial employee performance agreements are linked to appropriate strategic and annual performance goals and position competencies.

Park or Program Baseline: 98 employees

Comments:

Annual Performance Plan Summary for FY04

IVa3A Projected Park/Program Performance Target, end of this fiscal year: 98 Actual Result: 100% of Mount Rushmore National Memorial employee performance agreements are linked to appropriate strategic and annual performance goals and position competencies.

Park or Program Baseline: 98 employees

Comments:

Annual Performance Plan Summary for FY05

IVa3A Projected Park/Program Performance Target, end of this fiscal year: 98 Actual Result: 100% of Mount Rushmore National Memorial employee performance agreements are linked to appropriate strategic and annual performance goals and position competencies.

Park or Program Baseline: 98 employees

Comments:

Servicewide Goal ID Number: IVa4 Workforce Diversity Park/Program Goal ID Number: Iva4 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, Increase the servicewide representation of underrepresented groups over the 1999 baseline: IVa4A — by 25% in the 9 targeted occupational series in the permanent workforce; IVa4B — by 25% of women and minorities in the temporary and seasonal workforce; IVa4C — by 10% of individuals with disabilities in the permanent workforce; and IVa4D — by 10% of individuals with disabilities in the seasonal and temporary workforce.

IVa4A Projected Park/Program Performance Target, end of strategic planning period: By September 30, 2005, the number of Mount Rushmore National Memorial permanent positions in targeted occupational series filled by employees from underrepresented groups is increased from the fiscal year 1999 level of 0 to 1.

Park or Program Baseline: 3 targeted permanent positions

IVa4B Projected Park/Program Performance Target, end of strategic planning period: By September 30, 2005, the total number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by women and minorities is increased from the fiscal year 1999 level of 22 to 29 (32% increase).

Park or Program Baseline: 59 temporary/seasonal positions

IVa4C Projected Park/Program Performance Target, end of strategic planning period: By September 30, 2005, the number of Mount Rushmore National Memorial permanent positions filled by employees with targeted disabilities is increased from 1 in fiscal year 1999 to 4 (10% of permanent workforce).

Park or Program Baseline: 40 permanent and term employees

IVa4D Projected Park/Program Performance Target, end of strategic planning period: By September 30, 2005, the number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by employees with targeted disabilities is increased from 0 in fiscal year 1999 to 3 (5% of temporary workforce).

Park or Program Baseline: 59 temporary/seasonal positions

Annual Performance Plan Summary for FY01

IVa4A Projected Park/Program Performance Target, end of this fiscal year: 0 Actual Result: By September 30, 2001, the number of Mount Rushmore National Memorial permanent positions in targeted occupational series filled by employees from underrepresented groups is maintained at the fiscal year 1999 level of 0.

Park or Program Baseline: 3 targeted permanent positions

IVa4B Projected Park/Program Performance Target, end of this fiscal year: 24 Actual Result: By September 30, 2001, the total number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by women and minorities is increased from the fiscal year 1999 level of 22 to 24.

Park or Program Baseline: 59 temporary/seasonal positions

IVa4C Projected Park/Program Performance Target, end of this fiscal year: 1 Actual Result: By September 30, 2001, the number of Mount Rushmore National Memorial permanent positions filled by employees with targeted disabilities is maintained at the fiscal year 1999 level of 1.

Park or Program Baseline: 39 permanent and term employees

IVa4D Projected Park/Program Performance Target, end of this fiscal year: 1 Actual Result: By September 30, 2001, the number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by employees with targeted disabilities is increased from 0 in fiscal year 1999 to 1(2.8% increase).

Park or Program Baseline: 59 temporary/seasonal positions

Comments: Success in these goals may be difficult to measure since status in an underrepresented group is, in many cases, self-reported.

Annual Performance Plan Summary for FY02

IVa4A Projected Park/Program Performance Target, end of this fiscal year: 0 Actual Result: By September 30, 2002, the number of Mount Rushmore National Memorial permanent positions in targeted occupational series filled by employees from underrepresented groups is maintained at the fiscal year 1999 level of 0.

Park or Program Baseline: 3 targeted permanent positions

IVa4B Projected Park/Program Performance Target, end of this fiscal year: 25 Actual Result: By September 30, 2002, the total number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by women and minorities is increased from the FY 1999 level of 22 to 25.

Park or Program Baseline: 59 temporary/seasonal positions

IVa4C Projected Park/Program Performance Target, end of this fiscal year: 2 Actual Result: By September 30, 2002, the number of Mount Rushmore National Memorial permanent positions filled by employees with targeted disabilities is increased from the fiscal year 1999 level of 1 to 2.

Park or Program Baseline: 39 permanent and term employees

IVa4D Projected Park/Program Performance Target, end of this fiscal year: 1 Actual Result: By September 30, 2002, the number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by employees with targeted disabilities is maintained at 1.

Park or Program Baseline: 59 temporary/seasonal positions

Comments: Success in these goals may be difficult to measure since status in an underrepresented group is, in many cases, self-reported.

Annual Performance Plan Summary for FY03

IVa4A Projected Park/Program Performance Target, end of this fiscal year: 1 Actual Result: By September 30, 2003, the number of Mount Rushmore National Memorial permanent positions in targeted occupational series filled by employees from underrepresented groups is increased from the fiscal year 1999 level of 0 to 1.

Park or Program Baseline: 3 targeted permanent positions

IVa4B Projected Park/Program Performance Target, end of this fiscal year: 27 Actual Result: By September 30, 2003, the total number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by women and minorities is increased from the fiscal year 1999 level of 22 to 27.

Park or Program Baseline: 59 temporary/seasonal positions

IVa4C Projected Park/Program Performance Target, end of this fiscal year: 2 Actual Result: By September 30, 2003, the number of Mount Rushmore National Memorial permanent positions filled by employees with targeted disabilities is maintained at 2.

Park or Program Baseline: 39 permanent and term employees

IVa4D Projected Park/Program Performance Target, end of this fiscal year: 2 Actual Result: By September 30, 2003, the number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by employees with targeted disabilities is increased to 2.

Park or Program Baseline: 59 temporary/seasonal positions

Comments: Success in these goals may be difficult to measure since status in an underrepresented group is, in many cases, self-reported.

Annual Performance Plan Summary for FY04

IVa4A Projected Park/Program Performance Target, end of this fiscal year: 1 Actual Result: By September 30, 2004, the number of Mount Rushmore National Memorial permanent positions in targeted occupational series filled by employees from underrepresented groups is maintained at 1.

Park or Program Baseline: 3 targeted permanent positions

IVa4B Projected Park/Program Performance Target, end of this fiscal year: 28 Actual Result: By September 30, 2004, the total number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by women and minorities is increased to 28.

Park or Program Baseline: 59 temporary/seasonal positions

IVa4C Projected Park/Program Performance Target, end of this fiscal year: 3 Actual Result: By September 30, 2004, the number of Mount Rushmore National Memorial permanent positions filled by employees with disabilities is increased to 3.

Park or Program Baseline: 39 permanent and term employees

IVa4D Projected Park/Program Performance Target, end of this fiscal year: 2 Actual Result: By September 30, 2004, the number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by employees with disabilities is maintained at 2.

Park or Program Baseline: 59 temporary/seasonal positions

Comments: Success in these goals may be difficult to measure since status in an underrepresented group is, in many cases self-reported.

Annual Performance Plan Summary for FY05

IVa4A Projected Park/Program Performance Target, end of this fiscal year: 1 Actual Result: By September 30, 2005, the number of Mount Rushmore National Memorial permanent positions in targeted occupational series filled by employees from underrepresented groups is maintained at 1.

Park or Program Baseline: 3 targeted permanent positions

IVa4B Projected Park/Program Performance Target, end of this fiscal year: 29 Actual Result: By September 30, 2005, the total number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by women and minorities is increased to 29

Park or Program Baseline: 59 temporary/seasonal positions

IVa4C Projected Park/Program Performance Target, end of this fiscal year: 4 Actual Result: By September 30, 2005, the number of Mount Rushmore National Memorial permanent positions filled by employees with disabilities is increased to 4.

Park or Program Baseline: 39 permanent and term employees

IVa4D Projected Park/Program Performance Target, end of this fiscal year: 3 Actual Result: By September 30, 2005, the number of Mount Rushmore National Memorial temporary/seasonal positions annually filled by employees with disabilities is increased to 3.

Park or Program Baseline: 59 temporary/seasonal positions

Comments: Success in these goals may be difficult to measure since status in an underrepresented group is, in many cases, self-reported.

Servicewide Goal ID Number: IVa6 Employee Safety Park/Program Goal ID Number: IVa6 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, IVa6A — The NPS employee lost time injury rate will be at or below 5.39 per 200,000 labor hours worked (100 FTE); and IVa6B — the servicewide total number of hours of Continuation of Pay (COP) will be at or below 59,000 hours.

IVa6A Projected Park/Program Performance Target, end of strategic planning period: 3 (Number of lost time injuries. Rate will be automatically calculated and displayed by PMDS) By September 30, 2005, the number of Mount Rushmore National Memorial lost-time injuries is at 3 or less (greater than the FY1992-FY1996 five year annual average of 1.2 – see comments).

Park or Program Baseline: Lost Time Injuries FY ’92 – FY ’96 = 6 total (1.2 avg./year) (Average number of lost time injuries [not rate], FY92 -- FY96. Identify other baseline period if different.)

IVa6B (Continuation of Pay hours will be automatically displayed by PMDS)

Annual Performance Plan Summary for FY01

IVa6A Projected Park/Program Performance Target, end of this fiscal year: 3 Actual Result: (Number of lost time injuries. Rate will be automatically calculated and displayed by PMDS)

Park or Program Baseline: Lost Time Injuries FY ’92 – FY ’96 = 6 total (1.2 Avg.) (Average number of lost time injuries [not rate], FY92 -- FY96. Identify other baseline period if different.)

IVa6B (Continuation of Pay hours will be automatically displayed by PMDS)

Comments: The 5 Year GPRA Baseline rates were taken from information that was available on the SMIS website. Our goal is higher than the baseline due to an increase in the number of FTE’s that are now presently working at MORU.

Annual Performance Plan Summary for FY02

IVa6A Projected Park/Program Performance Target, end of this fiscal year: 3 Actual Result: (Number of lost time injuries. Rate will be automatically calculated and displayed by PMDS)

Park or Program Baseline: Lost Time Injuries FY ’92 – FY ’96 = 6 total) 1.2 Avg. (Average number of lost time injuries [not rate], FY92 -- FY96. Identify other baseline period if different.)

IVa6B (Continuation of Pay hours will be automatically displayed by PMDS)

Comments:

Annual Performance Plan Summary for FY03

IVa6A Projected Park/Program Performance Target, end of this fiscal year: 3 Actual Result: (Number of lost time injuries. Rate will be automatically calculated and displayed by PMDS)

Park or Program Baseline: Lost Time Injuries FY ’92 – FY ’96 = 6 total) 1.2 Avg. (Average number of lost time injuries [not rate], FY92 -- FY96. Identify other baseline period if different.)

IVa6B (Continuation of Pay hours will be automatically displayed by PMDS)

Comments:

Annual Performance Plan Summary for FY04

IVa6A Projected Park/Program Performance Target, end of this fiscal year: 3 Actual Result: (Number of lost time injuries. Rate will be automatically calculated and displayed by PMDS)

Park or Program Baseline: Lost Time Injuries FY ’92 – FY ’96 = 6 total) 1.2 Avg. (Average number of lost time injuries [not rate], FY92 -- FY96. Identify other baseline period if different.)

IVa6B (Continuation of Pay hours will be automatically displayed by PMDS)

Comments:

Annual Performance Plan Summary for FY05

IVa6A Projected Park/Program Performance Target, end of this fiscal year: 3 Actual Result: (Number of lost time injuries. Rate will be automatically calculated and displayed by PMDS)

Park or Program Baseline: Lost Time Injuries FY ’92 – FY ’96 = 6 total) 1.2 Avg. (Average number of lost time injuries [not rate], FY92 -- FY96. Identify other baseline period if different.)

IVa6B (Continuation of Pay hours will be automatically displayed by PMDS)

Comments:

Servicewide Goal ID Number: IVa7 Line Item Construction Park/Program Goal ID Number: IVa7 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, 100% of line-item projects funded by September 30, 1998, and each successive fiscal year, meet 90% of cost, schedule and construction parameters.

IVa7 Projected Park/Program Performance Target, end of strategic planning period: 1 By September 30, 2005, 100% of Mount Rushmore’s line item projects funded by September 30, 1998, and each successive fiscal year, meet 90% of cost, schedule, and construction parameters.

Park or Program Baseline: 1 (Cumulative number of line-item construction projects identified and funded since September, 30, 1998)

Annual Performance Plan Summary for FY01

IVa7 Projected Park/Program Performance Target, end of this fiscal year: 1 Actual Result: By September 30, 2001, 100% of Mount Rushmore’s line item projects funded by September 30, 1998, and each successive fiscal year, meet 90% of cost, schedule, and construction parameters.

Park or Program Baseline: (Cumulative number of line-item construction projects identified and funded since September, 30, 1998)

Comments: Currently, this is the only line item project funded. This goal will be updated for successive years after other projects are funded.

Annual Performance Plan Summary for FY02

IVa7 Projected Park/Program Performance Target, end of this fiscal year: Actual Result: (Number of line-item construction projects identified and funded by September 30, 1998, and each successive fiscal year, that meet 90% of cost, schedule, and project parameters in each project agreement or comparable document.)

Park or Program Baseline: (Cumulative number of line-item construction projects identified and funded since September, 30, 1998)

Comments:

Annual Performance Plan Summary for FY03

IVa7 Projected Park/Program Performance Target, end of this fiscal year: Actual Result: (Number of line-item construction projects identified and funded by September 30, 1998, and each successive fiscal year, that meet 90% of cost, schedule, and project parameters in each project agreement or comparable document.)

Park or Program Baseline: (Cumulative number of line-item construction projects identified and funded since September, 30, 1998)

Comments:

Annual Performance Plan Summary for FY04

IVa7 Projected Park/Program Performance Target, end of this fiscal year: Actual Result: (Number of line-item construction projects identified and funded by September 30, 1998, and each successive fiscal year, that meet 90% of cost, schedule, and project parameters in each project agreement or comparable document.)

Park or Program Baseline: (Cumulative number of line-item construction projects identified and funded since September, 30, 1998)

Comments:

Annual Performance Plan Summary for FY05

IVa7 Projected Park/Program Performance Target, end of this fiscal year: Actual Result: (Number of line-item construction projects identified and funded by September 30, 1998, and each successive fiscal year, that meet 90% of cost, schedule, and project parameters in each project agreement or comparable document.)

Park or Program Baseline: (Cumulative number of line-item construction projects identified and funded since September, 30, 1998)

Comments:

Goal Category IV

Multi-year Worksheet

Park/Program Name: MOUNT RUSHMORE NMEM

Park/Program Org Code:	1500                     			            	Date Prepared:  April 7, 2000

Servicewide Goal ID Number: IVb1 Volunteer Hours Park/Program Goal ID Number: IVb1 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, increase by 44.7% the number of volunteer hours [from 3.8 million hours in 1997 to 5.5 million hours].

IVb1 Projected Park/Program Performance Target, end of strategic planning period: By September 30, 2005, the number of Mount Rushmore National Memorial volunteer hours is increased from 1500 hours in FY 1998 to 2000 hours (33% increase).

Park or Program Baseline: 1500 (Number of hours contributed by park or program volunteers in FY97. If different baseline is used, please specify.)

Annual Performance Plan Summary for FY01

IVb1 Projected Park/Program Performance Target, end of this fiscal year: 1600 Actual Result: By September 30, 2001, the number of Mount Rushmore National Memorial volunteer hours is increased from 1500 hours in FY 1998 to 1600 hours.

Park or Program Baseline: 1500

Comments: Baseline data is from FY 1998; FY1997 numbers were skewed by an unusually large work group.

Annual Performance Plan Summary for FY02

IVb1 Projected Park/Program Performance Target, end of this fiscal year: 1700 Actual Result: By September 30, 2002, the number of Mount Rushmore National Memorial volunteer hours is increased from 1500 hours in FY 1998 to 1700 hours

Park or Program Baseline: 1500

Comments:

Annual Performance Plan Summary for FY03

IVb1 Projected Park/Program Performance Target, end of this fiscal year: 1800 Actual Result: By September 30, 2003, the number of Mount Rushmore National Memorial volunteer hours is increased from 1500 hours in FY 1998 to 1800 hours

Park or Program Baseline: 1500

Comments:

Annual Performance Plan Summary for FY04

IVb1 Projected Park/Program Performance Target, end of this fiscal year: 1900 Actual Result: By September 30, 2004, the number of Mount Rushmore National Memorial volunteer hours is increased from 1500 hours in FY 1998 to 1900 hours

Park or Program Baseline: 1500

Comments:

Annual Performance Plan Summary for FY05

IVb1 Projected Park/Program Performance Target, end of this fiscal year: 2000 Actual Result: By September 30, 2005, the number of Mount Rushmore National Memorial volunteer hours is increased from 1500 hours in FY 1998 to 2000 hours

Park or Program Baseline: 1500

Comments:

Servicewide Goal ID Number: IVb2 Donations and Grants Park/Program Goal ID Number: Ivb2 NPS Servicewide Goal Description (Mission or Long-term Goal text): By September 30, 2005, IVb2A — Cash donations are increased by 3.6% [from $14,476,000 in 1998 to $15,000,000]; IVb2B — Value of donations, grants, and services from Friends Groups and other organizations is increased to $50,000,000; and IVb2C — Value of donations, grants, and services from Cooperating Associations is increased by 35% [from $19,000,000 in 1997 to $25,600,000].

Annual Performance Plan Summary for FY01

IVb2A Projected Park/Program Performance Target, end of this fiscal year: 5280 Actual Result: By September 30, 2001, cash donations to Mount Rushmore National Memorial are maintained at the 1998 level of $5,280.

Park or Program Baseline: 5,280

IVb2B Projected Park/Program Performance Target, end of this fiscal year: 90,000 Actual Result: By September 30, 2001, the cash value of in-kind donations, grants, and services provided Mount Rushmore National Memorial by the Mount Rushmore National Memorial Society and other organizations is increased from $82,824 in FY 1998 to $90,000 (8.7% increase).

Park or Program Baseline: 82,824

IVb2C Projected Park/Program Performance Target, end of this fiscal year: 92,000 Actual Result: By September 30, 2001, the value of donations, grants and services received from the Mount Rushmore History Association is increased from $90,000 in fy1997 to $92,000.

Park or Program Baseline: 90,000

Comments:

Annual Performance Plan Summary for FY02

IVb2A Projected Park/Program Performance Target, end of this fiscal year: 5280 Actual Result: By September 30, 2002, cash donations to Mount Rushmore National Memorial are maintained at the 1998 level of 5,280.

Park or Program Baseline: $5,280

IVb2B Projected Park/Program Performance Target, end of this fiscal year: 100,000 Actual Result: By September 30, 2002, the cash value of in-kind donations, grants, and services provided Mount Rushmore National Memorial by the Mount Rushmore National Memorial Society and other organizations is increased from $82,824 in FY 1998 to $100,000 (20.7% increase).

Park or Program Baseline: $82,824

IVb2C Projected Park/Program Performance Target, end of this fiscal year: 94,000 Actual Result: By September 30, 2002, the value of donations, grants and services received from the Mount Rushmore History Association is increased from $90,000 IN FY1997 to $94,000.

Park or Program Baseline: 90,000

Comments:

Annual Performance Plan Summary for FY03

IVb2A Projected Park/Program Performance Target, end of this fiscal year: 5280 Actual Result: By September 30, 2003, cash donations to Mount Rushmore National Memorial are maintained at the 1998 level of $5,280.

Park or Program Baseline: 5,280

IVb2B Projected Park/Program Performance Target, end of this fiscal year: 110,000 Actual Result: By September 30, 2003, the cash value of in-kind donations, grants, and services provided Mount Rushmore National Memorial by the Mount Rushmore National Memorial Society and other organizations is increased from $82,824 in FY 1998 to $110,000 (32.8% increase).

Park or Program Baseline: $82,824

IVb2C Projected Park/Program Performance Target, end of this fiscal year: 96,000 Actual Result: By September 30, 2003, the value of donations, grants and services received from the Mount Rushmore History Association is increased from $90,000 in FY1997to $96,000.

Park or Program Baseline: 90,000

Comments:

Annual Performance Plan Summary for FY04

IVb2A Projected Park/Program Performance Target, end of this fiscal year: 5280 Actual Result: By September 30, 2004, cash donations to Mount Rushmore National Memorial are maintained at the 1998 level of $5,280.

Park or Program Baseline: 5,280

IVb2B Projected Park/Program Performance Target, end of this fiscal year: 115,000 Actual Result: By September 30, 2004, the cash value of in-kind donations, grants, and services provided Mount Rushmore National Memorial by the Mount Rushmore National Memorial Society and other organizations is increased from $82,824 in FY 1998 to $115,000 (38.8% increase).

Park or Program Baseline: 82,824

IVb2C Projected Park/Program Performance Target, end of this fiscal year: 98,000 Actual Result: By September 30, 2004, the value of donations, grants and services received from the Mount Rushmore History Association is increased from $90,000 in FY1997 to $98,000.).

Park or Program Baseline: 90,000

Comments:

Annual Performance Plan Summary for FY05

IVb2A Projected Park/Program Performance Target, end of this fiscal year: 5280 Actual Result: By September 30, 2005, cash donations to Mount Rushmore National Memorial are maintained at the 1998 level of $5,280.

Park or Program Baseline: 5,280

IVb2B Projected Park/Program Performance Target, end of this fiscal year: 120,000 Actual Result: By September 30, 2005, the cash value of in-kind donations, grants, and services provided Mount Rushmore National Memorial by the Mount Rushmore National Memorial Society and other organizations is increased from $82,824 in FY 1998 to $120,000 (45% increase).

Park or Program Baseline: 82,824

IVb2C Projected Park/Program Performance Target, end of this fiscal year: 100,000 Actual Result: By September 30, 2005, the value of donations, grants and services received from the Mount Rushmore History Association is increased from $90,000 to $100,000.

Park or Program Baseline: 90,000

Comments: