BASELINE REVIEW HANDBOOK

April 2004

U.S. Department of Energy

National Nuclear Security Administration Service Center

Environmental Programs Department

CONTENTS

PREFACE	iv

ACRONYMS	v

1.0	Purpose	1

2.0	Defining Baseline Reviews	2

2.1	What is a Baseline?	2

2.2	What Project Reviews are Conducted?	2

2.3	When Are Baseline Reviews Conducted?	3

2.4	What Do Baseline Reviews Determine?	3

2.5	Can More Than One Review Occur Simultaneously?	3

2.6	Who Reviews Baselines?	3

2.7	Where Do Baseline Reviews Occur?	3

3.0	Baseline Review Preparation	5

3.1	Select Review Team	5

3.2	Assign Review Team Responsibilities	5

3.2.1	Team Lead Responsibilities	5

3.2.2	Team member responsibilities	6

3.3	Conduct/Attend Kickoff Meeting	6

3.4	Distribute Review Tools	7

3.4.1	Requirements and Guidance Documents	7

3.4.2	EPD Baseline Review Checklist	7

3.4.3	EPD Baseline Review Questionnaire	8

3.4.4	EPD Baseline Review Comments and Findings Form	9

3.5	Establish Review Schedule	11

3.6	Review Preliminary Baseline Documentation	11

4.0	Baseline Review	12

4.1	Contractor Baseline Documentation	12

4.2	Other Project Documents	13

5.0	Review Examples – What to Look For	14

5.1	Schedule Review Example	14

5.1.1	Schedule Baseline Review Preparation Activities	14

5.1.2	Schedule Baseline Review Activities	15

5.2	Regulatory Review	19

5.2.1	Regulatory Baseline Review Preparation Activities	19

5.2.2	Regulatory Baseline Review Activities	21

5.3	Project Control Review	22

5.3.1	Project Control Baseline Review Preparation Activities	23

5.3.2	Project Control Baseline Review Activities	23

5.4	Cost Estimate Review	25

5.4.1	Cost Estimate Review Preparation Activities	25

5.4.2	Cost Estimate Baseline Review Activities	27

Appendix A:  EPD Baseline Review Checklist	32

Appendix B:  Baseline Review Questionaire	38

Appendix C:  Glossary	42

Appendix D:  References and Recommended Reading	46

##### Figures and Tables

Figure 1:  EPD Handbooks	iv

Figure 2: EPD Baseline Review Checklist Excerpt	8

Figure 3: EPD Baseline Review Questionnaire for Contractor (Page 1)	9

Figure 4: Baseline Review Comments and Findings Form	10

Table 1: Example Baseline Review Schedule	11

Figure 5. Gantt Chart Example	14

Figure 6. Report Example	15

Table 2. Example Regulatory Requirements	20

Table 3. Example Regulatory Impacts	21

PREFACE

The National Nuclear Security Administration (NNSA) Service Center (SC) Environmental Programs Department (EPD) provides handbooks listed in Figure 1 for supplementing U.S. Department of Energy (DOE) Order 413.3, Program and Project Management for the Acquisition of Capital Assets, and DOE Manual 413.3-1, Program and Project Management Manual (March, 2003). NNSA SC EPD developed these handbooks to provide guidance for the following DOE sites:

| Energy Technology Engineering Center (ETEC) General Atomics (GA) General Electric Vallecitos (GE) Inhalation Toxicology Laboratory (ITL) | Laboratory for Energy-Related Health Research (LEHR) Lawrence Berkeley National Laboratory (LBNL) Stanford Linear Accelerator Center (SLAC) |
| --- | --- |

This Baseline Review Handbook provides a primer on reviewing project baselines. In addition, the handbooks briefly described in Figure 1 provide guidance to Federal and contractor personnel with NNSA SC project management responsibilities. They describe project management planning, budgeting, executing, and reporting processes and processes associated with baseline reviews, cost estimating, project control systems, decontamination and decommissioning, long-term environmental stewardship, and value engineering. EPD personnel with project management responsibilities maintain these documents. Copies are available through EPD and at http://www.doeal.gov/erd/policy_and_guidance.htm.

Figure 1:  EPD Handbooks

ACRONYMS

ABC	activity-based cost

BPR	Baseline Performance Report

BCP	baseline change proposal

BCWS	budgeted cost of work scheduled

BOE	bases of estimate

BRMD	Budget Resources and Management Division

CCB	change control board

CD	critical decision

DOE	U.S. Department of Energy

EM	DOE Office of Environmental Management

EPD	Environmental Programs Department

ER	Environmental Restoration

ERD	Environmental Restoration Division

ETEC	Energy Technology Engineering Center

EVMS	Earned Value Management System

FPD	Federal Project Director

FY	fiscal year

GA	General Atomics

GE	General Electric Vallecitos

GFSI	Government Furnished Services and Items

Handbook	Baseline Review Handbook

HQ	DOE Headquarters

H&S	Health and Safety

ICE	Independent Cost Estimate

ICER	Independent Cost Estimate Review

IPABS	Integrated Planning, Accountability, and Budgeting System

IPABS-IS	IPABS-Information System

LBNL	Lawrence Berkeley National Laboratory

LEHR	Laboratory for Energy-Related Health Research

LTES	long-term environmental stewardship

Manual 	DOE Manual 413.3-1, Program and Project Management Manual, March, 2003

M&O	management and operating contractor

NNSA	National Nuclear Security Administration

OECM	Office of Engineering and Construction Management

PAD	Program Assumptions Document

PCS	project control system

PCSD	Project Control System Description

PEM	project execution module

PMB	performance measurement baseline

PMP	Performance Management Plan

POC	point of contact

RMP	Risk Management Plan

SC	Service Center

SLAC	Stanford Linear Accelerator Center

WBS	work breakdown structure

WM	Waste Management

WMD	Waste Management Division

# Purpose

The National Nuclear Security Administration (NNSA) Service Center (SC) Environmental Programs Department (EPD) Baseline Review Handbook (Handbook) is a reference for EPD personnel reviewing baselines developed by management and operating (M&O) contractors working on Office of Environmental Management (EM) funded projects. The Handbook is a quick reference of the why’s, when’s, where’s, and how’s. Examples aid the reader in understanding the material. More detailed information on baseline development, baseline components, definitions, and other project management material is contained in the EPD Project Control Handbook (April, 2004), DOE Manual 413.3-1, Program and Project Management Manual, March, 2003 (Manual), and DOE Project Management Practices, October, 2000, (Practices).

NOTES:

This handbook does not define terms that are included in the referenced documents above.

The term contractor as used in this document includes management and operating (M&O) contractors working on the Office of Environmental Management (EM) funded projects as listed in the preface.

# Defining Baseline Reviews

These sections answer basic questions concerning baseline reviews.

## What is a Baseline?

| Conceptually, baselines contain all scope, schedule, and cost documentation necessary to complete projects. Practically, the baseline consists of the various baseline documents describing scope, schedule, and cost. |  |
| --- | --- |

## What Project Reviews are Conducted?

Both the Manual and Practices describe various Office of Engineering and Construction Management (OECM) – directed reviews. EM also directs EPD to conduct reviews. Whether directed by OECM or EM, review objectives include:

Independent baseline validations are conducted following lifecycle baseline preparation by a team outside the project organization. Independent validations “prove that it (the baseline) is defensible relative to scope, schedule, and cost.” Baselines “do not generally require re-validation if changes are managed through a rigorous change control process.”

Independent reviews are conducted by outside agencies or by DOE to “verify the project’s mission, organization, development, processes, baselines, and progress.” Reviewers must not be project proponents.

EPD conducts annual baseline reviews, rather than validations. Reviews focus on baseline integrity in terms of scope, schedule, and cost. More or less emphasis on these baseline elements depends on reviewers.

## When Are Baseline Reviews Conducted?

Contractors prepare initial baselines or revise existing baselines, depending on project maturity. This document describes typical review activities for projects that are at Critical Design (CD-3), but before CD-4. Typically, reviews are conducted in the 4th quarter of the fiscal year, enabling contractors to make necessary adjustments prior to a new fiscal year. It is important for contractors to begin reporting against approved baselines when new fiscal year work begins.

## What Do Baseline Reviews Determine?

Baseline reviews determine baseline adequacy. Review teams comprised of an appropriate mix of experts must carefully review and evaluate baseline documentation, make inquiries when data gaps exist, and interview contractor staff (Section 3.1).

## Can More Than One Review Occur Simultaneously?

EM or other DOE/NNSA groups and EPD may perform reviews at the same time either as two teams, each with a different focus, or one combined team. Concurrent reviews involve significantly more reviewer coordination. Concurrent reviews are more disruptive to contractor work schedules because contractors must respond to more reviewers.

## Who Reviews Baselines?

Senior and junior Federal and contractor staff that are knowledgeable about project scope, schedule, and cost development, maintenance, and change control review baselines. Reviewers with diverse experience are selected from EM, EPD, NNSA SC, and site offices. Team selection is described in Section 3.1.

## Where Do Baseline Reviews Occur?

Baseline reviews usually are performed at the contractor’s facility (onsite review). Ideally, an onsite review team room is provided, enabling the team to freely discuss comments and concerns and to share materials and review documents. Contractor staff interviews also are conducted in the team room unless the contractor designates a separate location. Onsite reviews, especially at larger sites, are more practical than offsite reviews, for interviews with contractor staff and because staff can continue work when not attending daily out-briefings or addressing questions.

Reviews may be conducted offsite, at the SC or at the DOE Energy Training Center in Albuquerque, NM for contractors located near the SC or for smaller sites. Regardless of review location, review teams should cause the least possible impact to contractor work during reviews.

# Baseline Review Preparation

Baseline review preparation includes these steps:

## Select Review Team

EPD management selects a senior staff member to lead baseline reviews. The team lead selects the team members unless a higher authority requests specific individuals. Although there is no strict team size requirement, the standard is four to eight individuals, depending on the project scope complexity, risks, and costs. The team lead ensures appropriate expert representation from among the following areas:

Team members (reviewers, including the team lead) may be assigned to review more than one area (i.e., schedule and project controls). Similarly, large review teams may utilize more than one person per area. Team members have specific focus areas, but may contribute to any part of the baseline review. However, tight schedules usually restrict team members to reviewing assigned areas only.

## Assign Review Team Responsibilities

### Team Lead Responsibilities

Team leaders are responsible for logistics such as:

Choosing and assigning team members.

Understanding baseline review scope, risks, and issues and communicating information to the team.

Conducting a kickoff meeting.

Developing review roles and responsibilities.

Establishing priorities.

Developing the review schedule.

Providing travel information including travel dates, suggested airline, flight times, hotel accommodations, and other related information.

Acting as the point of contact (POC) between EPD (and HQ, if involved) management and the contractor.

Team leaders must also address team and contractor questions, coordinate meetings and interviews with contractor staff, including information requests, and provide contractor project managers verbal status reports, as necessary. Status reports are often provided each afternoon.

### Team member responsibilities

Team member responsibilities include maintaining objective and professional standards, staying on schedule, and understanding the following before beginning the onsite review:

The review focus (i.e., is schedule or cost the primary concern?).

Relevant political issues.

Review forms and the review package.

DOE Order 413.3 and DOE Manual 413.3-1.

Project scope.

## Conduct/Attend Kickoff Meeting

Baseline review team kickoff meetings are called and conducted by team leads to plan and discuss review scope, high visibility and high-risk subprojects, and sensitive contractor or EM issues. Topics discussed at the kickoff meeting include but are not limited to:

Review scope

Overall review strategies

Issues

Known baseline weaknesses and strengths.

Team roles and responsibilities.

Chains of command.

Review schedule.

Difference between findings and observations.

Consensus on methodology for collecting and consolidating findings and observations.

Logistics and travel information.

Availability of preliminary contractor baseline.

Availability of other project related documentation.

Prior year baseline review findings and contractor responses.

## Distribute Review Tools

Team leads distribute tools to review teams for facilitating the review and assembling review comments, including guidance documents, checklists, questionnaires, and forms described in the following sections

### Requirements and Guidance Documents

Reviewers should have access to and familiarity with the most recent versions of applicable DOE Orders, Manuals, and Practices.

http://www.directives.doe.gov/ provides the Manual and Order

http://oecm.energy.gov/project_reviews/reviews_index.html provides the Practices

Requirements from the guidance documents, directives, and current EM memos should be referenced, reinforcing observations and findings. For example, in fiscal year 2003, the EM-6 National Focus Project produced specific guidance for EPD, the site offices, and contractors.

### EPD Baseline Review Checklist

The EPD Baseline Review Checklist provides a comprehensive requirements list. Reviewers individually complete the checklist, including notes justifying responses. Teams may add checklist items associated with EM guidance or emergent information or issues. Checklists are not generally collected by the team lead because deficiencies are documented as findings or observations. A partial checklist is shown in Figure 2; the complete checklist is provided in Appendix A.

Figure 2: EPD Baseline Review Checklist Excerpt

### EPD Baseline Review Questionnaire

Team leads transmit baseline review questionnaires to contractors, to be completed and returned with preliminary baseline documentation no later than one week prior to onsite reviews. Review questionnaires provide contractors and project teams a record of areas requiring additional effort for meeting requirements as well as project strengths. Teams can modify the questionnaire to respond to current (new) guidance or site-specific conditions. The first page of the questionnaire is shown in Figure 3; Appendix B contains the entire questionnaire.

Figure 3: EPD Baseline Review Questionnaire for Contractor (Page 1)

### EPD Baseline Review Comments and Findings Form

Reviewers document findings and observations on the Baseline Review Comments and Findings form, which serves as the formal record of the review (See Figure 4). Reviewers document findings and observations as they are found in the pre-review or onsite review, clearly identifying findings, observations, information sources, and recommendations for addressing findings or observations using the following definitions:

Finding: A specific failure to meet requirements or established programmatic criteria. This must be documented on the review form, citing the specific requirement not met.

Observation: An opinion regarding a satisfactory or unsatisfactory condition that does not violate a specific requirement or criteria. This includes recognized professional practices that may have been observed, and which the DOE and contractors are not required to implement, but may benefit the overall project. Observations should include a recommendation for improvement.

Contractors respond to recommendations and provide timeframes for implementation. DOE reviews the contractor responses and approaches to issue resolution and ensures implementation before findings are closed.

Figure 4: Baseline Review Comments and Findings Form

Reviewers provide findings and observations electronically and the team lead assigns one member to consolidate findings and observations and assemble them into a single file, including author’s names or initials and initial finding/observation numbers. Contributing authors should review the combined findings to ensure correct documentation.

Baseline Review Comments and Findings form field descriptions are:

Reviewer:  Name or initials of reviewer. When duplicate findings are consolidated, all reviewer names or initials should be included.

Organization:  The reviewer’s employer.

Area of Concern:  Examples include technical scope, cost, project controls, schedule, and program management. May be more specific, such as “technical scope-well sampling analysis”.

Review Team Finding/Observation No.: Consecutive numbers assigned to consolidated findings and observations. This number is different than the Reviewer Finding/Observation No. because:

More than one reviewer could have the same finding, thereby requiring consolidation on one form. In this case, there will be more than one Reviewer Finding/Observation No.

Consecutive numbering permits easier reference by team and contractor.

Reviewer Finding/Observation No.:  Reviewer comments numbered consecutively and preceded by initials (e.g. VRW-01)

Specific Baseline Reference:  The specific place in the baseline document, if applicable, that resulted in the comment - (e.g. Page 3, Section X of the Project Execution Plan (PEP)).

Finding:  Check if comment is a finding.

Observation:  Check if comment is an observation.

Finding/Observation:  One sentence concisely stating the comment followed by additional clarifying narrative. Offer recommendations for resolving the issues and provide additional information as needed for supporting the finding such as technical references, DOE orders or guidance, or regulatory requirements.

Contractor Response:  The contractor describes actions to resolve the finding or observation.

## Establish Review Schedule

A review schedule is prepared by the team lead before the kickoff meeting or developed with team input during the meeting. The schedule may be a Gantt chart with logically tied activities or as simple as the table below. Review schedule information should be imparted to the contractor as soon as possible.

| Activity | Ideal Timing |
| --- | --- |
| Team lead and contractor agree to review schedule. | Four weeks before onsite review. |
| Team lead submits questionnaire and checklist to contractor. | Three weeks before onsite review. |
| Contractor returns questionnaire and submits (electronically or hard copy) preliminary set of baseline documentation to review team. | Two to three weeks before review but no later than one week prior to onsite review. |
| Team reviews preliminary documentation at the Service Center or Energy Training Center. The team lead verbally provides the contractor project manager any major issues, concerns, or major findings prior to the onsite review. | A few days to two weeks before onsite review. |
| Team lead provides an “in-brief” to the contractor staff regarding agenda, schedule, and focus areas. | First day of the onsite review |
| The contractor project manager or designee provides a project and baseline overview for the review team. | First day of the onsite review |
| The review team begins the formal review of documentation. | First or second day of onsite review. |
| Team lead presents daily findings and observations to contractor. | Each day of onsite review. |
| Team provides final out brief and draft findings. | Last day of onsite review. |
| Team submits final findings. | One week after onsite review. |
| Contractor responds to findings. | Two weeks after onsite review. |
| Contractor adjusts baseline per findings. | Three weeks after onsite review. |
| Team lead closes out baseline review. | Four weeks after onsite review. |

Table 1: Example Baseline Review Schedule

## Review Preliminary Baseline Documentation

Much of the baseline documentation received prior to onsite reviews is preliminary and incomplete. Reviewers must be aware that documents received prior to onsite review may undergo revision and reconcile deficiencies found during preliminary review with updated versions provided at the onsite review. Staff interviews also result in additional information and reports or plans received during the onsite review. Review methods described in Section 5 are the same regardless of when the baseline materials are received.

# Baseline Review

After review preparations are completed, the formal review begins. Although each team lead has a slightly different baseline review style, EPD teams successfully conduct reviews according to the schedule described in Table 1. Aggressive schedules require review teams to provide contractors daily findings, maintain communication throughout the review, reducing surprises, and enabling contractors to respond to comments before the formal findings package is completed.

How do I get started? This may be the most important question a new reviewer asks. However, the answer is not straightforward because there is no prescription for getting started. Reviewers should have a clear understanding of the review focus before beginning the review (i.e., regulatory issues, costs, schedule, or earned value). Factors influencing review focus and start-up are listed below. Inexperienced team members should aggressively question more experienced team members. . Team leads are responsible for ensuring access to all review materials in a comfortable setting.

Regardless of individual focus or expertise, team members should read the high level documents such as the PEP, PAD, Risk Management Plan (RMP), and work breakdown structure (WBS). Additionally, baseline change proposals documenting changes since the last approved baseline should be read by the entire team. These documents provide excellent project overview.

## Contractor Baseline Documentation

Baseline reviews focus on baseline documentation provided by contractors. As indicated in Section 3, some team leads request a preliminary set of baseline documents at least one week ahead of the actual onsite review, provided in hard copy or electronically. This enables team members to understand the project and the baseline and/or to provide preliminary findings to the contractor before the in-depth onsite review. This provides contractors opportunity to make some changes and adjustments before the team arrives for the onsite review.

Whether or not preliminary documentation is requested, contractors provide the review team (depending on team size) at least three sets of baseline documentation. This allows team members to review documents simultaneously and saves time making copies. The team lead also requests available electronic copies. Teams should be cognizant of reviewing final documentation provided at the onsite review because material is likely to be revised.

Baseline documentation must be a stand-alone and complete package, permitting independent team assessment of technical scope, schedule, and cost adequacy without additional information requested. Lack of required documentation can prevent review teams from preparing independent cost estimates or approving baselines, even if the missing information is available upon request.

Baseline documentation components are listed below. Section 5 provides review examples of some specific components.

## Other Project Documents

Other project documents include materials that reviewers may obtain or request prior to or during onsite review for additional information and clarification, such as:

Background Project Information – Useful to teams or team members not familiar with the project or current project status or issues, e.g., Community Relation Plan or Stakeholder Plan, Health and Safety Plan, or Site-wide Environmental Impact).

IPABS-IS Data - Data extraction from IPABS-IS provides additional information on the project scope and status. The budgeted cost of work scheduled (BCWS) can be compared to the proposed baseline. If reviewers detect inconsistencies, they can be noted on the Baseline Review Comments and Findings form.

Previous Baseline Review Findings – Copies of findings, if a contractor’s baseline was reviewed within a year or two of the current review. The team should verify baseline adjustments correcting findings not indicated as closed.

# Review Examples – What to Look For

Example strategies for reviewing scheduling, regulatory, project control, and cost estimating are presented below. These examples are not intended to represent the only methods for reviewing baselines, but demonstrate systematic approaches to different review components. Review approaches are useful to inexperienced reviews and contractors for understanding how baselines are evaluated.

## Schedule Review Example

One team member is assigned primary responsibility for reviewing the schedule and providing the most scrutiny. However, other team members review certain aspects of the schedule, such as regulatory or technical milestones and project control elements such as methods for measuring progress, collecting actuals, posting earned value, and application consistency. Reviewer overlap provides a useful redundancy and produces better schedule examination.

Schedule reviewers should have general knowledge of scheduling concepts, such as logical relationships, total float, and critical path. However, reviewers do not need to be knowledgeable in the contractor’s scheduling software. Schedule examples in this handbook were produced with Primavera 3.1, but Microsoft Project and Primavera 3E reports are similar in appearance.

### Schedule Baseline Review Preparation Activities

A cursory review of the schedule provided with baseline documentation, including a Gantt chart (Figure 5) is the first step in reviewing a schedule, The hard copy format or layout may not show total float or it may be summarized to a non-useful level. Therefore, electronic copies or other non-Gantt report layouts such as tabular reports (Figure 6) are requested of contractors to enable a thorough review. Logic is much easier to review from electronic schedule files than from paper copies. If a contractor is unable to provide an electronic copy or a reviewer is not familiar with the software, the contractor may be asked to navigate through the schedule at the contractor’s computer.

Figure 5. Gantt Chart Example

Figure 6. Report Example

### Schedule Baseline Review Activities

Typical schedule review items are described below. Reviewers determine the review order.

|  | Reviewers must verify that the schedule covers the entire project lifecycle, including all work and associated resources necessary for meeting the project end state and for environmental restoration projects, planning for transition to the landlord. Schedules do not typically include the entire project history, but depending on project type, as much historical information as possible is included. For projects recently compliant with lifecycle, critical path scheduling, only one year of history may be provided. Findings are written for schedules not including all scope or history if previously compliant. |
| --- | --- |
| WBS | The WBS contained in the schedule should exactly match the WBS presented throughout the baseline documentation. Discrepancies are reported as findings. Activity and milestone levels should be clear to reviewers. To the extent possible, all activities and milestones should be at the same WBS level, as shown in the following example: |
| WBS Level 7 (1.3.1.3.1A.06.08) FY03 Activities XX Some 1.3.1.3.1A.06.08.15 activities are at level 7 and some are at level 8 WBS Level 8 (1.3.1.3.1A.06.08.15) FY04, FY05, FY06 Activities XX |
| Total Float | The following total float scenarios may indicate schedule problems: |
| High, positive total float | Positive float should not be very high (e.g., >180 days), depending on the schedule duration (a 10-year project could have higher values than a shorter schedule). Very high float indicates weak logic or activities without successors or predecessors. For instance, the following example indicates that scheduled completion for purchasing WIPP containers is September 2005 and that the project end date will not slip if the activity is not completed until April 2008. This is probably not a true statement. Activity ID Activity description Original duration Early start Early finish Total float Late start Late finish HR0402EE12 WIPP Canister Procurement 246 01OCT04 30SEP05 612 05APR07 03APR08 |
| Negative total float | Float is not usually negative. Negative float indicates that the project end date cannot be met. The following example shows an early finish date that is 3 days later than the late finish date. This means that the project end date will slip by three days. Activity ID Activity description Original duration Early start Early finish Total float Late start Late finish BD12302D11 Shipment and/or disposal of MLLW 25 01SEP05 05OCT05 -3 29AUG05 30SEP05 |
| Zero total float | Zero total float means that the activity is on the critical path and any slip to the activity will cause a corresponding slip to the project end date (See below). While it is acceptable to have zero float activities, it is not acceptable to have a large percentage of activities with zero float because it indicates a high probability of not finishing the project on time |
| Critical Path | Reviewers should address the following questions about critical path: Does a critical path exist? How was the critical path defined? Is there more than one critical path? Is the critical path credible? Criteria defining the critical path should be documented in either the PEP or PAD and evident in the hard copy or electronic copy of the schedule. Lack of a critical path is cause for a finding. Reviewers should be able to recognize one or more critical paths. It is legitimate to have more than one credible critical path in the schedule. There are many ways to indicate critical paths on schedules, but the most common format view is a Gantt chart with red bars. The format does not define the critical path, however. Critical paths are defined by the longest schedule path or number of total float days. Critical path is closely related to total float. Total float is one way of defining the critical path and should be analyzed in terms of whether or not activities with zero or very low total float should actually appear on the critical path. To determine if critical paths are credible, reviewers should ensure that level of effort work, which typically has 0 total float, is not on the critical path. Level of effort activities should be filtered from the critical path using software features because slipping a level of effort activity by one day will not cause a day for day slip in the project end date. Discrete activities on the critical path should be analyzed for potential impact on the project end date. Schedule logic should be re-evaluated if activities that do not impact the end date are on the critical path merely because they have zero days of total float. Conversely, logic should be reviewed if critical paths lack activities that would impact the project end date if delayed. Review findings can result from both scenarios. Reviewers should consider the percentage of the schedule on the critical path. If 30 percent or more of project activities appear on one or more critical paths, a schedule logic problem is indicated. If the logic is correct, it is likely that the project end date will slip. |
| Logic |  |
| Work Sequence | Schedules should be reviewed for sound logic. That is, work sequence should progress according to work plans (activity X must occur before activity Y). Reviewer should evaluate the quantity of work planned using basic finish to start relationships. Schedules with a majority of finish to start relationships and few others, such as start to start with some lag, may indicate much schedule contingency because most work is occurring serially and little in parallel. |
| Open Ends | Schedules should not be open-ended, which means that activities should have predecessors and successors (except, of course, the first and last activities in the schedule). Open-ended activities cause unusually high total float numbers and unexpected changes when schedules are updated. High total float numbers indicate high probability that activities are either linked incorrectly or do not have predecessors and successors. |
| Detail Level | Schedule detail should be sufficient for capturing all the work and resources. That is, activities should not include numerous work types; they should be separately broken out. Two examples follow. Inadequate Adequate Characterize groundwater plume Develop characterization plan Receive state approval of plan Prepare drilling subcontractor documents Provide oversight of drilling subcontracts Analyze characterization data Perform project controls Prepare quarterly performance reports Conduct monthly schedule updates Update IPABS-IS monthly |
| Milestones | Reviewers should ensure that regulatory, budget, enforceable agreement, HQ monitored performance measures, and end-state milestones are included in the schedule and TSDs and have consistent titles and dates. |
| Resource Loading |  |
| a. Is the schedule resource loaded? | Reviewers should confirm that activities are resource loaded. Labor and non-labor (e.g., equipment, materials, subcontractor) costs must be included and clearly identified in lifecycle costs. Some contractors, especially for smaller projects, load labor by actual name and labor rate; others use generic labor categories. Generic labor categories (i.e., senior regulatory specialist) provide propriety and flexibility for changing staff. The disadvantage is that actual costs may differ from the average labor rates used. However, this tends to be insignificant on larger projects because higher labor costs in one area are balanced by lower labor costs in others. Either method is satisfactory as long as consistency is applied and project team members understand the system. Resources should include EM, NNSA, and GFSI resources. |
| b. Yearly Cost Profile | Contractors include yearly cost plans generated by scheduling software. Cost plans should include entire project annual profiles and profiles of lower levels of the WBS. If adequate level of detail is not included in baseline documentation, reviewers may request more of the contractor. Yearly profiles should match annual levels in TSDs and other baseline documentation, such as the PEP and include both EM and NNSA costs. |
| c. Do the resources make sense? | Review team cost estimators usually determine plausibility of resources in the schedule (and reflected in the TSDs). However, other team members reviewing schedules should peruse the resources, either in the software or through a software-generated report, for obvious problems. Unusually high unit numbers (hours, for example), rates, or labor categories that do not seem relevant to associated activities indicate potential problems. Resource questions or issues should be discussed among team members, possibly resulting in findings or observations. |
| Government Furnished Services and Items (GFSI) | Reviewers are responsible for ensuring that EPD-provided GFSI activities and milestones are integrated into lifecycle schedules. DOE is responsible for developing GFSI activities, milestones, and required hours for the activities, but contractors must ensure that they are included in schedules and logically tied to contractor activities. Methods developed by DOE and contractors for determining GFSI activity status should be documented in PCSDs. GFSI activities may be included in critical path or paths. |

## Regulatory Review

Baselines must account for regulatory compliance requirements. Section 3.2.6 of the Manual states that project directors must “[e] ensure the design, construction, environmental, safety, health, and quality efforts performed by various contractors are in accordance with the contract, public law, regulations, and Executive Orders.”

Regulatory reviews are important during baseline reviews because schedules can be adversely impacted if regulatory requirements are not anticipated, budgeted for, and met. Typically, a technical member of the review team is responsible for performing a regulatory review of the scope, schedule, and budget.

### Regulatory Baseline Review Preparation Activities

Reviewers should request a list of regulations for which the project routinely complies and verify that activities associated with compliance are included in the TSDs, schedules, and budget. If a list is not available, reviewers must determine probable regulations based on project scope and check for adequate resources to ensure compliance. Table 2 provides examples of scope associated with regulatory requirements:

| If the project activities include . . . | Requirements that may be applicable |
| --- | --- |
| Abandoned waste sites | Comprehensive Environmental Response Compensation, and Liability Act (CERCLA) Superfund Amendments and Reauthorization Act |
| Air emissions | Clean Air Act, National Emission Standards for Hazardous Air Pollutants (NESHAPS) |
| Cultural resources | State Historic Preservation Office |
| Excavation, rock crushing, other earth work | Clean Air Act Mine Safety and Health Administration |
| Federal or contractor staff in offices or in the field | Occupational Safety and Health Act Safe Drinking Water Act |
| Fuel farms, fleet maintenance areas | Oil Pollution Act of 1990 (OPA) |
| Hazardous wastes generated, stored, treated, or disposed as part of project activities | Pollution Prevention Act Resource Conservation and Recovery Act |
| Known or suspect endangered, threatened, or sensitive plant or animal species or habitat | Endangered Species Act (ESA) |
| Proposed new activities or construction | National Environmental Policy Act |
| Radioactive materials or waste | DOE O 435.1, Chg 1 (Order, 08/28/2001, EM) Radioactive Waste Management |
| Stakeholder communities nearby or who have expressed interest in project activities | Emergency Planning & Community Right-To-Know Act |
| Stored chemicals, PCB contamination, transformers | Toxic Substances Control Act |
| Vegetated or infested areas requiring vector control | Federal Insecticide, Fungicide and Rodenticide Act |
| Water discharges, surface water, or ground water | Clean Water Act Safe Drinking Water Act |

Table 2. Example Regulatory Requirements

EM project regulatory issues range from very high-level DOE/Other Federal Agency/State(s) negotiations to routine environmental monitoring. Schedules, costs, and risks associated with regulatory issues should be documented throughout the PEP, RMP, PAD, TSDs, and schedule. Table 3 shows how regulatory issues can impact project performance.

|  | Risk | Assumptions | Cost | Schedule |
| --- | --- | --- | --- | --- |
| High-level DOE/Other Federal Agency/ State(s) negotiations | The RMP should present mitigation measures if negotiations do not favor project cost and schedule. | Assumptions must be realistic. If negotiations have no precedence or high-level champion, assuming success of negotiations may not be realistic. | TSDs should include contractor and GFSI resources for planning meetings, travel, presenting materials, public meetings, etc. | The schedule should reflect a date for finalizing negotiations as a predecessor for activities dependent on negotiations. |
| Routine environmental media monitoring | Routine groundwater, air monitoring, and personnel dosimetry is usually considered low risk. However, mitigation measures for unexpected offsite contamination should be discussed. | Usually it is assumed that new monitoring will not be required and that environmental media beyond the project boundary will not be breached | Typical costs are: - Training monitoring staff - Personnel protective gear - Transportation to monitoring stations - Monitoring equipment, replacement filters - Monitoring-derived waste management | Routine monitoring is required by environmental regulation or site-specific agreements with oversight agencies. The source agreement documents should be compared to the baseline schedule. |

Table 3. Example Regulatory Impacts

### Regulatory Baseline Review Activities

The following describes baseline documents and regulatory activities or information they should contain or describe.

| Schedule | Negotiations within DOE or with other Federal agencies or states and dates by which negotiations must be successfully completed. Activities that cannot proceed without successful negotiations should tie to dates. Reviewers should identify regulatory activities and associated resources in the schedule. These may include periodic air, water, and soil monitoring; regulatory report preparation; and permit applications and renewals. Regulatory activities may be funded under other site-wide programs, but review interviews should confirm this. Regulatory milestones. If the PEP, PAD, or TSDs report permit application(s), the schedule should include a milestone date for receiving the permit and successor activities dependent on permit receipt. If activities subsequent to permit approval are important enough, risk and associated consequences of not receiving permit approval should be documented in the RMP. |
| --- | --- |
| WBS and WBS Dictionary | Regulatory monitoring, high-level negotiations, and other environmental compliance activities (i.e., monitoring, audits, and reporting). |
| Project Execution Plan (PEP) | Project regulatory requirements or other documents containing the information. Outstanding or major regulatory issues, such as lack of national capacity for disposal of certain wastes, disposal moratoria, or transportation limitations. |
| Program Assumptions Document (PAD) | Realistic programmatic regulatory assumptions. PADs typically assume that project performance will not be impacted by new regulations. Regulatory reviewers should be aware of pending legislation or new regulations that contractors should acknowledge in PADs. |
| Task Scope Descriptions (TSDs) | Regulatory compliance may be distributed among TSDs or contained in one TSD (e.g. regulatory compliance task). Either is acceptable, but reviewers must understand how the project manages regulatory compliance. |
| Priority List | Project activities that must be completed for meeting regulatory deadlines. |
| Risk Management Plan (RMP) | Regulatory risk management (risk identification; risk impact analysis and quantification; risk mitigation strategies development; risk monitoring; and risk documentation) process. Specific review areas are: General approach to regulatory requirements identification and compliance. Ability to manage high-risk regulatory negotiations. Ability to avoid fines for lack of regulatory compliance. Typically, an internal auditing process reduces this risk. |
| Metrics | Audits performed in one year for ensuring regulatory requirements are met. |

Below is an example of what to look for when reviewing required air monitoring.

The PEP scope states that excavation or drilling of potentially contaminated soils will occur. Reviewers should identify scope, schedule, and costs associated with site perimeter air monitoring throughout project activities, including:

Reviewing the baseline documentation (PAD, PEP, TSDs) for specific references to air monitoring and description of frequency, number of monitoring stations, types of data collected, and to whom reports are sent. If these cannot be found, the reviewer should ask the project staff how these activities are accounted for.

Verify that the schedule and associated resources reflect the baseline documentation. If air monitoring is performed four times a year throughout project activities, the schedule should include four data collection events per year. Reviewers should verify that resources for collecting data from the air monitoring stations are adequate. For instance, is adequate field staff budgeted if air monitoring station data can be downloaded in half a day by driving the perimeter of the site? Determine that relevant regulatory activities are addressed in the baseline scope, schedule, and budget.

## Project Control Review

The same person usually conducts project schedule and project control reviews of smaller projects since project control elements cross cut all baseline documents. Processes and procedures are documented in the PCSD, but inconsistencies in baseline documentation may indicate larger problems.

### Project Control Baseline Review Preparation Activities

Reviewers should gather and organize baseline documentation listed in Section 5.3.2. Make necessary additional copies of baseline documentation to ensure availability to reviewers.

### Project Control Baseline Review Activities

Baseline elements and documentation should be reviewed for:

| WBS and WBS Dictionary | WBS number and title included to the lowest level. The WBS Dictionary or a thorough description of the work in the TSDs. Consistent WBS title and numbers (PEP, PAD, TSDs, cost plan, RMP, and schedule). |
| --- | --- |
| Project Execution Plan (PEP) | Thorough description of project scope, including work to be completed and accomplishments to date. Realistic project scope, including major issues (regulatory, technical, cost, and schedule). Total project cost (TPC) overview and project level (minimally) yearly cost plan. Metrics (see #10). |
| Responsibility Assignment Matrix (RAM) | Assurance that the cost account manager (CAM) understands his role (by interviewing staff). |
| Program Assumptions Document (PAD) | Programmatic assumptions (technical, regulatory, cost, schedule). Note: WBS specific assumptions are included in TSDs. |
| Task Scope Descriptions (TSDs) | Confirmation that the described scope is the most likely case. Thorough scope description, schedule, and costs at WBS level 8 or 9, or mutually agreed upon level. Annualized cost profiles and TPC. Metrics (see #10), as appropriate. Specific risks (referencing RMP), assumptions, and issues. Bases of Estimate (BOEs). Gantt charts. |
| Priority List | Contractor execution year work priorities identifying discrete units or groupings of activities with associated funding requirements. Priority lists make scope adjustments easier if funding cuts or funding additions occur. |
| Risk Management Plan (RMP) | RMP (or PCSD) risk management process (risk identification; risk impact analysis and quantification; risk mitigation strategies development; risk monitoring; and risk documentation) descriptions, including: General approach to risk management. Roles and responsibilities for performing risk management functions. Risk identification process (i.e., team lead quarterly or annual brainstorming or written input from team leads to project managers) Risk impact analysis and quantification, including tools and methods used for analyzing individual risks. Is expected value or Monte Carlo used? Risk mitigation strategies, including development processes and re-evaluation schedules. Are strategy parameters targeted for different risk types? Is the project team risk adverse? Risk monitoring, including frequency. Risk documentation, including format, frequency, and distribution. Individual Identified Risks Clear and thorough description. Annualized cost impacts and whether values are escalated or not. Schedule impacts, including impact to project end date and regulatory milestones. Technical impacts Date prepared. Date updated. Date resolved or mitigated. Methods used for mitigating risks, especially moderate to high risks. Action plans for handling individual risks. Preparer and responsible individual names and titles, if different. |
| Cost Plans | Annual cost plan and history (total project cost [TPC]). Cost plan totals by WBS matching resource-loaded schedules by year, TSDs, and PEP overall cost plan. Visibility of contingency in the cost plan, if included in the TPC. |
| Contingency | Contingency should be clearly identified on the yearly cost plan if it is in the baseline TPC, either related to identified risks or as a percentage of the baseline. Contingency development methodology should be included in the PCSD or PEP. |
| Metrics | Documentation of metrics reporting and update processes (in the PCSD). Historical and annual projections in the PEP (project level) and TSDs (level at which TSDs are written). Example metrics included in the PEP and TSDs are annualized number of drums shipped to WIPP, number of dispositioned sealed sources, and number of potential release sites submitted to the regulators. Metric reporting by contractors in IPABS-IS and quarterly performance reports. |
| Overhead Rates | Reviewed by the project control person or the Service Center budget organization. Accurate contractor application, since rates are reviewed and validated by outside agencies. Occasionally, contractors receive unanticipated rate increases, which can cause significant changes to yearly cost profiles. |
| Escalation Factors | Rates used, correct application, and rate source (either Office of Management and Budget (OMB)-specified escalation rates or DOE-approved rates). Ensure that escalation is applied to each fiscal year estimates (excluding the execution year) to determine TPC. |
| Acquisition Plan or Procurement Plan | Stand-alone acquisition plans are not necessary for mature EM projects if acquisition plan elements are included in existing baseline documentation, such as the PEP. |
| Project Control System Description (PCSD) | PCSD documentation of project controls implementation. Additionally, interview project control staff on current project control processes and new processes the staff plans to implement (and document in the PCSD). Copies of performance reports submitted to the DOE should be requested to compare with methods described in the PCSD. Specific review elements include: Change control procedures Schedule updates-process and frequency Risk management process reporting frequency, content and format, process, roles and responsibilities (unless documented in the RMP, item # 7). |

## Cost Estimate Review

Cost estimate reviewers should have specific EM experience or be able to work closely with technical team members. For example, a construction estimator may know how to estimate well drilling but lack expertise about analyte testing.

### Cost Estimate Review Preparation Activities

| Initial baseline submittal top-down familiarity review | Become familiar with baseline documentation and organization and identify cost estimate sections. Prioritize the review criteria such as: Determining and reviewing high dollar subprojects comprising the majority of costs, following the Pareto principal/definition that 20 percent of items account for 80 percent of costs. Determining and reviewing subprojects incurring a majority of near-term costs (one to three years). Determining and reviewing high visibility and high-risk subproject cost and schedule impacts. Selection criteria exceptions should be understood prior to selecting and beginning the cost estimate review process. For example: Some high dollar subprojects involve long term, repetitive/level of effort (LOE) cost estimates that may not warrant a focused review. Long-term environmental stewardship (LTES) and many project management or technical support subprojects typically fall in this category. Projects with a TPC or near-term fiscal year cost under an established threshold of ($100K are generally not reviewed in detail. However, projects under the cost threshold sometimes have high visibility or risk associated, thereby justifying in-depth cost analysis. Some subprojects may be exempt from standard cost reviews because they (1) received previous, individual review because of high-risk status or (2) are near completion and have specific approvals for proceeding. |
| --- | --- |
| Compare the summary level current baseline submittal to the prior year(s) baseline | Verify that prior year cost estimate baseline review findings are addressed in the current baseline. New observations or findings should be generated for outstanding issues. Reference the prior year finding number and contractor commitment to address findings. ”Before” (last approved baseline submittal) and “after” (proposed baseline) cost plans for current year, five year window, out-years, and total project at subproject and project levels should be included in documentation, enabling reviewers to see summary level cost differences by comparing cost plans. Review areas include: Significant changes to subproject cost and schedules. Subprojects added after the last baseline approval. Subprojects removed since the last approved baseline. Variance analyses, if submitted. BCP documentation for understanding subproject changes. Detailed backup information supporting baseline changes. |
| Compare the contractor’s baseline documenta-tion to EPD submittal requirements (See Project Control Handbook) | Ensure that cost estimates are prepared at the lowest level of detail commensurate with available scope and schedule information. Note missing baseline cost sections, elements, or components. Note obvious deficiencies in estimate backup documentation, such as: Cost estimates not supported by an activity-based cost (ABC) estimating methodology. Estimates with undocumented, lump sum cost allowances. Check for appropriate cost estimate classification (planning, preliminary, detailed, or government) for tasks and subtasks. Check for appropriate cost estimating methodology (e.g., LOE, parametric, bottoms-up, and estimating model) Note estimates prepared using untraceable, ‘all-inclusive’, composite costs rather than a detailed cost component built from labor hours, labor rates, materials, equipment usage, and contractor mark-ups. For example, cost constituents cannot be identified if a well drilling estimate is simply shown as a lump sum (drill 100 foot well @ $10,000/ea. or drill 100 foot well @ $100/ft.). |
| Establish primary sections of the baseline on which to focus the cost review. | Pre-baseline review efforts enable reviewers to understand the baseline composition and recognize strengths and weaknesses well enough to: Prioritize TSDs requiring review (see Section 5.4.1). Select candidate TSDs for independent check estimates using parametric tools such as the RACER estimating model or a bottoms-up technique. Prepare first-cut parametric estimates for determining basic TSD information deficiencies. Reviewing initial parametric estimate(s) with other team members may result in a clearer understanding and/or provide more comprehensive questions for the contractor. Understand the systematic baseline cost components used in subproject estimates and determine relative importance for reviewing. The following are examples of baseline components that affect baseline cost estimates: Resource tables (provide unit costs and cost allowances for quantity survey application) Escalation rates (including application method) Indirect cost components (e.g., labor burden, G&A, and taxes) and application method Maximize efficiency by allocating review time according to the established priorities. Establish a preliminary plan for completing the review. |
| Prepare an initial list of observations and questions | Initial observations, questions, and requests for additional documentation and supporting documentation may be provided to the contractor before the onsite review, requesting: Response to initial pre-baseline review observations and questions. Deficient or missing baseline documentation. Specific sub-project scope/schedule information necessary for preparing parametric check estimates included in TSDs. For example, design parameters such as well depth, diameter, and material specifications, must be known to estimate sampling well costs. First-cut parametric estimates can be provided to contractors for clarifying potential TSD work scope deficiencies. Scheduled interviews with appropriate estimating points-of contact through the team lead. |

### Cost Estimate Baseline Review Activities

Contractors should present well-organized summary estimate results in baseline documentation. References must be clearly annotated and described in TSDs because estimator notes, quantity survey developments, vendor quotes, and sketches are seldom included in baseline documentation. Complete and concise references permit reviewers to request backup during the onsite review. Regardless of baseline information organization, cost estimates must meet the following minimum criteria:

Traceability. Documents should flow in a bottoms-up and top down manner. TSDs must provide detailed references, WBS assignments, resource code assignments, and estimate summary roll-ups for guiding the reviewer through the document. Baseline reviews have been postponed because reviewers were unable to trace cost estimates to TSD detailed work statements or because TSDs were written at too high a level and lacked detailed references and attachments.

Accuracy. Estimate items such as quantities, unit costs, contractor markups, and escalation are subject to review for application and extension accuracy. Scope and schedule information are cross-walked to estimates, ensuring accuracy. For example, if PCB contamination is indicated as a concern in a TSD, the estimate must include PCB sample analysis and remedial action activities. Specific site closure milestones or activity dates should be consistent in TSDs and reflect the same date and escalated costs.

Consistency. Estimate and schedule components such as unit costs, activity durations, and methods of accomplishment must be consistently applied to baseline elements.

Completeness. Project cost projections must include all work scope. Reviewers should ask comprehensive questions to ensure estimate completeness. In-depth questions can result in more cost-effective alternatives.

Reasonableness. Determining reasonableness is often subjective. The contractor’s best defense is providing objective baseline documentation. References to supporting technical documents, published databases, actual historical backup, other contractors’ information, and lessons learned, are necessary. A finding should be generated if this information is not available. The contractor should also avoid statements of ‘expert opinion’ and ‘historical knowledge' unless well documented and justified.

| Follow up on pre-baseline review action item list and information requests. | Cost estimators should review contractor responses and additional information provided before the onsite review. |
| --- | --- |
| Request site tour. | Site tours, preferably conducted by field personnel and subject matter experts at the beginning of onsite reviews, provide reviewers a better understanding of site conditions, resulting in more informed review comments. |
| Review contractor estimating processes. | Baseline cost estimate reviews usually focus on contractor estimating processes ensuring systematic applications or on specific subproject estimate reviews. Contractor cost estimating process reviews should be conducted before performing specific check estimates, including: Reviewing processes for ensuring cost estimates are developed consistently and correctly, including reviewing labor rate development, material and equipment unit cost sources, project mark-ups, escalation, and contingency. Reviewing processes often reveals inadvertent cost component double counting or omissions with potentially high cost impacts. Problems often occur when cost component details are not well developed, documented, or understood by contractors preparing estimates. For example contractors that develop and apply unit labor [wage rate] costs and mark-ups (labor fringe and/or burdens, overhead and profit, taxes, equipment usage, general requirements, and productivity adjustments) without fully understanding all the components risk duplicating or excluding cost items (e.g., OH&P costs or productivity allowances). Baseline cost estimating processes must be presented clearly and concisely and demonstrate traceability for reviewers to verify consistency and accuracy. Reviewers can recommend estimating process improvements rather than accepting contractor claims that rates are fully burdened and audited. Verifying that cost estimates were prepared using a consolidated resource table. A consolidated resource table is a common database of unit costs used for estimating baseline subprojects. Resource database details should be examined for understanding component costs. Determining direct cost (materials, labor and equipment) and indirect cost (overhead, profit, taxes, and corporate burdens) definitions and application are clear. Reviewers determine the unit cost (program/project, design, and inspection activities) components and the application method (percent allowances or specific estimates). |
| Prepare check estimate comparisons. | Reviewers select specific subproject(s) and prepare independent check estimates for comparison. Check estimates are prepared using software models such as RACER, a standard bottoms-up estimating technique, or various types of estimating analogies using historical or other parametric estimating data. Specific project selection is primarily based on whether or not the TSD contains sufficient information. However, cost reviewers may not know if information is complete until the check estimate commences. If information is lacking, reviewers may generate a finding, make assumptions regarding the missing information for completing the check estimate, or request additional information from the contractor. Incomplete definitions and insufficient data are barriers to performing quality check estimates. |
| Insufficient Details | Reviewers preparing comparable estimates often encounter insufficient TSD quantitative scope definition, activity descriptions, or design detail. Insufficient baseline documentation results in reviewers (1) excluding scope; (2) making unsupported (best guess) scope assumptions/exclusions; or (3) spending additional time and effort with contractor personnel to obtain sufficient details for preparing or modifying check estimates. |
| Data Gaps or Overlaps | Reviewers may encounter work scope data gaps or overlaps between work phases. Primary generic environmental restoration subproject phases are: Assessment/investigation Engineering and design Construction Operation and maintenance Primary subproject phase estimates must reflect complete and appropriate work scope activities, including defined scope boundaries governing start and completion. Estimates must also identify parties responsible for activities (e.g., contractor vs. subcontractors vs. GFSI). Reviewers should ensure defined and coordinated primary activity estimates are included, avoiding duplicative scope. For example, program management costs can easily be overstated if applied to primary elements and included in a separate program management TSD. |
| Compre-hensive Scope List | TSDs may lack comprehensive subtask scope lists because of simple oversight or the mistaken assumption that other TSDs cover a related work scope. For example, a description of site preparation and well drilling activities may reference a sample analysis plan, but not specifically include it in the work scope description, resulting in excluding the sampling analysis costs. The check estimate could include both well drilling and sample analysis costs because of imprecise TSD scope statements. Estimating comparisons prevent this problem. Reviewers should ensure that estimates include all project scope, including mobilization; site preparation; drilling and completing the well; installing sample analysis equipment and appurtenances; installing instrumentation and controls; installing fencing and security; and demobilization. |
| Assump-tions and Exclusions | Specific estimate assumptions and exclusions are often included only at the TSD programmatic level. For example, a TSD state may that nationally recognized DOE/Laboratory testing standards are assumed, but fail to list contractor specific assumptions allowing a stringent quality confirmation method. In this instance, assumed methodology significantly increases unit costs over a standard sample analysis technique. Reviewers should recognize that sample analysis costs are too high by using customary unit costs for pricing the check estimate. |
| Cost Database Descrip-tions | TSDs may not provide sufficient cost database descriptions or references detailing the estimate pricing cost components. Reviewers must be convinced that using similar database costs, check estimates are equivalent in structure and composition, ensuring appropriate comparisons. |
| Direct vs. Indirect Costs | Reviewers can elect to prepare check estimates against only the direct cost portion of TSD estimates. This is necessary when indirect costs are discernable from direct costs in the baseline estimate, but not specifically defined. The situation occurs when the baseline estimate includes indirect costs as a percentage multiplier allowance of the direct costs. |
| Contin-gency | Cost or schedule contingencies must be specifically identified in baseline estimates. Reviewers should note contingency allowances that are potentially buried in estimate details. For example, if a preliminary remedial design indicates four sampling wells are necessary for characterizing a site but five wells are included in the estimated to ensure a sufficient budget, the cost of the fifth well is considered contingency. |
|  | General Contingency. The American Association of Cost Engineers defines contingency as “[a] specific provision for unforeseeable elements of cost within the defined project scope. [Contingency is] particularly important where previous experience relating estimates and actual costs has shown that unforeseeable events, which will increase costs, are likely to occur.” DOE has elected to narrow the scope of this definition, defining contingency in the DOE Cost Estimating Guide (DOE G 430.1-1) as “costs that may result from incomplete design, unforeseen and unpredictable conditions, or uncertainties within the defined project scope. The amount of the contingency will depend on the status of design, procurement, and construction and the complexity and uncertainties of the component parts of the project. Contingency is not to be used to avoid making an accurate assessment of expected cost.” It is not DOE practice to set aside contingency for major schedule changes or unknown design factors, unanticipated regulatory standards or changes, incomplete or additions to project scope definition, force majeure situations, or congressional budget cuts. Project and operations estimates always contain contingency. Estimators should be aware that contingency is an integral part of estimates. |
|  | Buried Contingencies. DOE G 430.1-1 also states “Some estimators have sought to hide contingency estimates in order to protect the project so that the final project does not go over budget because the contingency has been removed by outside sources. This is affectionately known as buried contingency. All internal and external estimators should refrain from burying extra contingency allowances within the estimate. A culture of honesty should be promoted so that it is not necessary to bury contingency. In addition, estimators should be aware that estimate reviewers will identify buried contingency. The estimate reviewer is obligated to remove buried contingency.” |
| Prepare draft findings, observations, and recommenda-tions | Using the Baseline Review Comment and Findings form, cost reviewers prepare and submit cost estimate findings and observations to the team lead for consolidation and review. |

| Reviewer’s Name (please print): |  |
| --- | --- |
| Reviewer’s Signature: |  |
| Date Reviewed: |  |

Appendix A:  EPD Baseline Review Checklist

| Review Item | Yes? | No? | N/A? | Notes |
| --- | --- | --- | --- | --- |
| General Baseline Documentation |  |  |  |  |
| Is the Baseline Change Proposal (BCP) included? (See BCP Checklist). |  |  |  |  |
| Is a cover letter provided with appropriate signature(s)? |  |  |  |  |
| Was a Contents section prepared? |  |  |  |  |
| Does the baseline documentation include the WBS? |  |  |  |  |
| Does the baseline documentation include the WBS Dictionary? If all WBS elements are fully described in TSDs or ECWs, then Data Dictionary not necessary. |  |  |  |  |
| Is an organization chart provided depicting the organizations working on this project, as well as the supervisor name(s)? |  |  |  |  |
| Does the baseline documentation include a Responsibility Assignment Matrix (RAM)? |  |  |  |  |
| Is the number of full-time equivalents (FTEs) listed by year with an overall total? |  |  |  |  |
| Are FTEs differentiated between EM and DP? |  |  |  |  |
| Has the source of the escalation rates used been identified? |  |  |  |  |
| Are escalation rates properly applied? |  |  |  |  |
| Does the baseline documentation include the Programmatic Assumptions Document (PAD)? |  |  |  |  |
| Does the baseline documentation include the Project Execution Plan (PEP)? Is the overall project scope fully described in the PEP? |  |  |  |  |
| Do the TSDs or ECWs address the entire lifecycle scope, cost, and schedule? |  |  |  |  |
| Are the TSDs or ECWs signed and dated by the responsible control account manager or project team leader, not merely signed by the project manager? |  |  |  |  |
| Are Gantt charts included for each TSD or ECW? |  |  |  |  |
| Are task-specific assumptions included in each TSD or ECW? |  |  |  |  |
| Are TSD/ECW specific risks included in each ECW? |  |  |  |  |
| Does the site have a cost estimating procedure? Where is it described? ___________________ |  |  |  |  |
| If the site has a cost estimating procedure, was it used in preparing the baseline? |  |  |  |  |
| Are critical milestones and performance measures included in each TSD/ECW, as appropriate? |  |  |  |  |
| Does the baseline documentation include a full set of TSDs or ECWs covering all scope? |  |  |  |  |
| Does the baseline documentation include the Priority List? |  |  |  |  |
| Does the baseline documentation include the lifecycle, resource loaded schedule? |  |  |  |  |
| Does the baseline documentation include the lifecycle cost plans (these are really BCWS plans), to include history, out-years, and the total? |  |  |  |  |
| Does the baseline documentation include annualized metrics, such as drums shipped by year to WIPP? |  |  |  |  |
| Does the baseline documentation include overhead rates and other resource rates? |  |  |  |  |
| Does the baseline documentation include the Risk Management Plan? |  |  |  |  |
| Does the baseline documentation include the Project Control System Description? |  |  |  |  |
| Does the baseline documentation include the Acquisition Plan or Procurement Plan? |  |  |  |  |
| Is there traceability between all baseline elements? |  |  |  |  |
| Is a carryover analysis section prepared? |  |  |  |  |
| Does it appear as if THE SITE performed a quality check of the baseline submittal? |  |  |  |  |
| Scope |  |  |  |  |
| Is the TSD or ECW technical scope described in sufficient detail to support the cost estimate and provide an understanding of the work to be accomplished to an outside reviewer? |  |  |  |  |
| Does the scope describe waste operations by waste type? |  |  |  |  |
| Are any current and planned construction projects included in scope descriptions and cost sharing ratios between EM and DP? |  |  |  |  |
| Has the work scope been planned to reflect the way the work is actually performed and is it logical and consistent? |  |  |  |  |
| Is the work scope traceable to prior program work when historical data is being used as a basis? |  |  |  |  |
| Is the work scope traceable to the WBS and correct? |  |  |  |  |
| Is the work scope traceable to the schedule and cost estimates? |  |  |  |  |
| Does the PAD, project level TSD/ECW, or Risk Management Plan (RMP) include the appropriate level of risks? |  |  |  |  |
| Does the PAD or project level TSD/ECW include the appropriate level of assumptions? |  |  |  |  |
| Are the TSD/ECW assumptions specific to the TSD/ECW or do they apply to the entire project? |  |  |  |  |
| Are the risks specific to the TSD/ECW or do they apply to the entire project? |  |  |  |  |
| Have waste generator program personnel been consulted to determine the impact of the projected workload on the site waste management program? |  |  |  |  |
| Have DP personnel reviewed the baseline estimate and cosigned on the ECWs? |  |  |  |  |
| Are the nature, rate, and extent of projected waste generating and processing identified? |  |  |  |  |
| Have specific requirements for regulatory compliance been identified (e.g., permits)? |  |  |  |  |
| Have interfaces with external regulatory agencies been identified? |  |  |  |  |
| Have interfaces with external personnel or organizations to the WM Program but internal to the site been identified? |  |  |  |  |
| Is the scope of work traceable to the regulatory driver(s)? |  |  |  |  |
| Schedule |  |  |  |  |
| Have standard scheduling techniques been used (e.g. critical path method, resource leveling)? |  |  |  |  |
| Have task dependencies been identified? |  |  |  |  |
| Is there clear schedule logic connecting deliverables to supporting tasks? |  |  |  |  |
| Is the sequence of activities clear? |  |  |  |  |
| Is the sequence of activities logical? |  |  |  |  |
| Have all deliverables identified in the TSDs or ECWs been included and vice versa? |  |  |  |  |
| Are deliverables identified as milestones on the schedules (Gantt charts)? |  |  |  |  |
| Are activity durations for deliverables and other activities reasonable? |  |  |  |  |
| Does the schedule include time for safety analysis for environmental assessment approvals? |  |  |  |  |
| Have all DOE Headquarters, NNSA, site office, and site milestones been identified? |  |  |  |  |
| Is the schedule consistent with regulatory milestone due dates? |  |  |  |  |
| Is the schedule traceable to the WBS? |  |  |  |  |
| Does the schedule contain the same resource names and descriptions and allocations used in the cost estimate and described in the TSDs or ECWs? |  |  |  |  |
| Does the schedule interface with other site activity schedules? |  |  |  |  |
| Risk Management |  |  |  |  |
| Does the RMP include the project’s general approach to risk management? |  |  |  |  |
| Are the roles and responsibilities of project personnel performing risk management functions described in the RMP? |  |  |  |  |
| Is the frequency of risk evaluations and reporting included in the RMP? |  |  |  |  |
| Are the methods used to analyze individual risks been included in the RMP? |  |  |  |  |
| Have risks been identified and included in the RMP? |  |  |  |  |
| Have the identified risks been rated as to high, medium, and low? |  |  |  |  |
| Have cost, schedule, and technical impacts of individual risks been quantified and included in the RMP? |  |  |  |  |
| Have methods for mitigating risks, especially moderate to high risks, been included in the RMP? |  |  |  |  |
| Have action plans for handling individual risks been included in the RMP? |  |  |  |  |
| Cost Estimate |  |  |  |  |
| Was a cost estimator utilized for baseline preparation? |  |  |  |  |
| Is there a correlation between the waste management estimating process and the cost estimating process used in the construction and facility engineering divisions? |  |  |  |  |
| Is the cost estimate traceable to the work scope? |  |  |  |  |
| Is the cost estimate traceable to the lowest level of the WBS? |  |  |  |  |
| Is the cost estimate reasonable based on the work scope? |  |  |  |  |
| Are labor hours, material, equipment, and subcontracts each separately identified? |  |  |  |  |
| Have cost exclusions and assumptions been identified? |  |  |  |  |
| Have costs imposed by circumstances facing the project been identified and documented (i.e., funding constraints, changing regulatory requirements, directed changes, or imposed priorities)? |  |  |  |  |
| Are any resource constraints listed along with their effects on the work scope? |  |  |  |  |
| Are needed resources external to the waste management group identified? |  |  |  |  |
| Has the cost estimating software been identified? |  |  |  |  |
| Have data been verified? |  |  |  |  |
| Are backup estimates for all subcontracts greater than $100K available? |  |  |  |  |
| Do the backup estimates for subcontracts greater than $100K delineate the estimated cost for material, labor, and equipment? |  |  |  |  |
| Budget |  |  |  |  |
| Do the annual baseline cost estimates crosswalk to the funding targets for the current year and two years out? |  |  |  |  |
| Does the baseline cost estimate reflect the most current AFP? |  |  |  |  |
| Are resource rates correct? |  |  |  |  |
| Are overhead rates properly applied? |  |  |  |  |

Reviewers will receive checklists for individual TSDs or ECWs covering the same TSD/ECW information in the checklist above.

Appendix B:  Baseline Review Questionaire

| QUESTIONS | RESPONSES |
| --- | --- |
|  |  |  | Yes | No | N/A | Answer/Explanation |
| I - | PROJECT MANAGEMENT: |  |  |  |  |
|  | 1 - | Does the project conform to DOE O 413.3? |  |  |  |  |
|  | 2 - | Who is the Program Secretarial Officer? (Name/org./phone) |  |  |  |  |
|  | 3 - | Who is the Project Acquisition Executive? (Name/org./phone) |  |  |  |  |
|  | 4 - | Who is the Project Director? (Name/org./phone) |  |  |  |  |
|  | 5 - | Who is the Federal Project Manager? (Name/org./phone) |  |  |  |  |
|  | 6 - | Who is the Contractor Project Manager? (Name/org./phone) |  |  |  |  |
|  | 7 - | Has an Integrated Project Team (IPT) been chartered? |  |  |  |  |
|  | 8 - | Has the Project Execution Plan (PEP) been Approved? (Date) |  |  |  |  |
|  | 9 - | Is the project on the Cleanup Reform Account (CRA) list of small sites? |  |  |  |  |
|  | 10 - | Has the CRA Project Management Plan (PMP) been Approved? |  |  |  |  |
|  | 11 - | Has the National Focus Project (NFP) visited the site? (Date) |  |  |  |  |
|  | 12 - | Have all NFP Issues (Paul Golan Memo) been addressed? |  |  |  |  |
| II - | PROJECT SCOPE: |  |  |  |  |
|  | 1 - | Has all project scope been included in the baseline? (Including LTSM & LTRA) |  |  |  |  |
|  | 2 - | Has the regulator agreed to the project end state? |  |  |  |  |
|  | 3 - | Are all Programmatic Assumptions Documented? (Where?) |  |  |  |  |
|  | 4 - | Does a Task Scope Description (TSD or equivalent) exist? |  |  |  |  |
|  | 5 - | Do TSDs tie the scope with cost and schedule at WBS level 8 or lower? |  |  |  |  |
|  | 6 - | Are TSDs revised as Baseline Change Proposals (BCPs) are processed? |  |  |  |  |
|  | 7 - | Do TSDs identify all project milestones and deliverables? |  |  |  |  |
|  | 8 - | Does a Priority List exist? (Where?) |  |  |  |  |
|  | 9 - | Does the Regulator endorse the Priority List? |  |  |  |  |
|  | 10 - | Does a Soils Remediation Strategy Exist? |  |  |  |  |
|  | 11 - | Does a comprehensive Groundwater Remediation Strategy Exist? (Where?) |  |  |  |  |
|  | 12 - | Are all Waste Disposal Paths Identified? |  |  |  |  |
|  | 13 - | Has all GFS&I scope been included in the baseline? |  |  |  |  |
|  | 14 - | Do all waste streams have an identified pathway? |  |  |  |  |
|  | 15 - | Is the risk-based end state defined and documented? (Where?) |  |  |  |  |
| III - | PROJECT COST: |  |  |  |  |
|  | 1 - | What is the estimated Total Project Cost (TPC), as of 09/30/03? |  |  |  |  |
|  | 2 - | What are the Project To Date (PTD) actual costs, as of 09/30/03? |  |  |  |  |
|  | 3 - | What is the Estimate To Complete (ETC), as of 09/30/03? |  |  |  |  |
|  | 4 - | Has all project scope been estimated and included in the current ETC? |  |  |  |  |
|  | 5 - | Has an Activity Based Cost estimate been prepared for all baselined activities? |  |  |  |  |
|  | 6 - | Has a Government Estimate been performed (org./date)? |  |  |  |  |
|  | 7 - | Has an Independent Cost Estimate (ICE) been performed (org./date)? |  |  |  |  |
|  | 8 - | Has an Independent Cost Review (ICR) been performed (org./date)? |  |  |  |  |
|  | 9 - | Has a quantitative project Risk Analysis been performed? |  |  |  |  |
|  | 10 - | Has a project Contingency Analysis been performed? |  |  |  |  |
|  | 11 - | Does the level of confidence in the ETC exceed 80%? |  |  |  |  |
|  | 12 - | Are man-hours included in baseline resources? |  |  |  |  |
|  | 13 - | Has a Resource Dictionary been prepared? |  |  |  |  |
|  | 14 - | Does an Accounting Disclosure Statement exist? (Budget Issue) |  |  |  |  |
|  | 15 - | Have GFS&I activities been resource-loaded? |  |  |  |  |
| IV - | PROJECT SCHEDULE: |  |  |  |  |
|  | 1 - | What was the project start date? (EM funding began) |  |  |  |  |
|  | 2 - | What is the current project completion date? (EM funding ends) |  |  |  |  |
|  | 3 - | Has the project end state been flagged with a major project milestone? |  |  |  |  |
|  | 4 - | Does an Integrated EM Master Schedule exist? (High-level Gantt chart schedule) |  |  |  |  |
|  | 5 - | Does a resource-loaded schedule exist at WBS level 8 or lower? |  |  |  |  |
|  | 6 - | Are all resource-loaded baseline activities logically tied? |  |  |  |  |
|  | 7 - | What Project Planning Software system currently used? (System/version) |  |  |  |  |
|  | 8 - | Has a project Critical Path Schedule been identified? |  |  |  |  |
|  |  | a) How many activities have 0 days of float? (<1) |  |  |  |  |
|  |  | b) How many activities have 0 to 30 days of float? |  |  |  |  |
|  |  | c) How many activities have 30 to 60 days of float? |  |  |  |  |
|  |  | d) How many activities have greater than 60 days of float? |  |  |  |  |
|  | 9 - | Has Critical Decision 0 (CD-0) been approved? (Mission Need) |  |  |  |  |
|  | 10 - | Has Critical Decision 1 (CD-1) been approved? (Cost Range) |  |  |  |  |
|  | 11 - | Has Critical Decision 2 (CD-2) been approved? (Performance Baseline) |  |  |  |  |
|  | 12 - | Has Critical Decision 3 (CD-3) been approved? (Execution) |  |  |  |  |
|  | 13 - | Has a schedule contingency analysis been performed? |  |  |  |  |
|  | 14 - | Are all major milestones and deliverables identified in the baseline? |  |  |  |  |
|  | 15 - | Are all Enforceable Agreement (EA) milestones identified in the baseline? |  |  |  |  |
|  | 16 - | Have GFS&I activities/milestones been tied to schedule milestones? |  |  |  |  |
|  | 17 - | Does the Integrated Baseline Include all EM funded activities? |  |  |  |  |
|  | 18 - | Are all Integrated Baseline activities resource-loaded and logically tied? |  |  |  |  |
| V - | PROJECT CONTROLS: |  |  |  |  |
|  | 1 - | Has the baseline been prepared in accordance with DOE M 413.3-1? |  |  |  |  |
|  | 2 - | Who is the Project Controls Manager or Team Leader? (Name/org./phone) |  |  |  |  |
|  | 3 - | Has Control Account Manager/s been identified (name/org./phone)? |  |  |  |  |
|  | 4 - | Has an Integrated EM Project Baseline been prepared per NFP guidance? |  |  |  |  |
|  | 5 - | Has the project lifecycle baseline been validated (org./date)? |  |  |  |  |
|  | 6 - | Has the Earned Value Mgmt. Sys. (EVMS) been certified (org./date)? |  |  |  |  |
|  | 7 - | Has an External Independent Review (EIR) been performed (org./date)? |  |  |  |  |
|  | 8 - | Has a Project Development Rating Index (PDRI) been done (org./date)? |  |  |  |  |
|  | 9 - | What was the PDRI score? |  |  |  |  |
|  | 10 - | Does a Work Breakdown Structure (WBS) Data Dictionary exist? |  |  |  |  |
|  | 11 - | Does a Code of Accounts exist? |  |  |  |  |
|  | 12 - | Does the Code of Accounts crosswalk to the baseline WBS? (Give WBS Level) |  |  |  |  |
|  | 13 - | At what WBS level are actual costs recorded? |  |  |  |  |
|  | 14 - | Are actual costs accrued? |  |  |  |  |
|  | 15 - | How often are accrued costs reconciled with actual costs? |  |  |  |  |
|  | 16 - | Is the Baseline Change Control Process Documented? (Where?) |  |  |  |  |

Appendix C:  Glossary

Activity-based cost (ABC) estimating. ABC is a cost-estimating technique based on defining processes and activities. Each activity is defined in terms of a unit of measure; quantities and unit costs of labor-hours, materials, equipment, and subcontracted services; and overhead value(s). Resources are traced to activities based on consumption.

Annual. Annual refers to cost, schedule, or scope changes affecting any single fiscal year.

Baseline. An EM project baseline is a quantitative expression of the project scope, schedule, and requirements against which the status of resources and progress can be measured. The field typically maintains the baseline as a collection of documents, including resource loaded schedule networks, cost estimates, and assumptions. The baseline is the key component of the project control system because it documents the program plan for performing the work and provides the information required by DOE business practices for evaluating resource requirements and program performance. For planning purposes, project baselines should reflect full regulatory compliance and should be based on reasonable out-year funding assumptions. The degree of baseline detail should be consistent with the phase of the project and should adopt the “rolling wave” approach, such as greatest level of detail for near-term (FY plus 2 years) activities. The baseline is often referred to as the performance measurement baseline (PMB).

Baseline change proposal (BCP). Contractors normally generate the BCP for documenting baseline element changes. It should provide a complete description of a proposed change and its resulting impacts on project baselines. The BCP serves as an audit tool for all changes to the baseline components. The BCP must be submitted in accordance with the baseline change control guidelines contained in the EPD Project Control Handbook.

Baseline Performance Report (BPR). The BPR is the contractor quarterly performance report submittal to EPD. The BPR components are (1) executive summary, (2) CPR format, (3) performance indices, (4) cost plan format, (5) variance analyses and corrective actions, (6) schedule exception report, (6) contingency log, if applicable, (7) baseline change activity log, and (8) supporting detail, as required.

Budget at completion (BAC). BAC is equal to the sum of all resource allocated activities or BCWS. BAC will not change unless the budget is changed through the baseline change control process.

Budgeted cost of work scheduled (BCWS). The baseline dollars corresponding to scheduled work within a given time period. The sum of all BCWS equals the budget at completion (BAC). Although the BCWS plan and the cost plan are not technically identical, EPD and its contractors use these terms synonymously.

Change control. A documented process applying technical and management review and approval of changes to baseline technical, schedule, and cost elements.

Contractor. The term contractor as used in this document refers to management and operating (M&O) contractor unless otherwise stated.

Corporate performance measures. EM Corporate Performance Measures are included in IPABS-IS and statused monthly. They support budget justification and allow DOE to measure contractor progress. Corporate Performance Measures are subject to change control in IPABS. The reporting module of IPABS-IS produces a report of these performance measures and is referred to as the “Gold Chart”.

Cost plan (CP). The cost plan includes historical BCWS through the previous fiscal year (FY), baselined (BCWS) dollars by month for the execution year, and baselined (BCWS) dollars by year for the outyears at an agreed upon WBS level, generally level 6 or 7. The sum of all historical data through and including the current month data, should match the project’s BCWS in IPABS-PEM. The cost plan defines the activities in monthly increments for the current FY, thus providing time-phased data upon which performance can be measured and reported to EPD. Although the cost plan and the BCWS plan are not technically identical, the EPD and its contractors use these terms synonymously.

Cost variance (CV). The CV is a field on the CPR that provides dollar difference between the work performed (BCWP) and actual cost (ACWP).

CV = BCWP – ACWP

Critical decision (CD). A formal determination made by the AE, at a specific point in a project that allows the project to proceed. CDs occur during the course of a project. Example CDs are prior to commencement of pre-conceptual design, commencement of execution, and turnover.

Environmental Programs Department (EPD). EPD is the SC department responsible for the oversight of the Waste Management Division and Environmental Restoration Division.

Environmental Restoration Division (ERD). The EPD division that oversees planning, budgeting, execution, and reporting and evaluation activities for ER projects at the sites listed in this Handbook’s preface. It also provides input to decision making concerning dispositioning properties and facilities that do not support DOE's evolving missions (excess facilities), and assists communities in planning the future use of DOE site that are to be transitioned back to local ownership (land transfers).

Estimate at completion (EAC). EAC is synonymous with latest revised estimate (LRE). It is the total cumulative cost to date (ACWP) plus the estimated cost of all remaining work (ETC) plus contingency for ER projects. EACs change as project costs are tracked and estimates are updated. EAC indicates the most likely final cost of the project.

Estimate to complete (ETC). The current, best-estimated costs for completing remaining project work. ETCs are adjusted to reflect current information, such as expected performance, pending rate changes, and escalation. One method for computing ETC is:

ETC = BAC/CPI

Federal Project Director (FPD). As defined in DOE Manual 413.3-1, the FPD resides at either the field or HQ and serves as the single point of contact between Federal and contractor staff for all matters relating to the project and its execution. The Program Secretarial Officer (PSO) may be delegate certain authorities and responsibilities to the FPD.

Fiscal year (FY). The U.S. government FY begins on October 1 and ends on the following September 30 of every year.

Independent Cost Estimate (ICE). A “bottoms-up” documented, independent cost estimate for the express purpose of serving as an analytical tool for validating, cross checking, or analyzing cost estimates developed by the FPD.

Independent Cost Estimate Review (ICER). An essential project management tool used for analyzing and validating project costs estimates. An ICER is typically conducted on projects at the point of baseline approval. Congress, DOE management, HQ program offices, or field project management staff may require such reviews. The requiring office or agency provides specific requirements for such reviews. An ICER may be performed by an independent internal or external organization.

Integrated Planning, Accountability, and Budgeting System (IPABS). The objective of IPABS is to establish a single integrated EM corporate database to support all budget, performance, technical analyses, and inquiries. This will eliminate redundant requirements and reporting systems and provide a single source for data management. Baselines should be integrated as much as practical and as makes sense, in order to eliminate redundant baseline related efforts. The IPABS-IS is the user interface for data input and reporting.

Lifecycle. Lifecycle includes all costs, schedule, and scope from project inception through project completion.

Management and operating (M&O) contractor. The M&O is the onsite contractor responsible for the day-to-day operations of a DOE wholly owned production plant.

Milestone. A milestone is an important or critical event with no duration required for achieving project objective(s). Milestones are comprised of a noun; modifiers; active, results-oriented verb; and a date. Milestones can signify activity starts and completions.

NNSA Service Center. The NNSA Service Center includes the NNSA and EM personnel, facilities, and associated Site Offices providing oversight to DOE’s interests. NNSA SC’s management responsibilities encompass national laboratories, production plants, environmental management sites, and the contractors who manage and operate these sites for DOE.

Office of Engineering and Construction Management (OECM). The OECM is within the Office of the Chief Financial Officer. It serves as DOE’s principal point of contact relating to program and project management and develops policy and assists in the planning, programming, budgeting, and execution process for the acquisition of capital assets in coordination with the program secretarial officers (PSOs) and project management support offices.

Office of Environmental Management (EM). The DOE created this organization in 1989 to mitigate the risks and hazards posed by the legacy of nuclear weapons production and research. Included are an unprecedented amount of contaminated waste, water, and soil, and a vast number of contaminated structures that will remain radioactive for thousands of years. EM is composed of the Offices of ER and Waste Management.

Office of Management and Budget (OMB). OMB is housed within the Executive Office of the President and provides the most objective analysis possible for the President. It has the lead role within the Executive Branch for maintaining Federal fiscal discipline, allocating scarce resources, and promoting program efficiency. OMB provides leadership and assistance in financial management, procurement, information collection and dissemination, and other government-wide management functions. These responsibilities are carried out working cooperatively with the Congress and congressional agencies such as the Congressional Budget Office and the General Accounting Office. The OMB assists the President by (1) reviewing agency proposals and programs on a variety of topics from budgets to regulations; (2) assuring that these proposals and programs are consistent with relevant statutes and Presidential objectives; (3) providing analysis and advice on a variety of subjects; and (4) developing government-wide policies for the effective and efficient operations of the Executive Branch.

Performance Measurement Baseline (PMB). The time-phased budget (BCWS) plan plus any undistributed budget against which project performance is measured.

Priority list. A prioritized list of discrete execution year work scope and associated budget used for determining funding cut and funding addition impacts.

Project. A unique effort that supports a program mission, having defined start and end points, undertaken to create a product, facility, or system, and containing interdependent activities planned to meet a common objective or mission. Project types include planning and execution of construction, renovation, modification, line items for maintenance and repair, environmental restoration, deactivation and decommissioning efforts, information technology, and large capital equipment or technology development activities. Tasks that do not include the above elements, such as basic research, grants, ordinary repairs, maintenance of facilities, and operations are not considered projects. For simplicity, this document uses “projects” when referring to both programs and projects.

Project risk. A factor, element, constraint, or course of action on a project that introduces an uncertainty of outcome and the possibility of technical deficiencies, inadequate performance, schedule delays, or cost overruns that could impact a mission. In the evaluation of project risk, the potential negative or positive impacts and the probability of occurrence must be considered.

Schedule variance (SV). The SV is a field on the CPR that provides dollar difference between the work performed (BCWP) and the work scheduled (BCWS).

SV = BCWP – BCWS

Site Office. DOE’s primary points of contact with M&O contractors other than those listed in this handbook’s preface. They provide day-to-day direction and guidance, and are the contract managers implementing EPD contracting strategies and contractual requirements. They are involved in planning, budgeting, execution, and reporting and evaluation.

Total float. The amount of time an activity can be delayed from its early start or early finish date before impacting the project end date.

Total project cost (TPC). The sum of all costs identified for a project. TPC and TEC are equivalent for WM and ER projects.

TPC = actuals to date + ETC + contingency (for ER projects)

Waste Management Division (WMD). WMD is the EPD division responsible for the oversight of waste management projects and programs at the laboratories and production plants.

Work breakdown structure (WBS). The WBS is a product-oriented family tree subdivision of the work required to produce the end product. The WBS is structured in accordance with the way work will be performed and reflects the way in which project costs and data will be summarized and eventually reported.

Appendix D:  References and Recommended Reading

References

DOE, 2003. DOE M 413.3-1, Program and Project Management Manual, March 2003.

DOE, 2000. Project Management Practices, Draft. October. http://oecm.energy.gov/policies_guides/practices.pdf

DOE, 2000. DOE O 413.3, Program and Project Management for the Acquisition of Capital Assets, October 13, 2000.

NNSA SC, EPD, Cost Estimating Handbook, (TBD)

NNSA SC, EPD, Project Control Handbook, April 2004

NNSA SC, EPD, Decontamination and Decommissioning Handbook, September 14, 2001

NNSA SC, EPD, Long-Term Environmental Stewardship Handbook, 2003

NNSA SC, EPD, Project Oversight Handbook, (TBD)

NNSA SC, EPD, Value Engineering Handbook, (TBD)

Recommended Reading

ANSI/EIA-748, Earned Value Management System. August 28, 2002

DOE, Jess Hill Roberson (EM-1), Environmental Management Federal Baseline Development Policy, October 27, 2003

DOE G 430.1-1, Cost Estimating Guide, March 28, 1997

DOE O 412.1, Work Authorization System, April 20, 1999

DOE O 430.1, Life Cycle Asset Management (LCAM), August 24, 1995

DOE P 141.2, Public Participation and Community Relations, May 2, 2003

DOE P 413.1, Program and Project Management Policy for the Planning, Programming, Budgeting, and Acquisition of Capital Assets, June 10, 2000

DOE P 450.4, Safety Management System Policy, October 15, 1996

DOE P 455.1, Use of Risk-Based End States Policy, July 17, 2003

DOE, FM-50, DOE Cost Estimating Guide, Volume VI, Cost Guide, November, 1994

DOE, IPABS-IS Data Requirements, December 18, 1998, http://www.em.doe.gov/ipabs/

DOE, IPABS-IS Guidance, December 1999 – present, http://www.em.doe.gov/ipabs/

DOE, IPABS Handbook, February 16, 1999. http://www.em.doe.gov/ipabs/

DOE, Office of Environmental Management, DOE EM-15 Environmental Management FY1996 Performance Plan. June 1996

DOE, Office of Field Management, Life Cycle Asset Management Good Practices Guides. March 1996. 
Risk Analysis and Management, GPG-FM-007
Project Execution and Engineering Management Planning, GPG-FM-010
Performance Analysis and Reporting, GPG-FM-006
Performance Measures, GPG-FM-020
Interface Management, GPG-FM-013
Engineering Tradeoff Studies, GPG-FM-003
Baseline Change Control, GPG-FM-009
Configuration and Data Management, GPG-FM-012
Critical Decision Criteria, GPG-FM-002
Work Scope Planning, GPG-FM-008

DOE, Office of Project Management, EM-6, Office of Environmental Management Project Definition Rating Index (EM PDRI) Manual, Revision 0. March 6, 2000

DOE, Office of Training and Human Resource Development, Project Risk Analysis and Management, course number PMCE02

DOE, Office of Waste Management (EM-30) Standard Operating Practice and Procedure (SOPP), 2.2.2, Managing Baseline Change Control, 1992

DOE, Office of Waste Management (EM-30), Management Policies and Requirements (MPR), 1992.

DOE, Waste Management Division, Performance Measurement Processes, June 2001

DOE/MA-0040, Cost and Schedule Control Systems Criteria for Contract Performance Measurement, Work Breakdown Structure Guide, October 1981

Executive Order 13148, Greening the Government through Leadership in Environmental Management

National Research Council, 1999. Improving Project Management in the Department of Energy, National Academy Press

OMB Bulletin 95-03, Planning and Budgeting for the Acquisition of Fixed Assets, June 1995

OMB Circular A-109, Major Systems Acquisition, April 1979

U.S. Congress, H.R. 826, Government Performance and Result Act, February 1993

U.S. Office of the Inspector General, Audit Report-Best Practices for Environmental Management Baseline Development, DOE/IG-0476, July 2000

# Text boxes

See Project Control Handbook

Providing assurance of scope, new technologies, and regulatory compliance

Verifying project cost and schedule estimates

Verifying project ability to move to the next critical decision

Assessing risks

Baseline Reviews

Independent Baseline Validations

Independent Reviews

Technical Reviews

Operational Readiness Reviews

Independent

Non-independent

Combination

Project Reviews by outside agencies

Review Types

- NNSA (HQ or SC Site Office)

- DOE (OECM, HQ/EM or EPD)

Select review team

Assign review team responsibilities

Conduct/attend kickoff meeting

Distribute review tools

Establish review schedule

Review preliminary baseline documentation

Baseline Review Preparation

Technical

Waste Management

Environmental Restoration

Decontamination and Decommissioning

Geology/Hydrology

Long-Term Surveillance and Maintenance

Risk Management

Cost Estimating

Budget

Value Engineering

Schedule

Project Control/Project Management

Review Focus Areas

Area of expertise. For example, is the team member reviewing cost estimates, the schedule, or regulatory issues?

Knowledge of the project starting out. For example, has the team member previously worked on some aspect of the project?

Individual reviewer style. For example, does the reviewer prefer reading all relevant material before writing any findings or focusing on one specific item?

Buddy System. For example, do two team members want to split up the scope, schedule, and cost for a large or high profile TSD?

Factors Affecting Getting Started

Read

These

First

Baseline change proposal (if provided)

PEP

PAD

Risk Management Plan

WBS

Baseline Documentation

Components

Project Execution Plan (PEP)

WBS and WBS Dictionary

Responsibility Assignment Matrix (RAM)

Program Assumptions Document (PAD)

Task Scope Descriptions (TSDs)

Project Schedule

Government Furnished Services and Items (GFSI)

Priority List

Risk Management Plan (RMP)

Cost Plans

Metrics

Overhead Rates

Escalation Factors

Acquisition Plan or Procurement Plan

Project Control System Description (PCSD)

Previous Review Comments

- Providing assurance of scope, new technologies, and regulatory compliance.

- Verifying project cost and schedule estimates

- Verifying project ability to move to the next critical decision

- Assessing risks.