# IT Division PRD Calendar

| ACTION | DATE DUE |
| --- | --- |
| Chris sends level 1 to IT Division about employee worksheets | Monday, June 9 |
| Chris to calendar PRD normalization and salary meetings | Monday, June 9 |
| End of Performance Review Year | June 30, 2008 |
| Employee Worksheets due to supervisor | Monday, July 7 |
| Marcia to complete eRoom setup and instructions; update web pages | Friday, July 11 |
| Chris and Marcia to train administrative staff PRD Process ERoom Training | Week of July 14 |
| Chris briefs Group Leads on PRD process and timeline | July Group Lead meeting (tentative) |
| Supervisors remind employees that worksheets are due (including career goals and development plan) | As needed |
| Group Leads submit final drafts of PRDs and final PDs to eRoom (either directly or through administrative support staff) for one-up review | Friday, July 25 |
| Department/Division Office administrative staff to move PRDs and PDs to correct folder and set access control | Monday, July 28 – Thursday, July 31 |
| Department Heads iterate with Group Leads to complete review of PRDs | Thursday, August 1 - Friday, August 15 |
| Department Heads submit final drafts of Group Lead PRDs and final PDs to eRoom (either directly or through administrative support staff)for one-up review | Friday, August 15 |
| Division Office administrative staff moves PRDs and PDs to correct folders and sets access control | Monday, August 18 |
| Tammy and Chris/Marcia review PRDs and iterate with Department Heads and Group Leads | Monday, August 25 – Friday, August 29 |
| Ratings normalization meeting | Mid-August (see calendar for date) |
| Salary management meetings | Late August and early September (see calendar for dates) |