# MEMORANDUM

To:		Distribution

From:		George Neil

Subject:	FEL Upgrade Project Weekly Brief  - August 29-Sept. 2, 2005

Date:		Sept. 2, 2005

Highlights:

We commenced a month-long shut down for installation of the new STI wiggler, srf cavity work, and installation of UV beamline components.  The EM wiggler has been removed and the new wiggler has been delivered to the vault in preparation for installation.  UV magnet stands are being installed and aligned while many components are being assembled, cleaned and qualified (see individual reports below).

Management:

The laboratory had a DOE Science Review over a three day period this week to judge our performance in supporting DOE Nuclear Physics scientific research goals.  The lab overall got exemplary marks and the FEL program was specifically cited for contributions to the Nuclear Physics Program including ERL research and accelerator hardware development.

We are incorporating latest "lessons learned" from a national DOE laser safety review.  While we are in good shape in most areas there are a few (notably housekeeping and equipment storage) that we could improve on.  We expect a DOE audit of our facility and practices in the near future.

We hosted a group from Peking University who are interested in continuing development of their srf injector for an ERL.  We held discussions on collaboration on srf design and fabrication.

This week Gwyn Williams gave an invited talk at a special symposium at the American Chemical Society's annual meeting in DC on our high power THz facility.

The US Army Night Vision and Electronic Services Division, which is the programmatic office of our THz programs, held a THz workshop outside their headquarters of Fort Belvoir.  Gwyn Williams presented a talk on our THz facility and on recent spectroscopic measurements, while Alan Todd of Advanced Energy Systems presented a talk on the transportable high power THz system that is part of the same contract.

WBS 3.0 (Beam Physics) – Dave Douglas

Infused with relief spawned by the end of beam operations, we assaulted various issues related to IR performance and UV installation.

- Extensive discussions on UV quad specifications reinforced the message that "the spec is the spec is the spec" and thereby verified than a perceived 0.4% field asymmetry (ultimately attributed to instrumentation issues) was "out of spec". The brawl on quad powering continues, flames fanned by the fascinating results from last week's trim system test (specially calibrated trim cards failed to allow magnets to make loop and knocked 3 other channels out when swapped).

2. Review of difference orbit data taken during the final week of the run continues. Numerous problematic BPMs can be identified and are being checked. Quad excitations are apparently far enough from the set points that we are preparing SOLOMON 0.0: the "Systematic On Line Optics Monitor, Optimizer, and Normalizer" version 0.0, to crunch the data, as it has become apparent the available tools cannot reliably extract sensible beam matrix results from the data at hand. This information is critical for verifying BBU simulation models and to provide input for machine matching & beam loss control.

3. We spend time in discussion with visitors from Peking University, which is planning to build an ERL driven FEL.

WBS 4 (Injector) – C. H.-Garcia:

We started processing the first of three tube segments for the new gun assembly with the field emission suppression coating in the W&M's plasma chamber. The rotation system is working flawlessly and this tube has been processed for 20 hours. Each segment will be processed for a total of 48 hours to ensure coating uniformity and thickness.

The flange on the second tube segment is being polished in preparation for plasma processing next week, as well as other mounts needed for this purpose.

This week we also supported multislit and THz work.

PARMELA modeling of the 100 mA injector continued this week studying the effect of the added drift space on the transverse emittance.

WBS 5 (SRF) – G. Neil:

Testing and diagnostics continue on Renascence.

- An external rf feedthrough broke yesterday, creating a leak into insulating vacuum and making cavity 7 in operable. The module will be warmed up over the Labor Day weekend in order to replace the broken part early Tuesday, followed by recooldown.

- A problem with pressure stabilization has been traced to an apparent bypass of the helium dam on the return side. This has the effect of creating an extremely narrow stable operating range for liquid level.  Joe Preble's tentative assessment is that the range inadequate for operational use of the cryomodule. Options for repair are being evaluated.

- High power testing of began late yesterday with cavity 1. This cavity was found to be limited by a time-delayed quench ~ 8 MV/m CW, 9 MV/m with 50% pulsed duty cycle. Apparently, something is heating up outside of the cavity cells. Diagnosis will continue today and examination of cavities 3 & 5 for comparison will follow.

Given these issues we are planning for rf processing of the Admiral in place in the FEL to restore some of the previously achieved gradient capability.

WBS 8 (Instrumentation) –K. Jordan:

Monday we took advantage of the vault being opened to remove all of the I&C devices from the IR wiggler and surrounding area.  All of the cables were placed in the cable tray above the wiggler so the cables can be reconnected to the permanent magnet wiggler once installed.  The permanent magnet wiggler control box from STI was unpacked so a support structure could be designed and built.  A table that will fasten to the board and the box has been designed and some finishing touches are being completed today so the box can be mounted in place later today or early next week.  A plan for how to route the control and power cables is in place.

Testing of the BPM electronics continues this week.  The second channel has been calibrated successfully with no influence on the adjacent channel.  Testing of the on board ADC is the next step for the electronics.  Several control lines from the Coldfire were routed incorrectly but they have been moved to the correct locations.  The Coldfire communication will be tested at the same time.  The changes have been documented so the schematics are now correct.  Plans to get eight sets of the electronics ready for the new injector BPMs and various other locations is in the works.  The parts have been checked to ensure we have plenty of components for assembly, the few parts that are needed have been ordered. The existing BPM system is being characterized and will be finished early next week. We are proceeding with a detailed design for the 4 pass multipass BPMs in the linac. The intent is to have an operational multipass BPM system working when we come back up, we are proceeding with the Acqiris AP201 2Gs/sec Peak-detection card as the preliminary solution. This will be followed up with a cost estimate in order to best evaluate the final solution.

The Coldfire Processor/Power Card will be ready for production level boards next week.  All of the design changes have been incorporated into the schematic and are in the process of being changed.  The Coldfire Simulation board design has been completed and a quote for the card should go out today.  The Harmonic Blocking Filter Chassis is 95% completed.  A mistake in the schematic for the Stepper Motor Driver Chassis was found, resulting in some repairs to the spare stepper motor chassis.  This chassis should function properly now and testing will occur as soon as time permits.  The sextapole reversing switch schematic is being checked over carefully so boards can be ordered for these.

The suspended ceiling/cleanroom was officially completed this week. Tiles were installed in and the room is now fully complete and is in use. The coating of new beamviewer targets began this week.  Eight new targets have begun the coating process.  Four targets have the "slow" coating and four have the "fast" coating.  A new Temperature Diode crate has been bench tested and is ready to install in Zone 1 for the 1/4 Cryomodule.

WBS 9 (Beam Transport) G. Biallas:

# Sextupole (SF)

•     	At New England Techni-Coil they have four units at 90% assembled, four at 70% and three at 30%. Shipping of the first batch may be next week.

Replacement Chicane Dipoles (GW)

•     	The second unit was set on the stand to start its measurements.

•	Work continued at New England Techni-Coil on potting the last coil.  Rework of the mold again delayed potting the final coil with the mold finally being closed today.  Potting should start Tuesday.

# UV Line

• 	STI didn’t qualify its method of measuring even though noise and reproducibility are at the part in 10000 level. Their readings in the x plane are consistently 40 Gauss higher than in the Y plane regardless of magnet (They tested three) or turning the magnet by 90°. They are going through every operation in their scanning sequence to find the source.  No solution yet.  The hall probe system that slips into a fixture between poles of every magnet repeats to the part in 2500 level.

•	Meanwhile, quads are not tested and girder assembly remains on hold. The window to start assembly starts September 6. It now looks like first production-measured quads will not be here.

•	Most of the stands are now received and most of those are now in the enclosure.

•	Regional Assembly of the 8Fsub4 is in back checking before signature.

•	The Jlab Shop delivered three of the 5 chambers they have in production.

•	The downstream corner chamber with NEG Pumps is now in preliminary production.  The NEG Pump cartridge holder design is on hold until a designer is available.

# UV Wiggler Progress

•     	No progress on the new Wiggler vacuum chamber.

# IR PM Wiggler Vacuum Chamber Progress

•     	The support structures for the OCMMs and chamber are in fabrication.  We received both tubes for the chamber.  Fabrication can start.

WBS 10 (Wigglers) – S. Benson:

The EM wiggler was removed this week and the stands for the new permanent magnet were laid out for installation next week.   The detailed certification data was reviewed to see if there were any problems.  The wiggler looks excellent and exceeds almost all the specifications by a large margin.  The control panel was unpacked and is being mounted in place for initial tests.  STI Optronics is planning to come out the week of Sept. 19 to get the wiggler working with no vacuum chamber installed.

WBS 11 (Optics) – M. Shinn:

FEL mirrors:
The newly made DMA created with a newer, 3" deformer, had excellent performance (astigmatism was 0.04 waves or less), with moderate (1 wave) of deformation, but unacceptable amounts at the powers required to achieve the correct radius of curvature.  Coma and spherical aberration remained essentially constant.  We are considering adding the deformer stiffening ring that George Biallas devised (and is on the 2.8 micron DMA currently in the optical cavity). Meanwhile, we will have previously coated optics refurbished with a shorter ROC, so when coated, they will deform to about the correct value.

Other Activities

IR FEL activity for the month has several primary tasks: 1) Remove the OCMMS exterior hardware, so the EM wiggler could be removed 2) Housekeeping duties in the labs, especially those where class IV lasers 3) Prepare to install low aberration, low loss optics in the optical cavity.  4) Prepare for the 2nd generation OCMMS installation.  5) Preparations to extend the OTS from its present terminus in UL1 to UL6.  6) Bring the drive laser performance back to spec.  Item 1 was completed; the other items are in various stages of completion.  The test stand for the new delta ROC monitor (used for both the IR and UV systems), is working nicely with the addition of sturdier mounts, next week we'll look further into its performance.  The items required for the new OCMMS crosses are in fabrication.  Catalog items for most of the rest of the hardware are in Procurement.

UV FEL

The final assembly drawings for the OC internals were signed this week.  Alignment points were checked, to be transmitted to Survey and Alignment.  In the process, I found that we (WBS 10 & 11) system owners thought the wiggler was in the center of the optical cavity, when in fact it is not.  This forces us to transmit new ROC values to the vendor, and will cause a schedule slip.  We received the rest of the Macor thermal isolation parts; the issue that led to the cracking of the first one has been resolved.  We received management approval to complete the tasks we defined to do the scaled down cavity, and are proceeding with procurements.  The new pump cart nears completion.  We bid a "see you later" to Michael Snyder, a contract mechanical designer who has done the majority of the UV FEL optical drawings.  He also did the design of OTS Lite.  His talents and drive will be sorely missed, and we wish him the best.

Terahertz - G. Williams:

We continued working on the spectroscopy chamber designs and on specifications for the cooled detector.  A further meeting took place regarding safety of the existing bolometric detector cryogenic system.