| ISS Payload Integration Template |
| --- |
| International Space Station Program |
| Revision C |
| Type 1 – Approved by NASA |
| September 2007 |
| This document contains information that falls under the jurisdiction of the U.S. Department of Commerce Export Administration Regulations, 15 CFR 730-774, and is classified as EAR99. The export, re-export or re-transmission of this document or any of the data contained therein in violation of the Export Administration Regulations or other applicable U.S. export control laws and regulations is strictly prohibited. (HSV-07-0126) |
| National Aeronautics and Space Administration International Space Station Program Johnson Space Center Houston, Texas NAS15-10000 (F-MI-08) |  |

REVISION AND HISTORY PAGE

| Rev. | Description | Pub. Date |
| --- | --- | --- |
| - | Initial Release (Reference per SSCD 002654, EFF. 10-06-00) | 10-26-00 |
| A | Revision A (Reference per SSCD 006037, EFF. 09-11-02) | 10-21-02 |
| B | Revision B (Reference per SSCD 007991, EFF. 10-01-03) | 10-09-03 |
|  | This is the first release on IPIC. |  |
| C | Revision C (Reference SSCD 010342, EFF. 09-25-07) | 10-19-07 |

ERU:  /s/ Mary C. Nooney 10-19-07

INTERNATIONAL SPACE STATION PROGRAM

iss payload integration template

PREFACE

This document is the program definition of program milestones, products, and deliveries.  The schedule template dates assure the payload integration process is planned in a timely manner.  The integration template is defined and organized in terms of the following functional areas: Payload Developer (PD), Research and Payload Mission Integration, Payload Engineering Integration (PEI), Payload Software Integration, Payload Operations Integration Function (POIF), and Kennedy Space Center (KSC) Integration.  The payload milestone chronologies contained in Section 3 and the generic schedule templates contained in Appendix D are each organized in accordance with these functional areas.

| APPROVED BY: |  | /s/ William R. Jones II |  | 9-25-07 |
| --- | --- | --- | --- | --- |
|  |  | William R. Jones II Manager, ISS Payload Office National Aeronautics and Space Administration |  | Date |

INTERNATIONAL SPACE STATION PROGRAM

iss payload integration template

CONCURRENCE

September 2007

| PREPARED BY: | M. Nagy |  | IPI MI |
| --- | --- | --- | --- |
|  | Payload Integration Template Book Manager |  | ORGN |
|  | /s/ M. Nagy |  | 9/12/07 |
|  | SIGNATURE |  | DATE |
| CONCURRED BY: | G. Esquivel |  | OZ2 |
|  | Payload Mission Integration And Planning Manager |  | ORGN |
|  | /s/ A. Gerald Esquivel |  | 10/16/07 |
|  | SIGNATURE |  | DATE |
| Boeing DQA: | Annette Lehman |  | Boeing/GCS |
|  | Document Quality Assurance |  | ORGN |
|  | /s/ Annette Lehman |  | 9/12/07 |
|  | SIGNATURE |  | DATE |

INTERNATIONAL SPACE STATION PROGRAM

iss payload integration template

LIST OF CHANGES

September 2007

All changes to paragraphs, tables, and figures in this document are shown below:

| SSCD | Entry Date | Change | Paragraph(s) |
| --- | --- | --- | --- |
| SSCD 002654 | September 2000 | Baseline | All |
| SSCD 006037 | October 2002 | Revision A | All |
| SSCD 007991 | October 2003 | Revision B | All |
| SSCD 010342 | September 2007 | Revision C | All |

TABLE OF CONTENTS

PARAGRAPH	PAGE

1.0	INTRODUCTION	1-1

1.1	PURPOSE	1-1

1.2	SCOPE	1-1

1.3	PRECEDENCE	1-1

1.4	delegation of authority	1-2

2.0	documents	2-1

2.1	applicable documents	2-1

2.2	reference documents	2-2

3.0	iss payload milestone definitions	3-1

3.1	ISS PAYLOAD DEFINITIONS	3-1

4.0	ISS PAYLOAD MILESTONE CHRONOLOGY	4-1

5.0	INTERNATIONAL PARTNER LAUNCH VEHICLE UNIQUE MILESTONES	5-1

5.1	Automated Transfer Vehicle (ATV) Launch Milestones	5-1

5.2	RUSSIAN Vehicle (RV) Launch Milestones	5-3

5.3	HII Transfer Vehicle (HTV) Launch Milestones	5-5

APPENDIces

A	ACRONYMS AND ABBREVIATIONS	A-1

B	GLossary of terms	B-1

C	open work	C-1

D	SCHEDULE TEMPLATES	D-1

TABLEs

TABLE	PAGE

3.1-1	Iss payload milestoneS AND definitions (16 pages)	3-2

4.0-1A	pAYLOAD DEVELOPER MILESTONE CHRONOLOGY payload 
development phase (3 PAGES)	4-3

4.0-1B	pAYLOAD DEVELOPER MILESTONE CHRONOLOGY iss mission 
integration phase (10 pages)	4-6

4.0-2	PAYLOAD MISSION INTEGRATION MILESTONE CHRONOLOGY (7 pages)	4-16

4.0-3	PAYLOAD ENGINEERING INTEGRATION MILESTONE CHRONOLOGY 
(3 pages)	4-23

4.0-4	PAYLOAD SOFTWARE INTEGRATION MILESTONE CHRONOLOGY	4-26

4.0-5	PAYLOAD OPERATIONS INTEGRATION FUNCTION MILESTONE 
CHRONOLOGY (3 pages)	4-27

4.0-6	KENNEDY SPACE CENTER INTEGRATION MILESTONE CHRONOLOGY
(2 pages)	4-30

5.1-1	ATV Milestones (2 pages)	5-2

5.2-1	RUSSIAN VEHICLE MILESTONES	5-4

5.3-1	HII VEHICLE MILESTONES	5-5

# INTRODUCTION

## PURPOSE

The purpose of this document is to establish and define the generic integration schedule templates that are used to produce payload-unique integration schedules and payload flight complement integration schedules.

This document provides the single authoritative source for all International Space Station (ISS) payload integration milestone template dates.  This document serves as a reference source for ISS Payload Program implementing organizations for their respective integration product development schedules and corresponding processes.  This document also provides the Payload Developer (PD) community a reference source for all integration submittals required by the ISS Payload Program.

Schedule templates in this document reflect integration data submittals from the PDs, ISS Payload Program product deliveries, and major milestones such as Program-level reviews.  Schedule templates are used to ensure that the payload integration process can be completed successfully and in a timely manner. The Generic Payload Integration Manager (PIM) Schedule Templates are established by payload class (Pressurized, Small, Subrack, and Attached) and reflect detailed activities that are relevant to managing the successful mission integration of a given payload.  The Generic Payload Mission Integration Team (PMIT) Schedule Template reflects a high level rollup of milestones that are relevant to managing the overall integration of the payload flight complement.

## SCOPE

The templates and descriptive material contained in this document cover all ISS payload integration activities performed by the NASA ISS Payload Office for NASA sponsored or bartered payloads that are launched on the Space Shuttle vehicle.  Templates are applicable regardless of whether the payload will operate in the United States Laboratory (US Lab) or in an International Partner (IP) provided research module.

This document covers the integration template and products required for integration of payloads when launched on Space Shuttle, Russian Vehicles (Soyuz, Progress), European Space Agency (ESA) Automated Transfer Vehicle (ATV), and Japan Aerospace Exploration Agency (JAXA) H-II Transfer Vehicle (HTV).

## PRECEDENCE

Actual payload-specific or flight-specific implementation schedules may deviate from the templates in this document.  However, if there are discrepancies between other documentation and SSP 57057, Revision C, with regard to the schedule milestone template dates, the following order of precedence shall be used:

For ISS Program milestones, SSP 50489, ISS Mission Integration Template, shall take precedence.

For Space Shuttle Program milestones, JSC 25187, Appendix A, Flight Production Generic Templates, Shuttle Templates, shall take precedence.

<TBD 1-1>, ATV schedule milestone reference

<TBD 1-2>, HTV schedule milestone reference

SSP 57057, Revision C

## delegation of authority

This document is approved and controlled by the ISS Payload Control Board (PCB).

# documents

## applicable documents

The documents listed in this section are applicable to the extent specified herein.  Inclusion of applicable documents does not supersede the order of precedence identified in Paragraph 1.3 of this document.

| document | title |
| --- | --- |
| SSP 50489 | ISS Mission Integration Template |
| SSP-52000-IDD-ERP | Expedite the Processing of Experiments to Space Station (EXPRESS) Rack Payloads Interface Definition Document |
| SSP 52000-PVP-ERP | Generic Payload Verification Plan, Expedite the Processing of Experiments to Space Station (EXPRESS) Rack Payloads |
| SSP 52000-PIH-WRP, Volume III | Window Observational Research Facility (WORF) Rack Interface Definition Document, PIH Volume III |
| SSP 52000-PIH-WRP, Volume IV | Window Observational Research Facility (WORF) Generic Payload Verification Plan, PIH Volume IV |
| SSP 52000-PDS | Payload Data Sets Blank Book |
| SSP 52054 | ISS Program Payloads Certification of Flight Readiness Implementation Plan, Generic |
| SSP 5410X-ANX 1 | Increment Definition and Requirements Document for Planning Period X, Annex 1: Station Manifest (Series of Flight-Specific Station Manifests) |
| SSP 57001 | Pressurized Payloads Hardware Interface Control Document Template |
| SSP 57002 | Payload Software Interface Control Document Template |
| SSP 57004 | Attached Payload Hardware Interface Control Document Template |
| SSP 57072 | Standard Payload Integration Agreement for ISS Payloads |
| JSC 25187 Appendix A | Flight Production Generic Templates, Shuttle Templates |

## reference documents

The following documents contain supplemental information to guide the user in the application of this document.  These reference documents may or may not be specifically cited within the text of this document.

| document | title |
| --- | --- |
| SSP 50108 | Certification of Flight Readiness Process Document |
| SSP 50146 Revision A | NASA/RSA Bilaterial S&MA Process Requirements for International Space Station |
| SSP 50200-01 | Station Program Implementation Plan, Volume 1: Station Program Management Plan |
| SSP 50200-02 | Station Program Implementation Plan, Volume 2: Program Planning and Manifesting |
| SSP 50253 | Operations Data File Standards |
| SSP 50254 | Operations Nomenclature |
| SSP 50313 | Display and Graphics Commonality Standard |
| SSP 50431 | Space Station Program Requirements for Payloads |
| SSP 52000-PIH-WRP Volume VI-A | Window Observational Research Facility (WORF) Rack Payload Configuration Data Set Definition, PIH Volume VI-A |
| SSP 54504 | Increment Definition and Requirements Document, Annex 5: Payload Tactical Plan Blank Book |
| SSP 57000 | Pressurized Payloads Interface Requirements Documents |
| SSP 57003 | Attached Payload Interface Requirements Documents |
| SSP 57008 | Unique Pressurized Payload Non-Rack Interface Control Document Template |
| SSP 57059 | Standard Payload Integration Agreement for Pressurized Payloads |
| SSP 57061 | Standard Payload Integration Agreement for Attached Payloads |
| SSP 57063 | Standard Payload Integration Agreement for Small Pressurized Payloads |
| SSP 57064 | Payload Integration Agreement Blank Book for Small Pressurized Payloads |
| SSP 57066 | Standard Payload Integration Agreement for EXPRESS/WORF Rack Payloads |
| OPS-IDD-0-200 | ATV Dry Cargo Integration Interface Definition Document |
| P32928-103 (Russian Document) | Requirements for International Partner Cargoes Transported on Russian Progress and Soyuz Vehicles |
| POIF-1004 | Payload Operations Integration Center, Payload Operations Handbook Volume 1: Pre-/Post-Increment Operations |
| POIF-2001 | U.S. Payload Operations Data File Management Plan |
| NSTS/ISS 13830 | Payload Safety Review and Data Submittal Requirements for Payloads Using the Space Shuttle and International Space Station |
| D683-35491-1 | EXPRESS Rack Payload Configuration Data Set Definition |
| ESA-ATV-PR-13830 July 2004 | ATV Pressurized Payload/Cargo Safety Certification Process |

# iss payload milestone definitions

## ISS PAYLOAD DEFINITIONS

For the purposes of this document, the term “milestone” is used to define the completion of a product, activity or process.  A milestone may identify the submittal of a data item, the delivery, or shipment of a hardware item, the development of integration or operations product, or the completion of a Program or payload review.  Table 3.1-1, ISS Payload Milestones and Definitions, defines each of the milestones used in the ISS Payload Integration Templates and provides definitions for clarification.  The milestones acronyms are listed in alphabetical order to facilitate search.  Table 3.1-1 includes the following column headers:

Line Number:  The line number is assigned to each milestone acronym and is used to identify the milestone during documentation reviews, specific schedule development, and internal coordination.

Milestone Acronym:  The milestone acronym is the short-hand identifier used in the generic payload integration templates and on the flight and payload specific schedules.

Milestone Definition:  The milestone definition provides a brief description of the milestone acronym including reference to applicable documentation that provides a more detailed description.

| table 3.1-1 Iss payload milestoneS AND definitions (16 pages) |
| --- |
| Line # | Milestone Acronym | Milestone Definition |
| 1 | Assembly & Installation (A&I) Drawings | Assembly & Installation (A&I) Drawings Part of the Drawing Data Set, the Assembly and Installation Drawing shows the top assembly and complete information necessary to install the payload for launch. This drawing includes a listing of items to be installed by part number and nomenclature and quantity, locating dimensions and associated tolerances, required torques, and detail definition of any special requirements. Payload Developers provide the payload Main Unit Top Assembly drawing to PDL for use by KSC and PEI in developing integrated rack launch assembly and installation drawings, ECLs, or integrated rack level on-orbit drawings. See SSP 52000-PDS. |
| 2 | Acoustic Data (Middeck) | Acoustic Data (Middeck) Results from Acoustic Testing |
| 3 | BR KSC | Bench Review Kennedy Space Center Members of the Astronaut Office (crew members or designee) review cargo/stowage in its flight configuration during Bench Reviews (BR). Bench reviews are scheduled at KSC according to various MPLM/Node integration milestones. Hardware providers coordinate their shipments to KSC to meet processing schedules for turnover for the appropriate bench reviews based on rack integration, stowage location, and/or time. In addition, the ISS Program may also have pre-packed BR for other modules (ATV/HTV) at KSC and then ship payload and/or stowage items to final stowage integration facility. |
| 4 | BR JSC | Bench Review Johnson Space Center Members of the Astronaut Office (crew members or designee) review cargo/stowage in its flight configuration during BRs. All hardware on Russian Flights and hardware stowed in the Middeck are nominally conducted at JSC. In addition, the ISS Program may also have pre-packed bench review for other modules (MPLM/NODE/ATV/HTV) at JSC and then shipped to final stowage integration facility. |
| 5 | C&DH DS | Command and Data Handling Data Set C&DH DS is a segregation of PDL data that defines the flight unique software interface requirements between Integrated Payload Systems and ISS flight data handling elements. See SSP 57002, Payload Software Interface Control Document Template. |
| 6 | CCCD | Crew Compartment Configuration Drawings This is a SSP product to identify the MDK layout of all the hardware to review and support the CCCR. |
| 7 | CCCR | Crew Compartment Configuration Review This is a SSP review of the crew compartment configuration at the Integrated Product Team meeting. |
| 8 | CCCR Freeze | Crew Compartment Configuration Review Freeze The Middeck manifest requirements will be frozen to support preparation of the CCCR products which include the video, data and electrical plug-in plans in the Flight Requirements Document and CCCD. After CCCR, manifest changes must be approved by the SSP/ISS Program JPRCB if not classified as a mission success requirement. |
| 9 | CDR | Critical Design Review Most Payloads Projects as part of their hardware development effort will conduct a CDR when their hardware design reaches 90% maturity. The CDR represents completion of the classical Project Development Cycle Phase C. The CDR demonstrates a “build-to” detailed design baseline to fabricate, integrate and verify. The ISS Program provides a draft Interface Control Document in support of a CDR. The ISS Program also reviews the CDR data package for implications to ISS payload integration, and to provide verification guidance to the PD. |
| 10 | CEIT | Crew Equipment Interface Test CEIT allows the astronauts to interface with the flight hardware in its flight-like operational configuration with cabling. This provides the crew with the opportunity to check tools and the payload interfaces and become familiar with the hardware. |
| 11 | CIR Shuttle | Cargo Integration Review – Shuttle This review is conducted by the SSP Office to ensure that the ISS cargo elements manifested on a given Shuttle mission can be accommodated within the STS flight and ground capabilities. The Shuttle CIR is the major cargo-related review at which the ISS concurs with the integration and implementation of their requirements at the cargo/flight level. |
| 12 | CIR ATV | Cargo Integration Review – ATV This review is conducted by the ESA to ensure that the cargo elements manifested on a given ATV mission can be accommodated within the ATV flight and ground capabilities. The ATV CIR is the major cargo-related review at which the ESA concurs with the integration and implementation of their requirements at the cargo/flight level. |
| 13 | CIRD Shuttle | Cargo Integration Review Dry Run – Shuttle Conducted 3 weeks prior to CIR to identify any last issues that will possibly need to be worked at the CIR. Verify CIR electronic data package is complete for distribution. |
| 14 | CoFR OZ2 Pre-Coord Review | OZ2 Certification of Flight Readiness Pre-Coordination Review Primary objective is to review and concur with the CoFR letter including the schedule and identify CoFR responsibilities between IP/P and OZ |
| 15 | CoFR Bi-Lateral Pre-Coord Review | OZ2 Bi-lateral CoFR Pre-Coordination Review Primary objectives is for OZ and IP/P to review and concur with the CoFR letter including any product exchanges/schedules and determine participation requirements to support IP/P and OZ CoFR meeting |
| 16 | CoFR Release OZ Instruction Letter | Release OZ Certification of Flight Readiness Instruction Letter CoFR instruction letter defines CoFR endorsement requirements and schedule for a given flight, stage, or increment. Launch, on-orbit, and return/disposal payloads are identified. Included are PIRNs identifying ISS Program applicable requirement changes. |
| 17 | CoFR OWTL and LPA Inputs Due | Certification of Flight Readiness Open Work Tracking Log and Launch Package Assessment Inputs Due OZ2 conducts a program-wide review of all CoFR open work to focuses and identify any potential issues/threats and CoFR exceptions. Emphasis is made to prioritize work to close open endorsements prior to OZ SORR CoFR. |
| 18 | CoFR OZ2 OWTL & LPA Review | OZ2 Certification of Flight Readiness Open Work Tracking Log and Launch Package Assessment Review This review is only required if requested by the OZ Manager or if there is significant issues/threats to report to OZ management. |
| 19 | CoFR OZ OWTL and LPA Review | OZ Certification of Flight Readiness Open Work Tracking Log and Launch Package Assessment Review Certifying organizations specify open work required to certify all sub-endorsements as specified in SSP 52054. Identify any open items that would constrain or prohibit cargo integration/Shuttle rollout and provide a recovery plan and go/no go recommendation to proceed. |
| 20 | CoFR (ISS Program) LPA Dry Run and LPA | International Space Station Program Certification of Flight Readiness Launch Package Assessment Dry Run and Launch Package Assessment The Launch Package Management Team conducts the LPA Dry Run to prepare for the ISS Program LPA at the Space Shuttle Payload Control Board and for flights with International Partner elements, the LPA will be conducted at a joint Space Shuttle Control Board/SSPCB. The LPA addresses remaining open work, issues and constraints to ensure that there are no anticipated problems within ISS that would preclude the Scheduled delivery of payload to the pad. Including each certifying organizations providing a recommendation to proceed. The FPM is responsible for developing the presentation using the initial OWTL and LPA inputs data provided by the certifying organizations. |
| 21 | CoFR Endorsement Packages Due | OZ Certificate of Flight Readiness Endorsement Packages Due All OZ certifying organizations are required to submit a CoFR package per requirements referenced in SSP 52054. A nominal CoFR package includes a CoFR endorsement checklist OWTL, exceptions, and certification letter unless either the SSP 52054 or the OZ CoFR instruction letter identifies a reduction of these requirements. |
| 22 | CoFR IP/ IPM Readiness Review | Certificate of Flight Readiness IP/IPM Readiness Review Each IP/P conducts a CoFR review with their management to assure their readiness to support the ISS Program SORR. OZ participation is only required if there are issues or open work associated with OZ activities that would prevent an IP/P from satisfying any of the endorsements codes. |
| 23 | CoFR (OZ) Multilateral Package Review | OZ Certificate of Flight Readiness Multilateral Package Review OZ CoFR Review to approve the SORR charts developed by the IPM and for all certifying organizations to provide an OWTL statue in preparations for the ISS Program SORR. |
| 24 | CoFR SORR | Certification of Flight Readiness Stage Operations Readiness Review The SORR certifies that the Launch Package/Cargo Element ground support facilities and personnel are ready to support the flight stage, and/or increment. Additionally, it certifies the readiness of the on-orbit stage configuration to accept the Launch Package/Cargo Element and readiness for on-orbit increment operations. |
| 25 | Command & Telemetry Databases | Command and Telemetry Databases Contain the definitions needed to decom system and payload data on the ground; and to allow users to update and send commands. The payload portion is built from the information provided in the C&DH data Set. See SSP 57002. |
| 26 | Drawing DS | Drawing Data Set The Drawing Data Set controls the format and content of selected Payload Engineering Integration, and Configuration data required from Payload Developers to develop complement-level configuration drawings for the integrated International Standard Payload Rack (ISPR) and EXPRESS Rack. ISS Payload Engineering Integration uses the On-Orbit Operational Configuration Drawings to create Integrated Laboratory Module Configuration Drawings for the ground control team at Payload Operations and the Integration Facility (POIF). The ground control team uses these drawings to visualize what the planned payload configurations are during real-time operations. POIF uses the On-Orbit Operational Configuration Drawings to assist in building Payload Crew Procedures The configuration data is used to configure the payload during all phases of flight, including ascent, on-orbit, and return. See SSP 52000-PDS, Payload Data Sets Blank Book. |
| 27 | ECW | Export Control Worksheet, JSC Form 1724. Submitted to NASA, filed with USA Commerce Department, requesting approval for the Payload Developer (PD) to ship hardware out of the USA and in to a specific country. |
| 28 | EIRR | EXPRESS Integration Readiness Review The purpose of the EIRR is to conduct an assessment of all mission related systems of the experiment launch package to determine the readiness of the package to be integrated into the EXPRESS carrier. The data presented will be sufficient to validate the required certification that proves the experiment systems are ready for integration and on-orbit operations. |
| 29 | EMC Data | Electromagnetic Compatibility Data EMC RF Data is results from electromagnetic interference and compatibility analysis. EMC Test Data is test results from electromagnetic compatibility testing. |
| 30 | EMC Thermal Blanket Data (Cargo Bay Payload) | Electromagnetic Compatibility Thermal Blanket (Cargo Bay Payload) Results from Electromagnetic compatibility testing with the thermal blanket on the hardware item. |
| 31 | Engineering Configuration List (ECL) | Engineering Configuration List (ECL) Scoped payload hardware and drawing release definition (as-designed configuration) derived from the most current payload design drawings uploaded to PDL and the PDL ECL Report. Payload Developers provide hardware data and design drawings to PDL for their manifested payload hardware and embedded ORUs. PEI provides the comprehensive ECL which incorporates the as-designed configuration of all payloads for a given flights. See SSP 52000-PDS. |
| 32 | Engineering Stage Analysis Report | Element-Level Engineering Analysis Report The Payload Element-Level Engineering Analysis Report documents the stage-specific results of payload complement compatibility analysis for the specified element of the ISS, in response to the verification requirements of the Payload Verification Program Plan (PVPP). |
| 33 | EPAS | ETOV Payload Activity Summary The EPAS defines the ETOV Payload Planning Requirements to the Shuttle FAOs for development of the Flight Plan. |
| 34 | ETOV Payload Procedures | Earth-to-Orbit Vehicle Payload Procedures ETOV procedures are used for payload operations/monitoring during Shuttle ascent/descent and payload activities during docked phase of operations including research hardware transfer to/from ISS. The procedures reside in U.S. SODF. |
| 35 | Export Control Letter | Export Control Letter Per ISS Payload Program Policy and the Standard PIA requirements, an export control classification letter for the payload is required of the Payload Developer or sponsoring organization at the beginning of the payload integration process. The PIM will request this letter from the Payload Developer soon after a PIM assignment is made, and the delivery of this letter is independent of flight manifesting. This letter is needed for every new payload that the ISS Payload Office will integrate. The export control letter will identify to the ISS Program the export classification of the payload hardware, software, technical data, and payload project supporting documentation. |
| 36 | EXPRESS/ WORF Compatibility Analysis Report | The EXPRESS/WORF Compatibility Analysis Report The report is used to show compatibility of the integrated EXPRESS/WORF racks/payloads with the applicable requirements in SSP 57000, Pressurized Payloads Interface Requirements Document, as specified in the EXPRESS Interface Control Documents. The report documents the rack-level payload resource requirements for each stage and provides input to the element-level Stage Analysis. |
| 37 | FRD | Flight Requirements Document The document defines authorized requirements to be implemented on specific flights. |
| 38 | FOR | Flight Operations Review This review is conducted by MOD for the SSP and ISS Program Offices to ensure that the flight products to be used during real-time operations between the Space Shuttle and ISS meet ISS and SSP requirements for accomplishment of the mission. |
| 39 | FPSR | Flight Planning and Stowage Review This review baselines crew activities, crew compartment, and cargo bay stowage. It marks the final opportunity/freeze point to add powered MDK payloads or standard payload bay GAS payloads to the flight. |
| 40 | FR Annex | Flight Rules Annex The FR Annex documents pre-planned responses designed to minimize the need to develop real-time decisions in response to off-nominal situations that occur during mission operations. The FR Annex also documents the authority and responsibility of all organizations involved in the conduct of mission operations, including the IP mission control centers, POIC, engineering support functions, and the Mission Management Team. The FR Annex, Volume A contains the Space Shuttle generic rules. The FR Annex, Volume B will contain the generic ISS rules. The FR Annex, Volume C will contain generic joint ISS and Shuttle rules. Increment-specific flight rules will contain flight rules specific to a given increment activity or a joint ISS and Shuttle mission. A single annex will contain increment-specific rules for Volumes A, B, and C. The Increment-specific flight rules are submitted by POIF to JSC MOD to support FOR. |
| 41 | FRR | Flight Readiness Review The purpose of the FRR is to conduct an assessment of all mission-related flight and ground systems to determine the readiness to support the upcoming flight. NASA, NASA contractors, and IP representatives will certify readiness in their areas of responsibility. The data presented during the review will be sufficient to validate, in unambiguous terms, the required certification that proves the systems are ready for flight and on-orbit operations. |
| 42 | FSDP | Flight Safety Data Package Technical description of payload flight hardware and its operation. The data package includes definition of hazards, hazard controls, and verification. The Payload Developer submits the FSDP. |
| 43 | FSR | Flight Safety Review The flight safety review is conducted for all payloads and includes hazard analyses to systematically and objectively identify all hazards and hazard causes inherent in the design and flight operations, to evaluate controls, and to assess methods used to verify hazard controls. The integrated on-orbit safety encompasses both crew and vehicle safety. There are three phases of FSRs: Phase 0 /1, Phase II, and Phase III. |
| 44 | GCP Book | Ground Command Procedure Book The Ground Command Procedures Book contains step-by-step instructions for the POIC Cadre to control and monitor payloads and the ISS systems supporting those payloads. The Ground Command Procedures Book consists of multiple volumes. The Ground Command Procedures Book Volume 3 is for payloads and is updated as required due to changes in the payload compliment onboard. The other volumes are also updated as needed. The Ground Command Procedures Book is controlled by the U.S.PODFCB. |
| 45 | GL&C | Guidelines and Constraints The Payload Operations GL&C Report documents the stage element-level (including EXPRESS/WORF) operational restrictions for payloads located in the specified element of the ISS. These are derived from the Payload Element-Level Engineering Analysis Report. |
| 46 | GPVP | Generic Payload Verification Plan (EXPRESS/WORF Subracks only) The GPVP defines the complete set of payload verification requirements and provides instructions and guidelines for verifying interface compatibility and safety of as-built hardware and software for payloads to be placed on board the ISS. The requirements associated with the verification plan are identified in the Interface Definition Document (IDD). The GPVP also provides the required verification data and template dates for those submittals. |
| 47 | GSDP | Ground Safety Data Package Technical description of Ground Support Equipment (GSE) and its usage during ground processing. The data package includes definition of hazards hazard controls. The Payload Developer submits the GSDP. |
| 48 | GSR | Ground Safety Review The GSR process is conducted for the cargo elements, IP cargo elements, experiments, and all GSE/non-GSE planned for ground processing at KSC. There are three phases of GSRs: Phase 0/I, Phase II, and Phase III. |
| 49 | HFIT Hardware Evaluation | Human Factors Integrated Test Hardware Evaluation Evaluate the flight hardware requirement applicability against SSP 57000, with respect to Human Factors. The Human Factors Implementation Team (HFIT) provides feedback to the PD on requirements that have possible exceptions, list them in the internal forms and provides recommended closure of these requirements violations. Issues Certified of Compliance (CoC) to complete Payload Engineering Integration (PEI) requirement verifications. |
| 50 | HVR | Hardware Verification Review An internal ISS review coordinated by the Cargo Coordination function to verify the completion of cargo requirements (imagery, IMS bar code, Operations Nomenclature, labeling, paperwork) prior to the Bench Review. |
| 51 | H/W Audit | Hardware Audit A review conducted by the Launch Package Management Team of the Hardware Accountability Matrix Report (HAMR), to verify cargo requirements completion, manifest data, and establishes on dock delivery dates. The verified data is used to support the development of stowage drawings/engineering products such as SSCCD and CCCDs. The Hardware Audit is typically scheduled 3 months prior to the first bench review. |
| 52 | H/W ICD | Hardware Interface Control Document Defines the physical, functional, and environmental interfaces of PD H/W and the ISS. At CDR, a draft H/W ICD will be made available that provides “design –to” interface data and verification requirements applicability matrix. At L-12 the H/W ICD is baselined which will contain “mission-unique” configuration data. See SSP 57001, Pressurized Payloads Hardware Interface Control Document Template, SSP 57004, Attached Payload Hardware Interface Control Document Template, SSP 57008, Unique Pressurized Payload Non-Rack Interface Control Document Template, SSP 52000-PIH-WRP, Volume III, WORF Rack Interface Definition Document, PIH Volume III, and SSP 52000-IDD-ERP. |
| 53 | ICA (MDK) | Interface Control Annex (Middeck/Orbiter Crew Compartment) Interface control annex (ICA) defines payload equipment stowed or installed in the Orbiter crew compartment and requirements affecting interfaces, stowage, installation, or flight crew use. |
| 54 | IDRD | Increment Definition and Requirements Document The baselined IDRD documents the assigned flight dates; the resource and accommodation allocations among assembly, system, and utilization; an overview of the assembly, system, and utilization flight and increment activities; and prioritized requirements for execution planning of ISS Program flight- and increment-specific objectives within the planning period. See SSP 50489. |
| 55 | IDRD, Annex 1 | Increment Definition and Requirements Document, Annex 1 The IDRD, Annex 1 includes the detailed cargo manifest for all launch vehicles on a flight. The baselined IDRD, Annex 1 includes cargo items, newly manifested items, LON items, hazardous cargo, etc. The update contains manifest data for pre-packed items. See SSP 50489. |
| 56 | IDRD, Annex 5 PTP | Increment Definition and Requirements Document, Annex 5: Payload Tactical Plan This document provides the integrated multi-lateral utilization input to the IDRD. The Annex 5 PTP is an increment-specific multilateral Payload Program plan including: research objectives, crew training and baseline data collection requirements, the ascent/descent payload manifest for each flight in the increment, the on-orbit payload complement resource requirements, payload specific station and lab support equipment requirements, Utilization rack and subrack rack topologies, and inter-Partner cross-segment resource requests. The IDRD, Annex 5: PTP provides Payload Program direction to the Research Integration Offices, IPs, and implementing field centers. See SSP 50489. |
| 57 | IDRP | Increment Definition Requirements Plan The IDRP contains the Planning Period overview, major increment/flight specific objectives, and increment resources and accommodations for assembly, system, and utilization. OZ uses the utilization allocations to initiate Annex 5 PTP development. See SSP 50489. |
| 58 | IOR | Increment Operations Review The IOR is a major review between the ISS Program and those organizational elements responsible for executing operations planned for the increment. The IOR will assess the preparation and status of ISS mission operations. It will ensure that the ground facilities and operational documentation will be ready to support the final phase of training for both flight and ground personnel, as well as execute the real-time operations planned for the increment. Those products that are required to support crew training activities or are required at the beginning of the increment will be reviewed at the IOR. |
| 59 | IPLAT Label Evaluation | The ISS Payload Label Approval Team (IPLAT) IPLAT reviews and approves labels for compliance with SSP 57000, Appendix C, for all payload equipment that the crew will interface with during nominal operations, planned maintenance, and contingency operations. At the initial label evaluation phase, IPLAT provides a checklist to PD documenting the labeling requirements, which were violated as well as recommended solutions. At the final label evaluation phase, IPLAT reviews released engineering drawings/flight hardware labeling to check that all recommended changes were made and provides status for approval of the label drawing. IPLAT issues JSC Form 732-ISS Payload Label Final Disposition to complete label verifications. |
| 60 | IRR | Increment Requirements Review Integrated review by the ISS community involving Increment requirements, stage requirements, and joint docked operations. This review looks at allocations and preliminary feasibility of implementation per each flight of the Increment. |
| 61 | JMST | Joint Multi-Segment Station Training JMST involves payload training for a crew with the POIC (integrated simulations) and with all other control centers (joint integrated simulations). |
| 62 | KSC SRDS | Kennedy Space Center Support Requirements Data Set The SRDS documents the launch and landing site advanced planning for ground processing support requirements necessary to process a single ISS payload through the following activities: simulations preflight, in-flight, and post-flight phases associated with launch and recovery on the Space Shuttle system. This includes both hardware and science items to be processed at the launch and landing sites. See SSP 52000-PDS. |
| 63 | KSC TRDS | Kennedy Space Center Technical Requirements Data Set The payload-unique technical requirement submits are the detailed payload operations and maintenance requirements that are to be levied on KSC. These technical requirements are those that KSC is to perform on a payload during prelaunch, launch, recovery, and turnaround operations. See SSP 52000-PDS. |
| 64 | Lessons Learned Flight and Stage | Flight Lessons Learned The Flight Payload Manager (FPM) is responsible for pulling together all ISS Payloads lessons learned for the Increment Payload Manager (IPM) on a particular flight. That includes hardware integration prior to launch, during the joint timeframe and landing. Stage Lessons Learned The Increment Payload Engineer (IPE) is responsible for pulling together all ISS Payloads lessons learned for the Increment Payload Manager (IPM) on a particular stage. |
| 65 | Main Unit Top Assy Drawing, Subrack Payload | Main Unit Top Assembly Drawing, Subrack Payload Part of the Drawing Data Set, the Top level drawing is provided by an EXPRESS or WORF Rack subrack Payload Developer to PDL for use in development of integrated rack drawing products. The drawing includes all size dimensions, interface information (including torque valves), and special instructions required to integrate the payload. |
| 66 | Manifest and Stowage DS | Manifest and Stowage Data Set The Payload Manifest and Stowage Dataset define the flight-specific manifest items and their characteristics, which specify manifest requirements for payloads including subkit items and Inventory Management System (IMS)/barcode data. The Payload Manifest and Stowage Data are required by ISS Program Manifest, ISS Program Cargo Mission Contract (CMC), and the Flight Crew Support Division (FCSD). The data collected for the manifest will support the production of SSP 5410X-ANX 1, Increment Definition and Requirements Document for Planning Period X, Annex 1: Station Manifest (Series of Annexes of Flight-Specific Station Manifests). ISS Program CMC requires data in order to plan and design the launch, on-orbit, and return stowage configuration of payload stowage into on-orbit modules and logistic carriers. Physical data describing each payload manifest/stowage item to be packed and delivered/returned shall be electronically entered into PDL. FCSD requires data in order to plan and design the launch/return stowage configuration of the payload in the middeck locker(s). CMC also requires data in order to plan and design the launch/return stowage configuration of the payload stowage item into trays or bags. See SSP 52000-PDS. |
| 67 | MIP | Mission Integration Plan (MIP) The MIP is the Program-to-Program agreement between the ISS and the SSP for a specific Space Shuttle flight. The MIP is a joint Shuttle/ISS document that is mission-specific and covers agreed-upon overview requirements, products, and services. It also has annexes that contain detailed data and/or requirements for that particular mission. The Standard Integration Plan is used as the starting document to develop the mission-specific MIP and annexes. |
| 68 | MIP, Annex 1 | Mission Integration Plan (MIP), Annex 1 (Payload Data Package) MIP, Annex 1 provides information on weight and center of gravity, plus Launch Package configuration to determine compatibility of flight hardware to facilities and KSC support equipment. It consists of detailed data on the physical as-built characteristics of the payload. It includes a definition of the sequence mass properties, payload constrained frequencies, modes description, configuration drawings of all major payload elements, radio frequency transmitter characteristics, and functional data on the payload. It is used in conjunction with the ICD by systems and cargo engineering to develop engineering flight products. These data are also used by Mission Operations in the unique mission operations development. |
| 69 | MIP, Annex 2, Part 1 (Flight Planning) | Mission Integration Plan (MIP), Annex 2, Part 1 (Flight Planning) MIP, Annex 2, Part 1 comes from the VMDB Drop 1, which contains electrical power, energy, and cooling data. |
| 70 | MIP, Annex 4 | Mission Integration Plan (MIP), Annex 4 (Command and data) MIP, Annex 4 contains details of measurement and command parameters to implement IVT for LP/CEs via Orbiter resources. It consists of commands, telemetry, and software required operating the payload, measurements of the payload’s status and health, measurements necessary for accomplishing payload objectives, and other data needed for processing and interpreting data. It is used by those entities involved in building the flight software for each flight to understand parameter characteristics, fault detection and annunciation, scaling coefficients, digital and analog command specification, decom data, payload recorder requirements, channelization requirements, and the definition of the high-rate data transmitted via the Ku-Band. The ISS inputs to Annex 4 are contained in the ISS standard out deliveries. The ISS provided standard out data is the ISS launch package/payload data in ISS format and is integrated with the Shuttle Data Tape (SDT), channelization requirements, parameter characteristics, fault detection and annunciation, scaling coefficients, digital and analog command specification (Standard Out Data), decom data, and payload recorder requirements. It contains the 80 percent standard out and 100 percent standard out. It is baselined 6 months after 100 percent standard out. |
| 71 | MIP, Annex 5 | Mission Integration Plan (MIP), Annex 5 (MCC/Remote POCC Interface requirements) MIP, Annex 5 details interface agreement between SSP and the customer for operations support. Defines the format and content of the customer data required for SSP to integrate customer hardware into the flight and ground operations. Defines routing and the remote customer control center interface requirements and resources for a flight. |
| 72 | MIP, Annex 8 | Mission Integration Plan (MIP), Annex 8 (Launch Site Support Plan Addendum) The MIP, Annex 8, LSSP Addendum, is developed by KSC utilization to provide an overview of utilization payload processing that will take place at KSC. These plans are similar in content to the Launch Processing LSSP and are developed from the report capability of the PDL using the SRDS. LSSP milestones shown in the Payload Integration Flows reference LSSP Addenda. |
| 73 | OMRS | Operations and Maintenance Requirements and Specifications The MIP OMRS replaces MIP, Annex 9. The Payload Interface Verification Summary contains ISS Launch Package-to-Space Shuttle integration requirements at the launch site. It is used to develop and document the ISS and Orbiter integration requirements. ISS Payloads also use OMRS for KSC technical requirements imposed on KSC. See SSP 52000-PDS. |
| 74 | On-Orbit Configuration Drawing | On-Orbit Configuration Drawing, Part of the Drawing Data Set The drawing shows the on-orbit operational configuration for a given payload including all necessary hardware and the routing of cables and hoses that support the payload. This drawing includes a listing of items to be installed by part number, nomenclature, and quantity; cable and hose bend radius criteria; and detail definition of any special requirements. Payload Developers provide a payload level on-orbit drawing to PDL for use by PEI in developing the integrated rack level on-orbit drawing. See SSP 52000-PDS. |
| 75 | Ops Supportability Assessment | Operations Supportability Assessment Review of PD supportability to meet Ops assessment objectives. Appeal may be made by the PD on readiness for Ops assessment support taking into consideration P/L complexity, early product status, and cost implication to meet objectives. A PD Appeal route is PCB. |
| 76 | Ops Assessment | Operations Assessment: A End-to-End demonstration of the integrated payload crew interfaces including HFIT evaluation, pre-cursors to draft procedures, preliminary displays and OpNom, labeling plan, safety issues, hazard identification and operations concept. Attendees include the Payload Developer, Astronaut Office, HFIT-IPLAT, POIF representative. |
| 77 | Ops TIM | Operations Technical Interchange Meeting Early technical exchange meeting with the PD and POIF teams. Payload developers are introduced to the POIF ops team, ops products, and product timelines. Emphasis is placed on early definition of the PD ops concept, crew related tasks, OpNom, procedures and display development. |
| 78 | Passport | Passport An OC form includes additional data to support the export control request. |
| 79 | PCS Displays | Portable Computer System Displays The PCS displays are P/L unique crew displays for use on the P/L PCS that are built according to PD requirements. Payload-specific PCS displays are built (as needed) by PSIVF and delivered to the ISS Program. The ISS Program integrates the displays into a P/L PCS display load. See SSP 57002 (Software ICD). |
| 80 | PDR | Preliminary Design Review Most Payloads Projects as part of their hardware development effort will conduct a PDR when their hardware design reaches 30% maturity. The PDR is the completion activity of the Classical Project Development Cycle Phase B. The PDR demonstrates and baselines a feasible and credible design that will accomplish the stated goals within the constraints imposed by the fiscal and operating environment. The ISS Program provides preliminary interface control documentation in support of a PDR, reviews the PDR data package for implications to ISS operations, and provides development guidance to the PD. |
| 81 | PIA | Payload Integration Agreement The payload-unique PIA documents high-level agreements made between the ISS Program and the PD concerning ISS Station Support Equipment (SSE), Program Furnished Equipment (PFE), Ground Data Services (GDS) and unique agreements. |
| 82 | P/L Engineering Verification Memo | Payload Engineering Verification Memo A report produced for each ISS Stage containing status of unique payload verification, element level verification (including EXPRESS/WORF), ISS level verification and Requirements Change Assessment Report (RCAR) submittal. |
| 83 | P/L GDS BB Requirements | Payload Ground Data Services Blank Book Requirements The P/L GDS DS documents the ground system and communications requirements for supporting the on-orbit operations of the payload. GDS are provided by the ISS Program-furnished operations support center (e.g., POIC, U.S. OC, and a TSC), as well as by other operations facilities. See SSP 52000-PDS. |
| 84 | P/L GR&C | Payload Groundrules and Constraints Payload portion of the Increment-specific Execute Planning GR&C. |
| 85 | P/L Hazard Control Matrix | Payload Hazard Control Matrix The PHCM is an operations product that documents the completion of the Independent Safety Verification Review (ISVR) process. This process is lead by POIC Safety and independently verifies that all applicable operational hazard controls, defined in the payloads signed hazard reports, have been implemented properly. |
| 86 | P/L MDM Configuration Files | Payload Multiplexer/Demultiplexer Configuration Files P/L MDM Software functions and services are driven by payload configuration files. P/L MDM configuration files define current operational data and settings. P/L MDM services such as ancillary data services, file transfer, and health and status collection are controlled by PCF settings. See SSP 57002 (Software ICD). |
| 87 | P/L O/D | Payload On-Dock Relative to Launch Date KSC: Payload processing involves a variety of customer offline and/or KSC integrated activities and testing. Payload developers coordinate their arrival at KSC based upon their processing requirements and KSC turnover dates. Scheduled integrated activities are based upon the types of payloads. Attached payloads may require extensive final offline assembly, checkout, and servicing, and subsequent Shuttle and ISS integrated testing. Other attached payloads arrive at KSC already integrated on their carrier and have no planned KSC activities. O/D dates are based on each payload's unique processing schedule of activities. JSC: Stowage HDW that supports the JSC MDK or MPLM Bench Review will be delivered to JSC based on the LPMT need date (Reference BR JSC). |
| 88 | P/L OOS | Payload Increment On-Orbit Operations Summary The P/L OOS is a high-level plan providing a summary of payload activities for an entire increment. |
| 89 | P/L Planning DS | Payload Planning Data Set The P/L Planning DS contains the detailed payload operations and resource requirements specifications used to develop mission planning products. See SSP 52000-PDS. |
| 90 | P/L Regulations | Payload Regulations Payload regulations provide established priorities for payload activities, preplanned responses to off nominal situations, and unique information that enhances POIC’s ability to make real time operations decisions. See SSP 52000-PDS. |
| 91 | P/L Simulator | Payload Simulator The PD shall be responsible for providing a P/L Simulator to meet the training requirements for the crew and Ground Support Personnel (GSP) on the scientific and operational aspects of their payload. The P/L simulator requirements are agreed upon during the Training Strategy Team process and documented in the P/L Training Data Set. See SSP 52000-PDS. |
| 92 | P/L Training. | Payload Training P/L training is provided to the ISS crew going up on the first flight of the increment, regardless of launch vehicle. Training includes procedures training, increment-specific activities, proficiency training on skills, systems operations, and team training. Reflight - Reflight Training addresses payloads that have flown on a previous increment. Facility - New P/L Facility Training addresses new facility class payloads that have not flown on a previous increment. Subrack - New Payload Subrack Training addresses new subrack payloads that have not flown on a previous increment. Complement Training - Complement Training involves standalone training of the crew on the complement of payloads to be operated during ISS on-orbit activities. See SSP 52000-PDS. |
| 93 | Payload Transfer Dwgs/Reqmts | Payload Transfer Drawings/Requirement Part of the Drawing Data Set, these drawings conveys any special information needed to transfer payload hardware from a launch vehicle to the ISS. |
| 94 | P/L T/O | Payload Turn-Over (Kennedy Space Center) KSC: KSC receives custodial responsibility for payload hardware at turnover. Integrated racks will be turned over by KSC utilization to support MPLM install need dates. Hardware is turned over to support KSC “online” integrated mission processing activities as planned and required. When processing involves integrated testing activities, a thorough review of the flight hardware and its related IDP is performed. An IDP is not needed for flight-ready hardware, shipped directly to KSC logistics for stowage, and “turnover” is at hardware arrival, per shipping documentation. However, typically, hardware turnover follows a period of payload developer, offline activities at KSC. JSC: Stowage HDW that supports the JSC MDK or MPLM Bench Review will be turned over at JSC based on the LPMT need date (Reference BR JSC). |
| 95 | P/L Training DS | Payload Training Data Set The P/L Training DS documents requirements for user-provided and user/ISS Program-provided payload training for the ISS crew and ISS Program ground support personnel, and ISS Program requirements for training of user personnel. See SSP 52000-PDS. |
| 96 | P/L Verification Data | Payload Verification Data Stage Analysis – Unique, payload interface, verification data required by PEI to complete ISS element level verification for each stage; i.e., EMI, acoustics, thermal, protrusions, envelopes, power draws. Certificate of Compliance - Unique payload interface verification certification record that indicates the payload is in compliance with remaining applicable IRD requirements not utilized for Stage Analysis. |
| 97 | PPD DS | Payload Procedures and Displays Data Set The PPD DS addresses the requirements to supply United States (U.S.) Payload Operations Data File (PODF) products. Operations concept and analysis/flows, Payload displays, payload-unique Operations Nomenclature, manual procedures and support products, automated procedures, ground command procedures, and payload messages are included in this data set. See SSP 52000-PDS. |
| 98 | Proforma | Proforma A document, JSC Form 1735, must accompany the ECW. Includes financial data for hardware requested for export approval. |
| 99 | PRR | Payload Readiness Review The goal of the PRR is for the ISS Program, with payload developer support, to provide a payload readiness statement for launch, if there is a direct payload interface with the Orbiter’s payload bay or as requested by the cargo bay carrier integrator. This is applicable for large attached payloads. |
| 100 | PSM | Payload System Manual The PSM provides the PRO with the operating and reference data necessary to perform real-time commanding and monitoring of the facilities and payloads support systems. It also provides the POIC with a reference of operational concepts and technical data and schematics associated with payload systems. |
| 101 | PTDR | Payload Training Dry Run Prior to crew training, a PTDR will be held for each payload or experiment course, included on-board training products, to prove the readiness of the facilities, instructors, and training equipment/products. The instructor that has been designated to perform the training for the crew prepares the Payload Training Lesson Plan and courseware and then conducts the PTDR. Attendance is required by the responsible Operations Lead and crew representative in order to sign-off and certify the lesson. |
| 102 | PTP Input Tables | Payload Tactical Plan Input Tables PTP input tables are required of the Payload Developer prior to flight manifesting. Payload Developers – RPO working in conjunction with their PIM will fill out an investigation – level PTP input tables for each Increment which the Payload/investigation is operated. The PTP input tables are used as an initial source of payload integration data to perform tactical planning, and populate Increment-specific PTPs. |
| 103 | Rack Mass Properties and Test Verified Model | Rack Mass Properties and Test Verified Model Consist of rack weight, center of gravity, moment of inertia and product of inertia. Rack test verified model is a model that has been shown to behave in a manner acceptably close to test results of the item the model represents. For models intended to be used in coupled loads analysis, such as the EXPRESS rack model, this is usually done through comparison of normal modes analysis results generated by the model with the results of a modal survey performed on the hardware. This assures that the model behaves in a realistic fashion in terms of the dynamic behavior of the hardware, within a limited frequency range. Models intended for stress or displacement analysis would be verified against stress or displacement test results. |
| 104 | SDP | Safety Data Package A collection of safety and certification documents, to be submitted to the PSRP (Payload Safety Review Panel) by the hardware Payload Developer, requesting approval for flight upon a particular launch vehicle. |
| 105 | SSCCD/CMC Work Order | Space Station Configuration Control Drawings/Cargo Mission Contract Work Order The Space Station Configuration Control Drawings document the interior stowed configuration of the U.S. logistics carrier (currently, the MPLM) as required for launch and return. The top assembly drawing provides the mission unique cargo carrier configuration. Stowage rack level drawings provide the stowage locations of the hardware packed inside the racks. Bag/cushion level drawings provide the packed configuration and unique stowage instructions for the individual pieces of hardware. SSCCD bag level drawings are also provided for other launch vehicles such as the Shuttle Middeck, Soyuz, Progress, HTV and ATV to document JSC-packed Station hardware. Stowage Integration develops SSCCDs for the crew, systems, operational, logistics/maintenance hardware, and payload stowage items stowed in standard stowage racks. The results of all cargo layout planning are documented by the SSCCD which provide the physical installation requirements for the cargo with the logistics carriers. For KSC packed hardware the packing configuration can be documented in either an SSCCD or CMC Work Order which can be obtained from the assigned ISS Stowage Integration Flight Lead. |
| 106 | Stage Configuration Drawings | Stage Configuration Drawings US Lab Level Stage Configuration Drawings document the overall US Lab physical configuration of each payload rack (EXPRESS and Facility) and each integrated payload (subrack, deployed, and small payloads) that are on-orbit during a given stage. See SSP 52000-PDS. |
| 107 | Stowage H/W Drawings and Installed P/L Drawings | Stowage Hardware Drawings and Installed Payload Drawings Part of the Drawing Data Set, these drawings shows the as-built or as delivered configuration of the hardware being stowed for launch. Often the Main Unit Top Assembly Drawing is the Stowage H/W Drawing if a payload is being launched soft stowed, but drawings are also required for kits, sub-kits, or other hardware being launched separate from the main unit to show how the payload hardware should be configured for launch. |
| 108 | S/W ICD | Software Interface Control Document Documents requirements for command, data, and payload support software accommodations for the on-orbit and related ground-activity phases. See SSP 57002. |
| 109 | TDS | Technical Data Sheet OC form includes technical descriptions, pictures and drawings of hardware, to be sent to the Russians, to gain permission to fly on a Russian vehicle. |
| 110 | TGHR | Time-Critical Ground Handling Requirements MDK P/L time-critical Orbiter requirements are documented in a mission-specific TGHR table. The TGHR also includes time-critical requirements for other non-payload crew compartment items. MDK time-critical requirements include turnover, launch delay, and early turnover requirements. MDK orientation and power interrupt constraints are also documented in the TGHR. MDK IVT and any other requirements will be documented in OMRS File II, Volume II. See SSP 52000-PDS |
| 111 | Transfer List | Transfer List Transfer list is the product distributed and reviewed to support transfer cue card review meeting, which verify all stowage requirements/constraints are identified and scheduled to accommodate mission objectives. |
| 112 | TST | Training Strategy Team A NASA payload TST process has been defined to aid in the development of the payload training requirements for each payload or experiment and complements of payloads or experiments. Payload training requirements and what will be needed to fulfill those requirements, for both crewmembers and GSP, are discussed, defined, and agreed upon during this process. The official membership of the TST consists of MSFC training personnel, JSC training personnel, SSTF/PTC SME, PD Representatives, Crew Representatives, and Program Office personnel. See SSP 52000-PDS. |
| 113 | Usability Tests | Usability Tests The Usability Verification Event is a test/evaluation, conducted with case-appropriate rigor, to determine the readiness of payload on-board displays and procedures for PTDR, crew training and flight. It is performed to ensure operability for payloads, regardless of the type of Human Computer Interface (HCI). During the event, the candidate flight displays are evaluated for usability (per ISO 9241-11) and for commonality across payloads (i.e., common look and feel). Interoperability of the displays and procedures is also assessed. If warranted, a procedure only test/evaluation may be performed to ensure operability. Evaluations can be formal (i.e. conducted on flight representative hardware, face-to-face with crew and PD representatives), or informal (tabletop trial via telecon, with no hardware present, in a work session format). |
| 114 | U.S. PODF | U.S. Payload Operations Data File The U.S. PODF is the collection of procedures, displays and operations nomenclature necessary to perform U.S. payload operations. The procedures consist of manual, automated, and ground command procedures. The U.S. PODF is controlled by the U.S. PODFCB. See SSP 52000-PDS. |

# ISS PAYLOAD MILESTONE CHRONOLOGY

The tables in this section provide a detailed listing and identify all of the payload integration process milestones in chronological order.  The ISS payload integration milestones are grouped in this section within functional areas.  These functional groupings of integration milestones are:

Table 4.0-1: Payload Developer Milestone Chronology.  This table is separated into two parts, Payload Development Phase (Table 4.0-1A) and ISS Mission Integration Phase (Table 4.0-1B).  The Payload Development phase lists the typical payload project development activities that the ISS Program monitors or supports.  These activities normally occur prior to the manifest assignment; therefore, the dates provided represent a typical payload development template.  Although the ISS Payload Program does not require the activities and submittals identified in the Payload Development phase, it is in the best interest of the PD to solicit early ISS Payload Program guidance and support to avoid developmental cost and schedule impacts further downstream in the ISS Mission Integration phase.  The specific dates for these activities if applicable will be dependent upon the payload project’s unique development schedule, not the ISS payload integration process.  The ISS Mission Integration table lists the dates of all ISS Program “required” activities and submittals due from the PD.  These activities and submittals commence with the PD delivery of the Questionnaire/PTP input tables followed by manifesting of the payload via ISS Payload Program baseline of an Increment specific Payload Tactical Plan.

Table 4.0-2:  Payload Mission Integration Milestone Chronology.  This table lists ISS Payload Mission Integration (OZ2) submittals to the ISS Program/SSP and other key Program milestones.

Table 4.0-3:  Payload Engineering Integration Milestone Chronology.  This table lists ISS Payload Office Payload Engineering Integration (OZ3) submittals to the ISS Program/SSP and other key Program milestones.

Table 4.0-4:  Payload Software Integration Milestone Chronology.  This table lists ISS Payload Office Payload Software Integration (OZ5) submittals to the ISS Program/SSP and other key Program milestones.

Table 4.0-5:  Payload Operations Integration Function Milestone Chronology.  This table lists Payload Operations Integration submittals to the ISS Program/SSP and other key Program milestones.

Table 4.0-6:  Kennedy Space Center Integration Milestone Chronology.  This table lists Kennedy Space Center Utilization integration submittals to the ISS Program/SSP and other key Program milestones.

Dates within these chronology tables are for planning guidance and provide template data for the payload integration process generic schedule templates contained in Appendix D.  Actual payload-unique schedules implementation may deviate from the templates.  The chronology tables include the following column headers:

LINE #:  The line number is assigned to each milestone acronym and is used to identify the milestone during documentation reviews, specific schedule development, and internal coordination.

MILESTONE ACRONYM:  The milestone acronym is a short-hand identifier used in the generic payload integration templates and on the flight- and payload-specific schedules.

DATE (MONTHS):  Milestone date is referenced in relationship to start of an ISS Planning Period (PP), Increment (I), or Launch (L).  Some milestone dates may reference Payload Project development activity such as Preliminary Design Review (PDR), Critical Design Review (CDR) or Hardware Readiness.  The date is provided in months unless otherwise identified.  The milestone date indicated is the template date for the completion of a given milestone.

PREDECESSORS AND SUCCESSORS:  Identifies other milestones which typically occur prior to (predecessors) the milestone indicated, as well as other milestones that typically follow (successors) the milestone indicated.

F (Facility):  An ‘X’ in this column indicates the milestone is applicable to pressurized payloads and facility class payloads racks.  Payloads of this type typically have at least some amount of ISS interfaces or resources, which preclude them from meeting the “Small” payload criteria.

S (Small):  An ‘X’ in this column indicates the milestone is applicable to small payloads, including stowed/deployed.  Payloads of this type have minimal ISS interfaces and are very often passively stowed and temporarily deployed or setup in the US Lab aisle way when active.  Criteria for defining a Small payload are found in SSP 57063.

Sub (Subrack):  An ‘X’ in this column indicates the milestone is applicable to EXPRESS and WORF subrack payloads only.  Payloads of this type have some unique integration submittals not required by other payload types.

A (Attached):  An ‘X’ in this column indicates the milestone is applicable to attached (unpressurized) payloads.  Payloads of this type are attached externally to ISS for operations, but they can have some internal pressurized components.

PMIT (Payload Mission Integration Team):  An ‘X’ in this column indicates the milestone is included PMIT Flight schedules.

ORG (ISS Payload Program Organization):  This column header is only found in the PD Milestone Chronology Tables 4.0-1A and 4.0-1B.  This column is used to identify the ISS Payload Program organization that is the owner of the milestone with respect to this document.  The five organization choices for this column are:  PMI (Payload Mission Integration), PEI (Payload Engineering Integration), PSI (Payload Software Integration), Payload Operations Integration Function (POIF), and KSC (Kennedy Space Center Utilization integration).

The four payload classification columns identify which milestones are applicable to each payload class listed above.  If a unique date appears in one of these columns instead of an ‘X’, this date supersedes the milestone date for that payload class.  If a milestone is applicable to a payload classification, that milestone will appear on the Generic Payload Integration Manager (PIM) Schedule Template for that payload classification, and then used to develop unique payload schedules.

Some milestones within Table 4.0-2 will not have any payload classification applicability identified since they are for reference purposes only.

| table 4.0-1A pAYLOAD DEVELOPER MILESTONE CHRONOLOGY payload development phase (3 PAGES) |
| --- |
| Line # | Milestone Acronym | Date (Months) | Predecessors And Successors | F | S | Sub | A | PMIT | Org |
| 1 | Export Control Letter | * | Export Control Letter * Requested following new payload identification to the Program. Highly desirable to have prior to PDR or any ISS Program support of PDR or any PD development effort involving ISS Program personnel. Must have prior to Drawing Data Set submittal. | X | X | X | X |  | PMI |
| 2 | PDR | * | Preliminary Design Review * Typically would occur 3 years prior to launch. PD controls actual date of PDR. ISS Payload Program will support PDR. PDR may not be held by all PDs. | X | X | X | X |  | PMI |
| 3 | H/W ICD (P) | PDR | Hardware Interface Control Document (Preliminary) | X | X | X | X |  | PEI |
| 4 | OPS TIM | PDR | Operations Technical Interchange Meeting Payload Developers are introduced to Integration and Operations product timeline and flow. | X | X | X | X |  | POIF |
| 5 | PPD DS | PDR | Payload Procedures and Displays Data Set: Operations Concept; Operations Analysis/Flows These are optional PD submittals. | X | X | X | X |  | POIF |
| 6 | PPD DS | PDR | Payload Procedures and Displays Data Set: Operations Nomenclature (Baseline Payload Name) | X | X | X | X |  | POIF |
| 7 | Phase 0/I FSDP | Ph 0/I FSR -45 days | Phase 0/I Payload Flight Safety Data Pack 45 days before Phase 0/I FSR. | X | X | X | X |  | PMI |
| 8 | Phase 0/I P/L FSR | PDR+2 | Phase 0/I Payload Flight Safety Review | X | X | X | X |  | PMI |
| 9 | Phase 0/I GSDP | Ph 0/I GSR -45 days | Phase 0/I Payload Ground Safety Data Pack 45 days before Phase 0/I GSR. | X |  |  | X |  | PMI |
| 10 | Phase 0/I P/L GSR | PDR+3 | Phase 0/I Payload Ground Safety Review Timing to support Phase II definition of hazard controls by CDR. | X |  |  | X |  | PMI |
| 11 | CDR | * | Critical Design Review * Typically would occur 2 years prior to launch. PD controls actual date of CDR. ISS Payload Program will support CDR. CDR may not be held by all PDs, i.e. reflight or serial hardware. | X | X | X | X |  | PMI |
| 12 | Phase II FSDP | Ph II FSR -45 days | Phase II Payload Flight Safety Data Package 45 days before Phase II P/L FSR | X | X | X | X |  | PMI |
| 13 | HW ICD (Draft) | CDR | Hardware ICD (Draft) After HW ICD Preliminary | X | X | X | X |  | PEI |
| 14 | Ops Assessment Supportability | CDR+2 | Ops Assessment Supportability Two month before Ops Assessment. | X | X | X | X |  | PMI |
| 15 | Phase II P/L FSR | CDR+2 | Phase II Payload Flight Safety Review | X | X | X | X |  | PMI |
| 16 | Phase II GSDP | Ph II GSR -45 days | Phase II Payload Ground Safety Data Package 45 days before Phase II P/L GSR. | X |  |  | X |  | PMI |
| 17 | Phase II P/L GSR | CDR+2 | Phase II Payload Ground Safety Review | X |  |  | X |  | PMI |
| 18 | TST Process | CDR to CDR+4 | Training Strategy Team Process Participation Starts at CDR and typically requires 4 months to complete. | X | X | X | X |  | POIF |
| 19 | Drawing DS – Crew Interface Label Dwgs. | CDR+4 | Drawing Data Set: Crew Interface Label Drawings (Pre-released) Same time as Operations Nomenclature. (Abbreviations/Acronyms for Hardware Panels). | X | CDR+6 | CDR+6 | X |  | PEI |
| 20 | PPD DS | CDR+2 | Payload Procedures and Displays Data Set: Operations Nomenclature (Baseline Abbreviations/Acronyms for Hardware Panels, if needed); Initial Crew Displays Same time as Crew Interface Label Drawings (Pre-released). Before Candidate Flight Crew Displays submittal. | X | CDR+6 | CDR+6 | X |  | POIF |
| 21 | P/L Training DS | CDR+6 | Payload Training Data Set No later than 2 months after TST process complete. | X | X | X | X |  | POIF |
| 22 | PPD DS | CDR+7 | Payload Procedures and Displays Data Set: Operations Nomenclature (Baseline Abbreviations/Acronyms for Hardware Panels, if needed); Candidate Flight Crew Displays. After Crew Interface Label Drawings (Pre-released). | X | I-15 | I-15 | X |  | POIF |

| table 4.0-1B pAYLOAD DEVELOPER MILESTONE CHRONOLOGY iss mission integration phase (10 pages) |
| --- |
| Line # | Milestone Acronym | Date (Months) | Predecessors And Successors | F | S | Sub | A | PMIT | Org |
| 1 | PTP Input Tables | I-17 | Investigation Level Questionnaire for Payload Developer Increment Specific Requirements 7 months before IDRD Annex 5 PTP Baseline. | X | X | X | X | X | PMI |
| 2 | PPD DS | I-16 | Payload Procedures and Displays Data Set: Manual Procedures; Procedure/Display Files List; Reference Data; Validation Record Report; Log Files; IPV Links; Payload Messages 6 months before Start New P/L Training. | X | I-14 | I-14 | X |  | POIF |
| 3 | Reflight P/L Training | I-16 | Training for “Reflight” Payloads PD participation only required if PD provides instructor. Reflight Pressurized facility (rack-level) payloads not requiring PD training support could start earlier. 12 months before Start Complement Training. |  | I-16 | I-16 | I-16 |  | POIF |
| 4 | PCS Display Requirements (P) | L-16 | PCS Requirements for Program Built Displays (Preliminary) 7 months before P/L MDM Configuration Files/PCS Displays (P). 4 months before S/W ICD (P). | X |  | X | X |  | PSI |
| 5 | C&DH DS (P) | L-16 | Command and Data Handling Data Set (Preliminary) (If Program is not to build displays) Initial L-12. Preliminary L-8. Final L-3. | X |  | X | X |  | PSI |
| 6 | EXPRESS/ WORF Laptop Payload SW Application and Displays (P) | L-16 | EXPRESS/WORF Laptop Payload SW Application and Displays (Preliminary) (If application is not the sole payload application to be integrated onto the laptop) Demonstrate EXPRESS/WORF laptop integrated SW load is compatible. |  |  | X |  |  | PSI |
| 7 | Manifest and Stowage DS (B/L)- Middeck | L-15 to L-14 | Manifest and Stowage Data Set (Baseline) Middeck 1.5 months before ISS Program Preliminary Manifest available at same time as ISS Program. Call for manifest requests (MR cutoff date varies) for the Flight. | X | X | X | X | X | PMI/ PEI |
| 8 | H/W ICD – Draft Update | L-14 | Hardware Interface Control Document draft update | X | X | X | X |  | PEI |
| 9 | P/L Trainer O/D at JSC | I-13 | Payload Trainer hardware and software delivery to JSC training facility 3 months before New P/L Training. | X | I-11 | I-11 | I-11 |  | POIF |
| 10 | P/L GDS BB | I-13 | Payload Ground Data Services Blank Book sent to PD Teams 3 months before GDS Blank Book Requirements are Baselined. | X | X | X | X |  | POIF |
| 11 | EMC RF Data (Cargo Bay Payload) | L-12.9 | EMC Radio Frequency Data for Cargo Bay Payloads Prior to EMC Panel approval. 4 months before CIR. 8 months before ISS Program EMC Test Data to SSP. |  |  |  | X |  | PMI |
| 12 | KSC TRDS ISS to P/L OMRS, File 10, Volume 2 (P) submittal | L-12.5 | Kennedy Space Center Technical Requirements Data Set International Space Station to Payload Operations and Maintenance Requirements and Specifications, File 10, Volume 2 (Preliminary) submittal 0.5 month before KSC TRDS OMRS, File 10, Volume 2 (P). | X | X | X |  |  | KSC |
| 13 | KSC TRDS Bay to P/L OMRS, File 2, Volume 2 (P) submittal | L-12.5 | Kennedy Space Center Technical Requirements Data Set Bay to Payload Operations and Maintenance Requirements and Specifications, File 2, Volume 2 (Preliminary) submittal 0.5 month before KSC TRDS OMRS, File 2, Volume 2 (P). |  |  |  | X | X | KSC |
| 14 | Drawing DS - On-Orbit Configuration Drawings (B/L) | L-12 | Drawing Data Set: On-Orbit Configuration Drawings (Baseline) | X | X | X | X |  | PEI |
| 15 | Drawing DS - Main Unit Top Assy Drawing (B/L) | L-12 | Drawing Data Set: Main Unit Top Assembly Drawings Payload (Baseline) | X | X | X | X |  | PEI |
| 16 | P/L Verification Data and COCs | L-12 to L-3(or turnover) | Payload Verification Data COCs, and RCARs Payload Verification Data (stage analysis related), Certificates of Compliance (COCs), and Requirements Change Assessment Report (RCAR). Dependent upon payload type, verification submittals are required across a range of dates related to launch beginning at L-12 to L-3. Specific drop date are: L-12, L-11.5, L-11, L-10.5, L-10, L-9.5, L-9, L-7.5, L-7,L-6.5, L-5, L-4.5, L-3.5, L-3 (or turnover) | X | X | X | X | X | PEI |
| 17 | EMC Thermal Blanket Data (Cargo Bay Payload) | L-11.9 | EMC Thermal Blanket Data for Cargo Bay Payloads 1.5 months before ISS Program/SSP Final EMC Report. |  |  |  | X | X | PMI |
| 18 | PTDR | I-11 | Payload Training Dry Run This milestone is applicable to new payloads or payloads with major revisions in objectives or training products as determined by TST 1 month before Start New P/L Training. | X | I-9 | I-9 | I-9 |  | POIF |
| 19 | PCS Display Requirements (I) | L-11 | PCS Requirements for Program Built Displays (Interim) These requirement updates will be used as the basis for baselining the PL PCS SW Requirements Specification (SRS) 4 months before P/L MDM Configuration Files/PCS Displays (I). | X |  | X | X |  | PSI |
| 20 | Drawing DS - Stowage H/W Dwgs and Installed P/L Dwgs (B/L) | L-11 | Drawing Data Set: Stowage hardware drawings and installed P/L drawings 1 month before SSP need date for installed P/L drawings. 2 month before ICA B/L. Before Hardware Audit (MPLM and Middeck). | X | X | X | X |  | PMI/ PEI |
| 21 | IDRD Annex 3 | I-13 | IDRD Annex 3 – Imagery Requirement Orbiter – Docked, Pre, Post EVA Transfer | X | X | X | X |  | PMI |
| 22 | New P/L Training | I-10 | Training for “New” Payloads 1 month after PTDR. 2-4 months before Start Complement Training. | X | I-8 | I-8 | I-8 |  | POIF |
| 23 | Rack Mass Properties and Test Verified Model | L-10.5 to L-9.5 | Rack Mass Properties and Test Verified Model 3.5 months before VADAR. 3 months before submitting monthly mass properties. | X |  |  |  | X | PEI |
| 24 | P/L Exception Submit | L-9.5 | Payload Exception Submittal | X | X | X | X |  | PEI |
| 25 | P/L Verification Data | L-9.5 to L-7.5 | Payload Verification Data (Stage Analysis Data) 3 months before Final Stage Analysis Report. | L-7.5 | L-7.5 | L-9.5 | L-7.5 | X | PEI |
| 26 | C&DH DS (I) | L-9 | Command and Data Handling Data Set (Interim) 2 months before P/L MDM Configuration Files/PCS Displays (I). 1 month before S/W ICD (I). 2 months before POIC Command & Telemetry Database (I). | X |  | X | X |  | PSI |
| 27 | EXPRESS/ WORF Laptop Payload SW Application and Displays (I) | L-9 | EXPRESS/WORF Laptop Payload SW Application and Displays (Interim) (If application is not the sole payload application to be integrated onto the laptop) Demonstrate EXPRESS/WORF laptop integrated SW load is compatible. |  |  | X |  |  | PSI |
| 28 | Drawing DS – Crew Interface Label Dwgs | I-8 | Drawing Data Set: Crew Interface Label Drawings (Released) Before IPLAT grants approval for PD to produce/order labels. | X | X | X | X |  | PEI |
| 29 | Manifest and Stowage DS (U/D) – MPLM/Node & Middeck | L-6 to L-3 | Manifest and Stowage Data Set (U/D) MPLM/Node & Middeck – Subkit Data L-2 months before Bench Review (L-6 for MPLM/Node and L-3 for MDK). | X | X | X | X | X | PMI/ PEI |
| 30 | PCS Display Requirements (F) | L-8 | PCS Requirements for Program Built Displays (Final) These requirement updates will be used as the basis for updating the PL SW Requirements Specification (SRS) to its final flight baseline state 4 months before P/L MDM Configuration Files/PCS Displays (F). | X |  | X | X |  | PSI |
| 31 | P/L Planning DS Initial Submittal | I-8 | Payload Planning Data Set Initial Submittal 6 months before P/L OOS (F) and P/L GR&C (F). | X | X | X | X | X | POIF |
| 32 | Drawing DS – On-Orbit Configuration Drawings (U/D) | L-7.5 | Drawing Data Set: On-Orbit Configuration Drawings (Update) 4.5 months after Baseline. | X | X | X | X |  | PEI |
| 33 | Drawing DS – Main Unit Top Assy Drawing (U/D) | L-7.5 | Drawing Data Set: Main Unit Top Assembly Drawings Payload (Update) 4, 5 months after Baseline. | X | X | X | X |  | PEI |
| 34 | EXPRESS/ WORF Laptop Payload SW Application and Displays (F) (Multiple P/L applications being integrated on laptop) | L-7 | EXPRESS/WORF Laptop Payload SW Application and Displays (Final) (Multiple P/L applications being integrated on laptop) CD with the P/L application will be provided to the PSIVF so that an integrated laptop load can be developed. |  |  | X |  |  | PSI |
| 35 | PPD DS | I-7 – I-5.5 | Payload Procedures and Displays Data Set: ECR to Baseline Manual Procedures; Procedure Hazard Control List After Tabletop, Usability Verification, Crew Training window from I-7 to I-5.5 months. | X | X | X | X |  | POIF |
| 36 | Drawing DS – Stowage H/W Dwgs and Installed P/L Dwgs (U/D) | L-7 | Drawing Data Set: Stowage hardware drawings and installed P/L drawings (Update) 1.5 months before HAMR B/L. 2 months before SSCCD Released. | X | X | X | X |  | PMI/ PEI |
| 37 | Drawing DS – P/L Transfer Dwgs/Rqmts (B/L) | L-6 | Drawing Data Set: Payload Transfer Drawings/Requirements (Baseline) |  |  | X |  |  | PEI |
| 38 | KSC O/D for Activity Testing | L-6 | Kennedy Space Center On-Dock for Activity and Testing Arrival of Payload Hardware at KSC. PRCU Testing. | X |  | X | X | X | KSC |
| 39 | KSC Offline Activity | L-6 to L-4.5 | Kennedy Space Center On-Dock for Offline Activity Arrival of Payload Hardware at KSC. PRCU Testing. | X |  | X | X | X | KSC |
| 40 | KSC TRDS Orbiter MDK to P/L OMRS, File 2, Volume 2 (P) submittal | L-6 | Kennedy Space Center Technical Requirements Data Set Orbiter Middeck to Payload Operations and Maintenance Requirements and Specifications, File 2, Volume 2 (Nominal)(Preliminary submittal) 1 month before OMRS, File 2, Volume 2 (P). | X | X | X |  | X | KSC |
| 41 | PPD DS | L-6 | Payload Procedures and Displays Data Set: Final Ground Command Procedures 3 months before GCP Book (Final). | X | X | X | X |  | POIF |
| 42 | C&DH DS (F) | L-6 | Command and Data Handling Data Set (Final) 2 months before P/L MDM Configuration Files/PCS Displays (F). 3 months before S/W ICD (F). 2 months before POIC Command & Telemetry Database (F). | X |  | X | X |  | PSI |
| 43 | KSC SRDS (P) | H/W O/D-6 | Kennedy Space Center Support Requirements Data Set (Preliminary) 6 months before payload hardware on dock at KSC. 5 months before LSSP Addendum (B/L). | X | X | X | X | X | KSC |
| 44 | Phase III GSDP | Ph III GSR -45 days | Phase III Ground Safety Data Pack 45 days before Phase lll GSR. | X | X | X | X | X | PMI |
| 45 | Phase III GSR | L-5.6 | Phase III Ground Safety Review The phase III Safety Review must be completed 30 days prior to delivery to the launch site. Actual Safety Review date is flexible, but must consider the complexity of the hardware and operations, potential safety issues, and whether the safety activities will be required to support integrated assessments. | X | X | X | X | X | PMI |
| 46 | Phase III FSDP | Ph III FSR -45 days | Phase III Flight Safety Data Pack 45 days before Phase III FSR. | X | X | X | X | X | PMI |
| 47 | Phase III FSR | L-5.6 | Phase III Flight Safety Review The phase III Safety Review must be completed 30 days prior to delivery to the launch site. Actual Safety Review date is flexible, but must consider the complexity of the hardware and operations, potential safety issues, and whether the safety activities will be required to support integrated assessments. | X | X | X | X | X | PMI |
| 48 | Manifest and Stowage DS (U/D) Bar Codes/IMS and S/N data (MPLM/Node) | L-5 | Manifest and Stowage Data Set (Update) – Bar Code/IMS and Serial Number Data (MPLM/Node) L- 1 month from BR (L-5 MPLM/Node). | X | X | X | X | X | PMI |
| 49 | MPLM/Node HDW O/D & T/O #1 BR KSC | L-5 to L-4.5 | MPLM/Node Hardware On-Dock and Turn-Over #1 Bench Review at Kennedy Space Flight Center (dependent on processing requirements) 2 weeks before the #1 Bench Review. | X | X | X | X | X | KSC |
| 50 | EMC Test Data (Cargo Bay Payload) | L-5 | EMC Test Data for Cargo Bay Payloads 3.5 months before ISS Program/SSP Final EMC Report. |  |  |  | X |  | PMI |
| 51 | KSC TRDS Orbiter MDK to P/L TGHR Table (P) submittal | L-4.5 | Kennedy Space Center Technical Requirements Data Set Orbiter Middeck to Payload Time-Critical Ground Handling Requirements Table (Preliminary) submittal 0.5 month before Orbiter MDK TGHR table (P). | X | X | X |  | X | KSC |
| 52 | MPLM/Node H/W O/D & T/O #2 BR KSC | L-3 | MPLM/Node Hardware On-Dock and Turn-Over #2 Bench Review at Kennedy Space Flight Center 2 weeks before the #2 Bench Review. | X | X | X | X | X | PMI |
| 53 | KSC PRCU Testing | L-4.5 to L-3.5 | Kennedy Space Center Payload Rack Computer Unit Testing 2.5 months after Payload on-dock KSC. | X |  | X | X | X | KSC |
| 54 | CoFR OWTL and LPA Inputs | L-3 | Certificate of Flight Readiness Open Work Tracking Logs and Launch Package Assessment Inputs Open Work Tracking Log (OWTL). Inputs. | X | X | X | X | X | PMI |
| 55 | CoFR OZ2 OWTL and LPA Review | L-10 weeks | OZ2 Certification of Flight Readiness Open Work Tracking Log and Launch Package Manager Review Potential threats, exceptions, open work. | X | X | X | X | X | PMI |
| 56 | P/L COC | L-4.5 to L-3.5 | Payload Verification Data (Certificates of Compliance) | X | X | X | X | X | PEI |
| 57 | P/L Test Data for ICA | L-4 and L-2.5 | Payload Test Data for Interface Control Annex Due at L-4 months Thermal Structures Due at L-2.5 months EMC Acoustic | X | X | X | X |  | PMI |
| 58 | VAR | L-3.5 | Verification Acceptance Review 3.5 months after VADAR. | X |  |  |  | X | PMI |
| 59 | Manifest and Stowage DS – (U/D) Middeck | L-2 | Manifest and Stowage Data Set – (U/D) Middeck Bar Code/IMS and Serial Number Data 2 months before MDK Bench Review. | X | X | X | X | X | PMI |
| 60 | CoFR OZ OWTL and LPA Review | L-9 weeks | OZ Certification of Flight Readiness Open Work Tracking Log and Launch Package Managers Review Potential threats, exceptions, open work. | X | X | X | X | X | PMI |
| 61 | PPD DS | L-2 | Payload Procedures and Displays Data Set: Payload Automated Procedures (Timeliner Files) | X |  | X |  |  | POIF |
| 62 | CoFR Endorsement Packages Due | L-7 weeks | Certification of Flight Readiness Endorsement Packages Due -OWTL -Payload Developer’s Checklist -Exceptions -Certification Letter | X | X | X | X | X | PMI |
| 63 | CoFR OZ2 Endorsement Package Review | L-6 weeks | Certification of Flight Readiness Endorsement Package Review Updates to OWTL. Complete Endorsement Package. | X | X | X | X | X | PMI |
| 64 | MDK BR H/W O/D JSC | L-1.5 months | Middeck Bench Review Hardware On-Dock at Johnson Space Center 2 weeks before L-1 JSC MDK Bench Review. | X | X | X | X | X | PMI |
| 65 | MDK HDW O/D KSC (Nominal Installation) | L-22 days to H/W T/O | Middeck Hardware On-Dock Kennedy Space Center (Nominal Installation) Approximately 7 working days before MDK T/O KSC for launch. | X | X | X | X | X | KSC |
| 66 | HDW MDK O/D KSC (Late Installation) | L-15 days to H/W T/O | Middeck Hardware On-Dock Kennedy Space Center (Late Installation) Approximately 10 working days before MDK T/O KSC for launch. | X | X | X | X | X | KSC |
| 67 | MDK HDW T/O KSC (Nominal Installation) | L-8 days | Middeck Hardware Turn-Over Kennedy Space Center (Nominal Installation) Approximately 7 working days after MDK O/D KSC. | X | X | X | X | X | KSC |
| 68 | MDK HDW T/O KSC (Late Installation) | L-3 days to L-28 hours | Middeck Hardware Turn-Over Kennedy Space Center (Late Installation) Approximately 10 working days after MDK O/D KSC. | X | X | X | X | X | KSC |
| 69 | Lessons Learned Due | Landing + 2 months Stage + 2 months | Lessons Learned Due from the Payload Developer 2 months after the Landing for Flight Lessons Learned. 2 months after the Stage for Stage Lessons Learned. | X | X | X | X |  | PMI |

| table 4.0-2 PAYLOAD MISSION INTEGRATION MILESTONE CHRONOLOGY (7 pages) |
| --- |
| Line # | Milestone Acronym | Date (Months) | Predecessors And Successors | F | S | Sub | A | PMIT |
| 1 | ISS Payload Process Overview | * | ISS Payload Process Overview * Initial PIM meeting with PD following PIM assignment to present the ISS Payload process Overview (Roadshow). Also will cover optional services the Program could provide to the PD such as HFIT evaluation, procedures, displays and OpNom developmental guidance, and operations concept support. | X | X | X | X |  |
| 2 | Export Control Letter Concurrence | * | ISS Program concurrence for Export Control Letter * 1 month after receipt of Export Classification Letter from PD. | X | X | X | X |  |
| 3 | PIA (PCB) | CDR+1 | Payload Integration Agreement (Baseline) | X | L-11 | X | X |  |
| 4 | Ops Assessment | L-20 | Operations Assessment 2 months after the Ops Assessment Supportability. | X | X | X | X |  |
| 5 | Inc Res Plan Kickoff | I-18 | Increment Research Plan Kickoff The Increment Research Plan Kickoff results in the baseline of an Increment Research Complement at I-15 and resulting PTP CR |  |  |  |  |  |
| 6 | MIP Cargo Bay P/L B/L Input | L-17 | Mission Integration Plan Cargo Bay (Payload Baseline Input) Mission Integration Plan Cargo Bay Payload Baseline. PTP baseline, coordinate inputs with PIM for ISS payloads. |  |  |  |  |  |
| 7 | Feasibility Checklist | I-16 | Feasibility Checklist Completion by the PIMs drives the Feasibility Assessment (I-16 to I-15) in support of the Increment Research Directive Baseline | X | X | X | X |  |
| 8 | MIP (B/L) | L-16 | Mission Integration Plan (Baseline) 7 months before CIR. |  |  |  |  |  |
| 9 | IDRD (BL) | I-16 | Increment Definition and Requirements Document (Baseline) 8 months after IDRP release. This is an ISS Program product. |  |  |  |  |  |
| 10 | Feasibility Assessment | I-16 to I-15 | Feasibility Assessment Feasibility Assessment supports the baseline of the Increment Research Directive | X | X | X | X |  |
| 11 | IDRD P/L B/L Input | I-15 | Increment Definition and Requirements Document (Payload Baseline Input) In parallel with PTP development. 2 to 3 months before IDRD Rev A(U/D). |  |  |  |  |  |
| 12 | PTP CR Release | I-15 | Payload Tactical Plan Change Request Release The PTP CR is the resulting formal documentation of the data approved in the Research Directive and will occur simultaneously with the Research Directive baseline at the I-15 MPCB. | X | X | X | X | X |
| 13 | Inc Res Dir (B/L) | I-15 | Increment Research Directive Baseline The Increment Research Directive baseline initiates the release of the Increment PTP CR. Both occur simultaneously at the I-15 MPCB. |  |  |  |  | X |
| 14 | IDRD Annex 1 P/L (B/L) Input - | L-15 to L-12.5 | Increment Definition and Requirements Document Annex 1 Payload Baseline Submit Post Manifest approval at PCB via Research Post PD Manifest and Stowage submit. Before MR cut-off for IDRD Annex 1 B/L. | X | X | X | X | X |
| 15 | MIP Annex 1 P/L Input | L-14.5 | Mission Integration Plan Annex 1 Payload Data Package (Payload input) Input for Cargo Bay Payloads only. 4.5 months before MIP Annex 1 B/L. |  |  |  | X | X |
| 16 | MIP Annex 5 P/L Input | L-14.3 | Mission Integration Plan Annex 5 Payload Operations Control Center (Payload input) 7 months before Baseline. |  |  |  |  | X |
| 17 | FRD (B/L) | L-13.2 | Flight Requirements Document (Baseline) 2.8 months after MIP B/L. 4.2 months before CIR. |  |  |  |  | X |
| 18 | IDRD Rev A (U/D) | I-12 | Increment Definition and Requirements Document Revision A (Update) 4 months after IDRD (B/L). |  |  |  |  | X |
| 19 | IRR | I-12 | Increment Requirements Review Use PTP latest revision. |  |  |  |  | X |
| 20 | IDRD Annex 1 L-12 (B/L) | L-12 | Increment Definition and Requirements Document Annex 1 L-12 (Baseline) 3 months before CIR. |  |  |  |  | X |
| 21 | MIP Annex 4 P/L Input | L-11.6 | Mission Integration Plan Annex 4 Command and Data (Payload Input) 1.8 month minimum before MIP Annex 4 B/L. |  |  |  |  | X |
| 22 | P/L ICA Submit Due Date | L-11.1 | Payload Interface Control Annex Submit Due Date 2 months weeks before after ICA B/L with the IDRD Annex 1 B/L data. 2 weeks before ICA B/L CR release. |  |  |  |  | X |
| 23 | MIP –Appendix E Submit | L-11.1 | Mission Integration Plan Appendix E Submit 3 weeks after ISS Program IDRD Annex 1 manifest approved. 2.1 months prior to CIR to support powered payload requirements and ICA Baseline. |  |  |  |  | X |
| 24 | MIP Annex 2 Part 1 P/L Input | L-11 | Mission Integration Plan Annex 2 Part 1 Flight Planning (Payload Input) 5.1 months before MIP Annex 2, Part 1 B/L. |  |  |  |  | X |
| 25 | IDRD Annex 5: PTP (B/L) | I-10 | Increment Definition and Requirements Document Annex 5: Payload Tactical Plan (Baseline) | X | X | X | X | X |
| 26 | IDRD P/L Rev A Input | I-10 | Increment Definition and Requirements Document Revision A (Payload Input) 2 month before IDRD Rev B (U/D). |  |  |  |  | X |
| 27 | IDRD App I Sub to LPMT | L-10 | Increment Definition and Requirements Document Appendix I (Transfer Priorities) Submit due to Launch Package Management Team |  |  |  |  | X |
| 28 | MIP Annex 1 (B/L) | L-10 | Mission Integration Plan Annex 1 Payload Data Package (Baseline) 1 month before CIR. |  |  |  |  | X |
| 29 | CIRD | L-9.8 | Cargo Integration Review Dry Run |  |  |  |  | X |
| 30 | FPSR List | L-9.2 | Flight Planning and Stowage Review List |  |  |  |  | X |
| 31 | IDRD P/L Rev B Input | I-9 | Increment Definition and Requirements Document Revision B (Payload Input) 1 month before IDRD U/D to Rev B. |  |  |  |  | X |
| 32 | IORR | I-9 | Integrated Operation Readiness Review |  |  |  |  | X |
| 33 | CIR | L-9 | Cargo Integration Review |  |  |  |  | X |
| 34 | ICA (B/L) | L-9 | Interface Control Annex (Baseline) |  |  |  |  | X |
| 35 | IDRD ANNEX 3 | I-8 | Increment Definition and Requirements Document Annex 3 IDRD Annex 3 – Imagery Requirement: - Orbiter – Docked, Pre, Post - EVA - Transfer |  |  |  |  |  |
| 36 | HAMR Rel (MPLM/Node & MDK) | L-8 | HAMR Release (MPLM/Node & MDK) |  |  |  |  | X |
| 37 | IDRD App I Approval | L-8 | Increment Definition and Requirements Document Appendix I (Transfer Priorities) Approval |  |  |  |  | X |
| 38 | FPSR | L-7.7 | Flight Planning and Stowage Review 1.3 months after ICA B/L. 2.3 months after released stowage dwgs and installed P/L dwgs. Freeze point for Middeck Powered Payload requirements. |  |  |  |  | X |
| 39 | MPLM/Node & MDK H/W Audit | L-7.5 | MPLM/Node & MDK Hardware Audit 2 weeks after HAMR release. |  |  |  |  | X |
| 40 | MIP Annex 5 (B/L) | L-7.3 | Mission Integration Plan Annex 5 Payload Operations Control Center (Baseline) 4.3 months or greater before JMSTs. 3.5 months before FOR. |  |  |  |  | X |
| 41 | MIP Annex 4 (B/L) | L-7.7 | Mission Integration Plan Annex 4 Command and Data (Baseline) 3 weeks before CIR. |  |  |  |  | X |
| 42 | VADAR | L-7 | VADAR |  |  |  |  | X |
| 43 | MAPs B/L | L-7 | MAPs Baselined (MPLM/Node) |  |  |  |  | X |
| 44 | IDRD Annex 1 L-6 (U/D) | L-6 | Increment Definition and Requirements Document Annex 1 L-6 (Update) 2 months before FOR. 1 month after IDRD Annex 1 (L-6) MR Cut-off. 3 months after IDRD Annex 1 (L-9) Update. |  |  |  |  | X |
| 45 | OZ2 CoFR Pre-Coord Rev | L-5 | Certification of Flight Readiness Pre-Coordination Review |  |  |  |  | X |
| 46 | MIP Annex 2 Part 1 (B/L) | L-4.9 | Mission Integration Plan Annex 2, Part 1 Flight Planning (Baseline) |  |  |  |  | X |
| 47 | OZ2 Bilateral CoFR Pre-Coord Rev | L-4.5 | OZ2 Bilateral Certification of Flight Readiness Pre-Coordination Review |  |  |  |  | X |
| 48 | HAMR MDK | L-4.5 | HAMR Release (MDK Only) |  |  |  |  | X |
| 49 | IOR | I-4 | Increment Operations Review 2.5 months after P/L OOS (B). 2.5 months after P/L GR&C (B). |  |  |  |  | X |
| 50 | Release CoFR OZ Instruction Letter | L-4 | Release OZ Certification of Flight Readiness Instruction Letter | X | X | X | X | X |
| 51 | SSCCD (F) | L-4 | Space Station Configuration Control Drawings (Final) 2 weeks before Bench Review. | X | X | X | X | X |
| 52 | MPLM/Node Phase III FSDP | L-4 | MPLM/Node Phase III Flight Safety Data Package 1.5 month before the MPLM/Node Phase III FSR. |  |  |  |  | X |
| 53 | MPLM/NODE BR #1 KSC | L-4 | MPLM/NODE Bench Review #1 |  |  |  |  | X |
| 54 | MDK HDW Audit | L-4 | Middeck Hardware Audit 2 weeks after HAMR Release. |  |  |  |  | X |
| 55 | HDW BR JSC | L-3.75 | Hardware Bench Review JSC |  |  |  |  | X |
| 56 | FOR | L-3.7 | Flight Operations Review 3 weeks before the Start of JMST. |  |  |  |  | X |
| 57 | CoFR OWTL & LPA Inputs | L-3 | Certification of Flight Readiness Open Work Tracking Log and Launch Package Assessment Inputs Due |  |  |  |  | X |
| 58 | MPLM/NODE BR #2 | L-3 | MPLM/NODE Bench Review #2 |  |  |  |  | X |
| 59 | OFK Submit to SSP | L-3 | Official Flight Kit (OFK) Submit to SSP due date |  |  |  |  | X |
| 60 | CCCR Freeze | L-3 | CCCR Freeze 1 months before CCCR. |  |  |  |  | X |
| 61 | IDRD Annex 1 L-3 (U/D) | L-3 | Increment Definition and Requirements Document Annex 1 L-3 (Update) CR to support CCCR Freeze. 3 months after IDRD Annex 1 (L-6) Update. |  |  |  |  | X |
| 62 | CCCD Release | L-2 | Crew Configuration Compartment Drawings | X | X | X | X | X |
| 63 | OZ2 OWTL & LPA Rev | L-10 weeks | OZ2 Open Work Tracking Log and Launch Package Assessment Review |  |  |  |  | X |
| 64 | OZ OWTL & LPA Rev | L-9 weeks | OZ Open Work Tracking Log and Launch Package Assessment Review |  |  |  |  | X |
| 65 | MPLM/Node Phase III FSR | L-2.5 | MPLM/Node Phase III Flight Safety Review |  |  |  |  | X |
| 66 | OFK Items Del | L-2 | Official Flight Kit Items Delivered |  |  |  |  | X |
| 67 | CCCR | L-2 | Crew Configuration Compartment Review 1 month after CCCR Freeze. 1 month after CCCD Released. |  |  |  |  | X |
| 68 | ISS Program LPA | L-7 weeks | International Space Station Program Launch Package Assessment |  |  |  |  | X |
| 69 | CoFR Endorsement Pack Due | L-7 weeks | Certification of Flight Readiness Endorsement Packages Due |  |  |  |  | X |
| 70 | OZ2 CoFR Endorsement Pack Rev | L-6 weeks | OZ2 Certification of Flight Readiness Endorsement Package Review |  |  |  |  | X |
| 71 | IP/P CoFR RR | L-5.5 weeks | IP/P Certification of Flight Readiness Readiness Review (OZ participation, as required) |  |  |  |  | X |
| 72 | IRR Kickoff | L-4 weeks from HDW Installation | Increment Requirements Review (IRR) Kick-Off (MPLM/Node Only Flights) |  |  |  |  | X |
| 73 | CSRD | L-3.5 weeks | CSRD |  |  |  |  | X |
| 74 | Transfer List | L3 weeks | Transfer List Reviews begin |  |  |  |  | X |
| 75 | IDRD Annex 1 L-6 weeks (U/D) and subsequent | L-6 weeks to L-2 weeks | Increment Definition and Requirements Document Annex 1 L-6 weeks (Update) Weekly update as required. 1 week after IDRD Annex 1 weekly MR Cut-off. |  |  |  |  | X |
| 76 | CoFR OZ Multilateral Readiness Review | L-4.5 weeks | OZ Certification of Flight Readiness Multilateral Readiness Review 1 week before SORR. | X | X | X | X | X |
| 77 | MPLM/Node HDW BR #1 KSC | L-4 | Multi-Purpose Logistics Module/Node Hardware Bench Review #1 Kennedy Space Center MPLM HDW Bench Review #1 at Kennedy Space Center. 1 month after H/W O/D. | X | X | X |  | X |
| 78 | HDW VER REV | L-1 w from BR | Hardware Verification Review |  |  |  |  | X |
| 79 | IDRD Annex 2 B/L Flt Req | L-1.75 | Increment Definition and Requirements Document Annex 3 Baseline (Flight Requirements) |  |  |  |  | X |
| 80 | ICA Res for L-10 Day BR sub | L-1.3 | Interface Control Annex Reserve for L-10 days Bench Review Submit |  |  |  |  | X |
| 81 | MDK HDW BR JSC | L-1 | Middeck Hardware Bench Review at Johnson Space Center 2 weeks after H/W O/D. | X | X | X | X | X |
| 82 | ICA Res CR Approval for L-10 days BR Appr | L-28 days | Interface Control Annex Reserve Change Request for L-10 days Bench Review Approval |  |  |  |  | X |
| 83 | SORR | L-3.5 weeks | Stage Operations Readiness Review 2.5 weeks after CoFR submittal. |  |  |  |  | X |
| 84 | CCCD Rel for L-10 days BR | L-18 days | CCCD Release for L-10 days Bench Review |  |  |  |  | X |
| 85 | FRR | L-2 weeks | Flight Readiness Review |  |  |  |  | X |
| 86 | HDW O/D L-10 days BR | L-2 weeks from BR | Hardware On-Dock L-10 days Bench Review |  |  |  |  | X |
| 87 | IRR Final | L-2 weeks from HDW Installation | Installation Readiness Review Final (MPLM/NODE Only Flights) |  |  |  |  | X |
| 88 | MDK L-10 Day BR (JSC) | L-10 days | L-10 day Middeck Bench Review at Johnson Space Center 2 weeks after H/W O/D. |  |  |  |  | X |
| 89 | EIRR | Testing Start – 4 weeks | EXPRESS Integration Readiness Review 4 weeks before testing. |  |  | X |  |  |
| 90 | RMDP Rel | L-2 days | RMDP Release |  |  |  |  | X |
| 91 | RMDP B/L | Launch | RMDP Baseline |  |  |  |  | X |

| table 4.0-3 PAYLOAD ENGINEERING INTEGRATION MILESTONE CHRONOLOGY (3 pages) |
| --- |
| Line # | Milestone Acronym | Date (Months) | Predecessors And Successors | F | S | Sub | A | PMIT |
| 1 | Drawing DS - Crew I/F Label Dwgs (IPLAT Label Evaluation) (P) | CDR+4.5 | IPLAT Initial Label Evaluation of (Pre-released) Crew Interface Label Drawings 2 weeks after submittal of Crew Interface Label Drawings (Pre-released). IPLAT returns ISS Payload Label Verification checklist to PD containing IPLAT concurrence or recommendations. The PD will make corrections to label design if violations occur. | X | CDR +6.5 | CDR +6.5 | X |  |
| 2 | H/W ICD (DRAFT) | CDR+1 | Hardware Interface Control Document (Draft) only contains “design-to” data and verification applicability matrix except for subrack payloads which will also have “mission-unique” data | X | X | X | X |  |
| 3 | H/W ICD (B/L) | L-12 | Hardware Interface Control Document (Baseline) 2 months after PD submit of mission unique data. | X | X | X | X | X |
| 4 | Drawing DS - On-Orbit Configuration Drawing, EXPRESS/ WORF (P) | L-11 | On-Orbit Configuration Drawing, EXPRESS/WORF (Preliminary) 5 months before B/L. This milestone is applicable at the integrated EXPRESS or integrated WORF rack level only. It does not apply to Subrack level payloads. | X |  |  |  |  |
| 5 | Drawing DS - A&I Drawings, EXPRESS/WORF (P) | L-11 | Assembly and Installation Drawings, EXPRESS/WORF (Preliminary) 5 months before B/L. This milestone is applicable at the integrated EXPRESS or integrated WORF rack level only. It does not apply to Subrack level payloads. | X |  |  |  |  |
| 6 | Payload Exceptions | L-9.5 | Payload Exceptions to the IDD | X | X | X | X |  |
| 7 | Drawing DS – Crew I/F Label Dwgs (IPLAT Label Evaluation) (F) | I-7.5 | IPLAT Final Label Evaluation of (Released) Crew Interface Label Drawings 2 weeks after submittal of Crew Interface Label Drawings (Released). Before Bench Review. IPLAT will issue JSC Form 732 Label Approval. JSC Form 732 will be included into HFIT CoC and Form 883. | X | X | X | X |  |
| 8 | Drawing DS - On-Orbit Configuration Drawing, EXPRESS/WORF (B/L) | L-6 | On-Orbit Configuration Drawing, EXPRESS/WORF (Baseline) 5 months after Preliminary. This milestone is applicable at the integrated EXPRESS or integrated WORF rack level only. It does not apply to Subrack level payloads. | X |  |  |  |  |
| 9 | Drawing DS - A&I Drawings, EXPRESS/WORF (B/L) | L-6 | Assembly and Installation Drawings, EXPRESS/WORF (Baseline) 5 months after Preliminary. This milestone is applicable at the integrated EXPRESS or integrated WORF rack level only. It does not apply to Subrack level payloads. | X |  |  |  |  |
| 10 | Drawing DS – Stage Configuration Drawing (P) | L-6 | Stage Configuration Drawings (Preliminary) 3.5 months before B/L. | X | X |  |  |  |
| 11 | Engineering Configuration List (ECL) (B/L) | L-6 | Drawing Data Set: Engineering Configuration List (ECL) (Baseline) Parts List only – no drawing sheets. | X | X | X | X |  |
| 12 | EXPRESS/ WORF Compatibility Analysis Report for Stage XX | L-6 | EXPRESS/WORF Compatibility Analysis Report for Stage XX |  |  | X |  |  |
| 13 | HFIT Final Hardware Evaluation | L-4.5 | Issued CoC and Form 883 after Form 882 is completely closed. | X | X | X |  |  |
| 14 | Engineering Stage Analysis Report | L-4.5 | Payload Element Level Engineering Analysis Report 3 months after PD submittal of Stage Analysis verification data. | X | X |  | X | X |
| 15 | GL&C | L-4 | Payload Operations Guidelines and Constraints Element-Level Report | X | X | X | X | X |
| 16 | Drawing DS - Stage Configuration Drawings (B/L) | L-2.5 | Stage Configuration Drawings (Baseline) 3.5 months after Preliminary. | X | X |  |  |  |
| 17 | ISS Level P/L Complement Analysis report | L-3 | Payload Element Level Stage Analysis Report | X | X | X | X | X |
| 18 | P/L Engineering Verification Memo | L-6 weeks | Payload Engineering Verification Memo – Stage Level Before SORR activity start. | X | X | X | X | X |

table 4.0-4  PAYLOAD SOFTWARE INTEGRATION MILESTONE CHRONOLOGY

| Line # | Milestone Acronym | Date (Months) | Predecessors And Successors | F | S | Sub | A | PMIT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | P/L MDM Configuration Files/PCS Displays (P) | L-14 | Payload MDM Configuration Files/Portable Computer System Displays (Preliminary) 2 months after Preliminary C&DH data set. 2 months before Preliminary S/W ICD. | X |  | X | X |  |
| 2 | S/W ICD (P) | L-12 | Software Interface Control Document (Preliminary) 4 months before S/W ICD (I). | X |  | X | X |  |
| 3 | S/W ICD (I) | L-8 | Software Interface Control Document (Interim) 4 months after S/W ICD (P). 1 month before P/L MDM Configuration Files/PCS Displays (I). Submit to S/W ICD (F). | X |  | X | X |  |
| 4 | P/L MDM Configuration Files/PCS Displays (I) | L-7 | Payload MDM Configuration Files/Portable Computer System Displays (Interim) 2 months after Interim C&DH data set. 1 month after Interim S/W ICD. | X |  | X | X |  |
| 5 | P/L MDM Configuration Files/PCS Displays (F) | L-4 | Payload MDM Configuration Files/Portable Computer System Displays (Final) 2 months after Final C&DH data set. 1 month before Final S/W ICD. | X |  | X | X |  |
| 6 | S/W ICD (F) | L-3 | Software Interface Control Document (Final) 5 months after S/W ICD (I). | X |  | X | X |  |

| table 4.0-5 PAYLOAD OPERATIONS INTEGRATION FUNCTION MILESTONE CHRONOLOGY (3 pages) |
| --- |
| Line # | Milestone Acronym | Date (Months) | Predecessors And Successors | F | S | Sub | A | PMIT |
| 1 | PPD DS Displays (ECR to B/L) | I-13 | Payload Procedures & Displays Data Set: ECR to Baseline Displays 5 month after Usability Verification. | X | I-11 | I-11 | X |  |
| 2 | Reflight P/L Training | I-18 | Training for “Reflight” Payloads Reflight Pressurized facility (rack-level) payloads not requiring PD training support could start earlier. 12 months before Start Complement Training. |  | I-16 | I-16 | I-16 |  |
| 3 | Procedure Tabletop | I-16 | Procedures Tabletop After first procedure delivery. Before Usability Verification and/or PTDR. Window of 2 months. | X | I-14 | I-14 | X |  |
| 4 | Usability Verification | I-15.5 | Usability Verification of Payload Specific Displays Window is 2 months long. Before PTDR. After Candidate Display Delivery. After Procedures Tabletop. | X | 13.5 | 13.5 | X |  |
| 5 | P/L Training DS (B/L) | I-12 | Payload Training Data Set (Baseline) 1 month before PTDR. 2 months before Start New P/L Training. | X | I-10 | I-10 | I-10 |  |
| 6 | PTDR | I-11 | Payload Training Dry Run This milestone is applicable to new payloads or payloads with major revisions in objectives or training products as determined by TST. 1 month before Start New P/L Training. | X | I-9 | I-9 | I-9 |  |
| 7 | New P/L Training | I-10 | Training for “New” Payloads 1 month after PTDR. 2-4 months before Start Complement Training. | X | I-8 | I-8 | I-8 |  |
| 8 | GDS BB (B/L) | I-10 | Ground Data Services Blank Book (Baseline) 3 months after GDS Blank Book is sent to PDs. | X | X | X | X |  |
| 9 | POIC Cmd & Tlm DB (I) | L-7 | POIC Command & Telemetry Databases (I) 2 months after C&DH Interim dataset. | X |  | X | X |  |
| 10 | P/L Regs | I-7 | Payload Regulations 5 months before Payload Regulations (Baseline). | X | X | X | X |  |
| 11 | EPAS (Preliminary) | L-6.5 | Earth-To-Orbit Vehicle (Shuttle) Payload Activity Summary (Preliminary) Flight specific milestone. This is a POIF product submittal to MOD. | X | X | X | X | X |
| 12 | FOR Data Pack Review | L-6.1 | FOR Data Package Available for Review |  |  |  |  | X |
| 13 | Complement Training | I-6 | Complement Training for the Increment 2-4 months after Start New P/L Training. 3 months before Start JMST. | X | X | X | X |  |
| 14 | Flight Rules Annex | L-6 | Flight Rules Annex 2 months before Shuttle Flight FOR. This is a POIF product submittal to MOD. | X | X | X | X | X |
| 15 | ETOV Payload Procedures to U.S. SODF | L-5.5 | Earth-To-Orbit Vehicle (Shuttle) Payload Procedures Submit to U.S. Systems Operations Data File 1.5 months before Shuttle Flight FOR. This is a POIF product submittal to MOD. | X | X | X | X |  |
| 16 | P/L Planning DS (B/L) | I-4.25 | Payload Planning Data Set (Baseline) 3.75 months after Planning Data Set submittal. 2.25 months before P/L OOS and P/L GR&C. | X | X | X | X | X |
| 17 | POIC Cmd & Tlm DB (F) | L-4 | POIC Command & Telemetry Databases (F). 2 months after C&DH Final dataset. | X |  | X | X |  |
| 18 | Integrated ER P/L Safing Proc (B/L) | L-3 | Integrated EXPRESS Rack Payload Safing Procedure (Baseline) After individual payload safing procedures are baselined. | X |  |  |  |  |
| 19 | PPD DS Procedures (B/L) | I-4 | Payload Procedures and Displays Data Set: Manual Procedures (Baseline) | X | X | X | X |  |
| 20 | P/L Regs (B/L) | I-3 | Payload Regulations (Baseline) 4 months after Payload Regulations input. | X | X | X | X | X |
| 21 | JMST | I-3 | Joint Multi-Segment Station Training 3 months after Start Complement Training. | X | X | X | X |  |
| 22 | Integrated ER P/L Safing Proc (B/L) | L-3 | Integrated EXPRESS Rack Payload Safing Procedure (Baseline) After individual payload safing procedures are baselined. | X |  |  |  |  |
| 23 | GCP Book (F) | L-3 | Ground Command Procedures Book (Final) | X | X | X | X |  |
| 24 | PSM (F) | L-3 | Payload System Manual (Final) | X | X | X | X |  |
| 25 | EPAS (B/L) | L-2.5 | Earth-To-Orbit Vehicle (Shuttle) Payload Activity Summary (Baseline) Flight specific milestone. This is a POIF product submittal to MOD. | X | X | X | X | X |
| 26 | P/L OOS | I-5.5 to I-2.0 | Payload Increment On-Orbit Operations Summary | X | X | X | X | X |
| 27 | P/L GR&C (F) | I-2.0 | Payload input to Groundrules and Constraints (Final) 2.25 months after Planning Data Set (F). Same time as P/L OOS (F). 1.5 months before signed Integrated OOS (F) and GR&C (F). This is a POIF product submittal to MOD. | X | X | X | X | X |
| 28 | Transfer List Rev | L-3 weeks | Transfer List Review Start |  |  |  |  | X |

| table 4.0-6 KENNEDY SPACE CENTER INTEGRATION MILESTONE CHRONOLOGY (2 pages) |
| --- |
| Line # | Milestone Acronym | Date (Months) | Predecessors And Successors | F | S | Sub | A | PMIT |
| 1 | KSC TRDS ISS to P/L OMRS, File 10, Volume 2 (P) | L-12 | Kennedy Space Center Technical Requirements Data Set International Space Station to Payload Operations and Maintenance Requirements and Specifications, File 10, Volume 2 (Preliminary) 0.5 month after KSC TRDS OMRS File 10, Volume 2 (P) submittal. 3 months before KSC TRDS OMRS, File 10, Volume 2 (B/L). | X | X | X | X |  |
| 2 | KSC TRDS Bay to P/L OMRS, File 2, Volume 2 (P) | L-12 | Kennedy Space Center Technical Requirements Data Set Bay to Payload Operations and Maintenance Requirements and Specifications File 2, Volume 2 (Preliminary) 0.5 month after KSC TRDS OMRS File 2, Volume 2 (P) submittal. 4 months before KSC TRDS OMRS, File 2, Volume 2 (B/L). |  |  |  | X |  |
| 3 | KSC TRDS ISS to P/L OMRS, File 10, Volume 2 (B/L) | L-9 | Kennedy Space Center Technical Requirements Data Set International Space Station to Payload Operations and Maintenance Requirements and Specifications, File 10, Volume 2 (Baseline) 3 months after OMRS, File 10, Volume 2 (P). | X | X | X | X | X |
| 4 | KSC TRDS Bay to P/L OMRS, File 2, Volume 2 (B/L) | L-8 | Kennedy Space Center Technical Requirements Data Set Bay to Payload Operations and Maintenance Requirements and Specifications, File 2, Volume 2 (Baseline) 4 months after OMRS, File 2, Volume 2 (P). |  |  |  | X | X |
| 5 | KSC TRDS Orbiter MDK to P/L OMRS, File 2, Volume 2 (P) submittal | L-5.1 | Kennedy Space Center Technical Requirements Data Set Orbiter Middeck to Payload Operations and Maintenance Requirements and Specifications, File 2, Volume 2 (Preliminary) submittal 1 month after MDK OMRS, File 2, Volume 2 (P). 2 months before MDK OMRS, File 2, Volume 2 (B/L). | X | X | X |  | X |
| 6 | KSC TRDS Orbiter MDK to P/L TGHR Table (P) submittal | L-4 | Kennedy Space Center Technical Requirements Data Set Orbiter Middeck to Payload Time-Critical Ground Handling Requirements Table (Preliminary) submittal 0.5 month after Orbiter MDK TGHR table (P). 2 months before Orbiter MDK TGHR table (B/L). | X | X | X |  | X |
| 7 | CEIT | L-4 | Crew Equipment Interface Test Before Cargo Bay/Carrier installation. | X |  | X | X | X |
| 8 | KSC Utilization T/O Rack | L-3.5 | Kennedy Space Center Utilization Turn-Over to Rack KSC Utilization Hardware T/O for MPLM installation. H/W T/O need date will be provided by the ISS Program to support outfitting the MPLM schedule. | X |  |  |  | X |
| 9 | KSC TRDS Orbiter MDK to P/L OMRS, File 2, Volume 2 (B/L) | L-3 | Kennedy Space Center Technical Requirements Data Set Orbiter Middeck to Payload Operation and Maintenance Requirements and Specifications, File 2, Volume 2 (Baseline) 2 months after MDK OMRS, File 2, Volume 2 (P). | X | X | X |  | X |
| 10 | KSC TRDS Orbiter MDK to P/L TGHR Table (B/L) | L-2 | Kennedy Space Center Technical Requirements Data Set Orbiter Middeck to Payload Time-Critical Ground Handling Requirements Table (Baseline) 2 months after Orbiter MDK TGHR table (P). | X | X | X |  | X |
| 11 | CEIT (Middeck) | L-1.6 | Crew Equipment Interface Test for P/L flying in the Middeck | X |  | X |  | X |
| 12 | KSC SRDS (B/L) | H/W O/D-3 | Kennedy Space Center Support Requirements Data Set (Baseline) 3 months before P/L H/W O/D at KSC. 2 months before LSSP Addendum (B/L). | X | X | X | X | X |
| 13 | MIP Annex 8 LSSP Addendum (B/L) | H/W O/D-1 | Launch Site Support Plan Addendum (Baseline) 2 months after KSC SRDS (B/L). 1 month before P/L H/W O/D at KSC. | X | X | X | X | X |

# INTERNATIONAL PARTNER LAUNCH VEHICLE UNIQUE MILESTONES

The unique payload integration milestones for payloads launching on ESA ATV are covered in Section 5.1.  Integration milestones for payloads launching on Russian (Soyuz or Progress) vehicles are covered in Section 5.2.  Integration milestones for payloads launching on JAXA HTV are covered in Section 5.3, HII Vehicle Milestones.

## Automated Transfer Vehicle (ATV) Launch Milestones

Actual ISS Program flight schedules for ATV flights will vary greatly from flight to flight.  Variability will depend on whether the payload hardware is a first time flyer or re-flight.  The following list of ATV launch integration milestones does not encompass nominal payload submittals which are already contained in the four PIM Schedule templates (Pressurized, Subrack, Small, Attached).  The focus of this list is simply to identify cargo processing activities and unique data submittals exclusively related to ATV flights.

When first producing a unique PIM Schedule for a new payload, milestones in this table should be added to the appropriate PIM Schedule template if the payload is manifested or expected to be launched on an ATV vehicle.  The payload integration milestones for payloads launching on ESA ATV are covered in Table 5.1-1, ATV Milestones.

| Table 5.1-1 ATV Milestones (2 pages) |
| --- |
| ATV Milestones | Launch Minus Template (L-Date) |
| Payload Safety (Flight): |  |
| Flight Certification to ESA | L-4 M |
| Phase 3 Flight Safety Data Package (FSDP) [PD Submit] | L-7 M |
| Phase 3 Flight Safety Review (FSR) | L-5.5M |
| Export License (If required) | L-7.5 M |
| Payload Safety (Ground): |  |
| Ground Checklist to ESA | L-7 M |
| CoFR ATV Flight Template | Reference OZ CoFR Website |
| OZ2 CoFR Pre-Coordination Review | L-6 M |
| OZ2 Bi-Lateral CoFR Pre-coordination Review (if necessary) | L-6 M |
| Release OZ CoFR Instruction Letter | L-5.5 M |
| OWTL Inputs Due | L-4.5 M |
| OZ ATV Cargo Integration Readiness Review | L-4 M |
| ESA ATV Cargo Integration Readiness Review & CoC Signature | L-4 M |
| OZ2 OWTL Review | L-7 W |
| CoFR Endorsement Package Due | L-6.5 W |
| OZ2 CoFR Endorsement Package Review | L-5.5 W |
| IP/P CoFR Readiness Review (OZ participation as required) | L-5 W |
| OZ Multilateral CoFR Readiness Review | L-4 W |
| ESA ATV Cargo Integration Readiness | L-4 W |
| SORR Stage Operations Readiness Review | L-2 W to L-3 W |
| ATV Unique Documentation |  |
| Cargo Integration Agreement | L-4 M |
| Hardware Processing at JSC (nominal) |  |
| On-Dock at JSC | L-17.5 W |
| Hardware Verification Review (HVR) | L-16.5 W |
| Bench Review | L-15.5 W |
| Hardware Ship From JSC to Kourou | L-13 W |
| Hardware Processing at KSC (nominal) |  |
| On-Dock at KSC | L-19.5 W |
| Hardware Verification Review (HVR) | L-17.5 W |
| Bench Review | L-15 W |
| Hardware Ship From KSC to Kourou | L-13 W |
| Hardware Processing at KSC (late) |  |
| On-Dock at KSC | <TBD 5-1> |
| Hardware Verification Review (HVR) | <TBD 5-2> |
| Bench Review | <TBD 5-3> |
| Hardware Ship From KSC to Kourou | <TBD 5-4> |
| Hardware Processing at Turin (nominal) |  |
| On-Dock at Turin | L-4.25 M |
| Bench Review | L-3.5 M |
| Hardware Ship From Turin to Kourou | L-3 M |
| Hardware Processing at Turin (late) |  |
| On-Dock at Turin | L-2 M |
| Bench Review | L-1.75 M |
| Hardware Ship From Turin to Kourou | L-1 M |

Definitions:

Date Template:  M = month, W = week

This table is an OZ-specific subset of SSP 50489, Mission Integration Template, OZ CoFR website, ATV Flight Schedule:  http://iss-www.jsc.nasa.gov/ss/issapt/payofc/OZ2/COFR/COFR-schedule.html.

## RUSSIAN Vehicle (RV) Launch Milestones

Actual ISS Program flight schedules for Russian Progress and Soyuz flights will vary greatly from flight to flight.  Variability will depend on whether the payload hardware is a first time flyer or re-flight.  The following list of Russian launch integration milestones does not encompass nominal payload submittals which are already contained in the four PIM Schedule templates (Pressurized, Subrack, Small, Attached).  The focus of this list is simply to identify cargo processing activities and unique data submittals exclusively related to Russian Soyuz or Progress flights.

When first producing a unique PIM Schedule for a new payload, milestones in this table should be added to the appropriate PIM Schedule template if the payload is manifested or expected to be launched on a Soyuz or Progress vehicle.  The payload integration milestones for payloads launching on Russian (Soyuz or Progress) vehicles are covered in Table 5.2-1, Russian Vehicle Milestones.

TABLE 5.2-1  RUSSIAN VEHICLE MILESTONES

| Russian Vehicle (Soyuz or Progress) Milestones | Launch Minus Template (L-Date) |
| --- | --- |
| Payload Safety |  |
| Phase 3 flight Safety Data Package (SDP) (PD Submit) | L-7.5 M |
| Phase 3 Flight Safety Review (FSR) | L-6 M |
| PSRP review Complete, Approved (Confirmation received from PSRP) | L-3.5 W |
| CoFR Russian Template | Reference OZ CoFR Website |
| OZ2 CoFR Pre-Coordination Review | L-4 M |
| OZ2 Bilateral CoFR Pre-Coordination Review (if necessary) | L-15 W |
| Release OZ CoFR Instruction Letter | L-13 W |
| OWTL Inputs Due (ISS and Russian Vehicle-specific) | L-9 W |
| OZ2 OWTL Review | L-7.5 W |
| CoFR Endorsement Package Due | L-7 W |
| OZ2 CoFR Endorsement Package Review | L-6 W |
| IP/P CoFR Readiness Review (OZ participation as required) | L-5 W |
| OZ Multilateral CoFR Readiness Review | L-4 W |
| SORR - Stage Operations Readiness Review | L-2 W to L-3 W |
| FRR - Flight Readiness Review (Soyuz crew rotation flights only) | L-1 W to L-2 W |
| Manifest Changes |  |
| OZ CEF Submittal (PD) | L-6 M |
| OZ MR Submittal (Manifest Lead) | L-4.5 M |
| OC-sponsored manifest presented to MIOCB | L-3.75 M |
| OC MIOCB Manifest – final approval | L-3.5 M |
| Payload Engineering Integration |  |
| Verification Data (Non-EXPRESS, Stage Analysis (SSP L-7.5 M) | L-3.5 M |
| Re-Verification Memo | L-3 M |
| Russian Unique Documentation |  |
| Technical Data Sheet (TDS) | L-5 M (Progress) L-4 M(Soyuz) |
| Export Control Worksheet (ECW) (JSC Form 1724) | L-4.5 M (Progress) L-8 (Soyuz) |
| ProForma (formerly DUC, embedded within ECW) (JSC Form 1735) | L-4.5 M (Progress) L-8 M (Soyuz) |
| Technical Passport | L-12 W |
| Hardware Accountability Matrix review (HAMR) – Initial Reviewed by: RV PIM, PD PIM + PD | L-4.5 M |
| Hardware Accountability Matrix Review (HAMR) – Final (RV PIM) | L-4 M |
| On-Dock at Flight Crew Equipment (FCE) | L-9.5 W (Commercial) |
| Hardware Verification Review (HVR) | L-7.75 W (Commercial) |
| Bench Review | L-7.5 W (Commercial) |
| Hardware Ship From JSC to Russia | L-5.5 W (Commercial) |

Definitions:

Date Template:  M = month, W = week

This table is an OZ-specific subset of SSP 50489, Mission Integration Template, OZ CoFR website, Russian Flight Schedule:
http://iss-www.jsc.nasa.gov/ss/issapt/payofc/OZ2/COFR/COFR-schedule.html.

## HII Transfer Vehicle (HTV) Launch Milestones

The payload integration milestones for payloads launching on JAXA HTV will be covered in Table 5.3-1, HII Vehicle Milestones.

TABLE 5.3-1  HII VEHICLE MILESTONES

TBD <5-5>

Appendix A - Acronyms and abbreviations

| A | Attached |
| --- | --- |
| A&I | Assembly and Installation |
| ATV | Automated Transfer Vehicle |
| BB | Blank Book |
| B/L | Baseline |
| BR | Bench Review |
| C&DH | Command and Data Handling |
| CCCD | Crew Compartment Configuration Drawing |
| CCCR | Crew Compartment Configuration Review |
| CDR | Critical Design Review |
| CE | Cargo Element |
| CEIT | Crew Equipment Interface Test |
| CIR | Cargo Integration Review |
| CIRD | Cargo Integration Review Dry Run |
| CMC | Cargo Mission Contract |
| CMD | Command |
| CoC | Certificate of Compliance |
| CoFR | Certification of Flight Readiness |
| CR | Change Request |
| CSRD | Current Stage Requirements Document |
| DP | Data Pack |
| DS | Data Set |
| DUC | Data Usage Chart |
| Dwg | Drawing |
| ECL | Engineering Configuration List |
| ECR | Engineering Change Request |
| ECW | Export Control Worksheet |
| EIRR | EXPRESS Integration Readiness Review |
| EMC | Electromagnetic Compatibility (Control) |
| EMI | Electromagnetic Interference |
| EPAS | ETOV Payload Activity Summary |
| ER | EXPRESS Rack |
| ESA | European Space Agency |
| ETOV | Earth-to-Orbit Vehicle |
| EVA | Extravehicular Activity |
| EXPRESS | EXpedite the PRocessing of Experiments to the Space Station |
| F | Facility |
| FAO | Flight Activity Officer |
| FCE | Flight Crew Equipment |
| FCSD | Flight Crew Support Division |
| FOR | Flight Operations Review |
| FPM | Flight Payload Manager |
| FPSR | Flight Planning and Stowage Review |
| FR | Flight Rules |
| FRD | Flight Requirements Document |
| FRR | Flight Readiness Review |
| FSDP | Flight Safety Data Package |
| FSR | Flight Safety Review |
| GAS | Getaway Special |
| GCP | Ground Command Procedure |
| GDS | Ground Data Services |
| GL&C | Guidelines and Constraints |
| GPVP | Generic Payload Verification Plan |
| GR&C | Groundrules and Constraints |
| GSDP | Ground Safety Data Package |
| GSE | Ground Support Equipment |
| GSP | Ground Support Personnel |
| GSR | Ground Safety Review |
| HAMR | Hardware Accountability Matrix Report |
| HCI | Human Computer Interface |
| HDW | Hardware |
| HFIT | Human Factors Interface Team (Integration) |
| HTV | H-II Transfer Vehicle |
| HVR | Hardware Verification Review |
| H/W | Hardware |
| I | Increment |
| I- | Increment minus |
| ICA | Interface Control Annex |
| ICD | Interface Control Document |
| IDD | Interface Definition Document |
| IDP | Integrated Data Package |
| IDRD | Increment Definition and Requirements Document |
| IDRP | Increment Definition Requirements Plan |
| I/F | Interface |
| IMS | Inventory Management System |
| IOR | Increment Operations Review |
| IORR | Integrated Operation Readiness Review |
| IP | International Partner |
| IPE | Increment Payload Engineer |
| IPIC | ISS Payload Integration Contract |
| IPLAT | ISS Payload Label Approval Team |
| IPM | Increment Payload Manager |
| IP/P | International Partner/Participant |
| IPV | International Payload Viewer |
| IRD | Interface Requirements Document |
| IRR | Increment Requirements Review |
| ISPR | International Standard Payload Rack |
| ISS | International Space Station |
| ISVR | Independent Safety Verification Review |
| IVT | Interface Verification Test |
| JAXA | Japan Aerospace Exploration Agency |
| JMST | Joint Multi-Segment Station Training |
| JPRCB | Joint Program Requirements Control Board |
| JSC | Johnson Space Center |
| KSC | Kennedy Space Center |
| L | Launch |
| L- | Launch minus |
| LON | Launch On Need |
| LPA | Launch Package Assessment |
| LP/CE | Launch Package/Cargo Element |
| LPMT | Launch Package Management Team |
| LSSP | Launch Site Support Plan |
| MCC | Mission Control Center |
| MDK | Middeck |
| MDM | Multiplexer/Demultiplexer |
| MI | Mission Integration |
| MIDAS | Mission Integration Database Applications System |
| MIOCB | Multilateral Mission Integration And Operations Control Board |
| MIP | Mission Integration Plan |
| MOD | Mission Operations Directorate |
| MPCB | Multilateral Payloads Control Board |
| MPLM | Multi-Purpose Logistics Module |
| MR | Manifest Request |
| MSFC | Marshall Space Flight Center |
| NASA | National Aeronautics and Space Administration |
| OC | Operation Controller |
| O/D | On-Dock |
| OFK | Official Flight Kit |
| OMRS | Operations and Maintenance Requirements and Specifications |
| OOS | On-Orbit Operations Summary |
| OpNom | Operations Nomenclature |
| Ops | Operations |
| ORU | Orbital Replacement Unit |
| ORG | Organization |
| OWTL | Open Work Tracking Log |
| P | Preliminary |
| PCB | Payloads Control Board |
| PCF | Payload Multiplexer/Demultiplexer Configuration Files |
| PCS | Portable Computer System |
| PD | Payload Developer |
| PDL | Payload Data Library |
| PDR | Preliminary Design Review |
| PDS | Payload Data Set |
| PEI | Payload Engineering Integration |
| PFE | Program Furnished Equipment |
| PHCM | Payload Hazard Control Matrix |
| PIA | Payload Integration Agreement |
| PIM | Payload Integration Manager |
| PIRN | Preliminary/Proposed Interface Revision Notice |
| P/L | Payload |
| PMI | Payload Mission Integration |
| PMIT | Payload Mission Integration Team |
| POCC | Payload Operations Control Center |
| PODF | Payload Operations Data File |
| PODFCB | Payload Operations Data File Control Board |
| POIC | Payload Operations Integration Center |
| POIF | Payload Operation Integration Function |
| PP | Planning Period |
| PP- | Planning Period minus |
| PPD | Payload Procedures and Displays |
| PPIL | Payload Product Integrated List |
| PRCU | Payload Rack Checkout Unit |
| PRO | Payload Rack Officer |
| PRR | Payload Readiness Review |
| PSI | Payload Software Integration |
| PSIVF | Payload Software Integration Verification Facility |
| PSM | Payload System Manual |
| PSRP | Payload Safety Review Panel |
| PTC | Payload Training Compliment |
| PTDR | Payload Training Dry Run |
| PTP | Payload Tactical Plan |
| PVP | Payload Verification Plan |
| PVPP | Payload Verification Program Plan |
| RCAR | Requirements Change Assessment Report |
| Rev | Review |
| RF | Radio Frequency |
| RMDP | Return Manifest Dispositioning Plan |
| RPO | Research Program Office |
| RR | Readiness Review |
| RV | Russian Verification |
| S | Small |
| SC | Support Contractor |
| SDP | Safety Data Package |
| SDT | Shuttle Data Tape |
| SME | Subject Matter Expert |
| SODF | System Operations Data File |
| SORR | Stage Operations Readiness Review |
| SRDS | Support Requirements Data Set |
| SRS | Software Requirements Specification |
| Sub | Subrack Standard |
| SSCCD | Space Station Configuration Control Drawing |
| SSE | Station Support Equipment |
| SSP | Space Shuttle Program |
| SSPCB | Space Station Program Control Board |
| SSTF | Space Station Training Facility |
| STS | Space Transportation System |
| S/W | Software |
| TBD | To Be Determined |
| TBR | To Be Resolved |
| TDS | Technical Data Sheet |
| TGHR | Time-Critical Ground Handling Requirements |
| TIM | Technical Interchange Meeting |
| T/O | Turn-Over |
| TRDS | Technical Requirements Data Set |
| TSC | Telescience Support Center |
| TST | Training Strategy Team |
| U/D | Update |
| U.S. | United States |
| USA | United States of America |
| US Lab | United States Laboratory |
| US PODFCB | United States Payload Operations Data File Control Board |
| VADAR | Verification Analysis data Acceptability Review |
| VAR | Verification Acceptance Review |
| VER | Verification |
| VLA | Verification Loads Analysis |
| VMDB | Vehicle Master Database |
| WORF | Window Observation Rack Facility |

APPENDIX B – GLOSSARY OF TERMS

Hardware Accountability Matrix Report

The Hardware Accountability Matrix Report (HAMR) is used to track completion of ISS requirements and completion of physical processing actions associated with physical processing milestone activities.  The HAMR is generated from a subset of data in Mission Integration Database Applications System (MIDAS) to be used by the Launch Package Manager and Hardware providers.  MIDAS includes all components of the IDRD Annex 1 (the Manifest) and additional information for ISS hardware.  Categories utilized in MIDAS for the HAMR typically include, but are not limited to:  nomenclature, quantity, part number, on-dock and bench review dates, barcode/imagery/certification requirements, and hardware points of contacts.

Strategic Planning

Strategic planning is the long-range planning that occurs between PDR and I-18 months (start of ISS Program tactical phase).

Tactical Planning

Tactical planning and manifesting is performed for each Increment.  Tactical planning and manifesting is a multilateral function, which defines the resources, allocations, research objectives, priorities, and manifests for each increment (expedition).  These requirements are documented in the Increment Definition and Requirements Plan (IDRP) Increment Definition and Requirements Document (IDRD) series and annexes.

Verification Analysis Data Acceptability Review

The Verification Analysis Data Acceptability Review (VADAR) will be conducted between the SSP and the Cargo Element (CE) developers just prior to starting the Verification Loads Analysis (VLA).  The VADAR will be scheduled after all CE models have been received and validated.  Specific cargo bay configurations, math models, forcing functions, CE data, analysis methods, and response data recoveries that are planned for the VLA will be clearly identified by the Support Contractor (SC).  Each CE developer shall either concur with the SC provided data or provide updated data prior to or during the VADAR.  After completion of this review, formal authorization will be provided to begin the VLA.

Appendix C - open work

Table C-1 lists the specific To Be Determined (TBD) items in the document that are not yet known.  The TBD is inserted as a placeholder wherever the required data is needed and is formatted in bold type within brackets.  The TBD item is numbered based on the section where the first occurrence of the item is located as the first digit and a consecutive number as the second digit (i.e., <TBD 4-1> is the first undetermined item assigned in Section 4 of the document).  As each TBD is solved, the updated text is inserted in each place that the TBD appears in the document and the item is removed from this table.  As new TBD items are assigned, they will be added to this list in accordance with the above described numbering scheme.  Original TBDs will not be renumbered.

Table C-1  to be determined items

| TBD | Section | Description |
| --- | --- | --- |
| 1-1 | 1.3 | ATV Schedule Milestone Reference |
| 1-2 | 1.3 | HTV Schedule Milestone Reference |
| 5-1 | Table 51-1 | On-Dock at KSC |
| 5-2 | Table 5.1-1 | Hardware Verification Review (HVR) |
| 5-3 | Table 5.1-1 | Bench Review |
| 5-4 | Table 5.1-1 | Hardware Ship From KSC to Kourou |
| 5-5 | Table 5.3-1 | HII Vehicle Milestones |

Table C-2 lists the specific To Be Resolved (TBR) issues in the document that are not yet known.  The TBR is inserted as a placeholder wherever the required data is needed and is formatted in bold type within brackets.  The TBR issue is numbered based on the section where the first occurrence of the issue is located as the first digit and a consecutive number as the second digit (i.e., <TBR 4-1> is the first unresolved issue assigned in Section 4 of the document).  As each TBR is resolved, the updated text is inserted in each place that the TBR appears in the document and the issue is removed from this table.  As new TBR issues are assigned, they will be added to this list in accordance with the above described numbering scheme.  Original TBRs will not be renumbered.

TABLE C-2  TO BE RESOLVED ISSUES

| TBR | Section | Description |
| --- | --- | --- |

Appendix D - SCHEDULE TEMPLATES

| D5 -Generic PMIT Schedule | Template Date |
| --- | --- |
| Pressurized Payloads |  |
| Flight Safety Review (FSR) Data Package (DP) - Ph III | L-45 days from FSR |
| Ground Safety Review (GSR) DP - Ph III | L-45 days from GSR |
| FSR Safety Review - Ph III | L-5.6 |
| GSR Safety Review - Ph III | L-5.6 |
| MPLM Ph III FSDP | L-4 |
| MPLM Ph III FSR | L-2.5 |
| ISPR Payloads |  |
| Rack Mass Properties & Test Verified Model | L-10.5 to L-9.5 |
| VADAR | L-7 |
| Rack HDW O/D | L-6 |
| Verification Acceptance Review (VAR) | L-3.5 |
| KSC |  |
| SRDS (Cargo Bay) B/L PD Input | L-12.5 |
| SRDS B/L PD Input | L-6 HDW O/D |
| SRDS B/L | L-3 HDW O/D |
| MIP Annex 8 LSSP Addendum - B/L | HDW O/D -1 |
| HDW O/D for testing | L-6 |
| HDW Offline Testing | L-6 to L-4.5 |
| HDW PRCU Testing | L-4.5 to L-3.5 |
| Rack HDW T/O | L-3.5 |
| CEIT (Orbiter) | L-4 |
| HDW O/D for KSC nominal installation | L-22 Days to L-8 days |
| HDW O/D for KSC late installation | L-15 Days to L-28 hours |
| HDW T/O for KSC nominal installation | NLT L-8 days |
| D5 -Generic PMIT Schedule | Template Date |
| HDW T/O for KSC late installation | L-3 Days to L-28 hours |
| TRDS OMRS (ISS & Cargo Bay to PL)- Preliminary PD Submit | L-12.5 |
| OMRS (ISS & Cargo Bay to PL) B/L Submit to SSP | L-9 |
| OMRS (ISS & Cargo Bay to PL) - B/L | L-8 |
| TRDS OMRS (MDK to PL) - Preliminary PD Submit | L-6 |
| OMRS (MDK to PL)- B/L Submit to SSP | L-5.1 |
| OMRS (MDK to PL) - B/L | L-3 |
| TRDS PD Submit for TGHR | L-4.5 |
| TGHR inputs to SSP | L-4 |
| TGHR B/L | L-2 |
| CEIT (MDK) | L-1.6 |
| Program (Increment Reviews) |  |
| IRR | I-12 |
| IORR | I-9 |
| IOR | I-4 |
| Program (Increment Documents) |  |
| Incr Research Directive | I-15 |
| IDRD B/L (Rev A @I-12; Rev B @I-8, I-6, I-4) | I-16 |
| IDRD Appendix I (Transfer Priorities) Submit due to LPMT | L-10 |
| IDRD Appendix I (Transfer Priorities) Approval | L-8 |
| Current Stage Requirements Document (CSRD) | L-3.5w |
| IDRD Annex 5 B/L CR Release | I-15 |
| IDRD Annex 5 B/L CR Comments Due | I-15 + 3weeks |
| IDRD Annex 5 B/L CR CM | I-14 |
| IDRD Annex 5 B/L CR approved at MPCB | I-10 (+2 weeks from CM & per MPCB monthly schedule) |
| D5 -Generic PMIT Schedule | Template Date |
| IDRD Annex 3 B/L (Flight Requirements) | L-1.75 |
| Program (Flight Documents) |  |
| FRD B/L | L-13.2 |
| MIP Cargo Bay Inputs | L-17 |
| MIP B/L | L-16 |
| MIP Appendix E (MDK) Inputs Due | L-11.1 |
| MIP Annex 1 B/L Inputs | L-14.5 |
| MIP Annex 1 B/L | L-10 |
| MIP Annex 2 Part 1 Inputs Due | L-11 |
| MIP Annex 2 Part 1 B/L | L-4.9 |
| MIP Annex 4 B/L Inputs | L-11.6 |
| MIP Annex 4 B/L | L-7.7 |
| MIP Annex 5 B/L Inputs due | L-14.3 |
| MIP Annex 5 B/L | L-7.3 |
| Program (Flight Reviews) |  |
| CIR Dry Run | L-9.8 (or CIR+3w) |
| CIR | L-9 |
| FPSR List | L-9.2 |
| FPSR | L-7.7 |
| Official Flight Kit (OFK) Submit to SSP due date | L-3 |
| Deliver OFK items | L-2 |
| CCCR Freeze | L-3 |
| CCCR | L-2 |
| Installation Readiness Review (IRR) Kick-off (MPLM/Node Only Flights) | L-4 w from HDW Installation |
| IRR Final (MPLM/Node Only Flights) | L-2w from HDW Installation |
| D5 -Generic PMIT Schedule | Template Date |
| Program (CoFR) |  |
| OZ2 CoFR Pre-Coordination Review | L-5 |
| OZ2 Bilateral CoFR Pre-Coordination Review | L-4.5 |
| Release OZ CoFR Instruction Letter | L-4 |
| CoFR Open Work Tracking Log & LPA Inputs Due | L-3 |
| OZ2 OWTL & LPA Review | L-10w |
| OZ OWTL & LPA Review | L-9w |
| CoFR Endorsement Packages Due | L-7w |
| ISSP LPA | L-7w |
| OZ2 CoFR Endorsement Package Review | L-6w |
| IP/P CoFR Readiness Review (OZ participation, as required) | L-5.5w |
| OZ Multilateral CoFR Readiness Review | L-4.5w |
| SORR | L-3.5w |
| FRR | L-2w |
| Manifest & Stowage (Documentation) |  |
| Manifest &Stowage (M&S) Data Set (D.S.) BL Inputs Due | L-15 to L-12.5 |
| M&S Data Set Kit Contents Due | L-2M from BR (L-6 MPLM & L-3 MDK) |
| IMS/Bar Code Data Due | L-1M from BR (L-5 MPLM & L-2 MDK) |
| IDRD Annex 1 Call for MRs | L-15 |
| IDRD Annex 1 B/L MRs Due | L-12.5 |
| IDRD Annex 1 B/L (L-6, L-3, L-6w to 2w) | L-12 |
| ICA Submit Due date | L-11.1 |
| ICA B/L | L-9 |
| ICA Reserve CR inputs for L-10 day BR Submit | L-1.3 |
| ICA Reserve CR for L-10 day BR Approval | L-28 days |
| RMDP Release | L-2 |
| D5 -Generic PMIT Schedule | Template Date |
| RMDP B/L | Launch |
| Manifest & Stowage (Reviews & Drawing Data) |  |
| HAMR Release (MPLM/Node & MDK) | L-8 |
| MPLM/Node & MDK HDW Audit | L-7.5 |
| MAPs Baselined (MPLM/Node) | L-7 |
| HDW O/D MPLM/NODE | L-5 toL-4.5 |
| SSCCD Final | L-4 |
| MPLM/NODE BR #1 @ KSC | L-4 |
| Late Load HDW O/D MPLM/NODE | L-3.5 |
| MPLM/NODE BR #2 | L-3 |
| HAMR Release (MDK Only) | L-4.5 |
| MDK Only HDW Audit | L-4 |
| CCCD Release | L-2 |
| HDW O/D Nominal MDK Bench Review | L-2 w from BR |
| Hardware Verification Review | L-1w from BR |
| MDK Nominal Bench Review @ JSC | L-1 |
| CCCD Release for L-10 Day BR | L-18 days |
| HDW O/D L-10 Day MDK Bench Review | L-2 w from BR |
| MDK L-10 Day Bench Review @ JSC | L-10 days |
| POIC |  |
| PL Planning Data Set PD Submit | I-8 |
| PL Planning D.S. B/L | L-4.25 |
| PL OOS | I-5.5 to I-2 |
| P/L GR&C | I-2 |
| EPAS (Preliminary) | L-6.5 |
| EPAS B/L | L-2.5 |
| D5 -Generic PMIT Schedule | Template Date |
| Flight Rules Annex Submit to MOD | L-6 |
| P/L Regs (B/L) | I-3 |
| FOR Data Pacakge Available for Review | L-6.1 |
| FOR | L-3.7 |
| Transfer List Review Start | L-3 weeks |
| Payload Engineering & Integration |  |
| HDW ICD B/L | L-12 |
| Launch/Return Verification Data | L-12 to L-3 (or HDW T/O) |
| On-Orbit Verification Data PD Submit | L-9.5 to L-7.5 |
| Launch/Return CoC | L-4.5 to L-3.5 |
| Late Load HDW Verification Data and CoC | HDW T/O |
| Engineering Stage Analysis Report | L-4.5 |
| GL&C | L-4 |
| ISS Level P/L Complement Analysis Report | L-3 |
| P/L Engineering Stage Verification Memo | L-6w |