ALARA

Booster Injection Girder &

400MeV Reconfiguration

Fernanda G. Garcia

X3798

fgarcia@fnal.gov

Office: BWP-120

Introduction

During the 2005 shutdown, Booster 400 MeV Transfer Line injection will undergo a major modification.  In general, the job is relatively straightforward: remove beam line components downstream of quadrupole Q13, remove orbump girder, with all its components on it except for the ion pumps, install new girder with new magnets and vacuum components and finally reinstall 400 MeV components at different configuration.

There are two radiation areas in this section of the transfer line: one between Q15 and MH2-2 (~120mrem/hr @ contact) and the other at DCSEP magnet/girder region (~ 200 mrem/hr @ 1 foot). The picture below shows a sub set of the radiation survey data taken since last shutdown (Aug’04). The latest values are represented by the black line. These measurements were taken at 1 foot after some cooldown period.

This document will describe in details the necessary steps to modify the injection line into booster.

Through out this document, the following notation will be applied:

- BPM -- beam position monitor

- Trim	-- corrector magnet

- MW 	-- multi wire

- IP  -- ion pump

- QM -- quadrupole magnet

- BM -- bending magnet

- † -- normal dose expected

- ‡ -- high dose expected

General Procedure

Access Booster to survey area, assess job and do radiation survey. The radiation survey needs to be done one week prior start working.

This work will be divided in two parts: Removal and Installation. After completion of Removal Jobs the radiation in the area should drop considerably.

Removal Jobs

| Task | Duration* | Units | Resources | Status | Dose | Dose rate |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | on contact | (middle body) |
|  |  |  |  |  | (mrem/hr) | (mrem/hr) |
| Disassemble | 5.2 | days |  |  |  | 11/15/2005 |
| vent vacuum system | 2.0 | hrs | 2 |  |  |  |
| disconnect vacuum | 4.0 | hrs | 2 |  |  |  |
| disconnect water | 4.0 | hrs | 2 |  |  |  |
| disconnect electrical | 4.0 | hrs | 2 |  |  |  |
| remove BPM 13 | 0.5 | hrs | 2 | cool | 4 | 2.5 |
| remove quad 14 and corrector | 2.0 | hrs | 2 | cool | 6.50 | 2.5 |
| remove dipole MH2-1 | 0.5 | hrs | 2 | HOT | 95.00 |  |
| Upstream |  |  |  |  |  | 2.0 |
| Downstream |  |  |  |  |  | 10.0 |
| remove MW10 | 0.5 | hrs | 2 |  |  | 10 |
| remove quad Q15‡ | 0.5 | hrs | 2 | HOT | 55.00 | 10 |
| remove BPM 15 | 0.5 | hrs | 2 | HOT | 55.00 | 6 |
| remove dipole MH2-2 | 0.5 | hrs | 2 | cool | 7.50 |  |
| Upstream |  |  |  |  |  | 7 |
| Downstream |  |  |  |  |  | 4 |
| remove quad Q16 | 0.5 | hrs | 2 | cool | 3.00 | 2.5 |
| remove BPM 16 | 0.5 | hrs | 2 | cool | 3.00 | 2.5 |
| remove MW11 | 0.5 | hrs | 2 |  |  | 2.5 |
| remove ion pump | 0.5 | hrs | 2 |  |  | 2.5 |
| remove corrector | 0.5 | hrs | 2 |  |  | 2 |
| remove valve and turbo pump | 0.5 | hrs | 2 |  |  | 2.5 |
| remove BPM H23 | 0.5 | hrs | 2 | cool | 3.75 | 2.5 |
| remove dipole MH2-3 | 0.5 | hrs | 2 | cool | 5.00 | 4 |
| remove 2 correctors | 0.5 | hrs | 2 | cool | 5.00 | 5 |
| remove quad Q17 | 0.5 | hrs | 2 | cool | 6.25 |  |
| Upstream |  |  |  |  |  | 7 |
| Downstream |  |  |  |  |  | 10 |
| remove BPM 17 | 0.5 | hrs | 2 | cool | 6.25 | 10 |
| remove toroid | 0.5 | hrs | 2 |  |  | 15 |
| remove MW12 | 0.5 | hrs | 2 |  |  | 200 |
| remove beam valve | 0.5 | hrs | 2 |  |  | 200 |
| remove Booster corrector package | 1.0 | hrs | 2 | HOT | 201.09 | 120 |
| remove injection girder | 4.0 | hrs | 4 |  |  |  |
| ion pump before foil | 1 | hr | 2 | HOT | 201.09 | 250 |
| ion pump after foil | 1 | hr | 2 | cool | 40.00 | 40 |
| 4 single wire scanners | 1 | hr | 2 | HOT | 201.09 | 200 |
| disconnect stripline | 0.25 | hr | 2 | HOT | 201.09 | 200 |
| disconnect instrumentation cables | 0.25 | hr | 2 | HOT | 201.09 | 200 |
| remove foils | 0.5 | hr | 1 | HOT | 201.09 | 200 |
| remove DCSEPTUM BPM | 0.5 | hrs | 2 | HOT | 201.09 | 200 |
| remove DCSEPTUM magnet | 4.0 | hrs | 4 | HOT | 201.09 | 200 |

Redo radiation survey, review and revise ALARA plan as necessary.

Installation

Stake survey girder and 400 MeV

Pull new cables for Orbump magnets

Install girder

Rough alignment of the girder

Connect instrumentation, vacuum pumps, start pumping down girder

Final survey of girder

Reinstall 400 MeV components

Rough survey of 400 MeV

Connect electrical, vacuum, water

Final alignment 400 MeV

Removal Jobs

LOTO†

- Lock out 400MeV power supplies	20 min

- OrBump PS will probably be gone by the time this task starts

Disconnect vacuum, water, electrical† 	40 min

Remove 400 MeV components DW Q13†

- Disconnect BPMs, MWs,  BLMs cables 	14min

-     Remove 3 BPM’s, 3 Trims, 4 QM, 3 BM, 1 IP	2days

-     See table below for detailed tasks

Remove Booster injection girder‡

- Put on shielding blankets where necessary‡	10 min

- Disconnect instrumentation cables	14min

- Remove 2 ion pumps	60 min

- Foil and wire scanner flanges will be rescued at later time

- Girder will be stored at L13 region

Remove DCSEPTA‡

- Put on shielding blankets where necessary‡	10 min

- Disconnect cables, prep to move‡ 	15 min

- Move‡ DCSEPTA to storage area (L13)	20 min

According to the data, one expects to have the total activation in the tunnel, at that region, reduced by 70% after the removal of DCSEPTA magnet.  After components are removed, we will redo radiation survey, review and revise ALARA plan as necessary.

Installation

Stake survey girder and 400 MeV

Pull new cables for Orbump magnets

Install girder

Rough alignment of the girder

Connect instrumentation, vacuum pumps, start pumping down girder

Final survey of girder

Reinstall 400 MeV components

Rough survey of 400 MeV

Connect electrical, vacuum, water

Final alignment 400 MeV