Department of Health and Human Services

National Institutes of Health

Competitive Sourcing Guidebook

Section G – IHSP Implementation and Stand-Up

National Institutes of Health	i

Competitive Sourcing Guidebook	i

Section G:	Decision Implementation and Stand Up for an In-House Service Provider	1

G.1.	Policy	1

G.1.1	OMB Circular A-76	1

G.1.2	NIH Policy	4

G.2.	Roles and Responsibilities	8

G.3.	Procedures	17

G.3.1	Overview	17

G.3.2	Implementation of the IHSP	19

G.3.3	Stand-Up the Organization	40

G.4.	Potential Pitfalls	41

G.5.	Exhibits	41

# Decision Implementation and Stand Up for an In-House Service Provider

| Objectives for this Section |
| --- |
| ( | Implementation Policy |
| ( | Roles and Responsibilities |
| ( | Procedures |
| ( | Potential Pitfalls |

This Guidebook section discusses the implementation of an in-house decision, including the implementation of the Most Efficient Organization (MEO) and post-competition monitoring associated with performance under a Letter of Obligation (LOO).  The Implementation Team includes personnel from the organization implementing the MEO, the Contracting Officer (CO), the Human Resources Advisor (HRA), and a representative from the Commercial Activities Review Team (CART).  The primary goals for the Implementation Phase are:

- Establish the Letter of Obligation

- Implement staffing changes proposed by the MEO

- Implement any process changes, training, equipment changes, or other MEO proposals

- Complete any transition or phase-in period reports required in the Performance Work Statement (PWS) or Requirements Document (RD)

- Prepare to implement post-competition monitoring of the MEO, including cost monitoring, quality assurance, and workload tracking

- Train MEO and other personnel regarding their new duties

The end result of the implementation phase is the “stand-up” of the MEO, which becomes known as the In-House Service Provider (IHSP).

## Policy

### OMB Circular A-76

The following are specific sections of OMB Circular A-76 revised May, 2003 (the Circular) associated with the implementation phase.  If you are unfamiliar with the terms used in this Section, please refer to Section A, Competitive Sourcing Overview, and to the rest of this chapter, which covers the requirements in more detail.  These sections are mandatory and must be followed in all Implementation and Post-Competition work.

ATTACHMENT B, SECTION A.8.d (1) Employee and Labor-Relations Requirements. The Human Resources Advisor shall, at a minimum, perform the following (a) interface with directly affected employees (and their representatives) from the date of public announcement until full implementation of the performance decision; (b) identify adversely affected employees; (c) accomplish employee placement entitlements in accordance with 5 C.F.R. Part 351 (reduction-in-force procedures); (d) provide post-employment restrictions to employees; (e) determine agency priority considerations for vacant positions and establish a reemployment priority list(s) in accordance with 5 C.F.R. Part 330; and (f) provide the Contracting Officer with a list of the agency’s adversely affected employees, as required by this attachment and FAR 7.305(c) regarding the right of first refusal for a private sector performance decision.

ATTACHMENT B, SECTION A.8.d (2) MEO Team Requirements. The Human Resources Advisor shall assist the ATO [Agency Tender Official] and MEO [Most Efficient Organization] team in developing the agency tender. During development of the agency tender, the Human Resources Advisor shall be responsible for … (d) performing labor market analysis to determine the availability of sufficient labor to staff the MEO and implement the phase-in plan; … (f) assisting in the development of the timing for the phase-in plan based on MEO requirements; and (g) developing an employee transition plan for the incumbent agency organization early in the standard competition process.

ATTACHMENT B, SECTION D. 3.a. (13) Phase-in Plan. The Contracting Officer [Contracting Officer] shall include in the solicitation a separate CLIN [Contract Line Item Number] for a phase-in plan. Private sector, public reimbursable and agency sources shall propose a phase-in plan to replace the incumbent service provider. The Contracting Officer shall designate the phase-in period as the first performance period (see Attachment C). The CLIN is limited to the phase-in costs associated with phase-in actions as documented in the phase-in plan. Phase-in plans shall include details to minimize disruption and start-up requirements. The phase-in plan shall consider recruiting, hiring, training, security limitations, and any other special considerations of the prospective providers to reflect a phase-in period of realistic length and requirements.  (Applies to Standard Competitions.)

ATTACHMENT B, SECTION D. 4.a. (1) (d) Phase-in Plan. The ATO shall include a phase-in plan in the agency tender, as required by the solicitation, to replace the incumbent service provider with the MEO, even if the agency is the incumbent service provider. The ATO shall include phase-in costs for the agency tender on SCF [Standard Competition Form] Lines 1-6.

ATTACHMENT B, SECTION E. POST COMPETITION ACCOUNTABILITY FOR STREAMLINED AND STANDARD COMPETITIONS.

1. Best Practices and Lessons Learned. Agencies shall post best practices and lessons learned resulting from a streamlined or standard competition process on SHARE A-76! at http://emissary.acq.osd.mil/inst/share.nsf/. An agency shall maintain the accuracy and currency of their agency’s information, including links, on SHARE A-76!

2. Execution Tracking of Streamlined and Standard Competitions. Agencies shall maintain a database to track the execution of agency streamlined and standard competitions. Agencies shall maintain a database that (1) assigns a unique tracking number to each streamlined and standard competition, (2) includes data fields as defined on the OMB web site at www.omb.gov, (3) tracks each streamlined and standard competition as events occur (real-time) from the date of public announcement through either completion of the last performance period or cancellation of the competition, and (4) retains historical records of streamlined and standard competitions after the last performance period has been completed.

3. Competitive Sourcing Quarterly Report. An agency shall submit a Competitive Sourcing Quarterly Report to OMB, by the end of each fiscal quarter (December, March, June, September), that includes the following (1) in-progress streamlined and standard competitions (i.e., competitions with start dates and pending performance decisions); and (2) completed streamlined and standard competitions (i.e., competitions with performance decisions). The required format for these reports can be found on the OMB web site at www.omb.gov.

4. Monitoring Performance. Regardless of the selected service provider, after implementing a performance decision, an agency shall (1) monitor performance for all performance periods stated in the solicitation; (2) implement the quality assurance surveillance plan; (3) retain the solicitation and any other documentation from the streamlined or standard competition as part of the competition file; (4) maintain the currency of the contract file, consistent with FAR Subpart 4.8, for contracts, MEO letters of obligation, and fee-for-service agreements; (5) record the actual cost of performance by performance period; and (6) monitor, collect, and report performance information, consistent with FAR Subpart 42.15, for purposes of past performance evaluation in a follow-on streamlined or standard competition. To record the actual cost of performance for a specific performance period, the agency shall adjust actual costs for scope, inflation, and wage rate adjustments made during a specific performance period. The agency shall compare the actual costs to the costs recorded on SCF Lines 6 and 7 when the performance decision was made.

5. Option Years of Performance and Follow-on Competition.

a. Option Years of Performance. The Contracting Officer shall make option year exercise determinations for agency, public reimbursable, and private sector performance decisions in accordance with FAR 17.207. Consistent with the FAR, the Contracting Officer shall not approve performance periods that exceed the total number of years specified in the solicitation used in the standard competition.

b. Follow-on Competition. For agency or public reimbursable performance decisions, an agency shall complete another streamlined or standard competition of the activity by the end of the last performance period on the SCF or SLCF unless a specific exemption is granted by the CSO (without delegation) before the end of the last performance period. The CSO may extend the performance period for a high performing organization if the CSO (a) determines that continued cost savings justifies the extension; (b) documents these cost savings through the use of a COMPARE generated SCF or SLCF; (c) limits the extension to no more than 3 years after the last performance period; and (d) makes a formal announcement of the extension via FedBizOpps.gov. For private sector performance decisions, the Contracting Officer shall comply with the FAR for follow-on competition.

6. Terminations.

a. Terminations Based on Failure to Perform.

(1) Notification. Consistent with FAR Part 49, the Contracting Officer shall notify a service provider (i.e., private sector contractor, public reimbursable provider, or MEO) of poor performance through cure notices and show cause notices. The Contracting Officer shall inform the head of the requiring activity of such notices.

(2) Termination. If the Contracting Officer determines that a service provider (i.e., private sector contractor, public reimbursable provider, or MEO) has failed to perform to the extent that a termination for default is justified, the Contracting Officer shall issue a notice of termination, consistent with FAR Part 49. Upon terminating an MEO letter of obligation, an agency shall change the inventory coding to reflect that the activity is no longer performed by an MEO and shall perform either a streamlined or standard competition.

(3) Temporary Remedies. If the Contracting Officer terminates a contract, fee-for-service agreement, or MEO letter of obligation for the service provider’s failure to perform, an agency may use interim contracts, public reimbursable sources, or government personnel on an emergency basis. An agency shall not allow these temporary remedies to be used for longer than one year from the date of termination.

b. Terminations Based on Reasons Other than Failure to Perform. If an agency determines that performance by a service provider (i.e., private sector contractor, public reimbursable, or MEO) is to be terminated for reasons other than failure to perform, the CSO (without delegation) shall approve such terminations, in writing, and provide a copy to OMB before the termination. Examples of these terminations include, but are not limited to, elimination of an agency requirement through divestiture, privatization, reorganization, restructuring, national defense, or homeland security.

ATTACHMENT D, SECTION B.  Employee Transition Plan. A written plan developed by the Human Resources Advisor for the potential transition of the agency’s civilian employees to an MEO, or to private sector or public reimbursable performance. This plan is developed early in the streamlined or standard competition process, based on the incumbent government organization, to identify projected employee impacts and the time needed to accommodate such impacts, depending on the potential outcomes of the competition. The employee transition plan differs from a phase-in plan, which is developed by prospective providers responding to a solicitation.

ATTACHMENT D, SECTION B.  Phase-in Plan. A prospective provider’s plan to replace the incumbent provider(s) that is submitted in response to the solicitation. The phase-in plan is implemented in the first performance period and includes details on minimizing disruption, adverse personnel impacts, and start-up requirements. The phase-in plan is different from the employee transition plan developed by the Human Resources Advisor.

### NIH Policy

The following are additional post-competition policies set by NIH in order to implement the Circular in the NIH environment.

#### In-House Service Provider (IHSP) Administration Structure

For all in-house decisions, a Letter of Obligation shall be issued by the Contracting Officer to a Responsible Official designated by the Deputy Director for Management (DDM).  The Responsible Official acts in a similar capacity to a corporate officer or partner in a private firm.  He or she is responsible for performance and has the authority to negotiate on behalf of the IHSP.  The Letter of Obligation shall obligate the IHSP to perform the work in the Performance Work Statement or Requirements Document (PWS/RD).  It is to be signed by the Responsible Official and Contracting Officer (CO).

IHSPs shall be monitored during the performance periods specified in a Letter of Obligation using methods similar to those used to monitor a commercial contractor.  NIH will, therefore, maintain a separation between IHSP administration and IHSP performance of work.  This separation is designed to ensure that no conflict of interest, nor appearance of conflict of interest, occurs during the performance of work by an IHSP.

Specifically, the Responsible Official, Contracting Officer, and Project Officer must be separate individuals, and the Project Officer and Contracting Officer must not report to the Responsible Official.  Officials who perform IHSP administration on an IHSP may not serve in the IHSP, and vice versa.  Roles cannot be combined across the IHSP/ IHSP “Contract” Administration line.

Roles may be combined on each side of the line.  For example, the Responsible Official may be the MEO Manager, and the Project Officer may perform the duties of a Quality Assurance Evaluator.  The delineation of the IHSP administration/IHSP relationships is shown below.  These are not necessarily supervisory relationships; they reflect contracting responsibilities.

Figure G-1:  Post-Implementation “Contractual” Relationships

The IHSP has two distinct components that are parallel to the components of a private sector firm.  There is the work that is done under the Letter of Obligation – work that is directed by the PWS/RD – and there is a “corporate” structure that surrounds the work.  In the above chart, work associated with the PWS/RD is within the shaded area labeled “In Scope.”  Costs associated with personnel who are included in that portion of the IHSP were included as direct personnel in the Agency Cost Estimate.

The Responsible Official represents the larger “corporate” framework of the IHSP.  He or she is does not necessarily perform any work that is within the scope of the PWS/RD, but instead provides the corporate oversight necessary to ensure that the work is completed satisfactorily.

The dotted line relationship between the Project Officer and the MEO Manager indicates the day-to-day working relationship that exists in a good contract relationship.  Under most circumstances, the Responsible Official and the Contracting Officer will become involved only when formal contract action is necessary to resolve a situation.  The rest of the time, the Project Officer and MEO Manager, working within the scope of the PWS or RD, will handle and resolve day-to-day matters without recourse to higher-level officials or formal contract-related actions.

#### Implementation Activities

During Implementation, the Implementation Team, with the support of the Human Resources Advisor, Project Officer, Contracting Officer, Commercial Activities Review Team (CART), Commercial Activities Steering Committee (CASC), Transition Center, IC participants, and affected organizations and employees, shall complete all activities required to begin operations under the requirements of the PWS/RD with the structures proposed in the Agency Tender and Agency Cost Estimate.  These activities include, but are not limited to, Letter of Obligation signature, staffing the IHSP and IHSP “Contract” Administration structures, reviewing and implementing changes required by the PWS/RD and Agency Tender/Agency Cost Estimate, communicating with affected individuals and groups, determining training requirements, coordinating logistical changes, developing plans required by the PWS/RD or solicitation, and ensuring that all government property changes are made as required by the PWS/RD and Agency Tender/Agency Cost Estimate.

#### Implementation Team Personnel

The Implementation Team Members, MEO personnel, and others who play a role in implementation are appointed as shown in the following charts.

Other roles, and the parties responsible for approval of personnel assigned to the roles, are shown in the charts below.

| Role | Process | Timeline |
| --- | --- | --- |
| Project Officer | Identified by Preliminary Planning Team Approved by the DDM | Preliminary Planning |
| Responsible Official | Identified by Preliminary Planning Team Approved by the DDM | Preliminary Planning |
| Implementation Team Lead | Responsible Official serves as Implementation Team Lead, or delegation with approval by DDM with notification to the NIH Director | After competition decision(1) |
| Implementation Team | Responsible Official | After competition decision(1) |
| MEO Manager/Supervisors | Standard hiring practices | After competition decision(1) |
| Human Resources Advisor | Standard OSMP practices | Preliminary Planning(1) |
| Contracting Officer | Standard contracting practices | Preliminary Planning(1) |
| Quality Assurance Evaluators | Standard contracting practices | After competition decision(1) |
| Project Officer's Advisory Group | Standard contracting practices | After competition decision(1) |

#### Implementation Timeframes

The Implementation Timeframe is determined by the type of competition conducted.  The following table shows the maximum duration of an implementation by the type of competition:

| Competition Type | # of FTE | FTE Change | Maximum Length of Implementation |
| --- | --- | --- | --- |
| As-Is Organization | Any | Any | 2 months |
| Streamlined with MEO | Any | Any | 6 months |
| Standard | Any | Any | 6 to 12 months |

Implementation efforts should be implemented more quickly, when possible.  Deviations from this policy must be presented to the CASC for recommendation for approval by the DDM.  Letter of Obligation Kickoff meetings shall occur 14 days (10 business days) after a performance decision.

#### Affected Personnel

It is HHS policy that all affected personnel will be offered employment within HHS.  It is NIH policy to find employment for affected personnel within NIH whenever possible.

##### Immediate Reassignment of Affected Personnel

Unless circumstances dictate otherwise, affected employees that require placement outside of the MEO will be reassigned to new permanent positions throughout the NIH as of the implementation date of the MEO. Under this approach:

- Employees will be immediately reassigned to ICs/OD where they will be employed and housed.

- The ICs/OD will be responsible for developing a permanent position for employees assigned to them.

- Training to develop skills necessary for the target position and other employee services will be available to employees through the NIH Transition Center

- The OD, in addition to managing the NIH Transition Center, will provide guidance and assistance such as the development of generic job descriptions, minimum training requirements, etc. to assure a corporate-wide approach to managing the transition.

##### Allocation of Placements

The assignment of employees will be proportional across the ICs/OD to the degree possible. If the assignment of employees is less than proportional, a reallocation of FTEs from all ICs to the receiving ICs may be necessary to avoid inequities.

##### Costs

Training costs for needs assessment, career counseling, re-training, and outplacement support for transition employees will be covered through central services funds.

#### Lessons Learned

Posting of Lessons Learned at the Share A-76! Website is to be completed by the CART.  Others wishing to post lessons learned shall submit their materials to the CART for review and approval.

## Roles and Responsibilities

The following individuals and groups will serve as guides, resources, and key players during the Implementation Process.  Some of these individuals or groups have been involved throughout the competition process and may be able to provide background information on decisions made, an understanding of the overall A-76 process, or other helpful information.  The Implementation and Post Competition phases are dependent on these groups and individuals working together and coordinating their efforts.

Additional details on the individual and group responsibilities are included throughout this section and in Exhibit G-7, which includes one page descriptions of responsibility for the key players.  This list will provide a brief overview and serve as a quick reference for the reader.

- Deputy Director for Management (DDM):  The DDM has the ultimate responsibility for the A-76 program at the NIH, as delegated by the NIH Director, who serves as the NIH Competitive Sourcing Official (CSO).  The DDM may bring issues that require higher-level review to the NIH Steering Committee, Management and Budget Working Group, the NIH Deputy Director, or the NIH Director, as appropriate.  The DDM appoints the Responsible Official and Project Officer for all in-house decisions.

- Executive Officers (EO):  The EO is normally the highest-level IC point of contact for an IHSP; however, the EO may or may not be in the Supervisory chain of IHSP personnel and operations, depending on the specific structure of the IHSP.  The EO receives and certifies the list of all affected employees within the IC and nominates IC representatives for formal A-76 related roles.  The EOs coordinate the receipt of displaced employees, transition from the Transition Center, and ensure that displaced personnel are appropriately appointed into a position within the IC.  The EOs provides feedback to the Project Officer regarding requests for PWS/RD modifications and MEO deviations.  The EO may provide supporting documentation or initiate tracking of new work to justify a modification.  The EO coordinates with the IHSP Manager, Supervisor, Project Officer, or Contracting Officer as necessary regarding potential modifications and deviations, or services to their IC.  If the EO is within the supervisory chain of the MEO, the EO may have additional oversight responsibilities.

- Commercial Activities Steering Committee (CASC):  The CASC’s responsibility, by charter, is to recommend policy to the DDM and make operational decisions to ensure that NIH successfully meets its responsibilities under the FAIR Act and under the Competitive Sourcing component of the President’s Management Agenda, as outlined in OMB Circular A-76.  The CASC will recommend resolution of disputes that cannot be settled by the Project Officer, with the input of the Management Advisory Board.  The Project Officer or a majority of the Management Advisory Board have the authority to bring matters to the CASC for resolution.

- Office of Management Assessment (OMA)/Commercial Activities Review Team (CART):   CART Representatives are the NIH overall project leaders of the A-76 process.  The CART provides assistance to the Implementation Team throughout the process, develops implementation policy, gathers and analyzes the data necessary for NIH-wide A-76 program reporting, and provides technical guidance to the Project Officer for developing tracking systems.  On an exception basis, the CART provides staff support to the Project Officer for performance of quality assurance, performance tracking, and cost monitoring.  This includes clarification of reporting and processes, guidance, and direction on timelines and schedules

- Transition Center:  The Transition Center provides services, resources, and tools to assist NIH employees who are affected by Competitive Sourcing decisions.  The Services are specifically designed to support and facilitate the placement and, when needed, retraining of employees.  Services include training on developing and loading resumes, responding to KSAs, and retirement workshops.  For placements outside of the restructured organization, services include comprehensive career transition workshops, educational or career counseling and coaching, skills, aptitudes, and interests assessments, and tailored skill and job development.

- Office of Strategic Management Planning (OSMP) / Human Resources Advisor (HRA):  The Human Resources Advisor is an OSMP employee designated to coordinate the staffing of the IHSP through development of the Employee Transition Plan, and ensures that all personnel actions are handled appropriately and on time.  The Human Resources Advisor provides guidance and procedures for handling personnel actions in the course of implementation.  This includes the determination and application for Voluntary Early Retirement Authority (VERA)/Voluntary Separation Incentive Pay (VSIP), freeze exceptions, vacancy announcements, and certifications.  The Human Resources Advisor consults and coordinates with OHR to validate Employee Transition Plans and qualifications, provide assistance and training on voluntary changes to lower grade and retirement, announce vacancies, develop certificates, and effect selections, placements, and other personnel actions.  The Human Resources Advisor coordinates activities with the Transition Center Director or representative to identify, notify, and place transition status staff.  The Human Resources Advisor coordinates the placement of displaced employees.

- Labor Relations/Union:  An important player in the implementation process if there are Union employees in the affected population.  There may be multiple individuals associated with the Labor Relations Office that are involved.

- Office of Logistics and Acquisition Operations (OLAO) / Contracting Officer (CO):  The Contracting Officer is an OLAO employee who is designated to oversee the acquisition process.  After the performance decision, the Contracting Officer awards the contract or establishes the Letter of Obligation with the IHSP.  The Contracting Officer, as the overall authority over the contract or Letter of Obligation, monitors the Implementation and performance of the Service Provider, approves all modifications and deviations, verifies that the work performed meets the standards in the PWS or RD, monitors costs, makes option year determinations, issues notices of termination, and maintains the contract and competition files.

- Project Officer (PO):  The Project Officer assists the Contracting Officer in overseeing the Implementation and Stand Up process.  The Project Officer serves as the primary technical representative assigned to monitor the overall performance of the MEO and is the main point of contact between the Contracting Officer and the MEO Manager.  The Project Officer has delegated contract-related authority and responsibility for ongoing performance monitoring, cost tracking, and other contract-type oversight.  The Project Officer coordinates with the MEO Manager on a day-to-day basis to ensure that work required by the PWS/RD is completed satisfactorily.  The Project Officer serves as the chair of the Advisory Group, when needed.  The Project Officer oversees development and recommends approval of all modifications to the PWS/RD and resources required to complete work.  The Project Officer reviews new and changed requirements to determine potential changes to the scope of the PWS or RD.

- IHSP Advisory Group:  The IHSP Advisory Group advises the Project Officer on management issues associated with performance, staffing, and services provided by the implemented organization.  The Project Officer is the chair of the Advisory Group.  The IHSP Advisory Group is different than the Decision Implementation Team and provides an additional resource to the Project Officer when making decisions, particularly when such issues affect multiple ICs.  An Advisory Group will not normally be set up for an MEO that is whole or mostly contained within a single IC.

- In-House Service Provider (IHSP): The term used to describe the MEO or “as-is” organization (an “as-is” organization is one that made no changes during the competition) that competed and won an A-76 competition.  The IHSP includes both “in-scope” (i.e., work that is required in the PWS/RD) and the “corporate” structure associated with the Responsible Official’s duties.

- Responsible Official:  The official responsible for signing the Letter of Obligation and leading the implementation effort; the individual ultimately responsible for the MEO.  The Responsible Official provides information to the community regarding IHSP services and lines of work.  The Responsible Official represents the larger “corporate” framework of the IHSP.  He or she is does not necessarily perform any work that is within the scope of the PWS/RD, but instead provides the corporate oversight necessary to ensure that the work is completed satisfactorily.  In many cases, the Agency Tender Official (ATO) becomes the Responsible Official, or could be the MEO Manager or Project Officer.  The term “ATO” is typically not used after the award decision or after an MEO Manager or Project Officer is named.

- MEO Manager/Supervisors: The MEO Manager is the highest position or supervisor in the MEO.  The MEO Manager may be the original signer of the Letter of Obligation or may have this responsibility delegated to him or her.  The MEO Manager usually serves as the chair of the Implementation Team and oversees day-to-day efforts to ensure that the MEO performs within the limits proposed by the Agency Tender to accomplish the work in the PWS/RD.  The MEO Manager coordinates with the Project Officer on a day-to-day basis to ensure that work required by the PWS/RD is completed satisfactorily.  The MEO Manager provides reports to the Project Officer regarding IHSP work counts and overall work being provided.  The MEO Manager gathers cost data and provides quarterly cost monitoring reports to the Project Officer.  The MEO Manager documents deviations from the PWS/RD, MEO, and Technical Proposal, monitors staffing and resource requirements, and reports deviations to the Project Officer.  The MEO Manager responds to comments, complaints, requests for modification, and other customer input.

- Implementation Team:  The Implementation Team is the group of individuals assembled to assist in the transition from the current organization to the IHSP and “stand-up” the organization.  The Implementation Team Leader heads the implementation effort and ultimately selects the Team.

The relationships between major post-competition roles are particularly important; these personnel play an ongoing role in the In-House Service Provider’s performance.  Post-competition roles are modeled after a standard contract relationship, since the Circular defines an essentially contractual relationship for performance of work after A-76 cost comparison.  This involves an administration effort (known as the IHSP Administration) that will be comprised of the Contracting Officer, the Project Officer, and Quality Assurance Evaluator(s) and an IHSP effort that involves the Responsible Official, IHSP Managers and Supervisors, and the IHSP staff.

A formalized relationship between these two groups is created when the Letter of Obligation is issued by the Contracting Officer and signed by the Responsible Official.  The rest of the interactions between the groups derive from the Letter of Obligation, from the delegation of IHSP administration authority from the Contracting Officer to the Project Officer and Quality Assurance Evaluators, and in the supervisory relationships within the IHSP.  Figure G-1 shows the relationships between these parties.  The DDM, through OMA and its CART, and with the advice of the CASC as necessary, coordinates and oversees resolution of issues that arise between the IHSP administration and IHSP elements of post-competition performance, with the DDM serving as the final arbiter of disputes.

Figure G-1:  Post-Implementation “Contractual” Relationships

The IHSP has two distinct components that are parallel to the components of a private sector firm.  There is the work that is done under the Letter of Obligation – work that is directed by the PWS/RD – and there is a “corporate” structure that surrounds the work.  In the above chart, work associated with the PWS/RD is within the shaded area labeled “In Scope.”  Costs associated with personnel who are included in that portion of the IHSP were included as direct personnel in the Agency Cost Estimate.

The Responsible Official represents the larger “corporate” framework of the IHSP.  He or she does not necessarily perform any work that is within the scope of the PWS/RD, but instead provides the corporate oversight necessary to ensure that the work is completed satisfactorily.

The dotted line relationship between the Project Officer and the MEO Manager indicates the day-to-day working relationship that exists in a good contract relationship.  Under most circumstances, the Responsible Official and the Contracting Officer will become involved only when formal contract action is necessary to resolve a situation.  The rest of the time, the Project Officer and MEO Manager, working within the scope of the PWS or RD, will handle and resolve day-to-day matters without recourse to higher-level officials or formal contract-related actions.

Supervisory relationships are not shown in Figure G-1; there are multiple possible supervisory relationships that may arise depending on the specific structure of the IHSP and the organizations it supports.  For example, two likely scenarios arise for a centralized IHSP.  In the first instance, shown in Figure G-2, the Project Officer and Responsible Official both report to a higher-level Management Official within an IC.  The Responsible Official ensures that the IHSP performs its work satisfactorily, while the Project Officer ensures that NIH is receiving the work required in the PWS/RD, and ensures that customers are receiving the services that they need.

The Contracting Officer, DDM, CART, and CASC are all outside of this formal supervisory chain, but maintain their working relationships for the purposes of completing post-competition tasks.

In each case, there are certain separations that should be maintained.  Although there are no formal requirements to maintain a firewall or separation in the Circular or the Federal Acquisition Regulation, there is still a need to ensure that there is no real or apparent conflict of interest between the IHSP and the IHSP “Contract” Administration.  Because of this, it is NIH policy that the Project Officer must not report to the Responsible Official.  In addition, officials on the administration side of an IHSP may not serve on the performance side of an IHSP, and vice versa.  The Responsible Official and Project Officer must be separate.  Roles cannot be combined across the IHSP/LOO Administration line.  On each side of the line, roles may be combined.  For example, the Responsible Official may be the MEO Manager, and the Project Officer may perform the duties of a Quality Assurance Evaluator.

Figure G-2:  Post-Implementation Supervisory Relationships in a Centralized IHSP (Example 1)

In the second example, shown in Figure G-3, the Project Officer supervises the Responsible Official, and the rest of the relationships remain the same.

Figure G-3:  Post-Implementation Supervisory Relationships in a Centralized IHSP (Example 2)

The structure of a decentralized IHSP (shown in Figure G-4) leads to a more complex management structure and set of relationships.  The structure in Figure G-4 illustrates reporting and coordination requirements required when a function continues to be performed in multiple ICs without consolidation or restructuring.  The Points of Contact listed in the IHSP are supervisors or managers who are over the IHSP.  In the example shown, the POCs are not a direct part of the IHSP.  This will allow the EO or management official to designate one person as the POC for multiple studies, if he or she chooses to do so.  IC POCs may also be in-scope managers and supervisors for an IHSP.  Under most circumstances, the Project Officer and Quality Assurance functions should be located in the IC with the preponderance of the IHSP effort.

Figure G-4a:  Post-Implementation Supervisory Relationships in a Decentralized IHSP (Alternative 1: Project Officer and QA under each EO)

Figure G-4b:  Post-Implementation Supervisory Relationships in a Decentralized IHSP (Alternative 2: Project Officer and QA centralized under the CART)

## Procedures

### Overview

At this point in the competition process, the performance decision has been made and the competition has officially entered the Post Competition phase.   This Chapter discusses the Implementation activities that occur when there is an Agency decision.  In-House Service Provider (IHSP) is the term used to identify the Agency’s Most/More Efficient Organization (MEO) or as-is organization that has been selected as the winner of the competition.  The beginning of the Post-Competition period is referred to as Phase-In, Transition, or Implementation, depending on Agency practice.  NIH refers to the period between Award and the Start Date as Implementation.

Relevant Terms and Documents

Prior to getting started on the tasks listed in this section, it may be helpful to review some of the terms and related documents discussed in this section.

- Post Competition.  The period of time following the performance decision or Award, which continues for the duration of the contract or Letter of Obligation.

- Decision Implementation or Phase-In Period.  The time between Award and the Service Provider’s start date, where the functional operations are prepared to transfer to the Service Provider’s organization and operation.  The duration of this period is typically dependent on the type and size of a study and is usually specified in the solicitation.  The Phase-In Plan is typically executed after Award.

- Letter of Obligation.  A Letter of Obligation is the formal agreement between the in-house Government Service Provider (incumbent organization or MEO) and the contracting office regarding the work requirements that were the basis for the competition.  It is, in effect, the Government’s “contract” with the “winning” Government Service Provider.  It holds the IHSP accountable for the work defined in the PWS or RD and the costs “offered” to perform that work.

- Phase-In Plan.  The Phase-In Plan is the Service Provider’s plan to replace the incumbent provider, which is typically submitted in response to the solicitation.  The Phase-In Plan is implemented during the first performance period and includes details on minimizing disruption, adverse personnel impacts, and start-up requirements.

- Employee Transition Plan (Staffing Plan).   A written plan developed by the Human Resources Advisor for the potential transition of the agency’s civilian employees into the MEO, or into a private sector or public reimbursable organization.  The plan is developed early in the competition process.  The Employee Transition Plan is revised and refined during the implementation period with the input of the Implementation Team.  This Plan is prepared by the Human Resources Advisor in coordination with the Transition Center.  It outlines the options and plans for placing employees, from direct reassignment to advertising for positions.  The DDM has the final approval authority for all Employee Transition Plans.

- Start Date: Sometimes referred to as the “stand-up date,” “full performance date,” or the beginning of the “first period of full performance;” the date upon which the new Service Provider assumes full responsibility for the performance of work described in the Performance Work Statement (PWS)/Requirements Document (RD).

The complexity of the work to be done (and therefore the amount of work required) during Implementation will depend on the type and size of the competition.  For example, a Streamlined Competition with ten employees will likely be much easier to implement than a Standard Competition with 100 employees.  Furthermore, each Implementation will have its own unique activities and requirements based on the organization being implemented.

Implementation Process

As mentioned previously, the Implementation period is the time for the IHSP to transition from the current organization at time of Award to the proposed organization by Stand-Up.  There are many activities and tasks to be completed during this period of time, which will be discussed throughout this Section.  The following flow-chart provides an overview of the activities and milestones one should expect during Implementation.  Throughout this Section, flow charts will be included to highlight the steps and milestones within a certain area of responsibility.

Figure G-5  Implementation Process

Implementation Timeframe

The duration of the Implementation Period is determined by the type of competition conducted.  The following table shows the maximum duration of an implementation by the type of competition:

| Competition Type | # of FTE | FTE Change | Maximum Length of Implementation |
| --- | --- | --- | --- |
| As-Is Organization | Any | Any | 2 months |
| Streamlined with MEO | Any | Any | 6 months |
| Standard | Any | Any | 6 to 12 months |

While the above table shows the maximum time an implementation can take, the implementation efforts may require less time.  The greater the change from the “as-is” or current organization, the longer the Implementation Period may need to be; however, if the change is minimal, the implementation time may not need to be the full time allotted.  Deviations from this policy must be presented to the CASC for recommendation for approval by the DDM.  Use the table above and the requirements of the PWS/RD to choose a Stand-Up date when putting together Implementation Schedules.

### Implementation of the IHSP

The following describes the activities required during the Implementation Period.  As mentioned, each major section includes a flow chart to outline and clarify the steps.  Each Implementation effort will vary to some degree; however, there are specific items and tasks the Team must address.  In addition to the detailed descriptions contained in this Section, there is also a checklist to assist the Responsible Official and Implementation Team in determining responsibilities and priorities in Exhibit G-4.

#### IHSP Kickoff Meeting

Figure G-6

The IHSP Kickoff Meeting is organized and run by the Contracting Officer and is designed to facilitate the start of the implementation of the IHSP.

The Contracting Officer should invite the following individuals to the Kickoff Meeting:

- Responsible Official

- Project Officer

- IHSP Manager (or highest level supervisor)

- CART Representative

- Human Resources Advisor/Transition Center Representative

The following agenda is recommended for the IHSP Kickoff Meeting; however, the Contracting Officer may customize the agenda as needed.

| IHSP Kickoff Meeting Agenda |
| --- |
| 1. Letter of Obligation Review and Signature |
| 2. Roles and Responsibilities |
| 3. Performance Monitoring |
|  | a. Cost Monitoring |
|  | b. Quality Assurance |
|  | c. Reporting Requirements |
| 4. Modifications and Deviations |
|  | a. Requirements-Driven Changes |
|  | b. Resource-Driven Changes |
|  | c. Key Personnel Changes |
| 5. Implementation Efforts |
|  | a. Implementation Team Members |
|  | b. Required Stand-Up Date |
|  | c. Schedules and Milestones |
|  | d. Implementation Checklist |
|  | e. Change to Organizational Structures, Roles, and Responsibilities |

Kickoff meetings will normally occur 14 days (10 business days) after a performance decision.  During that time, employees are notified of the decision, public announcement of the decision occurs, the Letter of Obligation is developed and approved, debriefings are held, and information regarding the decision is made available to the public upon request.  In a standard competition, the kickoff may be delayed by a protest or appeal process.  See Exhibit G-9 for the template schedule of events between a performance decision and the kickoff meeting.  See Section C.12 and Section D.5 for additional detail regarding the performance decision.  See Section F for additional information regarding notifications and announcements.

One of the most important activities at the meeting is the review of the Letter of Obligation and the signing of the Letter of Obligation by the Responsible Official and Contracting Officer.  The Letter of Obligation obligates the IHSP to perform the work in the PWS/RD, which is why this task is important.  Additional information on preparing, issuing, and signing the Letter of Obligation is included below.

The meeting attendees should review the roles and responsibilities of personnel involved in the Implementation Process as well as the responsibilities and goals of the implementation effort.  There is typically an Implementation Team assembled to assist the Responsible Official with Implementation activities.  While the Team’s attendance is not needed at the Kickoff Meeting, outlining their roles and responsibilities is part of the agenda.

Another task for the Kickoff Meeting is to review the performance monitoring requirements, the modification and deviation processes, and the cost reporting requirement.  All of these are discussed in more detail in Chapter H.

The following is a check list of the materials needed for the Kickoff Meeting.  Make sure to have a copy for each of the attendees and make three record copies of the Letter of Obligation.

- Letter of Obligation with any applicable attachments

- Schedule templates

- Implementation checklist

- Study documents

- Report templates

- Cost monitoring forms and instructions

- Modification and deviation forms and instructions

##### The Letter of Obligation

For in-house performance decisions, the organization implemented is referred to as the IHSP.  Typically, this is the MEO as developed and proposed in Agency Tender.  In other cases, the IHSP will be an as-is organization.  Even though it is an in-house win, one can be assured things will be at least slightly different than they were before the performance decision.  This is primarily because the organization is now considered an IHSP, and is therefore accountable to the Government.  This accountability is formally established with the Letter of Obligation.  The Letter of Obligation is the formal agreement between the IHSP and the contracting office regarding the work requirements that were the basis for the competition.

##### Prepare and Issue the Letter of Obligation (Contracting Officer)

The official responsible for the preparation and issuance of a Letter of Obligation is a Contracting Officer from the Office of Logistics and Acquisition Operations (OLAO).  The CONTRACTING OFFICER must make sure the Letter of Obligation is issued, fully signed, and accepted, following the official contest period after the Award.  It is recommended this be completed as part of the IHSP Kickoff Meeting.  A sample schedule for completing this activity is provided in Exhibit G-9 for both decisions with and without protest.  The sample schedule also outlines who is responsible for carrying out the steps.

NIH has developed two templates for use when preparing a Letter of Obligation; one for Standard Competitions and another for Streamlined Competitions.  These templates are provided in Exhibit G-1 and Exhibit G-2.   The templates developed are applicable for virtually any in-house decision, but the Contracting Officer will customize them to meet the needs and requirements of each particular organization.

The Letter of Obligation should include a summary of the functional requirements (e.g., PWS or RD), the period of performance, estimated costs, reporting requirements, inspections and monitoring of services, and any other special requirements.  While not all of these items are required, this is the official and formal agreement that binds the IHSP to perform the work, so it is important to be clear in describing their obligations.

Other sections of this guidebook outline in more detail the responsibilities of the Contracting Officer, including authorizing amendments to the Letter of Obligation in order to accommodate workload changes, or other work environment issues that may change the scope of the requirements to be performed.

##### Sign the Letter of Obligation (Responsible Official)

The Letter of Obligation is signed by the individual who is responsible for the performance of the work and requirements in the RD or PWS.  The Deputy Director for Management appoints the Responsible Official during preliminary planning.  The Circular requires that the Letter of Obligation be issued to an official responsible for performing the commercial activity.  Thus, the person who signs the Letter of Obligation is normally in the management chain above the MEO.

The official who signs the Letter of Obligation is accountable to NIH management for the organization’s performance.  This accountability lasts for the entire term of performance, and this responsibility can be re-delegated as necessary.

Before identifying the Responsible Official, the Contracting Officer and Project Officer should review the potential organizational or management scenarios.  The CART will check all appointments prior to their approval to ensure that the appointments follow NIH policy for conflicts of interest.

###### Scenario 1:  One Function – One Organization

When the function competed is a well defined, cohesive business unit, organizationally structured and consistent with the commercial activity performed, it is relatively simple to determine the Responsible Official.  Typically, the Director of the organization becomes the Project Officer and his or her deputy becomes the Responsible Official.  For example, a motor pool is a business unit that supports an entire activity, with a Director, a clear organizational structure to perform the mission, and all employees ultimately responsible to a Motor Pool Director.  In this example, the Motor Pool Director would be the Project Officer and his or her deputy would be the Responsible Official and would sign the Letter of Obligation.  In a very small organization or study, it may be difficult to identify two personnel with detailed knowledge of the function.  In this case, the organization may request that a higher-level manager or a peer supervisor serve as the Project Officer.

###### Scenario 2:  Multi-Function – One Organization

If more than one function within a larger organizational component was competed, the scenario is a little more complex, but generally not difficult to address.  While there may be multiple activities or functions, and potentially a direct supervisor for each, the supervisors and their respective functional areas of performance are still part of a larger mission or functionally cohesive unit.  Therefore, the employees in the organization are ultimately accountable to one manager or supervisor at a higher level in the organization.  That manager or supervisor may serve as the Project Officer, with his or her deputy, or a lower-level manager who supervises part or all of the MEO, serving as the Responsible Official.  For example, a competition may be conducted for the Training and IT support functions within one IC.  Both the Training and IT groups have their own supervisors, who are responsible to a manager or supervisor at the next level.  The higher-level manager serves as the Project Officer while the IT group, which has two-thirds of the FTE within the MEO, serves as the Responsible Official.

###### Scenario 3:  One or Multi-Function – Multi-Organization

For competitions where functions cross operationally divergent organizational boundaries, the scenario is more complicated.  For example, a competition of administrative functions across multiple ICs would include multiple supervisors and managers accountable for the performance of the activity.  This can make it difficult to determine who the Responsible Official should be.

In this situation, the Preliminary Planning Team may identify multiple potential Responsible Officials and Project Officers.  They submit the identifications through the CASC for final approval by the DDM.  In some cases, the CASC will help identify an appropriate and qualified Responsible Official and Project Officer.

In all determinations of the personnel who will serve in the above roles, it is important to keep in mind the complex and potentially time-consuming interrelationships that are associated with post-competition implementation and oversight.  Section G.2 provides details regarding the relationships that occur in each scenario, and should be reviewed prior to determining the final structure of the Letter of Obligation administration and oversight functions.

#### Select the Implementation Team

##### Implementation Team Leader

The Responsible Official serves as the Implementation Team Leader, unless the Deputy Director for Management approves a delegation of this role.  The Implementation Team Leader ensures that the necessary milestones are met and everything moves as smoothly as possible during Implementation.  In general, the Team Leader will oversee all Implementation activities, make decisions, delegate tasks to the Implementation Team, and make sure the IHSP organization meets the Stand-Up date.  The Implementation Team Leader is also responsible for organizing meetings, making decisions, and managing the Post Competition activities, which continue after the Stand-Up of the organization.  A significant amount of effort is required of the Implementation Team Leader prior to stand up; however, while the level of effort may decrease after Stand-Up, the individual will have an obligation to the organization.  It is important for the person selected as the Implementation Team Lead to understand the level of effort and responsibility associated with this position.

##### Implementation Team Members (identified by the Responsible Official with notification to the Deputy Director for Management)

To effectively complete the implementation activities, the Implementation Team Leader will need the assistance of a knowledgeable Team.  The purpose of the Implementation Team is to provide leadership, guidance, and decisions throughout the implementation process; most importantly, they are vital to minimizing the effect the implementation has on the products and services of the organization.  The Team should include members with a variety of expertise and skills in the functional area and business unit, as well as human resources and personnel management.  This expertise will help ensure a successful, thoughtful, and positive transition to the IHSP.

The invitation to participate on the Implementation Team should be extended to all ICs with affected employees, and identification and approval of Implementation Team members should follow the process outlined in G.3.2.1.3.

Some or all of the members of the Implementation Team may have been identified or chosen before the performance award date (as suggested in Section B); if not, the Team should be identified as soon as possible after the Letter of Obligation is signed.  Potential team members can be identified during the initial Kickoff Meeting, and typically membership should be finalized within a few weeks of the signing of the Letter of Obligation.  Forming the Team quickly is particularly important when the Implementation period is short (e.g., two months).

The following is a list of typical Implementation Team Members, including a brief description of what their role on the Team is, and why they may be needed.  This list should serve only as a guide, and the Project Officer or MEO Manager may customize the membership of the Team to fit the needs specific to the IHSP’s organization.  The Implementation Team may have individuals with expertise in only one area, or whose expertise crosses several areas.  Furthermore, the Team is not limited to one person per area or expertise, with the sized of the Team dependent on the size of the competition.  Fill in the following table as the Implementation Team is selected.

Implementation Team Members

|  | Human Resources Advisor (required member) | The Human Resources Advisor is necessary to ensure all personnel actions are handled appropriately and applicable deadlines and timeframes are met. The Human Resources Advisor should already be identified and will have participated in the other phases of the competition process. The Human Resources Advisor is responsible for identifying and coordinating transition services. |
| --- | --- | --- |
|  | Implementation Team Leader (required member) | The Implementation Team Leader heads the implementation effort. Often, the Implementation Team Leader is the Responsible Official or former ATO. |
|  | CART Representative (required member) | The CART Representative is assigned to the Implementation Team by the Office of Management Assessment (OMA). This individual will be able to provide guidance on NIH policies and procedures for the implementation and post-competition efforts. |
|  | Communications Coordinator | The Communications Coordinator has skills and knowledge associated with contacting and providing information to affected personnel and the NIH community. The need for a dedicated individual will be dependent on the size of the organization and the level of communication expected. |
|  | NIH and/or Division Management | Management is a valuable resource for knowledge of the organization, process, and employees. Having the cooperation and understanding of Management will ease the implementation process. These individuals may be management representatives from the affected ICs. |
|  | Subject Matter Experts | Subject matter experts are beneficial when it comes to implementing changes identified in the MEO or private sector offer and maintaining the continuity of operations during the implementation. Depending on the function, there may be a need for several subject matter experts. These individuals may be representatives from the affected ICs. |
|  | Information Technology Resource | Including an individual familiar with IT on the Team is particularly helpful if there are new technology requirements or systems, or a large turnover of employees is anticipated during the implementation. The need for this individual is dependent on the IHSP organization and technological changes. |
|  | Administrative Officer (AO) | AOs are responsible for tasks such as timekeeping, ID badges, finance and budget, space and overall IC operations. New or exiting employees and changes in location or facilities will require coordination with these individuals. Having an AO representative familiar with the process as part of the Team might be beneficial especially if there are multiple locations and changes. |
|  | Union Representative | If there are affected employees who are in the Union, it is highly recommended that a Union Representative be on the team. The level of participation for the Union Representative will vary depending on the interest and number of employees affected. Regardless, the invitation to join the Implementation Team should be extended to the Union when Union employees are involved. |
|  | A-76 Consultant or Expert | While not required, having someone who is familiar with the A-76 and implementation processes is very beneficial. The CART representative will be able to identify possible consultant support or A-76 expertise available to the Team. |
|  | Other Team Members (Identify as needed) | Expertise/IC: |
|  |  | Expertise/IC: |
|  |  | Expertise/IC: |
|  |  | Expertise/IC: |

After selecting the Team, the Team Leader should schedule an initial team meeting to discuss the Implementation process, responsibilities, and schedule.  It is recommended the Team pick a time and a place for standing meetings and determine the best and most effective way to communicate amongst the Team members.  These meetings may continue even after the IHSP is implemented to track progress changes and reporting.  Taking minutes at the meetings will help to ensure everyone is aware of progress and assigned responsibilities.

#### The Implementation Schedule

##### Identify Milestones (Project Officer and Team Leader)

The milestones for the Implementation Team are the main activities the Team must complete between the Award and Stand-Up date.  The CART and Contracting Officer may provide specific or approximate dates, but the milestones should be set during the Implementation Kickoff Meeting.

The milestones are also the dates the CART is interested in for reporting purposes, specifically for OMB.  Therefore, the Implementation Team Leader must maintain the schedule of milestones included in Exhibit G-5 and submit an updated version weekly to the CART during the Implementation Period.

The following table will help identify the structure and timeframe for Implementation during the Kickoff meeting.

| Milestone | Date |
| --- | --- |
| Performance Award Decision |  |
| Award Announcement |  |
| Signing of Letter of Obligation (Kickoff Meeting) |  |
| Implementation Start |  |
| Stand-Up |  |

The Implementation Team should schedule the Stand-Up date to coincide with a pay period.  This may seem minor; however, it is very beneficial when coordinating the human resources activities.

If the projected Stand-Up date differs from the date originally projected for Stand-Up, the Implementation Team Lead must provide a writing justification to the Contracting Officer and the CART.  IHSPs are to be treated as contracts, and a change to Stand-Up is a significant event in a contract.

##### Set the Schedule (Implementation Team)

The Implementation process requires multiple steps to meet the milestones listed above.  To ensure the tasks described within this chapter are completed prior to Stand-Up, it is beneficial to develop a detailed schedule.  This schedule is internal to the Implementation Team and is designed to be customized to meet the needs of the Team and the Implementation efforts.  The Team will most likely have a better understanding of how long the tasks will take once they are familiar with the requirements.  Therefore, the Team should read this Chapter in its entirety prior to determining the schedule.

To help the Team plan accordingly, a sample detailed schedule is included in Exhibit G.  This schedule is designed to be customized by the Team and used as needed.  The following table may also help the Team plan some of the internal deadlines.

| Task | Date |
| --- | --- |
| Implementation Start |  |
| Review Key Documents |  |
| Develop Communication Strategy |  |
| Develop Employee Transition Plan |  |
| VERA/VSIP Request |  |
| Begin Staffing |  |
| Establish CGA |  |
| Implement QA and Cost Monitoring Procedures |  |
| Training |  |
| Stand Up |  |

In some situations, a Phase-In Plan may have been developed during the competition process.  The Team can use the general schedule typically included in the Phase-In Plan as a basis for the actual schedule to be developed.  However, it likely will need to be updated and further developed.

Generally, the Implementation Team must complete their activities within the maximum time allowed.  It may become apparent during schedule development that additional time is needed to complete implementation.  If this occurs, the Implementation Team must request an extension from the Contracting Officer.  This may be necessary if the identified activities cannot be completed within the timeframe specified when the Stand-Up date was decided.  For example, if there are many affected employees who must be placed, the Implementation may need more time to place all of them.  Allowing sufficient time to complete the key tasks is essential to a smooth transition.  However, it is also important and good practice not to let the transition take any longer than necessary because of the disruption the process can cause with affected personnel and customers.

#### Read the Key Documents (Implementation Team)

Another important step the Team should take is to review the key documents of the competition.  This includes the PWS or RD, MEO, the Agency Tender, Phase-In Plan, Quality Control (QC) Plan, Quality Assurance Surveillance Plan (QASP), and Cost Estimates.  Not all of these may be applicable to every competition, but the Team should identify and obtain all applicable key documents.

As part of the review, the Team should identify discrepancies or changes in the documents that need to be discussed or addressed.  For example, there may be changes in workload or revised performance periods.  The Team Leader may coordinate with the CART and Contracting Officer to obtain copies of the competition documents for the Team.  The following table shows they typical documents for each type of competition.

| Documents | Streamlined | Standard |
| --- | --- | --- |
| PWS |  | X |
| RD | X |  |
| MEO | X | X |
| Agency Tender | X | X |
| Phase-In Plan | * | X |
| Quality Control Plan | X | X |
| Quality Assurance Surveillance Plan | X | X |
| Cost Estimates | X | X |
| Letter of Obligation | X | X |

* Some streamlined competitions may have Phase-In-Plans.

The key documents are important as they identify the information that needs to be tracked and measured and help in determining the time-frame for implementation, interim steps and deadlines, and the responsibility of the IHSP.  In addition, the documents will assist the Team in understanding the new organization by becoming familiar with the requirements, procedures, and organizational structure.

The Team should review the documents to determine if there are changes that occurred between the development of the PWS/RD and Award.  Also, the Team should examine how the current organization and the MEO are different and the level of effort it will take to make the change.

The Team must identify where the IHSP has proposed new policies, procedures, and equipment beyond what is described in the PWS or RD.  Even if there are minimal changes, all changes should be identified to ensure the continuity of services and to inform all affected parties.  New equipment, procedures, and policy may have been developed or implemented since the development of the PWS/RD and Agency Tender, and, therefore, may affect the Stand-Up of the organization.

For example, the IHSP may have proposed using an electronic system to track workload, which eliminates some of the manual steps to log work.  As a result, there may be processes in the organization that may need to be modified.  This change may also lead to new training requirements.

The IHSP’s Agency Tender/MEO should be released to the affected employees at the time of the Implementation start; however, Implementation Team Members may wish to acquire a copy of the Agency Tender/MEO prior to the first Implementation Meeting from the Contracting Officer.  This will help if the Team members interact with affected employees who may have questions when the documents are released publicly.

The Team should also review the PWS, RD, or solicitation for additional plan requirements (e.g., Continuity of Operations Plan (COOP)).  The Team must identify what plans and other requirements for which they are responsible.  Again, not every Implementation is the same, and therefore, there may be some tasks that do not apply.

The Team may want to use the following checklist when reviewing the key documents to track changes, needs, and potential issues.

Document Review Checklist

| CHANGE or NEED | YES | NO | NOTES |
| --- | --- | --- | --- |
| PWS/RD Changes |  |  |  |
| Regulations and Directives |  |  |  |
| Services and Workload |  |  |  |
| Performance Standards |  |  |  |
| Quality |  |  |  |
| Timeliness |  |  |  |
| Work Locations |  |  |  |
| Customers |  |  |  |
| MEO Changes |  |  |  |
| Staffing |  |  |  |
| Processes and Procedures |  |  |  |
| Automated system for tracking workload |  |  |  |
| Training |  |  |  |
| Non-furnished equipment and property |  |  |  |
| Quality Control Program |  |  |  |
| Agency Cost Estimate Changes |  |  |  |
| Performance Periods |  |  |  |
| Staffing |  |  |  |
| Equipment and property |  |  |  |
| Quality Assurance/Quality Control Needs |  |  |  |
| System for measuring the performance of the organization |  |  |  |

The Chart above will help the Team process the information as they read and identify any factors that may affect the implementation process or the performance of the IHSP.  This will also help the Team identify where more information is needed and determine how to get the information.  The Team should document any changes for potential modifications and deviations and notify the appropriate individuals and groups (e.g., Contracting Officer, CART, CASC) of the issues and concerns that are identified.

The review of documents should be complete early in the Implementation process. These documents provide the basis for the IHSP’s organization and responsibilities, and are the primary source of information for the Implementation Team.

#### Staff the IHSP Organization (Human Resources Advisor, Implementation Team)

Staffing the organization is a critical step in “standing-up” the IHSP’s organization.  Potentially, the Implementation Team may encounter changes in structure, quantity of employees, and grades.  The following steps will help the Implementation Team identify the staffing activities needed, and meet the Stand-Up deadline.

Figure G-7

Develop an Employee Transition Plan (Human Resources Advisor, Transition Center Representative)

The Human Resources Advisor is responsible for developing and preparing an Employee Transition Plan for the organization.  The Employee Transition Plan should normally be prepared during development of the MEO.  The Plan is reviewed and refined by the Implementation Team and must be approved by the Deputy Director for Management (DDM).  The Employee Transition Plan addresses the changes between the current organization and the Service Provider’s organization.  For an IHSP win, this may also involve plans for VERA/VSIP and the Transition Center, as well as the use of directed reassignments, recruitment, and change to lower grade.

The Human Resources Advisor will follow NIH goals and guidance to ensure employees are fairly placed into new or existing organizations, while taking into consideration the competencies of the employee.  The NIH Staffing Principles are provided in Exhibit G-6.

The following outlines the content of an Employee Transition Plan:

Introduction:  The introduction provides a synopsis of the MEO.  Indicating the function that was studied, how the review was accomplished, a snapshot of the resulting organization, as well as the outcome and impact on the population.

Directed Reassignments:  The Human Resources Advisor, in coordination with the servicing HR Specialist, will identify all possible direct reassignments within the impacted population to reduce the amount of resources and time required to staff the organization.  Names, current titles, series and grades should be listed (even though they are not in the sample below).

Recruitment: The Human Resources Advisor will identify, in coordination with the servicing HR Specialist, the recruitment actions that will be required to complete the staffing of the MEO.  The process to be followed and areas of consideration outside of the impacted population will be identified.

Retirement Options and Buyouts: This should indicate whether this authority will be pursued, and the status of the request, and whether/hoe notification has been provided to the impacted staff.

Current Staff: This should indicate what may be required of current staff in order to be placed, as well as special circumstances that may exempt current staff from some of the efforts identified above.

Implementation Team: The approved Implementation Team should be listed here.  If the team does not reflect full representation, such as an impacted IC has chosen not to send a representative, then that should be stated here.

Once completed, the HR submits the Employee Transition Plan to the DDM.

Services Available Through the Transition Center

The NIH Transition Center was established to assist employees affected by organizational changes resulting from A-76 competitions, via a comprehensive career transition program.  Basic services provided by the Transition Center help employees find and successfully compete for available positions.  Intensive services support the individual needs of those employees when placement is less likely.

Training through the Transition Center is provided to employees, manager, supervisors, and union representatives affected by the process.  Job search skills, resume writing, skills assessment, interview techniques, stress management, and transition management, are all examples of basis services provided by the Transition Center.  In situations where the affected employee does not have the skills or competencies needed to be placed in any available NIH vacancy, more intensive services and support are provided.  The development of these employees is detailed and defined through individual training plans.

Training may also be provided to meet the demands of the organization under review, meet its future workforce needs, provide retraining strategies and plans, and help displaced employees obtain meaningful employment.  These efforts may require the Transition Center to coordinate with the other appropriate NIH Training entities.

The Implementation Team should be familiar with the services of the Transition Center.  The Transition Center is not an actual location or space where employees go to look for jobs; however, the Center is a source of resources and services to assist employees displaced from their positions.

Place Employees in the IHSP Organization

Once the Employee Transition Plan is approved, the Implementation Team can begin to work together with the Human Resources Advisor to handle recruiting, hiring, and staffing of the organization.  However, the Team should work to minimize disruption to the current employees and customers.

As IHSP positions are filled during the Implementation period, the Implementation Staffing Status Form must be completed and submitted twice per month (2nd and 4th Mondays) to the Contracting Officer.  This form should be submitted throughout the Implementation Period until Stand-Up, following the defined approval chain.  This Form will help the Implementation Team track the progress of the staffing efforts internally, as well as begin gathering information on the actual staff composition of the IHSP.  A copy of the Implementation Staffing Status Form is provided in Exhibit G-8.

Completing the Form

The Implementation Staffing Status Form has two sections: the left-hand section listing the positions identified in the Agency Tender and Agency Cost Estimate and the right-hand section for actual staffing information. The actual staffing information includes the Current Employee Name, Position Title, Position Type, Location, Grade, and Organization at the section level, IC, and FTE amount. The actual staffing information should be included on the same line as the Agency Tender/Cost Estimate position on the left.   If an IHSP employee does not correlate to an Agency Tender/Cost Estimate position listed in the left-hand section of the form, the employee information should be added in a blank line.  It may be helpful or necessary to add a comment for lines where there is a discrepancy between the Agency Tender and IHSP Staffing.

The Human Resources Advisor will pre-populate the left side of the form using the staffing information provided in the Agency Tender.  The Human Resources Advisor, Project Officer, and MEO Manager should monitor the staffing of the IHSP using this Form.  As the Stand-Up date approaches, it is recommended that the Form be completed and reviewed weekly.

The purposes for completing this form are to establish the exact positions in the organization, keep the organization on schedule, and to identify any deviations (even if just administrative; for example, a change in the position title) to the MEO.

When the staffing is completed, the Project Officer must submit the completed and final Form to the Contracting Officer for documentation and filing in the official contract file.  This information will also be used to recode positions in the FAIR Act Inventory.  The information gathered on this form will be directly applied to the Personnel Cost Tracking forms discussed in Section H.

If the IHSP has vacancies that cannot be filled prior to Stand-Up, or immediately thereafter, the IHSP may choose to utilize temporary contractors to fill these vacancies.  Since the Circular specifically prohibits direct conversions to contract without a competition, the IHSP cannot place contractors permanently in those positions unless they were proposed as a subcontract.  Instead, the IHSP may use temporary contractors to fill vacancies, and the cost of those subcontracts will be included in their cost reporting.  However, the IHSP should work to fill those positions with Government FTE as soon as possible.

Align IHSP Staff in FAIR Act Inventory

The IC, in coordination with the CART, must align IHSP staff with the FAIR Act Inventory.  This is an important step in the competition process because NIH must report their Inventory annually.  Therefore, it is imperative to keep this data up-to-date.

#### Communicate With Affected Individuals and Groups (Implementation Team)

Keeping employees, customers, and other affected personnel (directly and indirectly) informed is crucial to a successful decision implementation and phase-in.

Since it is important to keep people informed, the Implementation Team should identify or develop a communications strategy and Communications Plan.

The Communications Plan or strategy should address how to communicate with affected staff, customers, NIH leadership, and the overall NIH community.  The Team must identify and designate the lines of communication between the MEO Manager, Project Officer, and Contracting Officer within the structures required by the A-76 process and discussed in Section G.2.  For Standard Competitions, a Communications Plan may have already been included as part of the Agency Tender.  A sample Communications Plan is provided in Exhibit G-3.

Communications should be primarily directed at two different audiences: the affected staff and the customers who will be receiving the services of the organization.  The Team should keep both audiences aware and informed of timelines and changes in operations ahead of time.  Even if the only information to share is that there are no new developments or changes, communication is necessary and may alleviate tension with the affected individuals and groups. Providing opportunities throughout the implementation period for both audiences to ask questions and provide feedback will also help in keeping the communication lines open.

The Team should consider a variety of communication methods, including meetings, e-mail, and accessible information via the NIH Portal or Web-site.  The Team may also consider holding an all-hands meeting after the performance decision for affected employees.  This meeting may address the A-76 process, the new organization, and resources available to affected staff.  The Team should compile a list of Frequently Asked Questions (FAQ) based on the questions asked by the employees to post on the web or make available via other means, especially for those who were unable to attend the meeting.  The CART maintains a broader FAQ on its website; see http://a-76.nih.gov/.

#### Identify Training Needs and Strategies (Implementation Team)

The Implementation team should identify training needs and opportunities both before and after Stand-Up. In many scenarios, employees will need training both before and after Stand-Up.  Training needs are often dependent on the Employee Transition Plan and the differences between the current organization and the one being implemented.  More training will be needed if new hires are anticipated, duties and responsibilities change, or other changes from the existing organization and processes.

The Team can identify if there is a current training plan in place for the organization, ask the IC representatives and supervisors how new staff are usually trained, and collect information on any existing standard operating procedures.  The functions of the new organization will typically be the same, and therefore, obtaining historical training information from the affected organization will most likely be easier than developing a whole new training plan.  The Implementation Team may want to consider developing a Training Plan for the organization if one does not exist, or refining an existing Training Plan to align with the new organization.

The table below presents a summary of some helpful NIH training resources:

| Training Resource | Training Components | Cost |
| --- | --- | --- |
| NIH Training Center | Learning gateway to agency-specific training, strategic development programs and customized solutions for you and your organization. Along with providing a wide array of internal learning opportunities, the NIH Training Center collaborates with learning partners such as the HHS University, CIT Training, and CDC Corporate University. Information on a variety of external training resources is available through the NIH Training Center. | Free and training fee |
| HHS University | HHS U provides common needs training and development opportunities for HHS staff via traditional classroom training, online self-study, development programs, and career counseling. | Free online training and training fee |
| CIT | The CIT Training Program provided by the Center for Information Technology offers a wide variety of courses and seminars that enable users to make efficient and effective use of computers, networks, and information systems in their work at NIH. The training program is open to NIH employees and to all users of CIT computing facilities. Additional computer courses are available through the NIH Training Center, HHS University, and the NIH Library. | None |
| Transition Center | Available only to those individuals affected by an A-76 competition and those not placed in the resulting organization. | None |

#### Coordinate Logistical Changes (Implementation Team)

The Team will be responsible for coordinating with the applicable AOs to ensure the logistics for the Implementation and Stand-Up efforts are carried out and the necessary items are obtained or in place prior to the Stand-Up date.

Depending on the size of the Implementation, it may be helpful to assign specific individuals or groups responsibility for particular logistical changes and actions.  This might help things progress on schedule and alleviate some of the pressure on the Project Officer or Responsible Official, Contracting Officer, and Implementation Team.

#### Consider Developing Contingency Plans (Implementation Team)

The Implementation Team should consider developing contingency plans to prepare for the unexpected.  For example, delayed start dates or inability to fill the IHSP positions.  These are issues that frequently arise during the Implementation period and should be addressed by the Team throughout the process.  The Team may want to examine what the “worst-case” scenarios are in preparation for Stand-Up.  Another approach to consider is using phased or trial roll-outs of new systems and processes.  This will help address any problems on a smaller scale, thereby limiting the impact on employees and customers.

For instance, a contingency plan for staffing shortages may include the use of a subcontractor to temporarily fill vacancies until permanent staff are hired.  In a situation where the IHSP is proposing the development and use of a new technology or system, potential delays and correction of “bugs” should be addressed.  The Implementation Team may want to include in the Implementation Schedule time for beta-testing of new systems or procedures with a small portion of employees and customers before implementing completely.  This staggered or phase-in method would allow time for customer and employee feedback, and the ability to improve the new process before employing it for the entire organization and customer population.  Processes can also be transitioned gradually across the organization in sections, as opposed to an immediate change in operations.

#### Conduct Inventories of Property (Implementation Team)

Although the Team may have already reviewed the PWS or RD, the Team should review the Government Furnished Property and Government Furnished Supplies sections again prior to completing inventory requirements.  Normally, the Team will need to coordinate and conduct an inventory of the on-hand equipment and supplies that will be provided to the IHSP by the Government.  The Team should also check the planned utilization of Government Furnished Facilities to determine whether any space will need to be changed or personnel moved to accommodate new IHSP personnel or processes.  The Team will also want to identify equipment or facilities that need to be repaired or changed before they are officially turned over to the IHSP.  Any changes to facilities or equipment are likely to involve costs, and as such, should be included in budgets for work associated with support of the IHSP.  In some cases, the IHSP will also have facilities or equipment that it controls, and these items will also need to be included in the overall budget for the organization.

### Stand-Up the Organization

The Implementation Period is when the staffing of the organization takes place, the QASP is revised and prepared for implementation, and the new organization begins to take shape.  During this time, the IHSP may begin to assume partial responsibility (if they haven’t already been doing the work) for the products and services being provided.  The IHSP’s organization also begins to be accountable to the Contracting Officer and Project Officer.

The Stand-Up of the IHSP is the actual day the organization assumes full responsibility and performance of the products and services.  Ideally, all positions in the organizations are filled and any changes have been accomplished by Stand-Up.

In the last few weeks before stand-up, the Project Officer and Responsible Official or MEO Manager should regularly review the staffing status, the QASP and QA procedures, and monitor the full transition.  The following is a checklist of potential “last minute” tasks either to verify status or monitor closely.

- Transfer of employees to IHSP organizations (change job codes)

- Post vacancies, review applicants, select staff

- Finalize internal cost tracking methods

- Finalize logistical information (locations, phone, IT and NED accounts, timekeeper, AO)

On the date of Stand-Up, the employees should all be realigned with the IHSP organization, and the IHSP will be fully responsible and accountable for performance.

## Potential Pitfalls

There are several pitfalls those involved with the Implementation process should be aware of.  First, make sure to identify a schedule that is reasonable.  While it is important to make sure the process is not excessively long, be sure to allow enough time, particularly for the human resource activities.  The requests for VERA/VSIP and the approval of the Employee Transition Plan are dependent on outside parties, and therefore, the Team does not have a lot of control over when they are received.

Next, make sure the invitation to join the Implementation Team is extended to all ICs with affected employees.  While ICs may choose not to participate, it is very important they be given the opportunity.  The ICs are bound by the decisions of the Team regardless of whether they participate in the process or not.

Finally, make sure the individuals involved in the process understand the requirements and responsibilities they are assuming.  This is an important step in the overall A-76 process and the participants need to understand their roles.

## Exhibits

Letter of Obligation for Standard Competition

Letter of Obligation for Streamlined Competition

NIH CART Sample Communications Plan

Decision Implementation and Phase-In Checklist

Sample Implementation Schedule Tracking Tool

NIH Staffing Principles

Key Player Position Summaries

Contracting Officer

Human Resources Advisor

Project Officer

Implementation Staffing Status Form

Letter of Obligation Schedule

# Text boxes

Contracting Officer

OMA/CART

DDM

CASC

(IC) MEO Supervisors

MEO Manager

Letter of Obligation

DDM

OMA /CART / PO / QA

CASC

OAMP/CO

Management Officialn

Management Official2

Contracting Officer

OMA/CART

IHSP Operations

IHSP “contract” administration

Responsible Official

In Scope

Quality Assurance Evaluator(s)

Project Officer

Management Officialn

Management Official2

DDM

OMA/CART

IC POCn

CASC

OAMP/CO

IC POCn

IC POC2

IHSP

IHSP element n

IHSP element 2

IHSP element 1

Responsible Official

Project Officer & QA

Management Official1

In Scope

IC POC2

IHSP

IHSP element n

IHSP element 2

IHSP element 1

Responsible Official

Management Official1

In Scope

DDM

OMA/CART

CASC

OAMP/CO

IHSP

Management Official

MEO Supervisors

MEO Manager

Responsible Official

In Scope

Project Officer/ QA

DDM

OMA/CART

CASC

OAMP/CO

Management Official

IHSP

MEO Supervisors

MEO Manager

Responsible Official

In Scope

Quality Assurance Evaluator(s)

Project Officer

DDM

CASC

(IC) MEO Supervisors

MEO Manager

LOO

IHSP Operations

IHSP “contract” administration

Responsible Official

In Scope

Quality Assurance Evaluator(s)

Project Officer