| PRIORITY ONE: Increase housing opportunities available to chronic homeless individuals by at least 300 units within 3 years |
| --- |
| Objective 1: Increase housing opportunities available to chronic homeless by maximizing use of existing funding streams |
| Strategy | Action(s) | Manager¹ | Implementer² | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 1.1 Use HOME-Tenant Based Rental Assistance to provide 100 units of housing | Action 1.1.1 Develop program design | Nikki Nicholau | DHCD | # of units-100 | January 2004 | 10/2005 & ongoing |
|  | Action 1.1.2 Fund at $500,000 for FY2004-06 Action Plans |  |  |  | April 2004 |  |
|  | Action 1.1.3 Issue grant |  |  |  | July 2004 |  |
|  | Action 1.1.4 Award grant |  |  |  | August 2004 |  |
|  | Action 1.1.5 Track & report results |  |  |  | September 2005 CAPER |  |
| Strategy 1.2 Initialize VHDA/ DMHMRSAS special project using Mainstream Housing Opportunities for Persons with Disabilities vouchers with distribution through Community Services Boards in non-entitlement areas. | Action 1.2.1 Determine administrative eligibility for project. | Chris Hilbert | VHDA/ DMHMRSAS | # of units- 75 | December 2003 | 6/2005 & ongoing |
|  | Action 1.2.2 Develop proposal |  | Chris Hilbert/Joy Cipriano |  | March 2004 |  |
|  | Action 1.2.3 Get Memorandum of Understanding (MOU) signed |  | VHDA/ DMHMRSAS |  | April 2004 |  |
|  | Action 1.2.4 Complete competitive grant application |  | VHDA |  | June 2004 |  |
|  | Action 1.2.5 Distribute Vouchers |  | DMHMRSAS |  | December 2004 |  |
|  | Action 1.2.6 Track & report results |  | DMHMRSAS |  | June 2005 |  |
| Strategy 1.3 Expand VHDA/ DMHMRSAS special project using Mainstream Housing Opportunities for Persons with Disabilities vouchers with distribution through Community Services Board (CSB) in entitlement areas | Action 1.3.1 Request assistance from CSB throughout state to approach public housing authorities (PHAs) | TBD | DMHMRSAS |  |  |  |
|  | Action 1.3.2 Develop a talking paper |  | TBD |  |  |  |
|  | Action 1.3.3 Approach PHAs in a minimum of 5 localities |  | CSB |  |  |  |
|  | Action 1.3.4 Provide program design from Strategy 1.2 |  | CSB |  |  |  |
|  | Action 1.3.5 Follow-up to determine action taken |  | TBD |  |  |  |
|  | Action 1.3.6 Report number of vouchers provided under program |  | TBD |  |  |  |
| Strategy 1.4 Expand use of Veterans’ Administration, HUD and USDA-Rural Development foreclosed properties as a source of new housing units | Action 1.4.1 Obtain current program requirements | Bert Boyd Bill Burnham | DVS/HUD/ USDA-RD | # of units- 30 in 3 years | January 2004 | March 2005 |
|  | Action 1.4.2 Identify VHDA financing to assist with renovations/purchase |  | VHDA |  | January 2004 |  |
|  | Action 1.4.3 Develop information sheet/ packet for state non-profits |  | DVS/HUD/ USDA-RD |  | February 2004 |  |
|  | Action 1.4.4 Distribute sheets through VIACH, web site and other venues |  | All PA members |  | July 2004 |  |
|  | Action 1.4.5 Provide TA to groups at VCH conference and Governor’s Housing Conference |  | DHCD/VIACH/ VCH/Homeward |  | December 2004 |  |
|  | Action 1.4.6 Track & report |  | DVS/HUD/ USDA-RD |  | March 2005 |  |
| Strategy 1.5 Increase available HUD Supportive Housing Program funds available to support housing initiative through expansion of Continuum of Care (COC) to cover state. | Action 1.5.1 Identify localities without COC organizations – provide listing of localities | Nikki Nicholau | DHCD/VIACH/ HUD | # of units – 30 $1.4 million in new resources | January 2004 | July 2005 |
|  | Action 1.5.2 Identify localities in the process of developing CoC’s – provide listing |  | DHCD |  | January 2004 |  |
|  | Action 1.5.3 Provide technical assistance to those localities |  | DHCD/HUD |  | July 2004 |  |
|  | Action 1.5.4 Identify & contact localities that might expand to incorporate additional localities |  | DHCD/VIACH |  | March 2005 |  |
|  | Action 1.5.5 Develop Balance of State COC Statement |  | DHCD |  | May 2005 |  |
| Strategy 1.6 Expand use of housing resources available through the Veterans Administration – Per Diem | Action 1.6.1 Obtain current program requirements | Bert Boyd | DVS | # of units 50 units, 150 beds | January 2004 | December 2004 |
|  | Action 1.6.2 Develop information sheet/ packet for state non-profits |  |  |  | March 2004 |  |
|  | Action 1.6.3 Distribute sheets through Virginia Interagency Action Council on the Homeless (VIACH), team members’ web site and other venues |  | DHCD/VIACH/ VCH |  | March 2004 |  |
|  | Action 1.6.4 Provide technical assistance to groups at Virginia Coalition for the Homeless (VCH) and the Governor’s Housing Conference |  | DHCD/VIACH/ VCH/Homeward |  | July 2004 & November 2004 |  |
|  | Action 1.6.5 Track & report |  | DVS |  | Annually |  |

| Objective 2: Increase housing opportunities available to chronic homeless by developing new funding streams |
| --- |
| Strategy 1.7 Determine feasibility of VHDA set-aside in mixed use/ mixed income projects | Action 1.7.1 Develop information packet | Chris Hilbert | VHDA | # of units-20 | December 2003 | January 2004 |
|  | Action 1.7.2 Inquire about VHDA set aside for very low income (<30%AMI) |  |  |  | December 2003 |  |
|  | Action 1.7.3 Notify team of decision |  |  |  | January 2004 |  |
| Strategy 1.8 Initiate a Rental Assistance program for homeless individuals and families | Action 1.8.1 Obtain VCH proposal | Sue Capers | VCH | # of units-80 | December 2003 | March 2004 |
|  | Action 1.8.2 Develop Information packet |  |  |  | January 2004 |  |
|  | Action 1.8.3 Get General Assembly (GA) patrons |  |  |  | December 2003 |  |
|  | Action 1.8.4 Present to GA |  | Legislative Patrons |  | January 2004 |  |
|  | Action 1.8.5 Educate public and stakeholders on benefits in order to obtain public support |  | VCH |  | February 2004 |  |
| Strategy 1.9 Facilitate a feasibility study of a health-based Housing First model in Richmond through VCU/MCV | Action 1.9.1 Invite Virginia Hospital and Healthcare Association, VA Healthcare Foundation and VCU Health Systems to join PA team | Nikki Nicholau | Team Leader | # of units-TBD | February 2004 | July 2006 |
|  | Action 1.9.2 Use technical assistance from Policy Academy to bring Mark Trotz from Housing First to meet with partners |  | DHCD – Nikki Nicholau VHHA - Tyler DMAS – Diana Thorpe VDH-Foroobar VCU DHCD/VHHA Virginia Health Care Foundation DHCD/VCU/DH |  | April 2004 |  |
|  | Action 1.9.3 Develop proposal |  |  |  | July 2004 |  |
|  | Action 1.9.4 Identify funding available from all partners |  |  |  | July 2004 |  |
|  | Action 1.9.5 Initiate pilot project |  |  |  | January 2005 |  |
|  | Action 1.9.6 Evaluate cost/ benefit analysis of project |  | Program Evaluator |  | July 2006 |  |

| Strategy 1.10 Increase available funding for affordable housing through a State level Housing Trust Fund | Action 1.10.1 Identify dedicated source of funding | Sue Capers | VCH | Increase in available funds for affordable housing | Bill introduced in 2005 session and passed no later than 2006 session | January 2006 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Action 1.10.2 Write proposal |  | VCH |  |  |  |
|  | Action 1.10.3 Obtain GA patrons |  | VHC |  |  |  |
|  | Action 1.10.4 Introduce at GA | Sue Capers | Legislative Patrons |  | January-March of legislative sessions in 2005 & 2006 if necessary | April 2006 |
|  | Action 1.10.5 Educate public and stakeholders on benefits in order to obtain public support |  | VCH |  |  |  |
|  | Action 1.10.6 If passed, develop program guidelines | TBD | VHDA/DCHD |  | Legislation passed | July 2006 |
| Strategy 1.11 Facilitate successful acquisition of available grant funds for housing through technical assistance and information of grant opportunities | Action 1.11.1 Identify grant sources | Denise Goode | All Policy Academy members | Awarding of a minimum of 2 grants a year over 3 years that increase available funding and units by at least 50. | Grant awards | July 2007 |
|  | Action 1.11.2 Identify appropriate partners |  |  |  |  |  |
|  | Action 1.11.3 Develop project proposal |  |  |  |  |  |
|  | Action 1.11.4 Develop MOU |  |  |  |  |  |
|  | Action 1.11.5 Write grant proposal |  |  |  |  |  |
|  | Action 1.11.6 Administer grant |  |  |  |  |  |
| Strategy 1.12 Increase state funding for support of emergency shelters and transitional housing for homeless individuals and families | Action 1.12.1 Develop Budget Amendment proposal | Sue Capers | VCH Legislative Patrons | # of units-50 | Bill introduced in 2004 session and passed no later than 2005 session January-March of legislative sessions in 2004 & 2005 if necessary Legislation passed | January 2005 |
|  | Action 1.12.2 Develop Information packet |  |  |  |  |  |
|  | Action 1.12.3 Get General Assembly Patrons |  |  |  |  |  |
|  | Action 1.12.4 Present to GA |  |  |  |  |  |
|  | Action 1.12.5 Educate public and stakeholders on benefits in order to obtain public support |  |  |  |  | April 2005 |
|  | Action 1.12.6 Implement new program as part of annual application process |  | DHCD |  |  | July 2005 |
| PRIORITY TWO: Accessible Supportive Services |
| Objective: Reduce barriers associated with the delivery of supportive services to homeless persons |
| Strategy | Action(s) | Manager¹ | Implementer² | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 2.1 Explore use of State SSI supplement (Auxiliary Grant) in settings other than assisted living facilities (ALFs) for the chronically homeless. | Action 2.1.1 Explore this with the DSS Commissioner and try to expand only to homeless individuals. | Jane Clements Diana Thorpe | DMAS | Increase in support available for chronic homeless in supportive housing units | Decision from the DSS Commissioner | October 2004 |
|  | Action 2.1.2 If feasible, add strategy to implement decision |  | DSS/DMAS |  | Strategy added |  |
| Strategy 2.2 Conduct four workshops throughout the state on Disability Determination and Presumptive Decision Making | Action 2.2.1 Design workshop | Denise Goode | DRS | Reduction in time associated with accessing benefits as number of presumptive decision increase by a minimum of 5 percentage points. | Workshop design complete | February 2004 |
|  | Action 2.2.2 Establish locations and publicize |  |  |  | Schedule published | March 2004 |
|  | Action 2.2.3 Conduct workshops |  |  |  | Workshops held | July 2004 |
|  | Action 2.2.4 Measure results |  |  |  | Report on number of presumptive decision for FY2004 | August 2005 |

| Strategy 2.3 At all points of entry into the system, educate workers about use of the homeless checklist and resource guide (“no wrong door). | Action 2.3.1 Develop checklist and resource guide using existing models | Jane Clements | Policy Academy member agencies | All first-line workers trained | Checklist complete | July 2004 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Action 2.3.2 Identify opportunities for coordination of intake eligibility determinations and assessment and data collection to facilitate access to mainstream services (TANF, Medicaid, Primary Health Services, Mental Health and Substance Abuse Services) | Jane Clements | Policy Academy member agencies |  | Meeting held | January 2005 |
|  | Action 2.3.3 Identify all points of entry into the system | Jane Clements | Policy Academy member agencies |  | Listing of entry points exists | January 2005 |
|  | Action 2.3.4 Hold a meeting with all state-agency training staff to explore ways to disseminate information | Jane Clements | Policy Academy member agencies |  | Meetings held | January 2005 |
|  | Action 2.3.5 Have state trainers develop a training plan to complete the training | Jane Clements | Policy Academy member agencies |  | Training developed | March 2005 |
|  | Action 2.3.6 Execute plan | Jane Clements | Policy Academy member agencies |  | Completion of training | July 2005 |
|  | Action 2.3.7 Convert the screen checklist to electronic format | TBD |  |  | Electronic web-based list exists | January 2005 |
|  | Action 2.3.8 Update list annually as needed | Jane Clements | Policy Academy member agencies |  |  | Ongoing |
| Strategy 2.4 Simplify application for Food Stamps, TANF, and Medicaid | Action 2.4.1 Appoint a state-level interagency group to determine which rules are federally mandated | Jane Clements Diana Thorpe | DSS (Duke Storen) | A shorter, easier to complete, application | Group roster | July 2005 |
|  | Action 2.4.2 Determine which rules can be changed |  | Higher level group from 2.4.1 |  | List of rules |  |
|  | Action 2.4.3 Determine which rules should be changed |  | Higher level group from 2.4.2 |  | List of rules |  |
|  | Action 2.4.4 Change regulations and policy |  |  |  | Revised policy and regulations |  |
|  | Action 2.4.5 Train Workers |  |  |  | All designated staff trained |  |
| Strategy 2.5 Encourage all local departments of social services to designate an eligibility worker (and backup) to take applications from homeless individuals. | Action 2.5.1 Get buy-in from VDSS Commissioner | Jane Clements | Duke Storen | Designated workers in local DSS | 50% of agencies have designated worker by October 04; 75% by October 05 | October 2005 |
|  | Action 2.5.2 Commissioner communicate with local DSS directors the importance of ending homelessness and how DSS needs to be more involved in ending homelessness |  | DSS |  |  |  |
|  | Action 2.5.3 At quarterly local directors’ meetings, VDSS emphasize need to designate an eligibility worker and backup |  | DSS |  |  | Quarterly, beginning October 2004 |
|  | Action 2.5.4 At quarterly meetings of eligibility staff emphasize the need for designated staff and provide training about homeless issues. |  | DSS |  | Meetings held | Quarterly, beginning October 2004 |
| Strategy 2.6 Coordinate with statewide 211 to insure complete resource listing of services for the chronic homeless. | Action 2.6.1 Make presentation to the 211 Policy Board | Jane Clements | Marcella Williams |  | Presentation made & resource guide distributed | July 2005 |
|  | Action 2.6.2 Provide resource guide from Strategy 2.4 |  |  |  |  |  |
| PRIORITY THREE: Prevention initiatives that reduce homelessness |
| Objective: Insure that all individuals at risk for homelessness have a housing plan upon release from a state supported program that had included housing as a component. |
| Strategy | Action(s) | Manager | Implementer | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 3.1 Implementation of a statewide discharge policy for all at-risk individuals (foster care, adult and juvenile ex-offenders, persons released from medical and mental institutions.) | Action 3.1.1 Identify existing policies | a. Jane Clements b.Scott Richeson c.Tyler Cox d.Jim Reinhard e. Angela Valentine | DSS/DOC/VHHA/DMHMRSAS/ DJJS | Reduce the number of discharged persons entering homelessness from foster care, corrections, and medical institutions. Outcomes will vary by agency. Seek Governor’s directive to Cabinet Secretaries and agency heads on the need to ensure agency policies support ending chronic homelessness and increase the cooperation among state agencies. | Policies identified by each agency/ Organization | March 2004 |
|  | Action 3.1.2 Modify to meet the housing and employment needs of those released. |  |  |  | As needed, internal individuals/ committees for each agency will determine modifications needed. | May 2004 |
|  | Action 3.1.3 Gain buy-in for adopting policies at state and local levels |  |  |  | Policies developed and implemented by each agency | August 2004 (assuming no APA action required) |
|  | Action 3.1.4 Develop list of housing resource options available after discharge |  |  |  | Directory updated and published for each population. | April 2004 |
| Strategy 3.2 Support Job Corps as an appropriate discharge option for juvenile offenders and juvenile aging out of foster care. | Action 3.2.1 Determine how many juveniles currently exit to Job Corps from targeted systems. | a. Jane Clements b. Angela Valentine | DSS/DJJS | Provide greater job skills to young adults aging out of foster care to reduce the likelihood of them becoming homeless due to a lack of resources. | DSS and DJJ records tracked to determine if information exists. If not, survey relevant sources. | July 2004 |
|  | Action 3.2.2 Provide specific enrollment information to individuals involved in discharge planning for juvenile |  |  |  | Materials provided to agencies and individuals who could benefit. | March 2004 |
|  | Action 3.2.3 Do follow-up survey one year after implementation to determine number of juveniles enrolling who exited one of targeted systems. |  |  |  | Prepare a survey and send it to the Job Corps address or last known home address of participant | June 2005 |
| Strategy 3.3 Statewide summit on best practices for children aging out of foster care | Action 3.3.1 Convene a workgroup of state and local social services representatives to identify best practices and resources | Jane Clements | Ray Goodwin | DSS would place more emphasis on preparing young adults leaving foster care to become self-sufficient and better prepared to live independently and reduce the likelihood of them becoming homeless. | Individuals on the work group identified and the meeting convened. | March 2004 |
|  | Action 3.3.2 Determine if recommendations will need Administrative Process Act action |  | Richard Martin |  | Discuss recommend. with DSS APA staff. | June 2004 |
|  | Action 3.3.3 Take appropriate action to implement best practices |  | Ray Goodwin |  | Revise policy and procedures. Train local DSS staff. | October 2004 (if APA not needed) October 2005 (if APA needed) |
| Strategy 3.4 Determine feasibility of a respite program for family caregivers for a prevention strategy | Action 3.4.1 Look at respite care programs that exist for other populations and determine applicability | Jim Reinhard | TBD | Support and strengthen the family members who deal with individuals who are at-risk of becoming homeless. | TBD | TBD |
|  | Action 3.4.2 Develop a model program and potential funding sources |  | TBD |  | TBD | TBD |
| PRIORITY FOUR: Sufficient financial resources |
| Objective: Connect chronically homeless persons to available financial resources within 90 days of contact |
| Strategy | Action(s) | Manager¹ | Implementer² | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 4.1 Increase the number of prisoners and mental health consumers who have applications pre-filed for Medicaid benefits at release from institutions. | Action 4.1.1 Reinforce established procedures for pre-applications with local and state correctional centers statewide | Scott Richeson | DOC | Increase in number of institutions pre-filing claims for eligible prisoners | Meetings held and/or communication with impacted staff | July 1, 2004 |
|  | Action 4.1.2 Educate local CSB and Social Services departments of procedures and need to expedite processing | Jane Clements Jim Reinhard | DSS/ DMHMRSAS |  | Meetings held and/or communications with impacted staff |  |
|  | Action 4.1.3 Provide correctional facilities with point of contacts in CSB and DSS contacts for each jurisdiction in the state. | Scott Richeson | DOC/CSB Staff/DSS |  | List provided |  |
|  | Action 4.1.4 Do survey to determine number of institutions pre-filing for benefits. | Scott Richeson Jim Reinhard | DOC |  | Survey conducted |  |
|  | Action 4.1.5 Pursue changes in state-Medicaid policy that allows suspension of benefits for short-term incarcerations of one year or less | Scott Richeson | TBD |  |  | TBD |
| Strategy 4.2 Expedite veteran benefit claims for homeless veterans | Action 4.2.1 Provide necessary POA forms to organizations serving the chronic homeless to allow veterans services to act on behalf of the veteran | Bert Boyd | DVS |  | Forms distributed to homeless service providers statewide | March 2004 |
|  | Action 4.2.2 Insure all veterans services reps are briefed on need to expedite claims |  |  |  | Briefings held |  |
|  | Action 4.2.3 Provide quarterly updates on the number of cases received and expedited. |  |  |  | Receipt of report for April-June 2004 | July 2004 |
| Objective: Increase the availability of training opportunities and jobs to chronically homeless through WIA |
| Strategy 4.3 Have Governor declare homeless as a “hard to serve” population under WIA | Action 4.3.1 Prepare issue paper for Governor’s office and submit for approval | Willie Blanton | VEC | Increased number of homeless individuals served through WIA each year indicated in annual reports | Approval of Governor’s office | July 2004 |
|  | Action 4.3.2 Gain sign-off and communicate to local Workforce Investment Boards (WIB) |  |  |  | Communication to local WIB |  |
| Strategy 4.4 Seek release from performance measures from USDOL when serving the chronic homeless | Action 4.4.1 Prepare and submit necessary documentation for DOL | Willie Blanton | VEC | Increased number of homeless individuals served through WIA each year | Memo sent to DOL | July 2004 |
|  | Action 4.4.2 If granted, notify local WIBs |  |  |  | Communication to local WIB |  |

| Strategy 4.5 Access state 5% set-aside of Workforce Investment Act (WIA) funds for a pilot program targeted at employment for chronic homeless initiative | Action 4.5.1 Develop a position paper for Governor’s office | Willie Blanton | VEC | Increase in employment of chronically homeless in accordance with projected outcomes (TBD) | Paper developed | April 2004 |
| --- | --- | --- | --- | --- | --- | --- |
|  | Action 4.5.2 With Commissioner’s approval, submit to Governor’s office |  |  |  | Paper submitted |  |
|  | Action 4.5.3 Include in state Plan of Service |  |  |  | Plan of Service includes project for chronic homeless |  |
|  | Action 4.5.4 Implement Plan and monitor results |  |  |  |  | July 2004 |
|  | Action 4.5.5 Report outcomes |  |  |  | Report to Policy Academy Team | October 2005 |
| Objective: Increase employment opportunities for homeless and prisoner re-entry populations |
| Strategy 4.6 Market WOTC to increase employment opportunities for homeless and ex-offenders | Action 4.6.1 Educate local offices and one stop centers on how to use WOTC to assist with employment of DSS-eligible individuals who are homeless and with ex-offenders | Jim Ellenberger | WOTC Unit in VEC | Increase in number of homeless and ex-offenders employed with WOTC | Training provided to local offices | October 1, 2004 |
|  | Action 4.6.2 Work with DSS to determine how to best establish eligibility of chronically homeless |  | VEC/DSS |  |  | On-going |
|  | Action 4.6.3 Track number of WOTC provided to ex-offenders (and homeless, if possible) |  | WOTC Unit in VEC |  |  |  |
|  | Action 4.6.4 Provide annual report of number of credits issued for ex-offenders and homeless |  | WOTC Unit in VEC |  | Annual report submitted to Policy Academy | October 1, 2005 |
| Strategy 4.7 Increase focus on employment of chronic homeless by local one stop centers | Action 4.7.1 Establish a standard that VEC regional directors document at least one activity each quarter targeted at increased employment opportunities for chronically homeless | Jim Ellenberger | VEC Regional Directors | A minimum of 16 outreach activities targeted to increased employment of chronically homeless each year. | Standard incorporated in annual plan | July 2004 |
|  | Action 4.7.2 Have regional directors establish work plans and provide quarterly reports |  |  |  | Reports received in Central Office | On-going |
|  | Action 4.7.3 Share best practices and successful efforts with each other |  |  |  | Report to Policy Academy | September 2005 |
| Objective: Provide income opportunities through the Earned Income Tax Credit and other programs with focus on support to the chronic homeless |
| Strategy 4.8 Educate points-of-contact for the chronic homeless about the Earned Income Tax Credit | Action 4.8.1 Distribute information sheet and posters to all service providers | Nikki Nicholau | DHCD/VCH/DSS/CSB/VIACC | Increase income through annual tax return to receive earned income tax credit | Distribution of information | January 2005 |
|  | Action 4.8.2 Collate and distribute information about locations for free tax preparation services | TBD | DHCD/VCH/DSS/CSB/VIACC |  | Distribution of information | February 2005 |
|  | Action 4.8.3 Hold workshops at VCH annual meeting and the Governor’s Housing Conference | Nikki Nicholau Sue Capers | DHCD/VCH/IRS |  | Workshops held | December 2004 |
|  | Action 4.8.4 Send annual reminder to affiliated groups each January-March | Nikki Nicholau | DHCD/VIACH/ VCH |  | Annual reminders sent | On-going |

| PRIORITY FIVE: An understanding of chronic homelessness at all levels |
| --- |
| Objective: Insure clear, comprehensive data on the status of chronic homeless in Virginia |
| Strategy | Action(s) | Manager¹ | Implementer² | Expected Outcomes | Benchmarks | Completion Date (Estimated) |
| Strategy 5.1 Develop mechanism to capture and document the number of chronic homeless | Action 5.1.1 Develop and implement an independent standard zip code for use by service providers | Reggie Gordon | VA Housing Research Center (VHRC)/VIACH/ Policy Academy agencies | Ability to determine “as is” and track progress toward the desired state and support public relation efforts, and provide cost avoidance and other data for funding sources | Code established | August 1, 2004 |
|  | Action 5.1.2 Support implementation of HMIS systems statewide | Nikki Nicholau | DHCD |  | On-going |  |
|  | Action 5.1.3 Determine baseline data available from other agencies | Ted Koebel | VA Housing Research Center (VHRC)/VIACH/ Policy Academy agencies) |  | June 1, 2004 |  |
|  | Action 5.1.4 Consolidate data from CoC statewide with other data | Ted Koebel | VHRC |  | August 1, 2004 |  |
| Strategy 5.2 Document supportive housing availability, need, and costs | Action 5.2.1 Consolidate data from CoC statewide with other data | Ted Koebel | VHRC | Ability to determine “as is” and track progress toward the desired state and support public relation efforts, and provide cost avoidance and other data for funding sources | March 1, 2004 | July 1, 2004 |
|  | Action 5.2.2 Determine number of units needed |  | VHRC |  | April 1, 2004 |  |
|  | Action 5.2.3 Document costs of providing units and services |  | VHRC VHHA |  | May 1, 2004 |  |
|  | Action 5.2.4 Document cost of supportive services provided through existing systems |  | VHRC |  | May 2004 |  |
|  | Action 5.2.5 Conduct cost/benefit analysis of alternative service delivery |  |  |  | June 1, 2004 |  |
| Objective: Raise priority of ending chronic homelessness through education and awareness |
| Strategy 5.3 Create higher level of awareness in agency’s involved in Policy Academy | Action 5.3.1 Provide briefings to agency head and executive staff | Nikki Nicholau | Each team member | Insure that the activities of the Policy Academy are able to survive changes to team member and political leadership | By June 30, 2004 | On-going |
|  | Action 5.3.2 Use internal agency publications to highlight activities | Nikki Nicholau | Each team member |  | On-going with copies of articles in file |  |
|  | Action 5.3.3 Involve other agency staff in activities of implementation of the Action Plan |  |  |  |  |  |
|  | Action 5.3.4 Conduct briefings of impacted Cabinet Secretaries on activities | Denise Goode Nikki Nicholau Stuart Richeson |  | Insure the goals of Policy Academy are institutionalized | Quarterly |  |
|  | Action 5.3.5 Ask Secretaries’ offices to include accountability for Action Plan’s goals in agency’s performance contract, outcomes, and strategic plan | Denise Goode Nikki Nicholau Stuart Richeson |  |  | By June 1, 2004 |  |
| Strategy 5.4 Broaden participation of relevant stakeholders in the work of the Policy Academy | Action 5.4.1 Expand team to include representatives from all relevant agencies, impacted non-profit, legislators, and federal partners | Nikki Nicholau | Each team member | Appropriate representation will insure integration of efforts into service delivery and achievement of goals. | Invite new members to February 19 | On-going |
|  | Action 5.4.2 Coordinate efforts with Olmstead Task Force | Denise Goode |  |  | On-going |  |
|  | Action 5.4.3 Conduct series of regional meetings with community leaders and service agencies of Action Plan | Nikki Nicholau Denise Goode | Each team member |  | 4 regional meetings during first quarter 2004 | November 30, 2004 |
| Strategy 5.5 Increase public awareness and political support | Action 5.5.1 Develop a series of compelling stories related to chronic homelessness | Nikki Nicholau Chris Hilbert | DHCD/VHDA |  | 5 stories completed for use by partner agencies | July 1, 2004 |
|  | Action 5.5.2 Invite General Assembly members to events highlighting chronic homeless | Sue Capers | All PA Team Members |  |  | July 1, 2004 |
|  | Action 5.5.3 Issue a minimum of one press release per quarter related to the work of the Policy Academy or the chronic homeless | Nikki Nicholau | DHCD |  | July 1 & October 1, 2004, January 1 & April 2, 2005 | July 1, 2005 |
| Progress to Date | Barriers and/or Situational Changes | Immediate Next Steps (including potential technical assistance needs) |