# Construction Cost Estimate

# Examples

4R Examples

The preliminary 30% cost estimate (class “C”) for this project was $17,235,000. This estimate includes major pay items (excavation, surfacing quantities, etc…) and includes a 20% contingency for small work items, a 10% contingency for traffic control and a 5% contingency for erosion control (See appendix G). The cost estimates for the five alternatives that will be presented in the Environmental Document are as follows (contingency amounts are the same as those listed above): Alternative 1: No Action Cost Estimate: N/A Alternative 2: Reconstruction of the roadway along the existing alignment. Two minor realignment sections are proposed, including Bandit Curve and Hollowell Park. This alternative would utilize retaining walls along the edge of Glacier Creek to minimize resource impacts. This alternative would not address a multi-use path. Cost Estimate: $18,848,000 Alternative 3: Reconstruction of the roadway including three realignment sections. Realignments include Bandit Curve, Hollowell Park and relocation away from Glacier Creek. Under this alternative, half of the abandoned roadway near Glacier Creek would be rehabilitated and reclaimed using FLHP funds. The other half of the roadway would be converted into a multi-use trail. The remaining segments of the multi-use trail, from the YMCA to Bandit Curve, and from the Park and Ride facility to Sprague Lake, would be constructed by the NPS using a separate funding source. A small parking area would be constructed just north of the Park and Ride to allow for visitor parking to access the multi-use trail. Cost Estimate: $17,065,000 Alternative 4: Reconstruction of the roadway including three realignment sections. Under this alternative, all of the abandoned roadway near Glacier Creek would be reclaimed using FLHP funds. Bicycle lanes would be constructed along the shoulders of the roadway from Hollowell Park to just north of the Park and Ride using FLHP funds. The remaining segments of the multi-use trail, from the YMCA to Hollowell Park, and from the Park and Ride to Sprague Lake, would be constructed by the NPS using a separate funding source. Cost Estimate: $17,695,000 Alternative 5: Reconstruction of the roadway along the existing alignment. Two minor realignment sections are proposed, including Bandit Curve and Hollowell Park. Instead of utilizing retaining walls along the edge of Glacier Creek, this alternative would shift the roadway into a cut section with increased resource impacts. This alternative would not address a multi-use path. Cost Estimate: $18,810,000

The preliminary 30% cost estimate (class “C”) for this project is $970,000. This estimate includes major pay items (excavation, aggregate surfacing quantities, drainage, etc…) and includes a 30% contingency for small work items. The cost does not include a cost for widening and/or a wall at the Burr Canyon Side drainage due to the limited survey information. Also, the cost does not include any cost for revegetation and/or mitigation. Revegetation/mitigation measures will be discussed at the 30% Design Review if required. The current funding available for this project is $989,000.

The construction cost estimate for the Segment 3 50% design was $11,710,000 (April 2006). The current construction cost estimate for the Segment 3 70% design is $12,141,000. Significant Changes Major changes to the cost estimate resulted from a larger volumes of Roadway Excavation, Waste and higher Wall cost. Roadway Excavation changed from 148,000 CY to 155,000 CY and Waste changed from 29,500 CY to 46,400 CY based on the new alignment. The retaining wall’s increase in cost of $236k is due to the increase in Soil Nail Wall area and the addition of two new items, Rockery Wall and Shotcrete. The soil nail wall area increased by 1,350 SY based on the SMSE wall design and tiering one soil nail wall. The MSE wall area was reduced by 1,763 SY, however, the unit price for MSE walls is $150 /SY less then soil nail walls. Using the CFL – Engineer Estimate Inflation Spreadsheet, which applied inflation rates of 18% through 1/1/2008 and 12% beyond 1/1/2008, results in a construction cost estimate of $16,475,000 in March of 2009 and $18,195,000 in March of 2010.

3R Examples

The engineer’s estimate for the 95% PS&E submittal is $2,295,000.00 including a $25,000 incentive for meeting an interim completion date. The engineer’s estimate at the 70 % submittal was $2,020,000. Main increases in cost were due to revised quantities or estimated unit costs based on the anticipated complexity of the work for the following items: Surveying, clearing and grubbing, subexcavation, pavement milling and placement, additional roadway aggregate to supplement millings if needed, and additional equipment hours to cover unknown work items.

The current engineer’s estimate for this project is $664,659.30. The engineer’s estimate at 70% was $1,038,298.75. The cost difference in these estimates is due to the following items/issues: Cost sharing by Garfield County As part of this project Garfield County will assist with the construction cost. The 95% engineer’s estimate is based on Garfield County providing the following: Roadway aggregate: Contractor will have access to material stockpiled by the County approximately 12 miles from the project site at the Eggnog Pit. Riprap: Contractor will have access to material stockpiled by the County approximately 12 miles from the project site at the Eggnog Pit. Select Borrow: Contractor will have access to material stockpiled by the County approximately 12 miles from the project site at the Eggnog Pit. Cattleguard: County will supply one cattleguard to the contractor for replacement of the existing cattleguard. The Park will provide the other cattleguard. Concrete barrier: County will provide concrete barrier to be used as a cutoff wall at unvented low water ford locations. Signing: Signs will be installed by the contractor. Culverts and End sections: Culverts and end sections will be installed by the contractor. Waste: Contractor will stockpile waste on site which the County will haul off site and dispose of. With the supply of materials by the County, the cost estimate for this project has decreased significantly. Other Pay Item # Description 70% Quantity/Cost 95% Quantity/Cost 15216-2000 Survey and Staking, Grade Finishing Stake 0/$0 42.13 Sta./$8,847.30 Item added for construction of Roadway Aggregate. 15701-0000 Soil Erosion Control LS/$8,000 $30,100 (Cost for silt fence and sediment log) Item was broken out at 95% with a more accurate quantity takeoff. 20401-0000 Roadway Excavation 3,000 cy/$51,000 1,440 cy/$24,480 Profile was adjusted due to a change in the thickness of the roadway aggregate. 25101 Placed Riprap (All classes) 1,570 cy/$138,700 1,330/$47,880 Material will be supplied by the County. 30801 Roadway Aggregate 7,425 tons/$207,900 1,970 cy / $23,640 Thickness reduced from 12 inches to 8 inches. 50101-0900 Reinforced Rigid Pavement 1,350 sy/$101,250 1,610 sy/$201,250 Unit cost increased to reflect current costs. 60201 Pipe Culverts (All sizes) 780 lf/$91,850 710 lf/$44,000 Culverts to be supplied by the County. Unit cost decreased. 61801-0000 Concrete Barrier 800 lf/$48,000 750 lf/$9,000 Barrier to be supplied by County. Unit cost decreased. The remaining difference in cost is due to modifications to the design from 70% to 95% and a more complete quantity takeoff.

The preliminary 70% cost estimate for this project is $2,575,000 in 2007 dollars. Adjusting for inflation (+12%), the estimate in the year 2008 is $2,770,000. This estimate includes major pay items (excavation, surfacing quantities, etc…). The current funding available for this project is $2,800,000.00.