PACI DATA QUEST Expedition

Quarterly report (October 1, 2002 – January 1,2002)

### Expedition Leads:

Ian Foster, ANL foster@mcs.anl.gov

Robert Brunner, NCSA rb@ncsa.uiuc.edu

### Coordinator

Veronika Nefedova, ANL nefedova@mcs.anl.gov

### Site/Subproject leads

Tom DeFanti, UIC

Miron Livny, U.Wisconsin-Madison

Ray Plante, NCSA

Natalia Maltsev, ANL

Nagiza Samatova, ORNL

### Partners

Bob Wilhelmson, MEAD

Dennis Gannon, Portals

Rob Gardner, U. Chicago

Paul Avery, U. Florida

Rick Cavanaugh, U. Florida

Mike Wilde, ANL

Jens Voeckler, U. Chicago

OVERVIEW

Radio astronomy (Ray Plante, NCSA)

The target community here is the users of the VLA/EVLA and BIMA/CARMA radio telescopes. The BIMA Image Pipeline, now being deployed at NCSA, automatically calibrates and images radio interferometer data as it arrives from the BIMA telescope in northern California. The initial version was implemented to access data from the BIMA Data Archive at NCSA and distribute the computing between a single serial platform and the NCSA SGI Origin system. As part of this expedition, we plan to generalize the pipeline to use general Grid services to manage data and access compute resources. By incorporating these generic services, we can use the Grid with other data resources and pipelines. In particular, we plan to establish an instance of the NRAO End-to-end system at NCSA for processing VLA data. The distribution of data and computing between NCSA and NRAO will make a good testbed for extension to the TeraGrid. We can make real practical use of the distributed resources and users when the BIMA Array combines with the Caltech OVRO Array to create the CARMA telescope in 2005.

Bioinformatics (Natalia Maltsev, ANL; Nagiza Samatova, ORNL)

The first and most crucial step in genome analysis is the accurate assignment of function to the genes. This requires the capability to perform high throughput genetic sequence analysis based on comparative analysis of multiple genomes, and is essential for the development of applications in functional genomics and systems biology. However, such factors as exponential growth of the information in the public sequence databases, and the development of sophisticated and computationally intensive tools and algorithms for analysis of genomes dictate an urgent need for the development of the new approaches for high-throughput computations to support the bioinformatics effort.

In support of this work we propose to apply existing virtual data techniques to the labor-intensive process of gathering genomic data from multiple sources, reformatting that data, and transforming it for insertion into the ANL sequence database, and newly developed virtual data techniques that extend virtual data tracking into the realm of relation data provenance, to enable the recording and tracking of significant portions of the processes of comparative analysis of genomes and metabolic reconstructions from sequence data.

Algorithms Development. We will develop the following tools and algorithms that would allow increasing precision and reliability of high-throughput analysis of the genomes:

- Tools and computational infrastructure for adapting advanced TeraGrid based technologies for the needs of high-throughput genome analysis

- Clustering algorithms for partitioning protein space into protein functional families

- Algorithms for automated assignment of functions to the

Developed algorithms will enhance analysis of the genomes in a framework of the public genome analysis server and will be available for the use by the wide scientific community.

Virtual astronomy (Robert Brunner, NCSA)

The aim of this work is to utilize Grid-based data management for various astrophysical data archives. This effort would first work to integrate several public astronomical datasets, including SDSS (EDR only), DPOSS, 2MASS, NVSSS, FIRST, and ROSAT within the NCSA domain.  Once the catalog datasets have been integrated into the Grid, we will develop and deploy several archive services, including complex spatial queries and data federation functionality. Different commercial and open source data-mining toolkits will be tested on the federated datasets. We will also integrate image datasets within the NCSA domain, requiring several tens of Terabyte of near- and on-line storage. Finally, we will work to extend this work to the currently planned QUEST2 survey, which, once operational, will generate a Terabyte of new data every few months. QUEST2 requires high-speed data transfer from SDSC (where the data arrives from the mountain) and complex, on-demand processing for rapid variable identification.

Mesoscale weather (Bob Wilhelmson, NCSA)

We will work with the MEAD expedition to apply PDQ technologies to MEAD problems. In a first stage, we will apply basic data movement and replica management technologies. In a second, we will apply the Chimera virtual data system. Details can be found in the MEAD expedition proposal.

Integration of Optical Networks with Data Grid Tools (Tom DeFanti, UC)

Milestones, Deliverables and Status

| PACI Data Quest | Tue 10/1/02 | Tue 9/30/03 | Status | Expedition Leader: Ian Foster (Argonne), Expedition Co-Leader: Brunner (NCSA) |
| --- | --- | --- | --- | --- |
| Refine plan and hold initial all hands meeting; identify specific liaisons and responsible parties. | Tue 10/1/02 | Tue 10/1-2/0 | The first organizational meeting was held on 10/1-10/2, 2002.The second meeting was on 12/10/02. The third meeting is planned for 3/19/03 |  |
| Train developers on use of data grid technologies in the target application projects and educate administrators of Alliance resources | Tue 10/1/02 | Tue 12/31/02 | Ongoing consultations with all the involved parties (Globus,GridFTP, Condor). Chimera and VDT tutorial was held on 12/10/02. |  |
| Radio Astronomy Imaging | Tue 10/1/02 | Tue 9/30/03 |  | Plante (NCSA) |
| Incorporate GridFTP into BIMA pipeline transfer data between the archive and compute platforms; use GridFTP to deliver VLA data from NRAO to NCSA. | Tue 10/1/02. | Tue 12/31/02 | Initial GridFTP testing is underway. GridFTP servers installation at NCSA and extensive work on Unitree and GridFTP incorporation. Extensive research of Data mirroring tools. |  |
| Develop long-term Data Management plan for BIMA and VLA archives and pipelines based on Grid data management tools; identify any missing capabilities. | Mon 1/1/03 | Mon 3/30/03 | Both long-term and short-term plans have been developed. The candidate technologies are gsi-enabled rsync (for short-term, work is underway) and Reliable Replication Service (currently under development in Globus group) – for the long-term solution. |  |
| Install BIMA pipeline on NCSA platforms. | Wed 4/1/03 | Mon 6/30/03 |  |  |
| Deploy data management plan, extending use of Grid data management tools to make more efficient use of disk caching. | Tue 7/1/03 | Tue 9/30/03 |  |  |
| Establish initial mirror of VLA archive | Tue 9/30/03 | Tue 9/30/03 |  |  |
| Bioinformatics: High Throughput Genome Analysis | Tue 10/1/02 | Mon 9/29/03 |  | Maltsev (Argonne), Samatova (ORNL) |
| Develop detailed designs and identify any missing Data Grid technology elements | Tue 10/1/02 | Tue 12/31/02 | Extensive consultations and meetings on Data Grid technologies (GridFTP, Condor, Chimera). BLAST is working with CondorG. The extensive work on adapting of Bioinformatics tools to the Grid environment is now underway (work with Chimera and Virtual Data Toolkit) |  |
| Algorithms Development | Tue 10/1/02 | Mon 9/29/03 |  |  |
| Complete initial integration of generic grid data management tools into applications | Tue 4/1/03 | Mon 6/30/03 |  |  |
| Use standard bioinformatics tools to deploy a virtual data infrastructure on NCSA and Alliance resources | Tue 4/1/03 | Mon 6/30/03 |  |  |
| Execute simple genome sequence transfer, transformation, and import into WIT2/EMP database | Tue 7/1/03 | Mon 9/29/03 |  |  |
| GriPhyN | Tue 10/1/02 | Tue 9/30/03 |  | Foster, Wilde (ANL) |
| Develop detailed designs and identify any missing Data Grid technology elements | Tue 10/1/02 | Tue 12/31/02 | VDT and Chimera design overview. Chimera team is working extensively on helping the application groups with integration of their tools and VDT. |  |
| Execute SDSS data analysis application on PACI resources | Wed 1/1/03 | Tue 4/1/03 |  |  |
| Conduct large-scale cluster search on Alliance resources | Mon 6/30/03 | Mon 6/30/03 |  |  |
| Conduct CMS simulation and data analysis run on Alliance resources | Tue 7/1/03 | Tue 9/30/03 |  |  |
| Deploy Data Grid technology on TeraGrid resources | Tue 9/30/03 | Tue 9/30/03 |  |  |
| Virtual Astronomy | Tue 10/1/02 | Tue 9/30/03 |  | Brunner (NCSA) |
| CIT-> ANL transfer first steps, first dposs analysis, Quest document. GridFTP testing and installation at NCSA and the archive sites | Tue 10/1/02 | Tue 12/31/02 | Data transfer using Condor and SRB from the data archive. |  |
| CIT-> ANL reliable, repeated dposs analysis | Wed 1/1/03 | Tue 4/1/03 |  |  |
| I Prototype Quest2 pipeline | Tue 7/1/03 | Tue 9/30/03 |  |  |
| Automated Q2 pipe | Tue 9/30/03 | Tue 9/30/03 |  |  |
| Integration of Optical Networks with Data Grid Tools | Tue 10/1/02 | Tue 9/30/03 |  | DeFanti (UIC) |
| Conduct high-performance data movement experiments over optical networks. Position data storage at StarLight. | Tue 10/1/02 | Tue 12/31/02 | At this point we are learning, measuring and waiting for Condor group to specify disk cache requirements at Starlight. Starlight clusters are ready and enabled on the network. A new paper documents the high data performance movement tests performed this fall |  |
| Conduct engineering and testing work on Chimera, Terascope, and Nest technologies | Tue 10/1/02 | Mon 11/16/02 | We are doing extensive work on Terascope (to be shown at SC02), and have recently written a paper.. Ready to supply login accounts at StarLight anytime now for Chimera and Nest testing. |  |
| Deploy first production data Grid applications | Mon 6/30/03 | Mon 6/30/03 |  |  |
| Continue engineering and testing work on Chimera, Terascope, and Nest technologies | Tue 4/1/03 | Tue 9/30/03 |  |  |
| Extensively evaluate Data Grid tools for target applications. | Tue 4/1/03 | Tue 9/30/03 |  |  |
| Integrate the virtual data browser produced by the Portals expedition | Tue 7/1/03 | Tue 9/30/03 |  |  |
| Deploy Data Grid technology on TeraGrid resources | Tue 9/30/03 | Tue 9/30/03 |  |  |
| Network Storage Appliance, DAGMan Job Flow | Tue 10/1/02 | Tue 9/30/03 |  | Livny (Wisconsin) |
| Manage project and provide PACS leadership | Tue 10/1/02 | Tue 9/30/03 |  |  |
| Provide support for the Bioinformatics applications | Tue 10/1/02 | Tue 9/30/03 | BLAST is Grid-enabled! Successful multiple BLAST runs using Condor at UW. |  |
| Provide support for the mesoscale weather and radio astronomy applications | Tue 10/1/02 | Tue 9/30/03 |  |  |
| Integrate Network Storage (NeST) and DAGMan | Tue 10/1/02 | Mon 6/30/03 |  |  |
| Conduct CMS simulation and data analysis run on Alliance resources | Tue 9/30/03 | Tue 9/30/03 |  |  |
| Deploy NeST data caching nodes | Tue 7/1/03 | Tue 9/30/03 |  |  |
| MEAD | Tue 10/1/02 | Tue 9/30/03 |  | Wilhelmson (NCSA) |
| Test reliability of data movement from x to y (from out there to NCSA), Use ESG's technologies. netcdf, dods++ and design | Tue 10/1/02 | Tue 31/12/02 | Extensive GridFTP testing, GridFTP and Unitree incorporation. Java CoG as a base for GridFTP implementation. The GridFTP requirements meeting was held on 1/10/03. |  |
| Joint MDC design with ESG, Chimera design meeting and experiments, explore multiscale runs, establish MDC | 1/1/03 | 4/1/03 | ESG documents are extensively studied. Initial Chimera Design meeting was held on 12/10/02. Joint (with ESG) meeting on Metadata issues on 1/22/03. |  |
| Extend MDC to useful user scenarios, use of ESG's DODS++ server (OpenDAPg) | 4/1/03 | 7/1/03 |  |  |
| Pipeline for publishing and running at multiple sites | 71/1/03 | 9/30/03 |  |  |

Accomplishments

- The group has produced a number of internal documents that specify the basic requirements for data movement and replication.

- The development of new requested Data Grid capabilities has started at ANL.

- The group holds regular meetings to discuss the progress as a whole as well as in the specific technical areas.

- Starlight clusters are ready and enabled on the network.

Bioinformatics (ANL, ORNL)

- Further development of GADU (Genome Analysis and Database Update pipeline) (A.Rodrigez, D. Sulakhe)

  - Using GADU we have analyzed the sequence data from 106 publicly available genomes

  - Have developed the following enhancements to GADU:

    - Interface to allow usage of GADU by the users outside of ANL

    - Interface and tools to allow users to customize GADU usage (choice of the databases, tools, etc)

  - Provided access to chalant with Virtual Data Toolkit

  - Performed test run of Blast on Datagrid cluster.

  - Installed Chimera and ran examples on ANL systems

  - Developing approaches for running Blast under Chimera  (still on-going) on ANL Data Grid Cluster.

  - We are in a process of installing Blast on DOE Science Grid (PNNL) machines

  - One of the main Bioinformatic’s tools (BLAST) has been ‘Grid-enabled’: it runs successfully on CondorG pool at UW.

- Tools development

  - PhyloBlocks (Luke Ulrich). We have developed a analytical pipeline for analysis of evolution of protein families and prediction of functions to the genes. The following publicly available tools have been integrated into the PhyloBlocks framework in order to increase sensitivity of the sequence analysis: Blast, ANL Knowledge Base, Blocks, LAMA, ClustalW, HMMER, TreeView. We have developed a flexible user interface that allows interactive analysis of the protein families by an expert and a number of tools for visualization to assist such analyses.

  - SVMMER (Praveen Chandramohan, G.X. Yu) -- in collaboration with ORNL (Nagiza Samatova) we have developed a Support Vector Machines algorithm-based tool for classification of the protein sequences. SVMMER’s performance was optimized with the flexible training set selection interface and tools for the development of the models libraries.

  - Demonstrated the SVMMER at Supercomputing 2003, at Baltimore, November 16-23, 2003. Posters, tile display and laptop based demos have been presented at both ANL and ORNL booth areas

Radio Astronomy

  - We did an analysis of our data mirroring requirements and did a comparative assessment of the features of the Globus Reliable File Transfer package and the open-source rsync.  We analyzed the bandwidth with iperf, and did some comparative tests transferring data from the VLA to NCSA using GridFTP and rsync.  We found that since we were saturating the VLA's 5Mb/s pipe to Abilene, we concluded that there would not be much sense in investing much effort into grid-izing rsync.  We identified a simple way to GSI-enable rsync.

  - We have set up the VLA mirror hardware and are ready to begin transferring data.  Analysis of the network suggests it is more efficient to ship a box of disks with the current contents of the archive (~1 TB).  Subsequent data can be transferred via the network.

  - Integration of GridFTP into the BIMA pipeline has been postponed slightly as we finish the hardware upgrade and installation of pipeline on NCSA platforms.

  - Long term Data Management plan for BIMA and VLA archives is under way.

Virtual Astronomy

  - CondorG transfer jobs using Quest2

  - Working on data mining with D2K.

  - Working wit Java Cog so we can publish web services on the Grid.

  - Looking at how to replicate SDSS data, hardware on order.

MEAD

  - MEAD collaboration with PDQ falls into several areas:  GridFTP invocation and testing, management of model simulation data, and exploration of Chimera for use in data analysis.  During the last period the invocation and movement of data using GridFTP has been explored by Alameda, Hampton, and Rossi.  Primarily, the jftp client (version 0.9.14 plus patches) was tested against a set of gridftp (globus version 2.0)  servers, to control normal ftp (client-server) transfers and third party transfers.  A sufficiently large number of server and client issues were identified that we held special PDQ meeting in January 10, 2003 on GridFTP.  In this meeting, we learned that a key problem in the protocol implementation was uncovered in version of the globus toolkit prior to 2.2.3, and that in order to properly transfer files via gridftp we need to bring everything (gridftp server, gridftp server for unitree, c and java client libraries) to implement the protocol as implemented in 2.2.3.  We also discussed preferred functionality and preferred mechanisms for interacting with gridftp servers, as well as possible enhancements for gridftp implementations.  Finally we considered issues associated with measuring performance at the gridftp server, and possibly collecting this information as a whole for the PDQ Expedition.  Alameda will take up the issue of turning on the instrumentation and possibly gathering the data with Alliance grid administrators.

  - The GridFTP analysis and enhancements are a foundation piece to the next substantive collaboration between MEAD and PDQ, namely, reliable file transfer services.  As we iron out the issues with GridFTP we will transition to consideration of both reliable file transfer services and replica managment services, which in their fullest implementation present OGSA grid services for composition in complex workflows and for use by grid service client software in the creation of complex workflows.

  - Data management and access are key concerns in MEAD as they are in the Earth System Grid Project (http://www.earthsystemgrid) funded by DOE.  Middleton, an unfunded MEAD partner, is one of the leads in this effort along with Foster.  Wilhelmson is monitoring internal ESG communications and recently participated in a day long AG meeting (also attended by the NCSA portal group) with ESG (including representation from the e-Science effort) on the issue of metadata.  The metadata and data management working group in MEAD, along with PDQ, will pursue further collaboration with ESG.  This will include incorporation of the gird based Metadata Catalogue Service (MCS) into the MEAD framework along with links to the THREDDS Discovery System being utilized in the Digital Library for Earth System Education (DLESE).  An alpha version of the MCS should be available in the June time frame with a beta version in the fall.  The MCS prototype will have capability for storing attributes and querying holdings, it will be extensible and consistent, it will support authentication and authorization, logical collections, and logical views, handle creation information, annotations, audit records, transformation history, master copy support, and support for containers, and provide good performance and scalability.

Publications:

- TeraScope: Distributed Visual Data Mining of Terascale Data Sets over High Speed Photonic Networks by Chong (Charles) Zhang, Jason Leigh, Thomas A. DeFanti. Marco Mazzucco, and Robert Grossman

- QUANTA: A Toolkit for High Performance Data Delivery over Photonic Networks, by Eric He, Javid Alimohideen, Naveen K. Krishnaprasad, Jason Leigh, Oliver Yu, and Thomas A. DeFanti

- Hierarchical feature extraction based approach to functional differentiation of highly homologous protein functional groups, co-authored by Nagiza F. Samatova, Gong-Xin Yu, Praveen Chandramohan, Hoony Park, George Ostrouchov, Al Geist, and Natalia Maltsev to be submitted to the Bioinformatics journal.