INTERDEPARTMENTAL COMMITTEE FOR METEOROLOGICAL SERVICES AND SUPPORTING RESEARCH (ICMSSR)

COMMITTEE FOR ENVIRONMENTAL SERVICES, OPERATIONS AND RESEARCH NEEDS (CESORN)

JOINT ACTION GROUP FOR THE NATIONAL WILDLAND FIRE WEATHER NEEDS ASSESSMENT (JAG/NWFWNA)

Final Record of Actions

Meeting 2007-03

May 4, 2007, Silver Spring, MD

MEMBERS PRESENT

Mr. Eli Jacks, NOAA/NWS, Cochair

Dr. Allen Riebau, USDA/FS, Cochair

Lt Col David Andrus, OFCM, Executive Secretary

DOI/BLM:		Mr. Paul Schlobohm, Fire Environment Working Team

Mr. Rick Ochoa

NOAA/NWS:		Mr. Heath Hockenberry

GUEST ATTENDEES

CA Dept of Forestry	Mr. Wayne Mitchell

DOI/BLM:		Ms. Robyn Heffernan, NIFC

Mr. Rich McCrea, BIA, NIFC

Mr. Herb Arnold, NIFC

NIST:			Dr. William “Ruddy” Mell

Dr. Alex Maranghides

NOAA	:		Dr. Phillip Bothwell, SPC

Mr. Mark Ruminski, NESDIS

USDA/FS:		Ms. Linnea Keating

OFCM:			Mr. Ken Barnett

Mr. Tony Ramirez, STC

Dr. Robert Katt

Draft Issued:	8 May 2007

Final Issued:	23 May 2007

- Summary of active action items.

  - Action Item 06-4.8  OFCM has requested that a Predictive Services expert brief the JAG on available fire weather products and services along with their awareness of product and service shortfalls and customer concerns.  This is needed for the 7-8 Dec 2006 JAG meeting.  Lead agent is Rick Ochoa.

    - 18 April 2007 Update.  Robyn Heffernan provided preliminary results.  The formal results are expected to be released by the end of May.

    - Open

- JAG approved draft record of actions from previous meeting.

- Lt Col Andrus reviewed needs assessment process.

  - Evaluations of earlier analysis efforts continue.  The resultant analysis will likely identify:

    - Needs in each functional area

    - Cross-cutting issues with respect to the functional areas

    - Needs as being common throughout the community or unique to individual portions of the community

    - Common issues which cross-cut the community (examples are: Management, Coordination, Processes, Resources, Science, Technology, and Data)

    - Urgency of action for each need

    - Short-term or long-term nature of the solution for each need

  - The JAG is considering the following over-arching recommendations:

    - Agencies or existing interagency groups take actions on short-term needs that may immediately be addressed.

    - Agencies or existing interagency groups work together to assess current capabilities, any gaps in capability to meet the needs as presented in the assessment document, and agree upon program initiatives to fill the capability gaps. The product of this effort will be a detailed, rolling implementation plan with agreed-upon partner roles in meeting objectives.

- Lt Col Andrus reviewed the latest timeline.

  - Currently

    - JAG subgroup analysis work continues, 80% complete

    - OFCM analysis synthesis underway

      - Developing themes/needs document

      - Incorporating new analysis work as it is completed

  - 4/30 – Needs/issues to JAG for input regarding content

  - 5/4 – JAG meeting to solidify needs assessment

  - 5/8 – Brief Federal Coordinator on needs assessment

  - 5/11 – Develop white paper on needs assessment (Katt)

  - 5/11 – White paper to JAG for comment (5/16 suspense)

  - 5/21 – Brief JAG on final white paper

  - 5/31 – Brief ICMSSR on final white paper6/11 – WGA briefing

  - Jun – More detailed needs assessment completed

  - Jul/Aug – Final report is developed

  - Sep – Final report is published

- Lt Col Andrus reviewed the current version of the needs document and the needs matrix spreadsheet.  Recommended changes were incorporated as part of the meeting.  The JAG was supportive of all changes and the updated document was sent out to the JAG following the meeting.  This needs information is not being included in this ROA because it is not releasable outside of the JAG at this time.  Requests for this information outside of the JAG need to be directed to Lt Col Andrus.

- The next JAG meeting is planned for 21 May 2007 to discuss major themes, gaps, and recommendations.