NATIONAL AERONAUTICS AND SPACE ADMINISTRATION

Mars Exploration Program

Technology Plan

Draft v.1  - March 2002

MPO Release Date:

Issue Date:

JPL Doc. No.:

__________________			_____	______________________

Jet Propulsion Laboratory			MPO Document Release Approval

California Institute of Technology

Mars Technology Program Plan

Prepared by:

_________________________				________________

Dr. Samad A. Hayati							Date

Manager, Mars Technology Program, JPL

Concurrence:

________________________                                  		 __________________

Mr. Dave Lavery 							Date

Program Executive, Mars Exploration Program

Approved by:

_______________________					________________

Dr. Firouz M. Naderi							Date

Manager, Mars Program Office, JPL

Concurrence:

_________________________				________________

Mr. Orlando Figueroa							Date

Director, Mars Exploration Program

Space Science Enterprise, NASA Headquarters

Mars Technology Program Plan

Table of Contents

1	Introduction	4

2	General Goals of Program	4

3	Program Requirements	6

4	Customer Definition and Advocacy	6

5	Organization and Management Approach	7

5.1	Organization	7

5.2	Roles and Responsibilities	8

5.3	Collaborations	9

5.4	Agreements	9

5.5	Reviews	9

5.6	Schedule	10

5.6.1	Resource Management	10

5.6.2	Budget Profile	10

5.7	Controls	10

5.7.1	Program Documentation	10

5.7.2	Process Validation	11

5.7.3	Change Control	11

5.8	Risk Management	11

5.8.1	Areas of Emphasis	11

5.8.2	Approach	12

6	Technology Planning Process	13

6.1	Annual Replanning Process	13

6.2	Task Definition and Assignment	13

6.3	Leveraged Programs	15

6.4	Products and Infusion Strategy	15

7	Public Outreach and Commercialization	16

7.1	Public Outreach	16

7.2	Commercialization	16

8	Change Log	19

Document Change Log	19

Appendices	20

Mars Exploration Program

Technology Plan

# Introduction

The Mars Exploration Program (MEP) is a science-driven, technology-enabled effort to characterize and understand Mars, including its current environment, climate, geological history, and biological potential.  A critical component of MEP is the Mars Technology Program (MTP).

The MTP is a NASA program, managed by JPL, with significant participation by NASA Centers and other organizations.  It has the prime responsibility to develop enabling and strongly enhancing technologies for Mars exploration missions with launch dates through 2009.  Of particular importance are enabling technologies for the 2009 Mars Smart Lander (MSL) Mission. In order to be ready in time, technologies need to be demonstrated to have reached NASA Technology Readiness Level (TRL) 6 by preliminary design review (PDR) for each mission, which typically occurs about 40 months prior to launch (See Appendix B for NASA TRL definitions.)  Some technologies require verification in a relevant environment in space, which implies that they will be carried to TRL 7 by critical design review (CDR).  The MTP also has the responsibility to develop technologies with high potential for Scout and other missions with launch dates beyond 2009.

In this document, the following aspects of the MTP will be described:

- Program goals

- Program organization and management approach

- Technology planning process

- Description of technology plan (Appendix A)

# General Goals of Program

The MTP will develop and demonstrate the required technologies to enable the goals and objectives of the Mars Exploration Program, as specified in the Mars Exploration Program Plan.  Specifically, the Program will:

- Enable new classes of Mars science investigations – including, but not limited to, remote geology, remote astrobiology, and sample return.

- Increase the payload mass fraction delivered to Mars orbit and surface.

- Develop the capability to place payloads safely and precisely at any desired location on the surface of Mars.

- Enable full access to the subsurface, surface, and atmospheric regions, while protecting the planetary environment.

- Enable long-lived surface science investigations.

- Support the development of robotic assets that can provide a high rate data returns from the Mars surface.

These Program goals will be achieved by taking the following steps:

- Develop technology requirements by directly interacting with MEP baseline missions, such as MRO and MSL and other collaborative missions with international partners.

- Determine technology needs of future missions by developing a prioritized list of technology requirements obtained from a process that includes the following:

- Receiving NASA HQ’s level-1 technology requirements and updates for future missions

- Science measurement requirements as stated in the Mars Exploration Payload Analysis Group (MEPAG) document entitled “Science Planning for Exploring Mars,” and any updates to this document.

- Future mission concepts developed by the Pre-Projects and Advanced Studies Office at JPL. These mission concepts are developed specifically to address the science measurement requirements defined by MEPAG.

- Interaction with the Mars Program System Engineering Team (MPSET), which is tasked to develop a set of mission pathways that will be responsive to new discoveries.

- Present these derived requirements to MEPAG and the MTP Review panel for feedback

- Obtain approval from Mars Program Manager and concurrence from NASA HQ, indicating that the derived technology requirements satisfies NASA’s needs

- Modify the prioritized technology needs as the information stated above is updated due to programmatic or new scientific needs/discoveries.

- Assess the state of development of technologies important to Mars exploration via interaction with experts and holding focused workshops with participation from NASA and other institutions.

- Define, develop, and validate enabling technologies for MEP.

- Insert into flight missions the key technologies needed for Mars exploration.

- Commercialize technologies wherever appropriate.

The work breakdown structure of the MTP is subdivided into three major elements: Focused Technology, Technology Testbeds, and Base Technology.

- The Focused Technology element is aimed at advancing enabling technologies to TRL 6 by PDR for specified missions.  Missions will manage focused technologies with flight project discipline, including cost, schedule, and reviews.  The schedule to develop these technologies will be fixed due to the fact that TRL 6 technologies must be developed by PDR of each mission. Focused technology tasks are planned for a fixed period of time and will end at the specified date.

- The Technology Testbeds element develops testbeds that are required to integrate, infuse, and validate technologies into Mars missions.  Technology Validation Testbeds are aimed at providing long-term and sustained capability by JPL and NASA centers to develop and maintain MEP–required infrastructures that are essential for system–level technology design, integration, test, and validation. This element forms a bridge between the base and focused technology. Examples of technology testbeds are: Rover testbeds at JPL and Ames (includes software infrastructure, rover hardware, laboratory testbed elements, and indoor and outdoor test facilities), Mobility and EDL simulation testbeds, Sample Processing and Distribution testbeds, etc. The distinguishing feature that separates technology testbeds from other facilities and laboratories is that these testbeds are required to integrate disparate technologies developed in various institutions and therefore require integration and validation. Testbeds are required for multiple missions and therefore are managed by MTP rather than the focused technology programs that focus on particular missions.

- The Base Technology element will address technology advances for multiple missions including baselined and future missions.  When used for baseline missions, technology will be enhancing and will not be in the critical path of missions. When used for future missions, these technologies will in general be enabling. An important customer for the base technology program is Scout missions. MTP will identify those technologies that are essential for future Scout missions and will fund their development. NASA HQ will provide level-1 technology requirements for Scout missions based on their evaluation of technology gaps for future possible scout missions. The following areas have been identified for funding within the Base Program

  - Rover technology

  - Subsurface Access

  - Mars Instruments (MIDP)

  - Telecom and Navigation

  - Advanced Entry, Descent and Landing (EDL)

  - Planetary Protection

  - Low-Cost Mission Technologies (Scout Technologies)

:

# Program Requirements

The Mars Technology Program will be planned and implemented to satisfy the following Program-level requirements (Metrics indicated below will be further refined, as future missions are better understood) :

- The Program shall develop technologies that enable new classes of Mars science investigations at each launch opportunity, including remote geology, remote astrobiology, and sample return. Remote geology and astrobiology missions will be enabled by developing autonomous vertical and horizontal mobility technologies exceeding current state-of-the-art capability by an order of magnitude for each successive mission. Onboard sample processing and distribution capability will be developed to autonomously acquire samples and process them for use by onboard science instruments (such capability does not exists presently.)

Mars Sample Return (MSR) technologies will be developed to enable the return of  0.5 to 1.0 kg samples from Mars consistent with Mars and Earth planetary protection requirements provided by NASA HQ. This will include safe handling of Martian samples after they have been transferred to Earth

- The Program shall emphasize the development of long-life exploration tools for orbital reconnaissance, intermediate altitude reconnaissance via aerial platforms, local and long-range mobility, subsurface exploration. For solar powered systems, technologies will be developed to at least double the expected operations of the solar panels from 90 sols to 180 sols. For nuclear powered missions, long-life technologies will be developed to prolong the expected life of electronics and actuators to a Martian year. Nuclear power technology development is not in the scope of MTP.

- The Program shall continually increase the payload mass fraction delivered to Mars orbit and surface from 10% to 20% by 2020.

- The Program shall develop the capability to place payloads safely and precisely at any desired location on the surface of Mars. More specifically, technologies will be developed to land at higher latitudes and at least 2.5 km above MOLA reference, thus providing access to about 90% of the planet’s surface. This will provide an order of magnitude greater access to the surface of Mars than is currently possible.  “Go-To” capability will be enabled by developing precision landing technology (ability to land with a precision of at least 5km) and roving of 10km. The combination of the higher altitude access and “Go-To” capabilities will enable pin-point access to 90% of the planet via rovers. Pin-point landing technology will be developed to enable fixed landers to land with ~100m accuracy, in the second decade.

- The Program shall develop technologies that enable significantly greater access to the subsurface (20-50 m), surface (10- 50 km), and atmospheric regions (1000s of km), while protecting the planetary environment.

- The Program shall pursue technologies that support the development of a continuous robotic presence on Mars.

- The Program shall advocate competition to the greatest extent possible as a vehicle to stimulate new ideas and increased participation by the scientific, engineering and technology communities. 100% of the base technology program will be competed via NASA NRAs. Every effort will be made to compete portions of the focused technology program while maintaining in-house (JPL and NASA Centers) expertise to assure successful infusion of the critical technologies required by the missions.

- The Program will develop Mars specific communication technologies to enable high data return. (Increase Mars surface to Mars orbit transmission data rate from 10 kbps to 1-2 mbps)

- An MEP Technology Plan shall be prepared and maintained by the Mars Technology Program Office to identify and guide the development of technologies, in conjunction with the Agency and Space Science Enterprise technology plans, as required to implement the Program

.

# Customer Definition and Advocacy

In general, the Technology Program customers comprise the members of the space science community and the human space exploration community.  More immediately, the customers consist of Mars project planning teams whose missions will be the beneficiaries of technologies that confer improved performance, reliability, or cost effectiveness.  Interaction with customers will take place primarily through joint technology planning and development activities, support of Mars Program education and public outreach, and support of technology commercialization.  These activities are described in detail in the remainder of this Plan.

# Organization and Management Approach

## Organization

The Mars Technology Program Manager is the point of contact with all the implementing personnel of the Technology Program, both internal and external to JPL.  The MTP Manager reports to the Mars Program Manager.  The Program Executive defines technology program level-1 requirements, reviews program performance, and assures compliance with MEP and OSS directives and policies.   The Technology Program structure (focused, based, and testbeds, etc.) , the split of funding within the structure, planning and reviews are discussed by MTP manager with the program executive and consensus is reached before their approval by the Mars Program manager and concurrence by the Mars Director is sought.

## Roles and Responsibilities

The Mars Technology Program Manager will:

- Implement a balanced program of technology responsive to technology level-1 requirements defined by NASA HQ and required by the Mars Program Office (MPO).

- Implement a strategy for multi-center participation, competitive programs, and program balance in support of near-term and future missions as required by MPO.

- Support MPO to maintain the alignment of technology with mission needs and infuse technology into projects.

- Provide monthly, quarterly, and annual reviews of the Technology Program.

- Lead the definition of tasks, select task managers, and monitor tasks.

- Report status to MPO against agreed-upon metrics.

- Provide assistance to NASA HQ for Base Technology NRAs.

- Convene an external review board whose panel membership has been concurred by the MTP PE.

For focused technologies, the project managers and MTP jointly appoint a focused technology manager and level-1 managers (when required).

Focused technology manager is responsible for the day-to-day operations of the focused technology program. Changes to the program are handled by a Change Review Board (CRB), which includes the Project and the MTP Manager. MTP manager has the responsibility of obtaining concurrences form the MTP PE and Mars Program Manager when required (Major changes to the program).

The level-1 managers (also referred to as technical leads) have the day-to-day responsibility of managing elements of the focused technologies with guidance provided to them by the Focused Technology Manager and or project manager. They do, however, report to the MTP Manager on a regular basis their technical progress, cost, and schedules.

More specifically, the responsibilities of level-1 managers include:

- Coordinating and leading activities in their designated technology areas,

- Supporting Program Office activities,

- Holding monthly reviews and submitting monthly progress summaries,

- Supporting quarterly reviews, and

- Supporting year-end reviews.

An example of a level-1 manager is a person who manages all focused technologies for the Mars Smart Lander Project.  In a project such as MSL, the focused technologies effort might be organized into several level-2 technical areas.  Such level-2 technical areas for MSL might include: entry, descent, and landing (EDL); autonomy; in-situ sample handling and processing; etc.  Each level-2 technical area will normally include several tasks (level-3).  Tasks are assigned to task managers.  A task is the lowest technical entity that reports to the Program.

Each task is required to develop a technology development agreement (TDA) and a financial plan.  The TDA is written by a task manager and is approved by the level-1 manager, appropriate line organization (in the case of JPL, a section manager), and the focused technology manager or MTP Manager. The task manager’s responsibilities are to:

Plan the task

Assemble task members (JPL, NASA centers, universities, etc.)

Lead the technical development

Participate in monthly, quarterly, and year-end reviews

Provide support to the Technical Lead, and

Deliver task products to the Technical Lead

## Collaborations

MTP technical leads are instructed to engage all possible expertise from NASA centers, industry, and universities.

The MTP maintains close ties to the New Millennium Program, the Outer Planets Program, the Intelligent Systems Program, the In Space Propulsion and other programs, and seeks cooperative ventures wherever it is mutually beneficial.

## Agreements

MTP will document all formal agreements reached with other technology programs (funded by NASA and other agencies) in the form of memoranda of undertandings (MOUs) or letters of agreements (LOAs). hese are listed in Appendix C and will be updated each fiscal year.

## Reviews

The MTP will hold reviews regularly to monitor the technical progress and address any issues/concerns throughout the year.  Three types of reviews are planned:

- Monthly  -  The Technical Lead is responsible for organizing and conducting the monthly management reviews (MMR) with participation from the line organizations, the Program Office, and collaborating NASA centers.

- Quarterly – The MTP Manager is responsible for organizing and conducting the quarterly reviews in January, April, July, and October of each calendar year.  The technical leads will prepare and present the quarterly reports for their respective technical areas.  The participants include MPO staffs, program executives and representatives from collaborating NASA centers, line management, and technology customers (project and pre-project managers).  The MTP Manager will summarize the results and report in the GPMC Quarterly Review.

- Annual - A year-end external review will be held in October of each calendar year.  This review will assess the relevance and quality of the technology program for baselined and future missions. The MTP Manager is responsible for organizing this review and assembling a peer review panel with the concurrence of the program executive.  The panel will include appropriate technical and programmatic personnel from JPL, NASA centers, NASA HQ, and universities.  The Mars Program Chief Engineer or his designee will chair the peer review panel and provide a summary of review results and recommendations to the MTP Manager.  The review feedback will be used to improve the Technology Program by implementing the review panel recommendations as appropriate. The MTP manager will provide a report to the review panel on the corrective actions taken by the program as a response to the review panel’s feedback.

## Schedule

MTP’s program schedule is presented in Appendix D.  This schedule is updated each fiscal year.

### Resource Management

Top-level, multi-year budget guidelines will be provided by NASA Headquarters as part of each annual MEP Program Operating Plan (POP) developed by Mars Program Director and Program Executives.  In response, the MEP Program Manager will develop a budget request for the Technology Program along with other Mars Program elements.  The Mars Program Director, with input from the Program Manager, will advocate and negotiate budget requirements for the Program within the Office of Space Science and provide supporting information to the NASA Comptroller’s Office and to the Office of Management and Budget (OMB).

The Mars Program Manager will be responsible for management and administration of the overall Mars Program budget assigned to JPL, including the budget for the Technology Program. Requests for bypass funding to other agencies and NASA Centers will be based on a formal request from the Program Manager to the Program Director. The MTP manager will develop these requests. All requests will be based on the tasks reviewed during the annual review of the program. Any new request that was not reviewed during the year-end review will be concurred by the PE prior to the release of the bypass letter.  The Technology Program Manager will be responsible for detailed budget negotiation and budget reporting to the Mars Program Manager.  The MTP Manager will provide monthly management reporting on new obligation authority (NOA), obligations, cost, and workforce to the Program Office with an explanation of any variances between the plans and actuals.

### Budget Profile

The MTP budget profile is provided in Appendix E.  This appendix will be updated each fiscal year.

## Controls

### Program Documentation

The Mars Exploration Program policies and procedures for information management and documentation will be provided in its Information Management and Documentation Plan.  In addition, the Mars Program will define, set up, maintain, and operate a Program information management system.  The MTP will utilize this system, and will manage its information and documentation in accordance with the MEP Information Management and Documentation Plan.  The Program information management system will capture and store information and documentation in a way which:

- Facilitates information access and sharing, both internally and externally;

- Identifies the status of the information;

- Identifies what information exists and where to find it;

- Identifies documents requiring approval and the level of review required for approval; and

- Identifies those documents and data sets that will be archived at the end of Program to meet legal, contractual, and/or knowledge preservation purposes.

A Master Controlled Document List (MCDL) will be maintained by the MEP Program which identifies all documents under document control.  The MCDL will include this Technology Program Plan.

### Process Validation

The MTP Manager is responsible for collection and analysis of Program process metrics and for the identification of areas of exceptional or substandard performance. These metrics will be used to identify process corrective actions, to communicate lessons learned in using these processes, and for reporting status to the Mars Program Manager and MEP Director

Contractor cost reporting and performance measurement processes will be implemented in sufficient depth to enable Program management to:

- Review the cost and workforce expended in each element of the Technology Program relative to its schedule and technical progress.

- Determine significant elements of risk to the Program and its elements.

- Report progress relative to the Program and subsidiary plans.

### Change Control

Change control for the MTP and its elements will be consistent with NASA and JPL change control policies and procedures, sufficient to provide visibility into all interactions and interdependencies within the Program.  MTP change control will be coordinated with the Mars Program Manager and NASA HQ, as appropriate.

Life cycle cost effects will be projected for all major changes and be submitted as part of formal change control requests.

## Risk Management

The Technology Program risk management approach will be guided by a policy of resilience, especially where important planned missions depend on MTP-developed technologies for their success, or where meeting technology objectives relies on the success of anticipated technology flight demonstrations. Two key aspects of risk management in the Technology Program will be the continuing assessment of the impact of possible technology development or demonstration failure on the achievement of Program goals, and the tailoring of technology objectives or implementation plans in accordance with that impact.  The Technology Program approach will be designed to evolve throughout the life of the Program to meet changing needs, and will be updated as appropriate to reflect prevailing risk management practices.

### Areas of Emphasis

Risk management will be applied to both technical and programmatic risk. Programmatic and technical risk areas of particular emphasis for the identification and mitigation of specific risks are as follows:

Programmatic risk areas:

Technology development and implementation that satisfies MEP requirements within the established cost profile and with acceptable residual risks

Resiliency of the Program architecture to changes in funding and performance goals

Approval of funding external to the MTP for cross-cutting technology developments upon which the Program is dependent

Program architecture that is resilient to failure of individual missions, and adaptive to evolving science objectives and priorities

Ensuring that technologies developed and used by the MTP do not constitute a threat to the environment or human safety

Establishing and maintaining effective collaboration with international partners, consistent with ITAR requirements

Technical risk areas:

Development and implementation of technologies consistent with the requirements of planned missions

Flight demonstrations that are outside the experience base developed during ground test, or not otherwise simulated in a flight-like testbed environment prior to the in-flight use

Development of effective new technologies that meet safety and environmental requirements and concerns

Other important risk areas will be managed at the Mars Program level.  These include:

Affordable resolution of planetary protection issues

Demonstration to the broad scientific community and to the public that technologies developed by the MTP for mission applications constitute neither a real nor a perceived threat to the environment or human safety

### Approach

The Technology Program risk management approach will meet the requirements of NPG 7120.5B, ISO, ITAR, and other NASA and JPL policies and processes established for identifying, characterizing, mitigating, tracking, and reporting risks.  It will identify the responsibilities of Program participants and will provide a schedule of risk management activities.  Key features of the approach include:

- Assessing the Program impact of possible failure of planned technology development and application, and providing risk management requirements and guidelines consistent with technology criticality and cost constraints;

- Encouraging appropriate levels of technology investment prior to project starts;

- Establishing and managing programmatic/technical margins commensurate with development risks;

- Planning, scheduling, and conducting regular reviews of risk areas, assessing risk levels and status of risk mitigation;

- Strengthening processes for risk management to ensure early and continuing attention to:

Configuration management

Verification and validation

Rigorous reporting and resolution of anomalies throughout the development cycle

# Technology Planning Process

An intensive MEP planning process has resulted in the current set of technology requirements, and this Plan is responsive to those requirements.  A process for annual replanning of the MTP has now been defined and will be applied for the first time during planning of the MTP for FY’03.

## Annual Replanning Process

The MTP Plan will be updated annually in order to realign the Technology Program with mission goals as future missions are better defined or modified, and to reflect progress in meeting the goals of the Technology Program.  These updates will conclude prior to the start of each new fiscal year.  The process for developing and updating Technology Program content will be carried out by the MTP Manager with input from the Manager of Pre-Projects and Advanced Studies Office, MPSET Chair, and guidance from the program executives.  The MPO Manager approves the Technology Program content and its funding allocation.  As part of the annual replanning process, the MTP Manager will:

Receive level-1 technology requirement updates from NASA HQ

Update technology needs of future missions by developing a prioritized list of technology requirements obtained from the process described in Section 2.

Update the prioritized technology needs due to programmatic changes or due to new scientific needs/discoveries

Assess the state of development of technologies important to Mars exploration via interaction with experts and through focused workshops with participation from NASA and other institutions

## Task Definition and Assignment

The task definition and assignment process, which is updated on yearly basis, is described in this section.  The process is different for each of the technology categories (i.e., Focused and Base) and is outlined below.

Focused Technology Tasks. Tasks will be defined by missions, negotiated by the

Figure 6.1.  Mars Technology Program Process Summary

______________________________________________________________________________

MTP Manager, and reviewed and approved by the Mars Program Manager. The process includes the following steps:

Definition of mission technology needs and priorities

Assessment of technology readiness

Determination of uniqueness of Mars technology needs

Assessment of potential for co-funding

The funding strategy is to compete focused technology tasks when appropriate via RFP or other means, and to find the best team for technology development and delivery to the missions.  Tasks  also can be assigned directly by the project managers to JPL, NASA centers, or other institutions based on the expertise and other considerations.  The funding ratio of in-house (JPL) vs. out-of-house tasks will satisfy requirements defined by the Mars Exploration Director.  Technology Validation Testbed tasks are also reviewed as part of focused technology review and are updated as required.

Base Technology Tasks. All base technology tasks will be competed via NRAs issued by NASA HQ.  The MTP Manager will define technology areas, with guidance provided by the program executives, consultation with the MPSET Chair and approval of the MPO Manager.  The MTP Manager will develop the draft NRA call content for each base technology category. This document will be reviewed by the MPO Manager and submitted to NASA HQ for consideration as the basis for the NRA. The MTP PE will develop the final version of the NRA and issue it under the ROSS NRA.  MTP will assist NASA HQ in forming review panels for each technology area and providing other assistance as required by NASA HQ.  NASA HQ will receive the proposals, conduct reviews, and select tasks. The implementation, i.e., funding; day-to-day management; monthly, quarterly, and yearly reviews; and the delivery of technology products are the responsibility of the MTP.

## Leveraged Programs

The MTP also will attempt to leverage technology developed in other NASA and non-NASA programs to address Mars-specific needs.  These leveraged programs will be documented where appropriate in memoranda of agreement among the participants.

## Products and Infusion Strategy

The products of the MTP will fulfill the technology requirements and include hardware, software, and systems together with testing and validation data that demonstrates their performance and reliability.

Technology infusion has been planned as an integral part of the MTP. The objectives of the MTP will not be complete until the technologies are infused into technology validation experiments or flight projects.  Plans for technology infusion are being made early in the technology development life cycle when the technology is between TRL 3 and 4.  In order for a flight project to include a technology in its preliminary mission plan, it must have reached TRL ~5 by Preliminary Mission Systems Review (PMSR), and in order for the technology to be adopted by the project it must reach TRL ~6 by Preliminary Design Review (PDR).  TRL 6 implies that an engineering model has been validated in a simulated environment in the laboratory.  The MTP has been planned to achieve these goals by the appropriate dates for the relevant Mars missions.

Some technologies are of such a nature that laboratory testing is inadequate, and they must be validated in space, either in Earth orbit or at Mars.  Some technologies may contribute to validation of performance models and this may require validation of these models in the environment of Mars with its unique gravity field and atmospheric properties.  These technologies will have reached TRL ~7 by CDR.

For focused technologies, technology development is conducted in concert with pre-project development through the Mars Smart Lander pre-project. In many cases, the developers of the technology also will be the users, thus overcoming impediments to the acceptance of the technology.

For the Base Technology, developers usually will not be users, and communication efforts must be put in place to ensure the success of infusion.  One example of this is information technology (IT), where MPO is participating in a joint ARC/JPL strategy team focused on insertion of IT into flight projects.

The Technology Testbeds ensure that technologies developed via the Base Program are captured and integrated into useful products for near-term and future missions.

The MTP does not just produce tangible products (i.e., hardware, software, and demonstrations). It also produces intellectual capital and trained personnel.  These byproducts of the MTP are every bit as important as the tangible products.  In some cases, even when the a tangible MTP product is not adopted for flight, the people who were trained while developing that product end up working on the flight system, whatever its specific design.  The intellectual capital and expertise gained in developing an advanced technology product (even if it was not infused) will prove to be invaluable in implementing a mission that requires the similar or closely related technologies.

# Public Outreach and Commercialization

## Public Outreach

The MEP organizes its missions as an integrated, cohesive program, rather than as a collection of independent efforts.  In a similar fashion, MEP public outreach will be established as a set of closely-knit, mutually supportive efforts that collectively lead to the achievement of the Program’s long-term outreach goals. The Mars Technology Program will actively engage the MEP public outreach to help publicize the achievements of the program and thus create public enthusiasm, particularly the youth, for NASA missions in general and Mars in particular. Examples of such outreach efforts are participation and involvement in the FIRST robotics competition and the active participation of students in rove field tests.

MTP will support MEP public outreach objectives by providing timely information on technology plans, status, and impact on Mars missions that contributes to a variety of outreach efforts:

Public Outreach: products and activities that engage the general public, special interest groups, children, businesses, legislative and other audiences;

Media Relations: all products and activities required by the media to communicate effectively with the public, including press releases, visualizations (images, animations, and related A- and B-roll), event support (press rooms, press kits), and interviews (live shots, etc.);

Internet Communications: online information and activities for all audiences: the general public, the media, educators, students, informal education institutions, and the scientific and technical community. The Mars Technology Program will continue to provide information for the technology segment of the Mars Exploration Program external website currently in beta test at

http://stargate.jpl.nasa.gov/devel/redplanet/technology/

## Commercialization

The MTP is dedicated to assisting the commercialization of its technologies wherever appropriate. To accomplish technology and commercialization planning, the MTP will:

Explore innovative avenues to expand private sector participation and infuse the latest externally-developed technological capabilities into the Program.

Explore how assets (technology, discoveries, innovations, tools, processes, or software) developed through Program execution can be transferred to industry.

Assess teaming and partnering options to achieve various aspects of the Program.

Ensure that the plans for technological cooperation include a full description of the opportunities for partnering, the potential partners, the need for protection of intellectual property, the likelihood of the partnership coming to fruition, the expected contribution (personnel, facilities, and other funding) and the confidence that the partnership will remain in force through their commitment.

- In cooperation with JPL’s Commercial Services Office (CSO), secure participation of the NASA Commercial Technology Program (Code RW) that supports NASA Enterprises toward NASA’s goal of enhancing U.S. economic competitiveness while encouraging state, local, and private sector use of space technologies, as reflected in the Office of Space Science New Technology Strategy.

Encourage arrangements for identifying and initiating opportunities within the projects for commercialization in both aerospace and non-aerospace sectors:

Partnerships (mutually beneficial arrangements with no exchange of funds)

Memoranda of Understanding

Technology Cooperation Agreements (analogous to Space Act Agreements)

Strategic Alliance Agreements

Industry-funded technology development (funds-in to Project)

Technology Affiliates Program

Cost Reimbursable Agreements

Collaborative (jointly proposed) technology development (for further development and/or technology demonstration and validation in commercial environment)

NASA and government agency AOs and Broad Agency Announcements

Small Business Innovative Research (SBIR) and Small Business Technology Transfer Research (STTR) Programs

Licensing of hardware and software products (jointly with Caltech)

New ventures (primarily software business opportunities)

Spin-offs (addressing commercial marketplace but providing additional and cost-effective capabilities back to NASA/JPL, including potential reduction of life-cycle costs)

Require use of NASA-recognized commercialization metrics, e.g., resource-sharing partnerships that further commercialization potential, new technology reports, and licenses.

# Change Log

A change log process will be maintained for this Plan, consistent with NPG 7120.5B requirements and JPL change control procedures.

A record of changes to this document follows.

Document Change Log

| Version | Date | Description of Change(s) |
| --- | --- | --- |
| 0 | TBD | Approval and publication of final MTP Program Plan. |

# Appendices

# Footnotes

McCleese, D., Greely, R., and MacPherson, “Science Planning for Exploring Mars,” JPL Publication 01-7, July 2001.