FY09 Tactical Plan for Database Services
Prepared by J.Trumbo
June, 2009

Docdb 2889

Databases Goal

Continue to provide a stable, professional operation of laboratory scientific and information systems databases, providing maximum uptime and technical support.

Databases Strategy

Develop stronger expertise and support for open source databases, reducing the dependency on Oracle, with a goal of reducing development and support costs.

Tactical Objectives for FY 09

1.   Database & Systems Operations

Support running experiments at appropriate levels. Maintain a database uptime per SLA.   The % rate for uptime on mission critical production databases will vary depending on SLA and their commitment to up-time.  In addition, the system hardware will also help dictate up-time needs.   All databases will follow the baselines written, and we will provide support to the database user community to help insure a stable, performant, and smooth running environment.

List of Activities:

- DATABASES & INFO MANAGEMENT / Database Administration / Scientific

- DATABASES & INFO MANAGEMENT / Database Administration / Astro

- DATABASES & INFO MANAGEMENT / Database Administration /  Information systems

2. Database Support.

Promote Postgres and Oracle as a 1st tier database and MS-SQL and MySQL as second-tier databases. Understand the pros & cons for Oracle and Open Sources database options, gather information about what the customers needs and select the appropriate database as per the findings.  The legacy systems will proceed with Oracle and there may be an occasion for new experiments to use Oracle, but an analysis regarding appropriate database technology will be performed for all new customers.

a. Oracle Support

Support production, integration and development Oracle database information systemss. Configure, tune, test, and maintain databases.  Coordinate effort with application team for reviews of data modeling and database queries. Develop tools for operating, and monitoring of databases.   Perform and Define Oracle database backup and recovery.  Install and configure Oracle Internet Directory (oid), for Oracle v10 dbs.

b. Open Source Database Support.

Support production, integration and development open source database information systems. Configure, tune, test, and maintain database.  Coordinate effort with application team for reviews of data modeling and database queries as necessary. Develop/procure tools for operating and monitoring of databases   Perform and define database backup and recovery. Attain expertise on open source databases deployment.

- DATABASES & INFO MANAGEMENT / Database Administration / Tools_development

3.   Agile response to new and rapid shifts of responsibilities and demands accompanying the end of Run II data taking and reduction of effort in the Run II experiments.

4. Kerberize Oracle using Advanced Security Option.

5. Maintain expertise for new features. Work with databases on vm environments, oracle rac testing, etc.

7.  Complete upgrade to Oracle 10 for the information systems databases.

8.  Upgrade information systems hardware for databases, including major apps, computer security, 24.7 applications and nimi development.

9.  Continued Deployment of the 3par San technology, a high availability database disk storage array.  Continue testing, standardization and configuration of 3Par product to optimize additional hosts and database instances.  Move additional instances to the 3par that are currently running on aging arrays and/ to meet the space needs on development databases. Would like to investigate the potential of using Oracle snapshots on 3par as a substitute for rman backups. Potentially, this could mean significant savings in disk usage.  On 3par the Oracle database and open source database can be hosted.

10.  SDSS

In FY09, both DR7 and DR8 will be loaded and released.    DR7
will go public by June 30, 2007.  DR8 will go public by October 31, 2008 and will be the final data release.  DR7 will incorporate all final data model and schema
changes, as we won't have time between DR7 and DR8 for any additional changes.

Continue using Idera to monitor and track performance.   Produce quarterly summary reports regarding status of systems and uptime metrics per mou.

Support the transition from SDSS operations to long-term maintenance and stewardship of the SDSS archive. Activities will include updating all documentation associated with loading and hosting the SDSS SkyServer and CAS system. Also help the JHU and UC science libraries with the operation and maintenance of CAS
clusters for hosting DR5.

- ASTRO / SDSS II / Data Distribution Operations (SSP 268)

11.  DES

Fermilab has been asked to host an Oracle standby database for the Dark Energy Survey. This database will be used for scientific queries as well as failover from the master database hosted in Champaign, Il.  Current thinking is to implement this database under Oracle rac, as the master is implemented, insuring high availability.   DBI-DBA needs to train in rac and auto storage management techniques to accomplish this goal.

Database Support

Oracle Support     * indicates may not have time to do

- Activity type: Fy 09 project   16 fte months maintenance + 16 fte months projects = 32 fte months total

- Milestones:

  - Oracle general support

- Install, configure, and test new Oracle databases, perform version upgrades of existing databases.  12.0 fte months

- Administer and operate production and development Oracle database information systems.  1 fte month

- Participate in a 24x7 on-call rotation schedule for production issues.

- Perform Oracle database backups and data restores.   .5 fte months

- Disaster recovery for Oracle databases.  .5 fte months

- Replication support  1 fte month

- Diagnose problems, and monitor database performance.   .5 fte months

- Perform tuning of SQL queries.    .5 fte months

  - Install and configure Oracle Internet Directory (OID) for Oracle v10 dbs.    Dependant on hardware delivery.  4 fte months

  - Move database to 3par including fcdfora6, fcdfora4, fcdfora1, minos   1 fte month

  - Configure and implement 5 new d0 online database boxes to replace current d0 online, test new cluster software and failover.  1.5 fte months

  - *Configure and implement new cdf offline production box.  Reuse current production box for development replacement.  Dependant on hardware delivery.  1 fte month

  - *Configure and implement new d0 offline production box.  Reuse current production box for development replacement.  Dependant on hardware delivery.  1 fte month

  - Begin planning upgrade of Oracle databases to 11g.   .5 fte months

  - Begin upgrading Oracle databases to 11g.   4 fte months

  - Design and implement ITL asset management database.  Scope undefined and unknown.   4 fte month .

  - Implement ust1_fts, the cms database on new hardware  .5 fte months

  - Move the esh dev/int/prd database to a Unix platform from Windows.  2.5 fte months

- Metrics:  uptime statistics, performance

SqlServer Support

- Activity type: Fy 09 project   1 fte month total

- Milestones:

  - SqlServer general support

    - Install, configure, and test new SqlServer databases, perform version upgrades of existing databases if necessary

    - Support SDSS and Sharepoint databases, setup users, roles, etc.

    - Administer and operate production and development SqlServer database information systems.

    - Participate in a 24x7 on-call rotation schedule for production issues, if necessary

    - Perform SqlServer database backups and data restores.

    - Disaster recovery for SqlServer databases.

    - Diagnose problems, and monitor database performance.

    - Perform tuning of SQL queries.

    - Cross train dbas on MS SqlServer technology.

-Metrics:  uptime statistics, performance

-Dependencies:   scope of work in unknown in size. Fte calculation is based on minimal known scope.  This may prove inaccurate.

Open Source Database Support

-Activity type: Fy 09 project 6 fte months general support + 22 training/projects= 28 fte months

- Milestones:

  - Open Source general support

  - Install, configure, and test new Open Source databases, perform version upgrades of existing databases

  - Administer and operate production and development Open Source database information systems.

  - Participate in a 24x7 on-call rotation schedule for production issues.

  - Perform Open Source database backups and data restores.

  - Disaster recovery for Open Source databases.

  - Replication

  - Diagnose problems, and monitor database performance.

  - Perform tuning of SQL queries.

  - Implement strategy for Open Source implementations, including standards, procedures, best practices, scripts, policies, etc.

  - Continue assuming responsibilities of current production freeware databases, bring them up to standards.

  - Purchase and implement monitoring software for postgres and mysql

  - Purchase 24.7 3rd party support for mysql and postgres.

  - Backup & restores.

  - Continuity initiatives

  - Train dbas in both mysql and postgres to a level of production support, this includes formal classes as well as on the job training.  6 fte months

  - *Retrofit toolman application for open source database platforms, postgres&mysql, if possible, providing a monitoring tool for open source platforms   8 fte months.

  - *Rebuld mysql installations on flxd01&flxd04 so that products are not owned by root.  1.5 fte months

  - *Implement new machines to replace flxd01&flxd04. Dependant on hardware purchase.  1 fte month

  - *Implement new machine for nimi dev database. Dependant on hardware purchase  2 fte month

  - Upgrade minos production and development to v5 of mysql.  1.5 fte month

  - Implement new Minerva production machine  1 fte month

  - Nova support  .5 fte months

  - Support ilc/project x as needed.  .5 months

- Metrics:  # of people trained in different platforms

- Metrics:  stabilization and consistency of existing freeware environments that are being absorbed. Cross training of support personnel to support these environments to enable dependable support.

- Dependencies:  training, manpower

Kerberize Oracle with Advanced Security Option.

- Activity type: Fy 09 project  1 fte month

- Milestones:

- continue oracle aso kerberos project

- implement Kerberos authentication for DBA tasks

- install aso for users as needed

- define an action plan to support aso

- Metrics:  % of kerberized dba tasks, % of kerberized user tasks

- Dependencies:

- Maintain expertise for new features.

Investigate potential for using auto storage management

- Activity type: Fy 09 project   .5 fte month

- Milestones:

- *Proof of product

- *benchmark tests

- *document results

- *provide recommendations for auto storage mgmt

- Metrics:  benchmark figures

- Dependencies:  fte cycles need to be available

Evaluate rman incremental backups in Oracle 10

- Activity type: Fy 09 project    1 fte month

- Milestones:

  - *create test plan

  - *test

  - *recommend use or not of incremental backups

- Metrics:  na

- Dependencies: fte cycles need to be available

Complete upgrade to Oracle 10 for the information systems databases.

- Activity type: Fy 09 project  7 fte months

- Milestones:

- Information systems databases upgrade 10gR2 planning and testing.

- Metrics:  % of instances upgraded

- Dependencies:  application readiness

Upgrade infra structure hardware for databases

- Activity type: Fy 09 project  5 fte months

- Milestones:

- plan separation of information systems apps, including major apps, 24.7 and others  1 fte month

- plan for data movement to new databases  1 fte month

- Implement new databases, including oid repository and remedy.   3 fte months

- Metrics:  % upgraded

- Dependencies:  people resources

Migrate Databases to 3Par San technology

- Activity type: Fy 09 project 3 fte months total

- Milestones:

  - Move dev/int cdf offline databases to 3par to replace aging and unsupported disk array.   1 fte month

  - Move dev/int d0 luminosity databases/snapshots to 3par to allow for a full and complete testing environment.   .5 fte months

  - *Assess and move if possible the cdf online dev/int environments of aging array.   5. fte month

  - Move fcdfora6 replica database to 3par.   .5 fte month

  - Move Minos Sam databases to 3par  .5 fte month

- Metrics:  uptime, $ saving on time and materials repairs to unsupported hardware.

- Dependencies: successful implementation, budget

SDSS

- Activity type: FY 09 project   9.5 fte months

- Milestones:

  - Load and Release DR7   1 fte month

  - Loading Runs Database   1 fte month

  - Standardizing the Idrea Monitoring and metrics.    1 fte month

  - Support the transition from SDSS operations to long-term maintenance, including consultancy with JHU & UC.   6 fte months

  - *Implementing DR7 at UC   .5 fte months

- Metrics:  Meet Release Schedule dates.

- Dependencies:  UC dr7 implementation dependant on funding.

DES Standby Database

- Activity type: FY 09 project   4 fte months

- Milestones:

  - Test and develop expertise in oracle rac.

  - Test and develop expertise in auto storage mgmt.

  - Implement development stand by database at fermi, master in Champaign.

  - Install Oracle and implement production standby database at fermi

  - Investigate and implement proper rac, standby monitoring tools.

- Metrics:  Meet Release Schedule dates.

- Dependencies:  Hardware availability, Mou

Priorities

Top priority is to continue as strong, stable environment for RunII databases, optimizing database uptime in a 24.7 environment. This will be accomplished by proactively addressing hardware needs and constant database monitoring.

Priority 2 is to continue to develop stronger expertise and support for open source databases, reducing the dependency on Oracle, with a goal of reducing development and support costs is to maintain a stable and secure database environment.  Stability and security is achieved by following the standards and procedures set out in baselines and best practices.  This includes providing an agile response to the use of core standards and procedures for development, implementation and maintenance in a secure and consistent manner.

Priority 3 is to improve the information systems hardware situation.  We were able to procure hardware for this upgrade, thus, moving forward.   Fncdug1 is increasingly overloaded with users and products. A larger development team, along with additional information systems projects has overloaded fncdug1.  We have turned 2 of 3 integration databases to allow the 3rd to run with additional processes needed by the development team.  Not addressing this priority may lead to slower response, and denial of service, at times on the information systems database.  We are continually adding to the load on these machines with no additional resources.

Priority 4 is to move the information systems databases to Oracle 10.  The final software dependency has been eliminated, moving forward.

Priority 5 is get Oracle Advanced Security Option implemented.  Consequences of not being able to implement kerberos will be citings resulting from any upcoming DOE audits.  We would like to avoid this at all costs.  When Oracle provides the software, we will make it a priority to test and implement.  This is a no $ cost priority.

Priority 6 is to move the development and integration databases that are currently living on unsupported hardware to 3par SAN. This includes cdf online, which though still supported by D1, we have been warned the support will not continue much longer.  There is a firewall issue that must be resolved to move this database(s) to 3par.  Not enough disk capacity to refresh D0 luminosity dev/int databases from production in order to facilitate the testing on most recent production data.

Staffing Issues

Staffing should be adequate.  SDSS will be ramping down, DES, Open Source will require additional resources.  Total comes to 92 months of work, or 7.6 ftes.

Change Control

Delay of full implementation of the 3par array to b0dau36, fcdfora1 and d0lum1 pose some risk.  The stakeholders would need to be informed of the decision and potential consequences.

Risk Assessment

1. It is imperative the experimental databases are kept running and healthy.  This requires support, maintenance and hardware.  There is no hardware support for the array on fcdfora1, cdf offline dev/int, due to age. We need to move that to the 3par as soon as possible. The interface card has been purchased, however, furloughs and forced vaca have led to postponement of the move. B0dau36, cdf online dev/int, is almost in the same state. D1 has warned us that end of support is very near for its array. The complication with b0dau36 is a firewall that must be over come. A switch or another network option needs to be implemented to reach the 3par.  D0lum1, the d0 luminosity dev/int array has never had sufficient space for both a dev and int database, and now after the calibrations are complete, d0lum1 not have space for even 1 full copy.  The users do not have the ability to run thorough tests under these conditions, and our group’s ability to support the users is vastly diminished.  Again, the interface hardware from d0lum1 to the 3par has been purchased, manpower to do the move is pending.

2.  The risk assessment has the experiments as the highest risk (due to aging hardware, etc.) but this isn't discussed as part of the tactical plan.

3. Oracle Advanced Security Option needs to be deployed. We do not consider Oracle’s work around a ‘best solution’ however; we have gotten proof of product complete.  A full scale implementation plan across database for cron jobs needs to be completed.  There is a risk that this deficiency in security is called out in the next DOE audit. We continue to work with Oracle.

4. Upgrading the information systems databases to Oracle 10 is still on the list from fy 07.  The only databases still on v9 are the information systems dbs.  DSG had been waiting for the software dependency of matrix to be eliminated before starting.  As of May 08, matrix is gone and work can begin.  Having all the databases at a consistent version will ease maintenance effort. At this time, there is no risk of failure of the information systems applications if this upgrade is not completed.

5. The information systems hardware is being strained due to increased applications and users. New hardware to move the production databases to has been purchased and is in prep.  DSG will start installing asap, however, various leaves of sysadmin personnel has slowed this implementation   The new box will be prepared to move the production information systems dbs to, the old hardware, fncdug1, will remain in use for applications only. No budget was allocated to replace fncduh1, the development machine.

6. Continued absorption of production environments at varying levels of quality and resource demands is stretching our manpower limitations.  Lack of training in Open Source products and monitoring tools is a concern.

M&S

| Description | Notes | DEPT | ACTIVITY | Total Cost | EQ/OP |
| --- | --- | --- | --- | --- | --- |
| Oracle Licenses (scientific) | 1-year term licenses (56k shows up in REX) | css | All | 370000 | op |
| Krypton replacement | Console | Css |  | 4000 | eq |
| San storage experiment dbs | 3par 1T space anticipated & qlogic cards | css | All (waiting $ verification from ray) | 12000 | eq |
| flxd01 & flxd04 replacment, gen. mysql dev box | replace aging mysql general purpose dev box | css | Fnal mysql | 10000 | eq |
| dba32 replacement oem prod box | replace aging 32b oem monitoring box | Css | Oem prod | 3000 | eq |
| Cards for san | Ip cards for san | Css |  | 6000 | eq |
| misc cables/batteries, etc | misc cables/batteries, etc | Css | Misc hdw | 2000 | eq |
| oemora1&2 going to d1 3/09 | oemora1&2 going to d1 3/09 | Css | Expired sun support going to d1 | 630 | eq |
| Oemora1&2 larger disks | Oem server machines | Css | Running short on disk space | 1000 | eq |
| dbi-dba d1 support costs | dbi-dba d1 support costs | Css | D1 offline support | 15000 | eq |
| lt03 enstore tapes | new tapes for new robot, db backups | Css | Rman tapes | 14000 | Eq |
| MsSql Server conference | MsSql server conference | Css | Training & travel | 5000 | Op |
| Oracle conference | Oracle conference | Css | Training & travel | 4000 | Op |
| Mysql conference | Mysql conference | Css | Training & travel | 2000 | op |
| Postgres conference | Postgres conference | Css | Training & travel | 3000 | op |
| Foreign travel |  | Css |  | 22485 | op |
| 1 general ed class per employee | 1 general ed class per employee | Css | training | 41250 | op |
| Unsupported hdw repair |  | Css |  | 10000 | eq |

Changes in Personnel

Though the dbas are over extended, it is known that all activities will not be achievable.  There are several activities that can be delayed till manpower is available.  No additional staffing is requested.