Quality Assurance Project Plan

Growth rate of biofilm organisms in a distribution system simulator

Prepared by:

XXX

Address

Cincinnati, T&E facility

Telephone

Table of Contents

I. Project Management	3

A. Distribution List	3

B. Project Organization	3

C. Problem Definition/Background	4

D. Project Description and Schedule	4

E. Quality Objectives and Criteria for Measurement Data	5

F. Special Training Requirements	5

G. Documentation and Records	5

II. Measurement/Data Acquisition	5

A. Experimental Design	5

B. Sampling Methods Requirements	6

C. Sample Handling and Custody Requirements	10

D. Analytical Methods Requirements	11

E. Quality Control/Quality Assurance Requirements	11

F. Instrument/Equipment Testing, Inspection, and Maintenance Requirements
	12

G. Instrument Calibration and Frequency	12

H. Inspection/Acceptance Requirements for Supplies and Consumables	12

I. Data Acquisition Requirements (Non-Direct Measurements)	12

J. Data Management	12

III. Assessment/Oversight	13

A. Assessments and Response Actions	13

B. Reports to Management	13

IV. Data Validation and Usability	13

A. Data Review, Validation, and Verification Requirements	13

B. Validation and Verification Methods	13

C. Reconciliation with Data Quality Objectives	14

References	15

Appendix 1	16

List of Tables

Table 1.  Distribution system simulator operating conditions	6

Table 2.  Sample collection schedule for microbiological samples	8

Table 3.  Sample collection schedule for chemical analyses	9

Table 4.  Methods for analysis of water and biofilm samples	11

I. Project Management

A.	Distribution List

XX , Principal Investigator, Microbial Contaminants Control Branch (MCCB), Water Supply Water Resources Division (WSWRD)

XX, Acting Chief, MCCB, WSWRD

XX, Quality Assurance Manager, WSWRD

XX, Acting Chief and Project Manager, Water Quality Management Branch (WQMB), WSWRD

XX, Biological Science Technician, MCCB, WSWRD

XX, Engineering Technician, WQMB, WSWRD

XX, Biological Science Technician, MCCB, WSWRD

Indicates individuals who are responsible for implementation the quality assurance plan.

B.	Project Organization

XX, the principal investigator, is responsible for plan development, planning and overall coordination and implementation of the project, data management and report preparation.

XX, the acting chief, of MCCB, WSWRD, is responsible for supervision of project staff affiliated with the MCCB.

XX, the quality assurance manager, is responsible for ensuring that this quality assurance plan meets Division acceptance criteria.

XX, as Project Manager and Work Assignment Manager for the Distribution System Simulator (DSS) is responsible for ensuring that the DSS is operated in accordance with the criteria identified in this QA project plan.  As Acting Chief of the WQMB, XX, is responsible for supervision of project staff affiliated with the WQMB.

XX, the engineering technician, is responsible for ensuring that the DSS is operated in accordance with quality assurance guidelines, labeling of sample vessels, collection of samples, analysis of water samples and record keeping.

XX and XX, the biological science technicians, are responsible for preparation of sample vessels and equipment, analysis of samples for microorganisms and record keeping.

C.	Problem Definition/Background

Research is needed to identify the factors that affect the growth of biofilms and the survival of opportunistic pathogens in drinking water distribution systems.  There is also strong evidence of the interactions between water quality following treatment and regrowth of bacteria within distribution systems.   Bench scale reactor work indicates that the rate of attachment and growth of heterotrophic biofilms is influenced by the amount of bioavailable carbon and materials of construction.  This study seeks to evaluate the rate of attachment and biofilm growth in a distribution system simulator under defined water quality conditions.

D.	Project Description and Schedule

NRMRL has constructed a unique pilot-scale distribution system simulator at its Test and Evaluation facility (T&E).  The simulator consists of 6 independent 90-foot loops of 6-inch diameter ductile iron pipe. Each loop can be operated to represent a point in the distribution system with a different travel time and the loops can be configured in any parallel or series arrangement (Figure 1).  The quality of water entering a loop may be modified by process modifications or by adding specific amounts of known compounds.   An initial set of experiments will be run to examine the dependence of biofilm growth rate on the amount of organic carbon in the feed water.  Periodic sampling of the biofilm coupons will provide information on the amount and rate of biofilm growth as a function of organic carbon and residual disinfectant.

E.	Quality Objectives and Criteria for Measurement Data

This is a basic research project NRMRL Category IV.  Data collected as a result of this work will be used to estimate attachment and growth rates of heterotrophic bacteria within a simulated water distribution system.  Water quality parameters such as the amount of organic carbon as well as other nutrients and oxidizing agents can influence microbial growth.  Also, the materials of construction may also affect microbial attachment and growth.  Therefore, water quality parameters, specifically organic carbon concentrations (two levels 1.0  1.0 mg/L and 5.0  1.0 mg/L) will be quantified to determine if variation of this parameter affects heterotrophic biofilm growth.  Similarly, materials used in the construction of distribution systems will also be evaluated for growth of heterotrophic biofilms on a limited basis (ductile iron and PVC substrates). Results from this work are intended to provide information regarding growth trends rather than for the production of data for model development.

F.	Special Training Requirements

Specialized training or certification is not required for any of the procedures involved in this project.

G.	Documentation and Records

A log book will be used for recording operating conditions, sample dates and times.  Laboratory bench sheets will also be used for recording sample handling and assay results.  Electronic data files will be used for archiving operating data and analytical results.  A final project report in the form of a presentation and/or written report will be generated.

II.	Measurement/Data Acquisition

A.	Experimental Design

A single test loop of the distribution system simulator (DSS) located at the T&E will be used for this project.  Specific operating conditions will be set and maintained for at least one full week prior to sample collection to ensure that system operation is consistent.  Water supplied to the loop system will be obtained from the City of Cincinnati water distribution system which will be augmented with sodium hypochlorite and sodium acetate in accordance with the operating conditions listed below.  A series of slides will be used as a fixed substrate for biofilm formation and growth.  These slides will be submerged in the recycle water tank of the loop system, and retrieved at specified time intervals.  Biofilms from these samples will be assayed for total heterotrophic bacteria using R2A agar spread plates.

Operating conditions:

The following operating conditions will be evaluated:

Hydraulic retention time will be maintained at 24  4 h.

Water velocity will be maintained at 0.3  0.1 m/s (turbulent flow regime).

pH will be as received, i.e., not altered (approximately 8.0  0.3).

Table 1.  Distribution system simulator operating conditions

| Parameter | Series 1 | Series 2 | Series 3 | Series 4 |
| --- | --- | --- | --- | --- |
| Free Cl2 residual (mg/L) | 0.2  0.2 | 2.0  0.2 | 2.0  0.2 | 0.2  0.2 |
| Temperature (C) | 25  3 | 25  3 | 25  3 | 25  3 |
| Organic carbon (mg/L) | 1.0  1.0 | 1.0  1.0 | 5.0  1.0 | 5.0 1.0 |

Free residual chlorine concentrations will be adjusted by addition of a 10 - 7% sodium hypochlorite solution to achieve the stated conditions.

Loop water temperatures will be adjusted by indirect cooling through a shell and tube heat exchanger to achieve the stated conditions.

Organic carbon concentrations of the feed water will be adjusted by addition of sodium acetate or another defined soluble carbon source to achieve the stated conditions.

Operating conditions of the loop will be recorded daily including flow, recirculation rate, pH, ORP, dissolved oxygen, turbidity, free chlorine residual and water temperature.

B.	Sampling Methods Requirements

Microbiological samples:

Samples for microbiological analyses will be collected from the loop discharge (bulk water samples).  All liquid and slide samples will be collected in duplicate.  Biofilms will be collected from slides supported in a polycarbonate holder.  All slides in the holder will be 7.5  0.2 X 2.5  0.1 cm with a total exposed surface area of 37.5  2 cm2 constructed of ductile iron or a non-pourous media (such as glass or polyvinylchloride, PVC).  Slides inserted into the holder will be steam sterilized for 15 minutes at 121 C.  PVC slides will be sterilized by exposure to short wavelength ultraviolet light and then inserted into the steam sterilized polycarbonate holder.  After operating conditions have been stabilized and maintained for a minimum of seven days, the sterile holder with slides will be inserted into the recirculation tank of the DSS loop and the time noted.  Slide and water samples will be collected for analysis according to the schedule shown in Table 2.  Slides will be aseptically removed from the system and placed into new sterile 50 mL tubes containing 45 mL of phosphate buffered dilution water with 0.1 mL of a 10% sodium thiosulphate solution.  These will be assayed within four hours of sample collection for cultureable heterotrophs in accordance with section 9215 A and C of “Standard Methods for the Examination of Water and Wastewater 20th Edition,” or held under refrigeration at 42 C for no more than 24 h prior to initiation of assays.  The surfaces of each slide will be scraped using a flame sterilized stainless steel spatula, and sonicated for 30 s at low power.  Liquid samples will be collected in machine cleaned and steam sterilized polypropylene bottles.

Table 2. Sample collection schedule for microbiological samples †

| Sample | Num. | Code | Container | Volume | Time (h) |
| --- | --- | --- | --- | --- | --- |
| Loop Water | 2 | L2D-0 | Polypropylene | 100 mL | 0 |
| Biofilm: PVC slide | 2 | L2U-2 | Cent. tube | 50mL | 2 |
| Biofilm: iron slide | 2 | L2S-2 | Cent. tube | 50 mL | 2 |
| Biofilm: PVC slide | 2 | L2U-8 | Cent. tube | 50 mL | 8 |
| Biofilm: iron slide | 2 | L2S-8 | Cent. tube | 50 mL | 8 |
| Biofilm: PVC slide | 2 | L2U-24 | Cent. tube | 50 mL | 24 |
| Biofilm: iron slide | 2 | L2S-24 | Cent. tube | 50 mL | 24 |
| Biofilm: PVC slide | 2 | L2U-48 | Cent. tube | 50 mL | 48 |
| Biofilm: iron slide | 2 | L2S-48 | Cent. tube | 50 mL | 48 |
| Biofilm: PVC slide | 2 | L2U-72 | Cent. tube | 50 mL | 72 |
| Biofilm: iron slide | 2 | L2S-72 | Cent. tube | 50 mL | 72 |
| Loop Water | 2 | L2D-168 | Polypropylene | 100 mL | 168 |
| Biofilm: PVC slide | 2 | L2U-168 | Cent. tube | 50 mL | 168 |
| Biofilm: iron slide | 2 | L2S-168 | Cent. tube | 50 mL | 168 |
| Loop Water | 2 | L2D-336 | Polypropylene | 100 mL | 336 |
| Biofilm: PVC slide | 2 | L2U-336 | Cent. tube | 50 mL | 336 |
| Biofilm: iron slide | 2 | L2S-336 | Cent. tube | 50 mL | 336 |
| Loop Water | 2 | L2D-504 | Polypropylene | 100 mL | 504 |
| Biofilm: PVC slide | 2 | L2U-504 | Cent. tube | 50 mL | 504 |
| Biofilm: iron slide | 2 | L2S-504 | Cent. tube | 50 mL | 504 |

†Heterotrophic plate counts, critical measurements, duplicate assays, duplicate samples.

Upon collection of the last set of samples for a series, the next set of operating conditions for a given series will be implemented.

Chemical analysis:

In addition to the above, water samples will also be collected for analyses according to the following schedule:

Table 3.  Sample collection schedule for chemical analyses

| Parameter | Number | Volume (mL) | Time (h) |
| --- | --- | --- | --- |
| Metals* | 1 | 250 | 0 |
| Non-Metals* | 1 | 250 | 0 |
| Organic carbon † | 2 | 45 | 0 |
| Metals* | 1 | 250 | 168 |
| Non-Metals* | 1 | 250 | 168 |
| Organic carbon † | 2 | 45 | 168 |
| Metals* | 1 | 250 | 336 |
| Non-Metals* | 1 | 250 | 336 |
| Organic carbon † | 2 | 45 | 336 |
| Metals* | 1 | 250 | 504 |
| Non-Metals* | 1 | 250 | 504 |
| Organic carbon † | 2 | 45 | 504 |

*Assays considered to be non-critical, collected in pre-cleaned high density polyethylene bottles.

†Critical assays, duplicate samples, collected in carbon free brown borosilicate glass vials.

As noted above, water samples destined for analysis of metals and non-metal constituents will be collected in new pre-cleaned high density polyethylene disposable containers and assayed within 14 days of collection.  Samples collected for total organic carbon analysis are to be collected in new carbon free brown borosilicate glass vials with phenolic caps, and will be assayed within 7 days of collection.  Sample bottles destined for microbiological assays will be polypropylene.  These are machine cleaned with detergent, rinsed with hot water, deionized water, and steam sterilized.  A small volume (0.5 mL) of a sterile 10% sodium thiosulphate solution will be added to these bottles to reduce any residual oxidant in the sample. Slides used for collection of biofilms are described above.  These will be collected in new pre-cleaned sterile 50 mL polypropylene tubes containing 45 mL of sterile phosphate buffer water with 0.1 mL of a 10% sodium thiosulphate solution.  Water samples will be collected from valved sample taps located on the discharge line of the loop recycle tank.  Slide samples will be collected from the polycarbonate sample holder described above and in accordance with the sample schedule (Table 2).  All samples will be assayed as soon as possible following collection.  When assays cannot be completed within four hours of collection, they will be held at 42 C, and assayed within 96 hours of collection.  Excess samples will be discharged to the public wastewater collection system.  Spent sample vessels will be discarded (metals, non-metals, TOC) or re-used (slides, polypropylene bottles) as appropriate.

C.	Sample Handling and Custody Requirements

All sample vessels will be labeled according to the following code:

Loop number:		Loop 2 = L2

Sample location:	Discharge = D, Glass slide = G, PVC slide = P, Iron slide = I

Elapsed time:		0 through 504 h

Date:			collection date

For example, L2D-336-020804 designates a sample from loop #2 collected from the discharge tap at an elapsed time of 336 hours on February 8, 2004.

Analysis of collected samples will be conducted at the T&E facility and at the AWBERC facility laboratories.  Specifically, residual chlorine analysis will be conducted on site at the time of sample collection.  TOC analyses will be conducted at the T&E facility, normally within hours of sample collection.  To ensure that labeled samples are transferred to the analyst in a timely fashion following collection, the samples destined for TOC analysis are placed in the refrigerator in the instrumentation laboratory of the T&E facility.  This ensures that the samples are held under refrigeration prior to sample analysis.  All other samples are placed in a cooler and transported to the AWBERC facility.  Samples for metals and non-metals analysis are placed in the refrigerator in room B22, along with a sample custody sheet.  Samples for microbiological analysis are placed in room 379.

D.	Analytical Methods Requirements

Table 4.  Methods for analysis of water and biofilm samples

| Critical Measurement | QC Procedure | Frequency | Acceptance Criteria | Corrective Actions |
| --- | --- | --- | --- | --- |
| HPC, Method 9215 C 1 using R2A agar | Growth control, known HPC colonies grown on R2A agar | Each new lot of media | growth with no atypical colony morphology | Discard media batch, remake, rerun experiment |
|  | Precision Assessment | Each Sample assessed in triplicate | Any one of 3 counts must have a RPD <70% from other two samples | measurements not meeting this requirement are outliers. |
|  | Sterility check | Each sampling | No growth | Check for sources of contamination, reanalyze sterility check, assess sample results |
| pH, Method 4500-H+ B 1 | Accurcy | See Facility Manual Section 7.5.1 | See Facility Manual Section 7.5.1 | Recalibrate pH electrode using buffers |
| Residual Chlorine, Method 4500-Cl G 1 | Accuracy | Daily, Deionized water blank | No color development | Recalibrate colorimeter. |
| Organic carbon, Method 415.1 2 | Accuracy | See Section II E. | See Section II E. | Recalibrate organic carbon instrument. |

1	American Public Health Association, American Water Works Association, Water Environment Federation. 1998. Standard Methods for the Examination of Water and Wastewater 20th  ed. Washington, D.C.

2 	U.S. Environmental Protection Agency. 1983. Methods for Chemical Analysis of Water and Wastes.  EPA-600/4-79-020 Revised March 1983.  Washington, D.C.

E.	Quality Control/Quality Assurance Requirements

The quality assurance checks for operation of the DSS include calibration and standardization of flow meters, thermocouples, pressure indicators, and on-line monitors which include pH, turbidity, oxidation-reduction potential, residual oxidant, and dissolved oxygen.  The nature and frequency of these checks are identified in the Distribution System Simulator Facility Manual.  The QC checks for heterotrophic plate count (HPC) assays, pH, and residual chlorine measurements are presented in Table 4.  For organic carbon analysis, prior to initiating sample analysis a four point calibration is run using standard solutions containing 0.0, 0.5, 3.0, and 5.0 mg/L of a  lab control samples(LCS) .  A surrogate tap water is analyzed  with a tap+spike.  After every five samples a1.0 mg/L LCS or a 3.0 mg/L standard check is run. Following an analytical series, carbon free water is injected into the instrument.

F.	Instrument/Equipment Testing, Inspection, and Maintenance Requirements

DSS equipment testing, inspection and maintenance will be in accordance with the specifications identified in the  Distribution System Simulator Facility Manual.  Testing inspection and maintenance of equipment required for completion of analytical measurements will be conducted as needed to ensure proper operation, however given the limited duration of this study it is not anticipated that inspections will be required outside of the normal quality assurance checks identified above.

G.	Instrument Calibration and Frequency

The protocols and frequencies of calibration of the instruments, gauges, and meters associated with the DSS are identified in the Distribution System Simulator Facility Manual.  Calibration and standarization of the organic carbon analyzer are identified in Section II. E. of this document.

H.	Inspection/Acceptance Requirements for Supplies and Consumables

Supplies and consumables will be inspected upon receipt by the biological science or engineering technicians.  Acceptance of these will be based upon visually determining that received material is consistent with project requirements, packaging is in tact or there is no obvious damage to the received materials.  Items identified as damaged or contaminated will be declined.

I.	Data Acquisition Requirements (Non-Direct Measurements)

Use of non-direct measurements is not anticipated.  However, if such measurements are used, the source of this information will cited.

J.	Data Management

DSS operating data will be recorded at the time of sample collection in a bound notebook.  Organic carbon and chemical analyses will be recorded electronically and archived by the analysts, in a database or spreadsheet format.  Laboratory bench sheets will be used to record conditions and results of microbiological tests (see attachment).  These sheets will be archived in a binder.  Operating conditions and analytical results will be entered into an electronic spreadsheet (Lotus 1-2-3 or equivalent) and archived.  Data transferred to the spreadsheet will be reviewed for accuracy and consistency with recorded values.  Data reduction and manipulation will be via transfer of electronic data files to alternate spreadsheet formats.

III.	Assessment/Oversight

A.	Assessments and Response Actions

This is a basic research project.  No assessments of the research are planned.

B.	Reports to Management

This work will be conducted over a relatively brief period of time.  A final report detailing the research completed from this effort is planned.  The principle investigator is responsible for preparation of the final report which will be in the form of a presentation (oral or poster) and/or a written article for submission to a scientific journal.  Review of this output will be at the Branch and Division level via normal ORD clearance procedures.

IV.	Data Validation and Usability

A.	Data Review, Validation, and Verification Requirements

System operations data will be collected daily and reviewed on a weekly basis to determine if operating conditions are within range of the quality assurance criteria.  If these conditions are found to be outside the ranges as specified in this document, appropriate actions will be taken to bring systems operations within specifications.  Additionally, data obtained while the system was operating outside of specified ranges will be flagged, and will be reported as out of range.

All samples assayed for critical parameters will be conducted in duplicate and compared against known standards.  Analysis of duplicate samples will be used as a measure of precision while accuracy of individual measurements will be determined based upon comparison of analytical results to known standards.

B.	Validation and Verification Methods

The quality assurance objectives of this project are based upon project requirements and are designed to ensure that the data generated during the project are of known and acceptable quality to achieve the projects technical objectives.

Variables being monitored for this project are identified in Section II. D. of this document.  Validated methods to be used for analysis of total organic carbon, free residual chlorine, and total heterotrophic bacteria are consistent with standard protocols as described in Standard Methods for the Examination of Water and Wastewater, 1998.  Calibration of the monitors used for determinations of pH, and residual chlorine will be completed weekly, in accordance with the Facility Manual (1996).  Samples submitted for HPC analysis will be analyzed in triplicate spiking such samples is not considered feasible, however, for each lot of media produced control plates will be incubated and inspected for growth.  Similarly, dilution water sans sample will be used to inoculate R2A media and will be inspected for growth.  These “control” plates will be used to verify sterility of the media and dilution water.  Growth of microbes on R2A media will be verified by inoculation of the R2A agar plates with water samples containing heterotrophic bacteria.  Failure of the media to produce colonies following incubation as described in Section II B. indicates that the growth medium may be flawed.  If this occurs, data collected during this phase of the experiment will be flagged, the experiment will be terminated, and repeated with freshly prepared media.

Systems operating data will be collected daily (5 days/week) and recorded by the engineering technician or a designee.  Similarly, the engineering technician or a designee will collect all samples according to the schedule described in Section II. C.  Recorded information will be transmitted to the principle investigator or a designee and will be archived in a spreadsheet format.  Manually recorded information will be retained in a file folder and/or a record book which will be maintained by the principle investigator or a designee.  Similarly, results obtained from the analysis of all samples will be archived in a spreadsheet format and manually recorded results will be retained as above.

C.	Reconciliation with Data Quality Objectives

Results from individual analyses will be calculated in accordance with the appropriate standard method.  For samples obtained from coupons, results will be calculated on the basis of surface area.

Precision:

For HPC determinations, countable R2A plates (30-300 colonies/plate) will be recorded and the sample standard deviation will be computed according to the following equation:

standard deviation

Where:

n = the number of analyses

x = each value from an HPC analysis for a given sample.

If any one of the three values has a relative percent difference >70% from either of the other two values, that value will be treated as an outlier.  Relative percent difference will be calculated according to the following equation:

relative percent difference =

Where:

s = sample value

d = duplicate value

Accuracy:

By definition, visible colonies formed on R2A media following a 7-8 day incubation period at 20-28oC will be considered to have developed from individual cells.  To ensure that the R2A media will support growth, a dilute culture of laboratory grown heterotrophic bacteria will be plated out on each lot of media and checked for growth.  If no growth occurs, or if colony morphology is atypical, the media will be discarded.  To ensure that sterility is maintained, sterility controls will be used.  For biofilm samples this means that a sterile coupon will be treated as a biofilm sample, and analyzed for HPC.  Cell growth on these samples indicates that sterility was not maintained, and data collected from that sample session must be adjusted to  account for such growth.

Completeness:

Objectives for data capture are 80% for the critical parameters.  Completeness is defined as the ratio of the number of valid measurements to the total number of measurements planned.

References

American Public Health Association, American Water Works Association, Water Environment Federation. 1998. Standard Methods for the Examination of Water and Wastewater 20th  ed. Washington, D.C.

Facility Manual for NRMRL's Experimental Pipe Loop System, NRMRL internal document. Sam Hayes, NRMRL, Cincinnati, OH  1996.

U. S. Environmental Protection Agency. USEPA. 1983. Methods for the Analysis of Water and Wastes. EPA-60014-79-020 Office of Technology Transfer, Washington, D.C.

Appendix 1

Distribution System Simulator (Ductile Iron Pipe)

Microbiological Analysis Laboratory Bench Sheet

Sample Collection Date:_____________ Time:___________Analyst:___________

Plates Inoculated on:_________________Time:___________Analyst:___________

Plates Enumerated on:_______________Time:___________Analyst:___________

Incubation Temperature, in:____________C;	 out:____________C

|  | R2A Colony Forming Units |
| --- | --- |
| Lab. No. | Sample I.D. | Dilution | Plate A | Plate B | Plate C | Avg. |

Include media control and dilution water control samples for each analytical series.