AMS-02 Weekly Activity Report, October 21, 2005

Upcoming Events:

- AMS General Technical Interchange Meeting (TIM) at CERN October 24-28, 2005 – Geneva

- Modal & Static Test Meeting – October 31, 2005 – IABG, Munich, Germany

- Sine Sweep Test Meeting – November 2, 2005 – INFN, Terni, Italy

- AMS-02 Phase II Safety Review – Date TBD (Schedule under review) – JSC

Upcoming Tests:

- Interface Plate Static Test – Date TBD – Location TBD

- Lower Joint Static Test – Date TBD – Location TBD

- STA Sine Sweep Test – August 2006 – INFN, Terni, Italy

- STA Acoustic Test – October 2006 – ESTEC, Noordwijk, Netherlands

- Full Assembly Modal & Static Tests – January 2007 – IABG, Munich, Germany

General

- ESCG personnel are preparing to support an AMS General Technical Integration Meeting (TIM) at the Center for European Nuclear Research (CERN) in Geneva Switzerland.  Some of the key focuses of this TIM will be: AMS Integration schedule, facilities, and plan; Phase II Flight Safety Package review and clarifications; and sub-detector progress reports.

- ESCG AMS personnel attempted to submit a drawing using the new ESCG Cage code to EDCC.  It was determined that the new signatory list applicable to the ESCG Cage code had not been submitted to the system which caused a rejection of the drawing.  The process is still in work, and it has been determined that the EDCC system is not yet ready for the ESCG Cage Codes.  Charles Crews/SR&QA has promised to notify the DTMs when this change is ready for implementation; and plans to report the latest process changes at an upcoming DTM meeting.

AMS-02 Flight and GSE Hardware Design

- The Thermal Blanket for the Inner Conical Flange is in development.  A number of Interdependent systems exist relative to experiment integration that could affect the final design of the thermal blankets.  These include the Anti-Coincidence Counter Light Splitters and Photomultiplier Tubes, Tracker Thermal Control System plumbing, and Tracker electrical cable bundles. A splinter meeting discussing these issues is scheduled for next week at the Technical Interchange Meeting in Geneva.

- The current placeholder for the design of the inner conical flange blanket has been decided up until further discussion at the TIM.   The outer blanket will most likely be completed after installation of the experiment hardware as this will be a complex system.  Currently too many unknowns exist that preclude a final design solution.

- The PDA Bracket design is in engineering review.  The solid models are tentatively complete.

- A PDA Bracket motion video was produced and provided to project management.

AMS-02 Flight and GSE Manufacturing:

- The Lower USS-02 Center Body Box Joints were aligned relative to the Lower USS Assembly Fixture.  The assembly cannot continue until shims have been fabricated.  The shims are due in from our supplier Monday.  Once they are received they will be forwarded to metal finish for anodizing.  It is expected that shimming can take place by next Friday.  This is approximately one week behind schedule.

- The USS-02 Assembly Sequence was modified based on suggestions from manufacturing.  The change did not modify any drawings.

- Manufacturing personnel tested the stability of jack stands that were reserved for AMS to use to support the Assembly and USS-02.  The jacks were determined to be unacceptable.  A fabrication table, provided by the shop will be used in conjunction with a stable set of jack stands.

- The Trunnion Joints are currently being reworked to fix the Trunnion pin bore.  The bore is undersized due to internal nickel plating that is too thick.

Vacuum Case

- STADCO support is continuing with contracts and weld inspections.

- Work is scheduled to be completed this Monday on the ultrasonic inspections of the VC upper weld.  Once completed, a preliminary report will be written and reviewed to determine if any repairs are necessary to the weld.  This work is being performed at STADCO by ESCG personnel.

- The Thermal Blanket for the Inner Conical Flange is in development.  A number of Interdependent systems exist relative to experiment integration that could affect the final design of the thermal blankets.  These include the Anti-Coincidence Counter Light Splitters and Photomultiplier Tubes, Tracker Thermal Control System plumbing, and Tracker electrical cable bundles. A splinter meeting discussing these issues is scheduled for next week at the Technical Interchange Meeting in Geneva

- The current placeholder for the design of the inner conical flange blanket has been decided up until further discussion at the TIM.   The outer blanket will most likely be completed after installation of the experiment hardware as this will be a complex system.  Currently too many unknowns exist that preclude a final design solution.

GSE & STE

- Redlines were made to the VCTF machining drawing to incorporate additional holes for the transition frames.  The drawing was uploaded to the EDCC for release.  The VCTF can now be released from building 10 to be sent to the vendor for machining.

- Three additional VCTF drawings were submitted to the EDCC for release

Modal & Static Tests

- Presentations are in work to support the upcoming Modal and Static test meeting at IABG in Munich, Germany.

STA Sine Sweep Test / Cold Mass Replica

- Presentations are in work to support the upcoming STA Sine Sweep test meeting at INFN in Terni, Italy.