# MEMORANDUM

To:		Distribution

From:		F. Dylla

Subject:	FEL Upgrade Project Weekly Brief  - October 31 - November 4, 2005

Date:		November 4, 2005

Highlights:

This week we continued to work through our punch list as we interleave the

close-out of shut-down activities with machine start-up activities. Specific accomplishments during the week included:

-	both optical cavities are now under high vacuum

-	we are going through the final wiggler alignment procedures; the chamber alignment was completed and the final wiggler alignment is scheduled for next week when the adjacent vacuum work is completed

-	the optical transport system to Lab 1 has been pumped down

-	RF operation in the first and second cryomodules has been checked out during 2nd shift runs

-	we also put a shift into additional operation of the injector and confirmed that the emittance diagnostic (the “multi-slit”) is operating properly

-	work remains on the 3rd cryomodule which had its second window replaced today after diagnosis of a flange seal problem by the SRF crew. It had just passed initial leak test as of this writing.

-	the shielding blocks behind the FEL vault access door were re-installed today in preparation for resumption of full beam ops

Next week we hope to complete the alignment and vacuum activities and devote more operational time to tuning up the injector

Management:

We prepared FY05 summary and FY06 planning documentation for discussions with ONR on our cost-performance reporting system.

Gwyn Williams and Fred Dylla attended the American Vacuum Society meeting in Boston of which Fred is the Chair of the Board of Trustees and Gwyn serves on the Executive Board of the Surface Science Division.  The meeting presented many opportunities to meet FEL users and discuss research opportunities. 

During these Boston trips, Fred Dylla gave a talk on the FEL Program at MIT’s Center for Accelerator Science and technology (CAST) and Gwyn Williams gave a talk at MIT’s Lincoln Laboratory on the JLab high power THz source.  This meeting was attended by over 100 LL staff and scientists and business development managers from local companies, and aroused a high level of interest in applications of THz for security applications.

WBS 4 (Injector):

This week we received the coil for sputtering a NEG coating on the gun vacuum chamber. We also moved to our lab the IR Demo Gun vacuum chamber for testing the NEG sputtering system. We also ran beam for injector setup centering the beam through the buncher and the solenoid and tested the functionality of the new QJ/VT0F03 downstream of the unit. More work is needed to thread the beam through the unit.

WBS 5 (SRF):

The third harmonic cavity for the 100 mA injector module has completed its initial chemistry cycle and will go through heat treatment today.  Initial TVA testing is scheduled to begin early next week.  A new RF warm window is being designed and procured through AES to accommodate the higher power requirements associated with the change from 30mA to 100mA.

The requirements for the two all metal warm valves have been specified and budgetary costs have been collected.  This information has been passed onto AES for procurement.

A status meeting was held at the vendor’s site regarding the procurement of the fundamental power couplers (FPC).  AES personnel were present during this meeting which included discussions specific to the fabrication and schedule of the four FPC’s.  Delivery is expected mid December.

The design of the beam pipe section between the gun and the cryounit is proceeding along with a goal of achieving high vacuum and minimizing particulate contamination.

The tooling design modification for the cavity tuner apparatus is complete and signed off.  Procurement of the parts needed for this modification shall begin next week.

WBS 8 (Instrumentation):

The majority of this week was spent working with the vacuum folks to rework the beam viewers with new silicon flags. The 3F region was reinstalled and ran into some issues with lighting and focusing on the newer flags.  Student version of work: "It seems as though the upstream cameras are lighting the cameras downstream from them. (i.e. 3F05 can actually be seen well when 3F01 is on). When this does not happen, the viewer that is trying to be focused/aligned is too dim in this region to see. However, upstairs in the control room the image isn't so bad, which is strange because the image on the TV in the vault goes through the same epics that the control room does...:scratches head: With the new targets in it seems like there either needs to be more light on the viewport or the LED's need to be farther away from the viewport so they scatter more light onto the target as opposed to scattering it in the ring surrounding the target and into the beampipe. In fact since we are putting a 1000 angstrom gold mask on a polished silicon wafer we are facing the old problem of looking at a mirror. These features have been resolved. (chuckle). Five new cameras were also fabricated with the new CCD elements. As far as the silicon flags are concerned they will likely be changed again when the holy grail of OTR materials are developed. The requirements are three fold: 1. Must be thin to minimize the radiation created when inserted; 2. must be flat and mirror-like; 3. must have fiducials to calibrate frame grabber system. One plan which is in the works is to coat the 250 micron silicon wafers (50mm dia.) with 5 microns of Cubic Boron Nitride (CBN) (or diamond) then etch the silicon out of the middle, leaving the outer frame as a support then deposit a gold mask for fiducials. A company; 'Le Bond' near Atlanta has agreed to try their tool coating techniques on our wafers. 
   Three sets of BPM Electronics have been installed and are working properly through EPICS, with the embedded IOCs.  Some initial operation data has been taken while the injector was being setup for operations.  Understanding how these electronics operate with the FEL is the next major step in developing this system.  Currently some design changes are being looked into for more remote functionality as far as rebooting the IOC and remote programming. We also updated the database and sequencer for the new Coldfire BPM. The other 5 BPMs are ready to install. The Coldfire chips for these 5 BPM are coded and programmed, and the databases were built too. So we total have 8 new Coldfire BPM, and all the diagnostic screens are created. 
   The Beam Viewer Crate backplane is nearing completion, some minor changes were made to accommodate the control cards design.  These changes are being corrected and then the board will be ready for quotes and ordering.  The Control Card design is making progress, EECAD is currently working on the schematic of the card.  The firmware has been verified to fit in the PLD under the current layout with room for expansion.  Some measurements have been made on the crate to ensure that the boards dimensions are correct.   The reversing switch boards have been ordered and will be ready for installation next week.  Some final parts are being ordered so the switches will be ready for operations next week.  The new dump monitor pcbs are being populated at this time for testing before several are built up.  The enclosure documentation for these electronics has been completed and signed off.  These will be ordered as soon as possible. 
   The design continues on for the general purpose I/O card.  More functionality is being incorporated into the design to take advantage of the Coldfire's functionality.  The parts that will need to deal with the Coldfire directly are being chosen so the software design can begin.  Other details for protecting the inputs and outputs to the Coldfire are being looked at as well.  The pin assignments are nearing completion for the card and more of the electronics design will begin once that is completed. 
   The software for the minimum gap of the wiggler was changed from 16.5mm to 17mm. The firmware minimum gap will be updated next week. The EPICS sequencers for the K value conversions are still under development. Next week the software focus will be on completing and testing the EPICS wiggler controls as well as setting up a new IP address for the 
controller. 
   We are currently trying to wrap up the framegrabber upgrade. Also researching JCA (Java Channel Access) for potential use on future control system applications. This would include its user interface, data processing, and channel access capabilities. JCA maybe the solution to bridging the gap between the control system and database tracking. 
   Progress has been made this week on video system maintenance. Not all of the video system outputs have been recommissioned since the system was upgraded. The optics team has developed a Lab-view program which controls a single video switcher card (F0253). This is an ideal upgrade to our IOC based testing setup. We are working towards setting up a new PC/Lab-View based Video Switcher Test Area. A USB-CanBus interface has been ordered. 
   Progress has also been made in developing EPICS tools which work with the Configuration Control Database. This will allow us to automate information updates with the database from the EPICS screens that we are so familiar with. The goal is to move away from "web-page" interfaces. 
   Installation of a new fabrication/machining station in the FEL I&C trailer also began this week; this station will contain a drill press, vice, hole punch, and several other pieces of hardware which will cut the layover time for fabrication of new chassis panels and increase the productivity and efficiency of the group. This relocation effort is in part motivated by the injector test stand work in the FEL building.

WBS 9 (Beam Transport):

Sextupole (SF)

•	Production measurements revealed that though the high harmonics were very small, the sextupoles have a quadrupole component that is beyond specification.  Magnet test tried torquing the bolts and this changed the value of the quadrupole.  They also tried removing the field clamps to get a feeling on their contribution.  We will evaluate the data today.  In the mean time we put the original sextupoles back into the 2nd Arc.

Replacement Chicane Dipoles (GW)

•	The remaining two units in at Magnet Test, awaiting the testing of Sextupoles before the GWs get measured.

UV Line

• 	STI’s has tested all the QX quads and they should be picked up Monday.  We are working on getting another lab to test two of these quads absolutely on their test stand.

•	Meanwhile, quads are not tested and girder assembly remains on hold.

• 	The NEG Pump cartridge holder design for the second corner UV chamber is on hold.

#### UV Wiggler Progress

•	No progress on the new wiggler vacuum chamber until new funding is available.

Down period issues for the IR portion of the FEL

•	The QJ/VT magnet was fixed by changing the lead configuration.

WBS 10 (Wiggler):

The wiggler chamber, having been straightened last week, was leak checked this week.  A damaged conflat seal was repaired but the chamber would not come down in pressure.  The vacuum crew decided to bake the chamber to get accumulated water out of it.  Once this was  done the chamber was reinstalled and aligned.  The final hookup of the vacuum chambers must be done before final wiggler alignment is carried out.  This should be done by early next week. 
The UV wiggler measurements should restart next week now that the QX measurements are nearly done.

WBS 11 (Optics):

FEL mirrors:
The HR and OC assembly's hot nitrogen purges were terminated and pumpdown commenced.  With the activation of the new NEG pump on the HR, this assembly went quite well.

Other Activities

With work on the optical cavity assemblies complete, attention turned to the optical transport system (OTS).  The OTS was aligned to User Lab 1 (UL1) following test firings of the fast valve.  Optics were installed and aligned in the lab cassettes and turning cans and Brewster windows in UL4 & 6.  In-vacuum wiring was completed or repaired in the UL2 & 4 lab cassettes.  We anticipate pumping down and starting a hot N2 purge of this long section of beamline by COB today, the first time it's been pumped down in 4 years.  I&C pulled cables for the PZTs in each optical cavity assembly so the driver electronics could be moved to the Control Room.  This will speed troubleshooting and commissioning of the fast feedback part of the OCMMS.  A new support for the X-ray cube was designed that permits access to the OCMMS apertures and exterior electronics and lasers.  For the THz pump probe design; the AD9850 Direct digital synthesizer board was brought up with a clock at 50 MHz. The accompanying configuration software was used to achieve phase synchronized outputs down to 1Hz. The 1 GHz ultra low phase noise op amp board was received (spec'ed at -120 dBc/Hz at 100 MHz and

1 KHz deviation).  The drive laser optical transport was aligned to properly illuminate the photocathode.  The Injector could then produce beam, as is reported elsewhere.  Work on the advanced drive laser continued, with an emphasis in characterizing the phase noise.  For the master oscillator, the value read out by the synchronization electronics was as low as 260 fs.  Measurements using the RF group's newly-assembled system yielded a value of 400 fs.  (Both are better than the 1ps spec.)  Nevertheless, we would like to understand the difference in values.  Then we will characterize the phase noise of the entire laser system.  Work to synchronize this laser to the accelerator RF and to transport a high quality mode to the photocathode progresses.  The extended range NIR camera was received, and we've started evaluating it (It appears to give very detailed images), as well as determining how to install it so it can view the surface of the optical cavity mirrors.

Chris Behre (the current Safety Warden) coordinated the safe handling and use of KOH in UL5.

Michelle Shinn presented two JLab proposals to a panel of experts assembled by the Joint Technology Office (JTO) in Albuquerque. She also answered questions as to the role JLab will play in fulfilling work proposed by two industrial firms.

Joe Gubeli wrote a status report on User Lab 4.  The outgassing test chamber is undergoing some redesign, it is now to be made out of 8" diameter pipe. This is to allow a simpler design for custom heat jackets. David Hardy completely disassembled the new turbo pump to fix all of the leaks that happened during the bake out last week. When Dan Oprisko finishes the new chamber and bellows the apparatus will be reassembled and baked out.

Terahertz:

This week we ordered optical components for the imaging experiment, and continued discussions regarding a new superconducting transition edge detector, which should be able to detect individual pulses at 75 MHz.