Excerpts from High Impact Plan

Proposals/initiatives related to forecast uncertainty

Requirements: Warn-on-Forecast

This concept of operations extends predictability of tornadoes by optimally utilizing NEXRAD data in real time which is linked with high resolution stormscale models that use advanced assimilation schemes. The requirement is to couple radar detections with model predictions to get warnings based upon a combination of both – rather than just upon detection, as we do today.

# Activities in Current Program: New program

Gap-MOD-01: Couple high resolutions observations detecting an event with high resolution cloud scale models (WWS) to support “Warn-on Forecast”

Alt-MOD-01:

- Description:  Using experimental high resolution data (e.g., radar) and advanced ensemble data assimilation techniques with high resolution cloud-scale models

- Benefit: Extends warnings through high-resolution prediction coupled with high resolution detection beyond current 13 minutes lead time towards 30 minutes or more

- Responsible Program(s): WWS

- Cost (100%): FY09-13 ($K): 1150, 1150, 638, 638, 638

Variation for Constrained Super Alternative (<100%)

- Description: Reduce request by 50% would allow some progress to be made on several sub-tasks, while other sub-tasks would be delayed.

- Benefit:  Some progress could be made on data quality control, testing of temporal and spatial impact on scanning strategies, testing of parameterization errors on storm scale analysis, and an initial assessment of value radar data assimilation is to warnings. However, delays would include extension of forecast of storm-scale system by 5-10 minutes via reduction of model parameterization error (to FY10), incorporation of polarimetric data into analyses (to FY11), real-time single radar, multi-sensor regional storm-scale analysis and forecasts for NWS forecaster evaluation (to FY12). Finally, these tasks are not achievable without full funding (too much scientific and software development needed): synthesis of mesoscale/cloud scale models into single analysis/forecast system and testing of a real time mesocyclone development. Without full funding for these sub-tasks, NEXRAD radar data would have to be used (vs. PAR data) for Warn on Forecast, reducing the tornado lead time from 30+ min down to the current NWS GPRA estimates

- Reduced Cost (<100%): FY 09-13 ($K): 575, 575, 320, 320, 320

Requirements: Hydrology

# For NOAA in the Carolinas, WW-HYD will coordinate with WW-CEO to develop and transition to operations: new high resolution (in space and time) flash flood and river forecast and warning capabilities, estuary and coastal flood-forecast capabilities and products coupled with improved prediction of water quality, and estuarine ecosystem health using the Tar River Basin and Pamlico Sound in North Carolina for development and operational prototyping.

# Activities in Current Program: New activity

Gap-MOD-03: Apply hydrologic observations and technologies to support high resolution forecast modeling through the proposed "NOAA in the Carolinas" activity.

Alt-MOD-03:

- Description:  This activity will provide uncertainty information to better satisfy needs at the local level; faster transition of research results to applications; improved communication with field personnel and other water agencies; and, new products and services implemented faster by leveraging existing related activities.

- Benefit:  Improved flash and river flood, storm surge and water resource forecasts/warnings in the Tar River Basin, improved ecosystem forecast and management tools in the Tar River Basin and Pamlico Sound, improved protection of life, property and natural resources and an enhancement of public and private decision support capabilities in the coastal zone. In addition, the new capabilities will serve as a prototype for new NOAA capabilities that could be deployed in all coastal zones

- Responsible Program(s): HYD

- Cost (100%): FY09-13 ($K):  2610,  2610, 3090, 3090, 3240

Variation for Constrained Super Alternative (<100%)

- Description:  Same as above but complete over 10 year (vs. 5 year) period

- Benefit:  Same as above

- Reduced Cost (<100%): FY 09-13 ($K):  1305, 1305, 1305, 1305, 1505

Requirements: Probabilistic Information

Users require high quality probabilistic information on which to base business decisions.

# Activities in Current Program: New effort

Gap-MOD-05: High quality probabilistic information

Alt-MOD-05:

- Description: Develop missing parts of multi-scale unified environmental data assimilation, modeling, ensemble forecast, and probabilistic bias correction system capable of delivering high quality probabilistic information on high impact events on various scales.

- Benefit: Provision of automated and seamless suite of probabilistic numerical forecast guidance on scales from hours to seasons

- Base level THORPEX funding addresses gap for global scale forecasts in the 3-14 day range.

- Requested funding to be used to generalize procedures, develop adaptations and run data assimilation/ensemble forecasting/post-processing tests covering local (0-24 hr) and regional (24-72 hrs) scales.

- Integration of longer than 16-day forecasts (weather-climate linkage) is to be covered under Drought and Water Resources plan.

- Responsible Program(s): WWS/THORPEX, EMP

- Cost: FY09-13 ($K):	700, 700, 700, 700, 700

Variation for Constrained Super Alternative (<100%)

- Description: Reduced effort

- Benefit: Reduced from above

- Reduced Cost (<100%): FY 09-13 ($K):: 300, 300, 300, 300, 300

Requirements: Forecast Engine

Establish comprehensive suite of ensemble forecast systems (“forecast engine”) that will facilitate the generation of automated forecast guidance products in the framework of the new NOAA CONOPS as the basis (“forecast engine”) for NOAA operations regarding high impact events:

- Design of new adaptive NWP. This new adaptive system constitutes the backbone of the new NOAA concept of operations. The design of this new system will exploit guidance from the international THORPEX program whose goals are aligned with the new concept of operations, and the development work can build on related NOAA ST&I/THORPEX capabilities:

- Enhanced data assimilation procedures for high impact events

- Enhanced resolution integrations over areas affecting/affected by high impact weather - Run LAM ensembles or Enhance resolution of variable resolution global model

Many of these special procedures will require new dedicated resources in terms of specially designed observing platforms such as UAS, and increased computational facilities.

- Comprehensive suite of ensemble forecast systems. The generation of high quality automated probabilistic forecast guidance requires the use of sophisticated ensemble forecast systems. Ensemble systems are based on an estimate of the initial state by data assimilation methods, using the observing system (link with GEOSS), using state of the art numerical models. An ensemble of forecasts can  predict the future state of the environment and assess the case dependent uncertainty in such forecast. An adaptive and integrated probabilistic product generation suite will require the following components:

  - Global ensemble forecast system (Days 1-16 days, global coverage)

  - Regional ensemble forecast system (Regular runs: days 1-3 days, regional – NA coverage; special high impact runs at longer lead times)

  - Local ensemble forecast system (up to 6-24 hours) for warning type activities, run only in a high impact, adaptive mode

  - Seasonal (climate) ensemble forecast system – to provide numerical guidance extending beyond 16 days

- Statistical post-processing and automated probabilistic product generation

  - Removal of systematic errors from ensemble/probabilistic forecasts

  - Generation of specific products for various high impact events

# Activities in Current Program:

# Support of external and internal NOAA research in ensemble-based data assimilation and numerical modeling through the NOAA/THORPEX grant program

# Multi-center ensemble development (statistical post-processing and product development) for the 3-14 day range on the global scales (North American Ensemble Forecast System)

Gap-MOD-06: Develop missing parts of multi-scale unified environmental data assimilation, modeling, ensemble forecast, and probabilistic bias correction system capable of delivering high quality probabilistic information on high impact events on various scales

Alt-MOD-06:

- Description: Generalize data assimilation, ensemble generation, statistical post-processing and product generation procedures developed by THORPEX for global scales for 3-14 day time range and then adapt and apply them to cover local (0-24 hr) and regional (24-72 hrs) scales. Integration of longer than 16-day forecasts (weather-climate linkage) is to be covered under Drought and Water Resources plan.

- Benefit: Provision of automated and seamless suite of probabilistic numerical forecast guidance on scales from hours to seasons

- Responsible Program(s): WWS/THORPEX, EMP

Cost: FY09-13 ($K):	700, 700, 700, 700, 700

Variation for constrained alternative:

- Description: Adapt procedures only on regional scales, for 24-72 hrs time range

- Benefit: Full benefit for regional forecasting; gap remains on time scales shorter than a day.

- Constrained alternative cost FY09-13 ($K): 300, 300, 300, 300, 300

# Requirements: Hazardous Weather

# Forecasters have a requirement for quick infusion of latest science and technology into operations and test beds provide the most optimal solution to this need.

# Activities in Current Program: New Program

Gap-T&B-01: Develop new warning guidance tools from multiple sensors and numerical cloud-scale models in Hazardous Weather Test (HWT) Bed

Alt-T&B-01:

- Description: The HWT is the newly established formal project name given to the annual joint NWS/NCEP and NSSL research to operations activity held during the last decade.  Recently the HWT was strengthened by a Congressional action that provided funding for NASA’s SPoRT project and the University of Alabama’s severe weather research program, both in Huntsville, AL to join the HWT and focus on severe weather including supercell tornadoes and tornadoes from tropical systems (note: VORTEX-II not included here)

- Benefit: Improves basic understanding of severe weather processes through sharing of observations taken from equipment owned by each partner.  Alabama partners are better positioned to study tornadoes and hazardous weather associated with tropical systems, while the Oklahoma partners are better positioned to study classical mid-western supercells. Together improvements can be made in warning and short-term forecast products for both NCEP’s Storm Prediction Center and Forecast Offices.

- Responsible Program(s): WWS

- Cost (100%): FY09-13 ($K): 538, 538, 538, 538, 538

Variation for Constrained Super Alternative (<100%)

- Description: At a 50% reduction in requested new funding the HWT could continue to function with a chief scientist position leading the effort on the NSSL side, along with 50% of an IT support person and funds for computer time, hardware, and software.

- Benefit: A 50% reduction would allow the HWT to continue to function in support of both NCEP/SPC and the Forecast Offices.  It would provide coordination of a visiting scientist/forecaster/researcher program (funded by the visitor’s home organization, unless the LFW request for travel funds is successful). A robust HWT allows researchers and operational forecasters to concentrate on specific forecast problems, analyze how the models behave under certain circumstances relevant to the forecast problems, and to find ways to improve the tools forecasters have to address the problem.

- Reduced Cost (<100%): FY 09-13 ($K):  269, 269, 269, 269, 269

# Requirements: Probabilistic products

Sophisticated Partners and Users demand probabilistic information to make informed business case decision to support commerce, transportation and prepare for high impact events.

# Activities in Current Program: New program

Gap-T&B-02:  Guidance for developing probabilistic based products

Alt-T&B-02:

- Description: This activity includes two components.  First, at ESRL/GSD, new warning techniques are being developed based upon probabilities provided by WRF-based ensemble data assimilation systems.  Second, at NSSL, NCEP-scale models are being run using ensemble Kalman filter techniques to provide, among other things, boundary conditions for Warn-on-Forecast models.

- Benefit: Probabilistic techniques quantify uncertainty in forecasts and warnings in support of decision support systems and Warn-on-Forecast research.

- Responsible Program(s): WWS

- Cost (100%): FY09-13 ($K): 880, 1130, 1130, 1130, 1130

Variation for Constrained Super Alternative (<100%)

- Description:  At a 50% reduction in requested new funds, the OAR labs could make progress moving NWS toward its goal of using probabilistic forecasts to drive for decision support systems.

- Benefit: Progress by NSSL could be made on both statistical post-processing tools for ensemble forecasting systems and an ensemble Kalman filter data assimilation system, but at a slower pace. Merging regional ensemble systems with local convective-scale ensembles would need to be dropped. Assuming delayed advances in diabatic initialization and QPE-QPF blending, ESRL/GSD research would require forecasters to rely on extrapolation techniques during WRF model spin-up (1-3 hrs)

- Reduced Cost (<100%): FY 09-13 ($K):  440, 565, 565, 565, 565