## SCC List
Standard Cost Categories for Capital Projects
(Rev.9, Feb. 6, 2007)
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES

## SCC Definitions
Standard Cost Categories for Capital Projects D E F I N I T I O N S |  | NOTE: The SCC cost breakdown is based on a traditional Design Bid Build model. If your project is Design Build, to the best of your ability, separate construction costs from design, administration, testing, etc. Put all construction costs in 10 through 50. Put design, administration, testing, etc. in 80 Professional Services.
(Rev.9, Feb. 6, 2007)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | Include guideway and track costs for all transit modes (Heavy rail, light rail, commuter rail, BRT, rapid bus, bus, monorail, cable car, etc.) The unit of measure is route miles of guideway, regardless of width. As associated with the guideway, include costs for rough grading, excavation, and concrete base for guideway where applicable. Include all construction materials and labor regardless of whom is performing the work. In your written description of the scope and in supporting graphic diagrams, indicate whether busway or rail track is single, double, triple, relocated, etc. Put guideway and track elements associated with yards in 30 Support Facilities below.
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure | Include foundation excavation; guideway structures including caissons, columns, bridges, viaducts, cross-overs, fly-overs.
10.05 | Guideway: Built-up fill | Include construction of earthen berms.
10.06 | Guideway: Underground cut & cover | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.07 | Guideway: Underground tunnel | Include tunneling by means of a tunnel boring machine, drill blasting, mining, and immersed tube tunneling; tunnel structure and finishes.
10.08 | Guideway: Retained cut or fill | Include excavation, retaining walls, backfill, underground guideway structure and finishes.
10.09 | Track: Direct fixation | Include rails, connectors.
10.1 | Track: Embedded | Include rails, ties; ballast where applicable
10.11 | Track: Ballasted | Include rails, ties and ballast.
10.12 | Track: Special (switches, turnouts) | Include transitional curves.
10.13 | Track: Vibration and noise dampening | Include upcharge for vib/noise dampening to any track condition above.
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | As associated with stations, include costs for rough grading, excavation, station structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, station power, lighting, public address/customer information system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include all construction materials and labor regardless of whom is performing the work.
Put guideway and track associated with stations in 10 Guideway & Track Elements above.
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform | Include station structures including caissons, columns, platforms, superstructures, etc.
20.03 | Underground station, stop, shelter, mall, terminal, platform | Include retaining walls, backfill, structure.
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development | Per FTA's Joint Development Guidance, "Joint development is any income-producing activity with a transit nexus related to a real estate asset in which FTA has an interest. . .Joint development projects are commercial, residential, industrial, or mixed-use developments that are induced by or enhance the effectiveness of transit projects. . ." See http://www.fta.dot.gov/17973_18027_ENG_HTML.htm
20.06 | Automobile parking multi-story structure | Include retaining walls, backfill, structure.
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | As associated with support facilities, include costs for rough grading, excavation, support structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, facility power, lighting, public address system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include fueling stations. Include all construction materials and labor regardless of whom is performing the work.
Where a support facility shares the structure with a station, its cost may be included with station cost. Identify this with a note.
Except for guideway and track associated with a yard, include all guideway and track costs associated with support facilities in 10 Guideway & Track Elements above.
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility | Include service, inspection, and storage facilities and equipment.
30.03 | Heavy Maintenance Facility | Include heavy maintenance and overhaul facilities and equipment.
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track | Include yard construction, guideway and track associated with yard.
40 SITEWORK & SPECIAL CONDITIONS |  | Include all construction materials and labor regardless of whom is performing the work.
40.01 | Demolition, Clearing, Earthwork | Include project-wide clearing, demolition and fine grading.
40.02 | Site Utilities, Utility Relocation | Include all site utilities - storm, sewer, water, gas, electric.
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Include underground storage tanks, fuel tanks, other hazardous materials and treatments, etc.
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | Include other environmental mitigation not listed.
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping | Include sidewalks, paths, plazas, landscape, site and station furniture, site lighting, signage, public artwork, bike facilities, permanent fencing.
40.07 | Automobile, bus, van accessways including roads, parking lots | Include all on-grade paving.
40.08 | Temporary Facilities and other indirect costs during construction | As a general rule and to the extent possible, appropriately allocate indirect costs among the construction costs in Categories 10 through 50. Where that is not possible, include in 40.08 Temporary Facilities costs for mobilization, demobilization, phasing; time and temporary construction associated with weather (heat, rain, freezing, etc.); temporary power and facilities; temporary construction, easements, and barriers for storm water pollution prevention, temporary access and to mitigate construction impacts; project and construction supervision; general conditiions, overhead, profit. NOTE: Include contractor's general liability and other insurance related to construction such as builder's risk in Cats. 10 - 50, not in 80 Professional Services below.
50 SYSTEMS |  | Include all construction materials and labor regardless of whom is performing the work.
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection | Include signal prioritization at intersections.
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications | Include passenger information systems at stations and on vehicles (real time travel information; static maps and schedules). Include equipment to allow communications among vehicles and with central control.
50.06 | Fare collection system and equipment | Include fare sales and swipe machines, fare counting equipment.
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS |  | Include professional services associated with the real estate component of the project. These costs may include agency staff oversight and administration, real estate and relocation consultants, legal counsel, court expenses, insurance, etc.
60.01 | Purchase or lease of real estate | If the value of right-of-way, land, and existing improvements is to be used as local match to the Federal funding of the project, include the total cost on this line item. In backup documentation, separate cost for land from cost for improvements. Identify whether items are leased, purchased or acquired through payment or for free. Include the costs for permanent surface and subsurface easements, trackage rights, etc.
60.02 | Relocation of existing households and businesses | In compliance with Uniform Relocation Act.
70 VEHICLES (number) |  | Include professional services associated with the vehicle component of the project. These costs may include agency staff oversight and administration, vehicle consultants, design and manufacturing contractors, legal counsel, warranty and insurance costs, etc.
70.01 | Light Rail | Include light rail and streetcar rail using electric, diesel or other power supply.
70.02 | Heavy Rail
70.03 | Commuter Rail | Include locomotives (diesel, electric, or other), trailer cars, self-propelled multiple units (EMU electric or DMU diesel, or other power supply)
70.04 | Bus | Includes "rubber-tired" buses and trolleys including new, used, historic replica, articulated, using electric, diesel, dual-power, or other power supply.
70.05 | Other | Include Vans, Sedan/Station Wagon, Cable Car, People Mover, Monorail, Car/Inclined Railway, Ferry Boat, Transferred Vehicle
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES |  | See Cats. 60 and 70 for professional services related to ROW/Land and Vehicles. Cat. 80 includes all professional, technical and management services (and related professional liability insurance costs) related to the design and construction of fixed infrastructure (Cats. 10 - 50) during the preliminary engineering, final design, and construction phases of the project. This includes environmental work, design, engineering and architectural services; specialty services such as safety or security analyses; value engineering, risk assessment, cost estimating, scheduling, Before and After studies, ridership modeling and analyses, auditing, legal services, administration and management, etc. by agency staff or outside consultants. As required, use back-up worksheets to track detailed costs within each of the line items. (Note that costs for alternatives analysis and NEPA work done before FTA approval to enter preliminary engineering (PE), regardless of funding source, are not included in an FFGA and therefore, should not be included in the Standard Cost Category worksheets. For example, on one and the same grant, costs incurred prior to FTA approval to enter PE should be omitted from these worksheets whereas costs incurred after FTA approval to enter PE should be included.)
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up | Include start up and training. Include in Cats. 10 - 50 above access and protection work by agency staff or outside contractors.
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY |  | Includes unallocated contingency, project reserves. Document allocated contingencies for individual line items on the Main worksheets.
Subtotal (10 - 90)
100 FINANCE CHARGES |  | Include finance charges expected to be paid by the project sponsor/grantee prior to either the completion of the project or the fulfillment of the New Starts funding commitment, whichever occurs later in time. Finance charges incurred after this date should not be included in Total Project Cost. (See FFGA Circular FTA C5200.1A Chapter III for additional information.) Derive finance charges from the New Starts project's financial plan, based on an analysis of the sources and uses of funds. The amount and type of debt financing required and revenues available determine the finance charges. By year, compute finance charges in year-of-expenditure (YOE) dollars. On the Inflation Calculation to YOE worksheet enter the finance charges for the appropriate years.
Total Project Cost (10 - 100)

## TEAM Scopes ALIs
14-Series TEAM Scopes / Activity Line Items Required for all grants that serve a Capital Project
(Rev.9, Feb. 6, 2007)
1. HOW DO THE SCC AND TEAM RELATE? TEAM is for grants management. Many grants can serve a capital project -- e.g. CMAQ, 5307, 5309, etc. The Standard Cost Categories (SCC) are for cost management, day to day as well as at important milestones. To manage capital project costs use the SCC worksheets, back up sheets, detailed cost estimates, etc. At important milestones, "paperclip" the SCC worksheets to the applicable grants in TEAM. TEAM and the SCC support each other but TEAM doesn't duplicate the level of information in the SCC. The idea is to keep grants budgets simple and focus on cost management. 2. WHEN SHOULD I USE THE 14-SERIES? Use it for capital projects. For New Starts project, use it from the very first grant that funds Preliminary Engineering, and include all grants issued through the FFGA; these grants may be small or large and may derive funding from diverse sources such as CMAQ, 5307, 5309 Fixed Guideway Mod, 5309 New Starts, Federal Non-Transportation funding from HUD, Defense, etc. 3. HOW IS THE 14-SERIES ORGANIZED AND WHY? The 14-Series has only 10 pairs of Scopes and ALIs. This is intentionally simple. Do not mix and match Scopes and ALIs or change the standard text. For example, put only guideway costs under the Guideway Scope. If kept simple, the information will be correct and will produce a reliable database at the program-wide level. 4. WHAT'S WITH THE VEHICLES? For now, use 14-Series SCOPE (14070) and 13-Series ALIs. | 14010 | GUIDEWAY & TRACK ELEMENTS |  | .01 Bus STD 40 FT
| 140110 | Guideway & Track Elements |  | .02 Bus STD 35 FT
.03 Bus 30 FT
| 14020 | STATIONS, STOPS, TERMINALS, INTERMODAL |  | .04 Bus < 30 FT
| 140220 | Stations, Stops, Terminals, Intermodal |  | .05 Bus School
.06 Bus Articulated
| 14030 | SUPPORT FACILITIES: YARDS, SHOPS, ADMIN BLDGS |  | .07 Bus Commuter / Suburban
| 140330 | Support Facilities: Yards, Shops, Admin Bldgs |  | .08 Bus Intercity
.09 Bus Trolley STD
| 14040 | SITEWORK & SPECIAL CONDITIONS | Engineering & Design | .10 Bus Trolley Artic.
| 140440 | Sitework & Special Conditions | 13.11.XX | .11 Bus Double Deck
.12 Bus Used
| 14050 | SYSTEMS | Purchase - Replacement | .13 Bus School Used
| 140550 | Systems | 13.12.XX | .14 Bus Dual Mode
.15 Vans
| 14060 | ROW, LAND, EXISTING IMPROVEMENTS | Purchase - Expansion | .16 Sedan / Station Wagon
| 140660 | ROW, Land, Existing Improvements | 13.13.XX | .20 Light Rail Cars
.21 Heavy Rail Cars
| 14070 | VEHICLES | Rehabilitation / Rebuild | .22 Commuter Rail Self Propelled Electric
| 13____ | Note! Please use the 13-Series ALIs for vehicles. | 13.14.XX | .23 Commuter Rail Car Trailer
.24 Commuter Rail Locomotive Diesel
| 14080 | PROFESSIONAL SERVICES | Mid Life Rebuild (Rail) | .25 Commuter Rail Locomotive Electric
| 140880 | Professional Services | 13.15.XX | .26 Commuter Rail Cars Used
.27 Commuter Rail Locomotive Used
| 14090 | UNALLOCATED CONTINGENCY | Lease - Replacement | .28 Commuter Rail Self Propelled - Diesel
| 140990 | Unallocated Contingency | 13.16.XX | .30 Cable Car
.31 People Mover
| 14100 | FINANCE CHARGES | Lease - Expansion | .32 Car, Incline Railway
| 141010 | Finance Charges | 13.18.XX | .33 Ferry Boats
.39 Transferred Vehicles
|  |  | Vehicle Overhaul | .40 Spare Parts/Assoc.Capital
|  |  | 13.17.00 | / Maintenance Items

## BUILD Main
M A I N W O R K S H E E T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.9, Feb. 6, 2007)
Project Sponsor Name | [6 empty] | Today's Date |  | 2007-02-06
Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2007
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2012
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 9 | 100000 | 12000 | 112000 | 12444.4444 | 37.66% | 24.39% | 125759.3234 | 1.1229
10.01 | Guideway: At-grade exclusive right-of-way | 9 | 100000 | 12000 | 112000 | 12444.4444 |  |  | 125759.3234
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) |  |  |  | 0 |  |  |  | 0
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  |  |  | 0
10.04 | Guideway: Aerial structure |  |  |  | 0 |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0 |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0 |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0 |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0 |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0 |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0 |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0 |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0 |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0 |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 18 | 100000 | 20000 | 120000 | 6666.6667 | 40.35% | 26.14% | 136781.3446 | 1.1398
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 18 | 100000 | 20000 | 120000 | 6666.6667 |  |  | 136781.3446
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0 |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0 |  |  |  | 0
20.05 | Joint development |  |  |  | 0 |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0 |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0 |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 9 | 10000 | 2000 | 12000 | 1333.3333 | 4.035% | 2.614% | 13859.3239 | 1.1549
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0 |  |  |  | 0
30.02 | Light Maintenance Facility |  | 10000 | 2000 | 12000 |  |  |  | 13859.3239
30.03 | Heavy Maintenance Facility |  |  |  | 0 |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0 |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0 |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 9 | 21420 | 2800 | 24220 | 2691.1111 | 8.144% | 5.275% | 25937.7469 | 1.0709
40.01 | Demolition, Clearing, Earthwork |  | 920 | 100 | 1020 |  |  |  | 1092.3411
40.02 | Site Utilities, Utility Relocation |  | 5500 | 500 | 6000 |  |  |  | 6425.536
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0 |  |  |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 4000 | 200 | 4200 |  |  |  | 4497.8752
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0 |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 11000 | 2000 | 13000 |  |  |  | 13921.9946
40.07 | Automobile, bus, van accessways including roads, parking lots |  |  |  | 0 |  |  |  | 0
40.08 | Temporary Facilities and other indirect costs during construction |  |  |  | 0 |  |  |  | 0
50 SYSTEMS |  | 9 | 25490 | 3700 | 29190 | 3243.3333 | 9.815% | 6.358% | 33543.087 | 1.1491
50.01 | Train control and signals |  | 8000 | 2000 | 10000 |  |  |  | 11491.2939
50.02 | Traffic signals and crossing protection |  | 2500 | 500 | 3000 |  |  |  | 3447.3882
50.03 | Traction power supply: substations |  | 7500 | 500 | 8000 |  |  |  | 9193.0352
50.04 | Traction power distribution: catenary and third rail |  | 5500 | 500 | 6000 |  |  |  | 6894.7764
50.05 | Communications |  | 1000 | 100 | 1100 |  |  |  | 1264.0423
50.06 | Fare collection system and equipment |  | 990 | 100 | 1090 |  |  |  | 1252.551
50.07 | Central Control |  | 0 | 0 | 0 |  |  |  | 0
Construction Subtotal (10 - 50) |  | 9 | 256910 | 40500 | 297410 | 33045.5556 | 100% | 64.78% | 335880.8258
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 9 | 17000 | 4000 | 21000 | 2333.3333 |  | 4.574% | 23582.1369 | 1.123
60.01 | Purchase or lease of real estate |  | 17000 | 4000 | 21000 |  |  |  | 23582.1369
60.02 | Relocation of existing households and businesses |  |  |  | 0 |  |  |  | 0
70 VEHICLES (number) |  | 10 | 25404 | 8000 | 33404 | 3340.4 |  | 7.275% | 37880.9088 | 1.134
70.01 | Light Rail | 10 | 25404 | 8000 | 33404 | 3340.4 |  |  | 37880.9088
70.02 | Heavy Rail |  |  |  | 0 |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0 |  |  |  | 0
70.04 | Bus |  |  |  | 0 |  |  |  | 0
70.05 | Other |  |  |  | 0 |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0 |  |  |  | 0
70.07 | Spare parts |  |  |  | 0 |  |  |  | 0
80 PROFESSIONAL SERVICES |  | 9 | 65895 | 19000 | 84895 | 9432.7778 | 28.54% | 18.49% | 90199.8485 | 1.0625
80.01 | Preliminary Engineering |  | 12000 | 3000 | 15000 |  |  |  | 15937.3076
80.02 | Final Design |  | 17395 | 3000 | 20395 |  |  |  | 21669.4259
80.03 | Project Management for Design and Construction |  | 9000 | 3000 | 12000 |  |  |  | 12749.8461
80.04 | Construction Administration & Management |  | 9000 | 3000 | 12000 |  |  |  | 12749.8461
80.05 | Insurance |  | 2500 | 2000 | 4500 |  |  |  | 4781.1923
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 3000 | 1000 | 4000 |  |  |  | 4249.9487
80.07 | Surveys, Testing, Investigation, Inspection |  | 3000 | 1000 | 4000 |  |  |  | 4249.9487
80.08 | Start up |  | 10000 | 3000 | 13000 |  |  |  | 13812.3332
Subtotal (10 - 80) |  | 9 | 365209 | 71500 | 436709 | 48523.2222 |  | 95.12% | 487543.7201
90 UNALLOCATED CONTINGENCY |  |  |  |  | 21971 |  |  | 4.785% | 24559.0492 | 1.1178
Subtotal (10 - 90) |  | 9 |  |  | 458680 | 50964.4444 |  | 99.9% | 512102.7693
100 FINANCE CHARGES |  |  |  |  | 454.7199 |  |  | 0.09904% | 500 | 1.0996
Total Project Cost (10 - 100) |  | 9 |  |  | 459134.7199 | 51014.9689 |  | 100% | 512602.7693 | 1.1165
Allocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 19.58%
Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 6.016%
Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 25.59%
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | 5.031%
YOE Construction Cost per Mile (X000) | [8 empty] | 37320.0918
YOE Total Project Cost per Mile Not Including Vehicles (X000) | [8 empty] | 52746.8734
YOE Total Project Cost per Mile (X000) | [8 empty] | 56955.8633
Note on J3: Year of Base Year Dollars should match the year in "Today's Date."
Note on J6: YOE Dollars automatically arrive from Inflation Worksheet.
Note on F76: Enter finance charges on Inflation Worksheet.
Note on J8: YOE costs for individual line items within a Category are derived as a percentage of the YOE cost of the Category.

## Project Description
P R O J E C T D E S C R I P T I O N - B U I L D A L T E R N A T I V E |  |  |  | (Rev.9, Feb. 6, 2007)
Project Sponsor Name |  |  | Today's Date | 2007-02-06
Project Name and Location
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops)
Describe elements of the project and/or the entire project to explicate the unit costs shown on the Main Worksheet. As an example -- a project may include ten miles of on-grade guideway and one-quarter mile of aerial structure for a river crossing. Because of its uniqueness within the project, the aerial component (two-tracks) may have a high unit cost when compared with the unit cost for a ten-mile long two-track aerial structure. The unit cost for the longer aerial structure benefits from the economy of scale. Mention precedents and reference points used in the development of costs for this project. Mention other aspects of this project that were important considerations in estimating costs. These could include the physical context and site constraints; design parameters; institutional, contracting and procurement conditions; project schedule, etc. Below, expand lines and delete lines as required to accommodate your commentary.
10 GUIDEWAY & TRACK ELEMENTS (route miles)
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure | For each garage provide station name, number of floors below/above grade, total number of parking spaces
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots | For each parking lot provide station name and number of parking spaces
40.08 | Temporary Facilities and other indirect costs during construction
50 SYSTEMS
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
Construction Subtotal (10 - 50)
60 ROW, LAND, EXISTING IMPROVEMENTS
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
70 VEHICLES (number)
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
Subtotal (10 - 80)
90 UNALLOCATED CONTINGENCY
Subtotal (10 - 90)
100 FINANCE CHARGES
Total Project Cost (10 - 100)
Allocated Contingency as % of Base Yr Dollars w/o Cont.
Unallocated Contingency as % of Subtotal (10 - 80)
YOE Construction Cost per Mile (X000)
YOE Total Project Cost per Mile Not Including Vehicles (X000)
YOE Total Project Cost per Mile (X000)

## Inflation
I N F L A T I O N W O R K S H E E T | [5 empty] | (Rev.9, Feb. 6, 2007)
Project Sponsor Name |  |  |  | Today's Date |  | 2007-02-06
Project Name and Location |  |  |  | Yr of Base Year $ |  | 2007
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops) |  |  |  | Yr of Revenue Ops |  | 2012
Below, show all project costs in the year in which they occurred or are planned to occur through the completion of the project or the fulfillment of the New Starts funding commitment, whichever is expected to occur later in time.
BASE YEAR DOLLARS (X$000) | Base Yr Dollars | Double-Check Total | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 112000 | 112000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22000 | 20000 | 50000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 120000 | 120000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 50000 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 24220 | 24220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 11595 | 7025 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 29190 | 29190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19190 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 21000 | 21000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 9000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 33404 | 33404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12000 | 12000 | 9404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES | 84895 | 84895.2976 | 1029.4373 | 2059.9518 | 2060.3818 | 2060.1674 | 2060.4084 | 2059.9511 | 2065 | 5000 | 11000 | 15000 | 15000 | 15000 | 10500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 21971 | 21971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2228 | 2588 | 2000 | 2000 | 3000 | 10155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 454.7199 | 454.7199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.8523 | 93.8037 | 90.851 | 87.9913 | 85.2216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 459134.7199 | 459135.0175 | 1029.4373 | 2059.9518 | 2060.3818 | 2060.1674 | 2060.4084 | 2059.9511 | 2065 | 7228 | 18684.8523 | 50688.8037 | 96115.851 | 164877.9913 | 108144.2216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Below insert estimated inflation rates for each year. For 2007 and beyond, the YOE dollars are calculated automatically. For 2006 and previous years, the Base Year dollars are automatically inflated to reflect the value of past expenditures in 2007 dollars.
Inflation Rate |  |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325 | 0.0325
Compounded Inflation Factor |  |  | 1.2329 | 1.197 | 1.1621 | 1.1282 | 1.0954 | 1.0635 | 1.0325 | 1 | 1.0325 | 1.0661 | 1.1007 | 1.1365 | 1.1734 | 1.2115 | 1.2509 | 1.2916 | 1.3336 | 1.3769 | 1.4216 | 1.4678 | 1.5156
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 125759.3234 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23453.2375 | 22014.0616 | 56823.7964 | 23468.2279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 136781.3446 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33021.0923 | 56823.7964 | 46936.4558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 13859.3239 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6818.8556 | 7040.4684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 25937.7469 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5162.5 | 12360.9222 | 7732.4391 | 681.8856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 33543.087 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21808.9731 | 11734.114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 23582.1369 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11007.0308 | 10228.2834 | 2346.8228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 37880.9088 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13208.4369 | 13637.7111 | 11034.7608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES | 90199.8485 |  | 835 | 1721 | 1773 | 1826 | 1881 | 1937 | 2000 | 5000 | 11357.5 | 15990.8437 | 16510.5462 | 17047.1389 | 12320.8197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 24559.0492 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2228 | 2672.11 | 2132.1125 | 2201.4062 | 3409.4278 | 11915.9927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 512602.7693 |  | 835 | 1721 | 1773 | 1826 | 1881 | 1937 | 2000 | 7228 | 19292.11 | 54037.116 | 105795.0131 | 187379.8682 | 126897.662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on E33: Enter Finance Charges on this line
Note on L21: In the Base Year no inflation multiplier is used.
Note on E24: For past years, enter the actual dollars spent in each year.
Note on K8: Please note that costs incurred in the past would cost more if they were incurred in 2007. Using a 3% inflation rate, an item that cost a dollar in 2006 would cost $1.03 in 2007.

## Schedule
S C H E D U L E |  |  | (Rev.9, Feb. 6, 2007)
Project Sponsor Name | Today's Date |  | 2007-02-06
Project Name and Location | Yr of Base Year $ |  | 2007
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops) | Yr of Revenue Ops |  | 2012
|  | Start Date | End Date | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Preliminary Engineering |  | 2005-01-01 | 2006-06-01
Design Build and Baseline Alternatives
Cost estimating, scheduling, ridership forecasting
Reviews
Develop FEIS, receiving Record of Decision
Submit request / receive FTA approval to enter Final Design
Final Design |  | 2006-06-01 | 2008-09-01
Develop design/contract docs for Build Alternative
Cost estimating, scheduling, ridership forecasting
Reviews
Submit request / receive FTA approval for FFGA
Bid period and award
Construction |  | 2008-09-01 | 2012-01-01
Construction of Fixed Infrastructure
ROW, Land, Existing Improvements, Relocation
Vehicle acquisition and testing
Revenue Ops / Closeout of Project |  | 2012-01-01 | 2014-03-01
Revenue Operations
Before and After Study: Two years post Rev Ops
Fulfillment of the New Starts funding commitment
Completion of project close-out, resolution of claims

## BUILD Annualized
A N N U A L I Z E D C O S T - B U I L D A L T E R N A T I V E | [8 empty] | (Rev.9, Feb. 6, 2007)
Project Sponsor Name | [6 empty] | Today's Date |  | 2007-02-06
Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2007
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2012
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Years of Useful Life | Annualization Factor (based on 7% rate) [.07/1 - (1.07)^-no. yrs] | Annualized Cost (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 9 | 112000 | 31970.1422 | 7000 | 150970.1422 |  |  | 10570.1544
10.01 | Guideway: At-grade exclusive right-of-way | 9 | 112000 | 31970.1422 | 7000 | 150970.1422 | 125 | 0.070015 | 10570.1544
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0 | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 35 | 0.077234 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 18 | 120000 | 34253.7238 | 10000 | 164253.7238 |  |  | 11599.5203
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 18 | 120000 | 34253.7238 | 10000 | 164253.7238 | 70 | 0.07062 | 11599.5203
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.05 | Joint development |  | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.06 | Automobile parking multi-story structure |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
20.07 | Elevators, escalators |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 12000 | 3425.3724 | 0 | 15425.3724 |  |  | 1117.7202
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.02 | Light Maintenance Facility |  | 12000 | 3425.3724 |  | 15425.3724 | 50 | 0.07246 | 1117.7202
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 24220 | 6913.5433 | 1000 | 32133.5433 |  |  | 2681.5812
40.01 | Demolition, Clearing, Earthwork |  | 1020 | 291.1567 |  | 1311.1567 | 125 | 0.070015 | 91.8005
40.02 | Site Utilities, Utility Relocation |  | 6000 | 1712.6862 |  | 7712.6862 | 125 | 0.070015 | 540.0027
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | 0 |  | 0 | 125 | 0.070015 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 4200 | 1198.8803 |  | 5398.8803 | 125 | 0.070015 | 378.0019
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 13000 | 3710.8201 | 1000 | 17710.8201 | 20 | 0.094393 | 1671.7761
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
40.08 | Temporary Facilities and other indirect costs during construction |  | 0 | 0 |  | 0 | 100 | 0.070081 | 0
50 SYSTEMS |  |  | 29190 | 8332.2183 | 500 | 38022.2183 |  |  | 3007.3458
50.01 | Train control and signals |  | 10000 | 2854.477 | 500 | 13354.477 | 30 | 0.080586 | 1076.1893
50.02 | Traffic signals and crossing protection |  | 3000 | 856.3431 |  | 3856.3431 | 30 | 0.080586 | 310.7688
50.03 | Traction power supply: substations |  | 8000 | 2283.5816 |  | 10283.5816 | 50 | 0.07246 | 745.1468
50.04 | Traction power distribution: catenary and third rail |  | 6000 | 1712.6862 |  | 7712.6862 | 30 | 0.080586 | 621.5376
50.05 | Communications |  | 1100 | 313.9925 |  | 1413.9925 | 20 | 0.094393 | 133.4709
50.06 | Fare collection system and equipment |  | 1090 | 311.138 |  | 1401.138 | 25 | 0.085811 | 120.2324
50.07 | Central Control |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
Construction Subtotal (10 - 50) |  |  | 297410 | 84895 | 18500 | 400805 |  |  | 28976.3218
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 21000 |  | 1000 | 22000 |  |  | 1540.3271
60.01 | Purchase or lease of real estate |  | 21000 |  | 1000 | 22000 | 125 | 0.070015 | 1540.3271
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 125 | 0.070015 | 0
70 VEHICLES (number) |  | 10 | 33404 |  | 1655 | 35059 |  |  | 3008.4309
70.01 | Light Rail | 10 | 33404 |  | 1655 | 35059 | 25 | 0.085811 | 3008.4309
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.04 | Bus | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.05 | Other | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
80 PROFESSIONAL SERVICES |  |  | 84895
80.01 | Preliminary Engineering |  | 15000
80.02 | Final Design |  | 20395
80.03 | Project Management for Design and Construction |  | 12000
80.04 | Construction Administration & Management |  | 12000
80.05 | Insurance |  | 4500
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 4000
80.07 | Surveys, Testing, Investigation, Inspection |  | 4000
80.08 | Start up |  | 13000
Subtotal (10 - 80) |  |  | 436709
90 UNALLOCATED CONTINGENCY |  |  | 21971
Subtotal (10 - 90) |  |  | 458680 | 84895 | 21155 | 457864 |  |  | 33525.0798
Note on H60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.

## Fund Source by Cat
F U N D I N G S O U R C E S B Y C A T E G O R Y | [11 empty] | (Rev.9, Feb. 6, 2007)
Project Sponsor Name | [9 empty] | Today's Date |  | 2007-02-06
Project Name and Location
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops)
| Cost |  | Funding Summary |  |  | 50% | 50% | 71% | 29%
| YOE Cost (X000) | Double- check Total | Federal 5309 New Starts Funds | Federal Other Funds | Local Funds
[6 empty] | Federal 5309 New Starts | Local | Federal Other | Local | Federal Other | Local | Federal Other | Local
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 125759.3234 | 125759 | 759 | 100000 | 25000 | 759 | 25000 | 100000
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 136781.3446 | 136781 | 70000 | 0 | 66781 | 70000 | 26781 | 0 | 40000
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 13859.3239 | 13859 | 7000 | 0 | 6859 | 7000 | 6859 | 0
40 SITEWORK & SPECIAL CONDITIONS | 25937.7469 | 25938 | 15000 | 0 | 10938 | 15000 | 10938 | 0
50 SYSTEMS | 33543.087 | 33543 | 18000 | 0 | 15543 | 18000 | 15543 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 23582.1369 | 23582 | 10000 | 0 | 13582 | 10000 | 13582 | 0
70 VEHICLES (number) | 37880.9088 | 37881 | 15000 | 0 | 22881 | 15000 | 22881 | 0
80 PROFESSIONAL SERVICES | 90199.8485 | 90200 | 45000 | 0 | 45200 | 45000 | 45200
90 UNALLOCATED CONTINGENCY | 24559.0492 | 24559 | 4559 | 0 | 20000 | 4559 | 20000 | 0
100 FINANCE CHARGES | 500 | 500 | 250 | 0 | 250 | 250 | 250 | 0
Total Project Cost (10 - 100) | 512602.7693 | 512602 | 185568 | 100000 | 227034 | 185568 | 187034 | 100000 | 40000 | 0 | 0 | 0 | 0
Percentage of Total Project Cost | 100% |  | 36.2% | 19.51% | 44.29% | 36.2% | 36.49% | 19.51% | 7.803% | 0% | 0% | 0% | 0%
|  |  | 36.2% | 63.8%
100%
Note on H6: Indicate pairs or groups of funds, percentage match etc.
Note on O8: Insert additional columns as required.

## Fund Source by Year
F U N D I N G S O U R C E S B Y Y E A R | [6 empty] | (Rev.9, Feb. 6, 2007)
Project Sponsor Name |  |  |  |  | Today's Date |  | 2007-02-06
Project Name and Location
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops)
|  |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
Total Project Cost In YOE Dollars Below insert funding sources and amounts for each year. | 512602.7693 | double check | 835 | 1721 | 1773 | 1826 | 1881 | 1937 | 2000 | 7228 | 19292.11 | 54037.116 | 105795.0131 | 187379.8682 | 126897.662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Federal 5309 New Starts | 185568 | 185568 | 2009: 4037; 2010: 105795; 2011: 75000; 2012: 736
Local | 227034 | 227034 | 2000: 835; 2001: 1721; 2002: 1773; 2003: 1826; 2004: 1881; 2005: 1937; 2006: 2000; 2007: 7228; 2008: 19292; 2009: 50000; 2011: 38541; 2012: 100000
Federal Other | 100000 | 100000 | 2011: 73838; 2012: 26162
Total Project Cost (10 - 100) | 512602 | 512602 | 835 | 1721 | 1773 | 1826 | 1881 | 1937 | 2000 | 7228 | 19292 | 54037 | 105795 | 187379 | 126898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## BASELINE Main
M A I N W O R K S H E E T - B A S E L I N E A L T E R N A T I V E | [8 empty] | (Rev.9, Feb. 6, 2007)
Project Sponsor Name | [6 empty] | Today's Date |  | 2007-02-06
Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2007
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2012
|  | Quantity | Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Base Year Dollars Unit Cost (X000) | Base Year Dollars Percentage of Construction Cost | Base Year Dollars Percentage of Total Project Cost | Baseline Alternative Cost Parameters (X000) see New Starts Reporting Instructions for additional info
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 9 | 8000 | 1000 | 9000 | 1000 | 26.63% | 14.83%
10.01 | Guideway: At-grade exclusive right-of-way |  |  |  | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 9 | 8000 | 1000 | 9000 | 1000 |  |  | 1040/route mile
10.03 | Guideway: At-grade in mixed traffic |  |  |  | 0 |  |  |  | 1040/route mile
10.04 | Guideway: Aerial structure |  |  |  | 0
10.05 | Guideway: Built-up fill |  |  |  | 0
10.06 | Guideway: Underground cut & cover |  |  |  | 0
10.07 | Guideway: Underground tunnel |  |  |  | 0
10.08 | Guideway: Retained cut or fill |  |  |  | 0
10.09 | Track: Direct fixation |  |  |  | 0
10.1 | Track: Embedded |  |  |  | 0
10.11 | Track: Ballasted |  |  |  | 0
10.12 | Track: Special (switches, turnouts) |  |  |  | 0
10.13 | Track: Vibration and noise dampening |  |  |  | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 36 | 6000 | 1000 | 7000 | 194.4444 | 20.71% | 11.53%
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 36 | 6000 | 1000 | 7000 | 194.4444 |  |  | 208/station
20.02 | Aerial station, stop, shelter, mall, terminal, platform |  |  |  | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform |  |  |  | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. |  |  |  | 0
20.05 | Joint development |  |  |  | 0
20.06 | Automobile parking multi-story structure |  |  |  | 0
20.07 | Elevators, escalators |  |  |  | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 9 | 4000 | 1000 | 5000 | 555.5556 | 14.79% | 8.239%
30.01 | Administration Building: Office, sales, storage, revenue counting |  |  |  | 0
30.02 | Light Maintenance Facility |  | 4000 | 1000 | 5000
30.03 | Heavy Maintenance Facility |  |  |  | 0
30.04 | Storage or Maintenance of Way Building |  |  |  | 0
30.05 | Yard and Yard Track |  |  |  | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 9 | 8300 | 1800 | 10100 | 1122.2222 | 29.88% | 16.64%
40.01 | Demolition, Clearing, Earthwork |  | 5000 | 100 | 5100
40.02 | Site Utilities, Utility Relocation |  | 1000 | 500 | 1500
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  |  |  | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 1000 | 200 | 1200
40.05 | Site structures including retaining walls, sound walls |  |  |  | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 1000 | 1000 | 2000
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 200 |  | 200 |  |  |  | 5.2/on-grade space
40.08 | Temporary Facilities and other indirect costs during construction |  | 100 |  | 100
50 SYSTEMS |  | 9 | 2305 | 392 | 2697 | 299.6667 | 7.98% | 4.444%
50.01 | Train control and signals |  |  |  | 0
50.02 | Traffic signals and crossing protection |  | 1125 | 200 | 1325 |  |  |  | 26/intersection
50.03 | Traction power supply: substations |  |  |  | 0
50.04 | Traction power distribution: catenary and third rail |  |  |  | 0
50.05 | Communications |  | 600 | 72 | 672 |  |  |  | 12.5/bus and 12.5/sign
50.06 | Fare collection system and equipment |  | 180 | 20 | 200 |  |  |  | 10.4/bus
50.07 | Central Control |  | 400 | 100 | 500 |  |  |  | 15.6-26 /bus
Construction Subtotal (10 - 50) |  | 9 | 28605 | 5192 | 33797 | 3755.2222 | 100% | 55.69%
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 9 | 1000 | 200 | 1200 | 133.3333 |  | 1.977%
60.01 | Purchase or lease of real estate |  | 1000 | 200 | 1200
60.02 | Relocation of existing households and businesses |  |  |  | 0
70 VEHICLES (number) |  | 20 | 10000 | 3000 | 13000 | 650 |  | 21.42%
70.01 | Light Rail |  |  |  | 0
70.02 | Heavy Rail |  |  |  | 0
70.03 | Commuter Rail |  |  |  | 0
70.04 | Bus | 20 | 10000 | 3000 | 13000 | 650 |  |  | 416 conventional or 676 articulated bus
70.05 | Other |  |  |  | 0
70.06 | Non-revenue vehicles |  |  |  | 0
70.07 | Spare parts |  |  |  | 0
80 PROFESSIONAL SERVICES |  | 9 | 9800 | 0 | 9800 | 1088.8889 | 29% | 16.15% | Max 35%*Const.Cost
80.01 | Preliminary Engineering |  | 2000 |  | 2000
80.02 | Final Design |  | 3500 |  | 3500
80.03 | Project Management for Design and Construction |  | 2000 |  | 2000
80.04 | Construction Administration & Management |  | 1500 |  | 1500
80.05 | Insurance |  | 500 |  | 500
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  |  |  | 0
80.07 | Surveys, Testing, Investigation, Inspection |  | 150 |  | 150
80.08 | Start up |  | 150 |  | 150
Subtotal (10 - 80) |  | 9 | 49405 | 8392 | 57797 | 6421.8889 |  | 95.24%
90 UNALLOCATED CONTINGENCY |  |  |  |  | 2889.85 |  |  | 4.762% | Max 5%*Subtotal (10 - 80)
Subtotal (10 - 90) |  | 9 |  |  | 60686.85 | 6742.9833 |  | 100%
100 FINANCE CHARGES |  |  |  |  | NA
Total Project Cost (10 - 100) |  | 9 |  |  | 60686.85 | 6742.9833 |  | 100%
Total Base Year Cost per Mile Not Including Vehicles (X000) | [5 empty] | 5298.5389
Allocated Contingency as % of Base Yr Dollars w/o Cont. |  |  |  |  | 16.99%
Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 5.849%
Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  |  | 22.84%
Unallocated Contingency as % of Subtotal (10 - 80) |  |  |  |  | 5%
Note on J9: Feb 2007: Please note that these cost parameters have been increased by 4% from the 2006 costs. They include allocated contingency as before.

## BASELINE Annualized
A N N U A L I Z E D C O S T - B A S E L I N E A L T E R N A T I V E | [8 empty] | (Rev.9, Feb. 6, 2007)
Project Sponsor Name | [6 empty] | Today's Date |  | 2007-02-06
Project Name and Location | [6 empty] | Yr of Base Year $ |  | 2007
Current Phase (In AA, Applic. for PE, In PE, Applic. for FD, Applic. For FFGA, In Construction, In Rev Ops) | [6 empty] | Yr of Revenue Ops |  | 2012
|  | Quantity | Total Base Year Dollars (X000) | Cat. 80 Prof. Svc. spread proportionally over Cats. 10 - 50 (X000) | Spread Cat. 90 Unalloc. Cont. according to perceived risks (X000) | Revised Total Base Year Dollars (X000) | Years of Useful Life | Annualization Factor (based on 7% rate) [.07/1 - (1.07)^-no. yrs] | Annualized Cost (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 9 | 9000 | 2609.6991 | 1000 | 12609.6991 |  |  | 1016.1703
10.01 | Guideway: At-grade exclusive right-of-way | 0 | 0 | 0 | 0 | 0 | 125 | 0.070015 | 0
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 9 | 9000 | 2609.6991 | 1000 | 12609.6991 | 30 | 0.080586 | 1016.1703
10.03 | Guideway: At-grade in mixed traffic | 0 | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.04 | Guideway: Aerial structure | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.05 | Guideway: Built-up fill | 0 | 0 | 0 |  | 0 | 80 | 0.070314 | 0
10.06 | Guideway: Underground cut & cover | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.07 | Guideway: Underground tunnel | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.08 | Guideway: Retained cut or fill | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
10.09 | Track: Direct fixation |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.1 | Track: Embedded |  | 0 | 0 |  | 0 | 20 | 0.094393 | 0
10.11 | Track: Ballasted |  | 0 | 0 |  | 0 | 35 | 0.077234 | 0
10.12 | Track: Special (switches, turnouts) |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
10.13 | Track: Vibration and noise dampening |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 36 | 7000 | 2029.766 | 1000 | 10029.766 |  |  | 708.2973
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 36 | 7000 | 2029.766 | 1000 | 10029.766 | 70 | 0.07062 | 708.2973
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0 | 0 | 0 |  | 0 | 125 | 0.070015 | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0 | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.05 | Joint development |  | 0 | 0 |  | 0 | 70 | 0.07062 | 0
20.06 | Automobile parking multi-story structure |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
20.07 | Elevators, escalators |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 5000 | 1449.8328 | 200 | 6649.8328 |  |  | 481.8459
30.01 | Administration Building: Office, sales, storage, revenue counting |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.02 | Light Maintenance Facility |  | 5000 | 1449.8328 | 200 | 6649.8328 | 50 | 0.07246 | 481.8459
30.03 | Heavy Maintenance Facility |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.04 | Storage or Maintenance of Way Building |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
30.05 | Yard and Yard Track |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40 SITEWORK & SPECIAL CONDITIONS |  |  | 10100 | 2928.6623 | 200 | 13228.6623 |  |  | 995.3947
40.01 | Demolition, Clearing, Earthwork |  | 5100 | 1478.8295 | 200 | 6778.8295 | 125 | 0.070015 | 474.6188
40.02 | Site Utilities, Utility Relocation |  | 1500 | 434.9498 |  | 1934.9498 | 125 | 0.070015 | 135.4753
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments |  | 0 | 0 |  | 0 | 125 | 0.070015 | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks |  | 1200 | 347.9599 |  | 1547.9599 | 125 | 0.070015 | 108.3802
40.05 | Site structures including retaining walls, sound walls |  | 0 | 0 |  | 0 | 80 | 0.070314 | 0
40.06 | Pedestrian / bike access and accommodation, landscaping |  | 2000 | 579.9331 |  | 2579.9331 | 20 | 0.094393 | 243.5274
40.07 | Automobile, bus, van accessways including roads, parking lots |  | 200 | 57.9933 |  | 257.9933 | 20 | 0.094393 | 24.3527
40.08 | Temporary Facilities and other indirect costs during construction |  | 100 | 28.9967 |  | 128.9967 | 100 | 0.070081 | 9.0402
50 SYSTEMS |  |  | 2697 | 782.0398 | 0 | 3479.0398 |  |  | 293.6794
50.01 | Train control and signals |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
50.02 | Traffic signals and crossing protection |  | 1325 | 384.2057 |  | 1709.2057 | 30 | 0.080586 | 137.7387
50.03 | Traction power supply: substations |  | 0 | 0 |  | 0 | 50 | 0.07246 | 0
50.04 | Traction power distribution: catenary and third rail |  | 0 | 0 |  | 0 | 30 | 0.080586 | 0
50.05 | Communications |  | 672 | 194.8575 |  | 866.8575 | 20 | 0.094393 | 81.8252
50.06 | Fare collection system and equipment |  | 200 | 57.9933 |  | 257.9933 | 25 | 0.085811 | 22.1385
50.07 | Central Control |  | 500 | 144.9833 |  | 644.9833 | 30 | 0.080586 | 51.9769
Construction Subtotal (10 - 50) |  |  | 33797 | 9800 | 2400 | 45997 |  |  | 3495.3876
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 1200 |  | 0 | 1200 |  |  | 84.0178
60.01 | Purchase or lease of real estate |  | 1200 |  |  | 1200 | 125 | 0.070015 | 84.0178
60.02 | Relocation of existing households and businesses |  | 0 |  |  | 0 | 125 | 0.070015 | 0
70 VEHICLES (number) |  | 20 | 13000 |  | 490 | 13490 |  |  | 1698.4178
70.01 | Light Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.02 | Heavy Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.03 | Commuter Rail | 0 | 0 |  |  | 0 | 25 | 0.085811 | 0
70.04 | Bus | 20 | 13000 |  | 490 | 13490 | 12 | 0.1259 | 1698.4178
70.05 | Other | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.06 | Non-revenue vehicles | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
70.07 | Spare parts | 0 | 0 |  |  | 0 | 12 | 0.1259 | 0
80 PROFESSIONAL SERVICES |  |  | 9800
80.01 | Preliminary Engineering |  | 2000
80.02 | Final Design |  | 3500
80.03 | Project Management for Design and Construction |  | 2000
80.04 | Construction Administration & Management |  | 1500
80.05 | Insurance |  | 500
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. |  | 0
80.07 | Surveys, Testing, Investigation, Inspection |  | 150
80.08 | Start up |  | 150
Subtotal (10 - 80) |  |  | 57797
90 UNALLOCATED CONTINGENCY |  |  | 2889.85
Subtotal (10 - 90) |  |  | 60686.85 | 9800 | 2890 | 60687 |  |  | 5277.8232
Note on H60: The range for buses is 12 to 18 years. Provide supporting documentation for an estimated useful life of more than 12 years.

## By-Segment
Major Capital Project Costs - By Segment |  |  | (Rev.9, Feb. 6, 2007)
Project | (please insert your project name) |  | Today's Date
Location | (insert location) |  | Yr of Base Year Dollars
Number of Route Miles in the Segment |  |  | Number of Stations
Segment No. ___ of ___ (attach plan of segment and typical sections through segment, along with cost estimate per typical section)
|  | Low costs in Base Yr (X$000) for potential cost savings* | "Most Likely" cost estimate in Base Yr (X$000) | High costs in Base Yr Dollars (X$000) for potential cost increases*
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 0 | 0 | 0
10.01 | Guideway: At-grade exclusive right-of-way
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic)
10.03 | Guideway: At-grade in mixed traffic
10.04 | Guideway: Aerial structure
10.05 | Guideway: Built-up fill
10.06 | Guideway: Underground cut & cover
10.07 | Guideway: Underground tunnel
10.08 | Guideway: Retained cut or fill
10.09 | Track: Direct fixation
10.1 | Track: Embedded
10.11 | Track: Ballasted
10.12 | Track: Special (switches, turnouts)
10.13 | Track: Vibration and noise dampening
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 0 | 0 | 0
20.01 | At-grade station, stop, shelter, mall, terminal, platform
20.02 | Aerial station, stop, shelter, mall, terminal, platform
20.03 | Underground station, stop, shelter, mall, terminal, platform
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc.
20.05 | Joint development
20.06 | Automobile parking multi-story structure
20.07 | Elevators, escalators
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 0 | 0 | 0
30.01 | Administration Building: Office, sales, storage, revenue counting
30.02 | Light Maintenance Facility
30.03 | Heavy Maintenance Facility
30.04 | Storage or Maintenance of Way Building
30.05 | Yard and Yard Track
40 SITEWORK & SPECIAL CONDITIONS |  | 0 | 0 | 0
40.01 | Demolition, Clearing, Earthwork
40.02 | Site Utilities, Utility Relocation
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks
40.05 | Site structures including retaining walls, sound walls
40.06 | Pedestrian / bike access and accommodation, landscaping
40.07 | Automobile, bus, van accessways including roads, parking lots
40.08 | Temporary Facilities and other indirect costs during construction
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 0 | 0 | 0
60.01 | Purchase or lease of real estate
60.02 | Relocation of existing households and businesses
TOTAL SEGMENT COST |  | 0 | 0 | 0
* Describe the risks, uncertainties, and opportunities associated with this segment, that prompted the inclusion of a low or high cost, in addition to a "most likely cost" for particular line items. |  |  | Using costs from this column, total all segments and insert into Main Worksheet Base Yr Dollars Total (X$000)

## Project-wide
Major Capital Project Costs - Project-wide |  |  | (Rev.9, Feb. 6, 2007)
Project | (please insert your project name) |  | Today's Date
Location | (insert location) |  | Yr of Base Year Dollars
Total Number of Route Miles in Project |  |  | Number of Stations
Project-wide Costs
|  | Low costs in Base Yr (X$000) for potential cost savings* | "Most Likely" cost estimate in Base Yr (X$000) | High costs in Base Yr Dollars (X$000) for potential cost increases*
50 SYSTEMS |  | 0 | 0 | 0
50.01 | Train control and signals
50.02 | Traffic signals and crossing protection
50.03 | Traction power supply: substations
50.04 | Traction power distribution: catenary and third rail
50.05 | Communications
50.06 | Fare collection system and equipment
50.07 | Central Control
70 VEHICLES (number) |  | 0 | 0 | 0
70.01 | Light Rail
70.02 | Heavy Rail
70.03 | Commuter Rail
70.04 | Bus
70.05 | Other
70.06 | Non-revenue vehicles
70.07 | Spare parts
80 PROFESSIONAL SERVICES |  | 0 | 0 | 0
80.01 | Preliminary Engineering
80.02 | Final Design
80.03 | Project Management for Design and Construction
80.04 | Construction Administration & Management
80.05 | Insurance
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc.
80.07 | Surveys, Testing, Investigation, Inspection
80.08 | Start up
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES
TOTAL PROJECT-WIDE COST |  | 0 | 0 | 0
* Describe the risks, uncertainties, and opportunities associated with this segment, that prompted the inclusion of a low or high cost, in addition to a "most likely cost" for particular line items. |  |  | Insert costs from this column into Main Worksheet Base Yr Dollars Total (X$000)

## A3T1
Table 1 - BCE by Standard Cost Category
Applicable Line Items Only |  | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  | 125759.3234
10.01 | Guideway: At-grade exclusive right-of-way | 125759.3234
10.02 | Guideway: At-grade semi-exclusive (allows cross-traffic) | 0
10.03 | Guideway: At-grade in mixed traffic | 0
10.04 | Guideway: Aerial structure | 0
10.05 | Guideway: Built-up fill | 0
10.06 | Guideway: Underground cut & cover | 0
10.07 | Guideway: Underground tunnel | 0
10.08 | Guideway: Retained cut or fill | 0
10.09 | Track: Direct fixation | 0
10.1 | Track: Embedded | 0
10.11 | Track: Ballasted | 0
10.12 | Track: Special (switches, turnouts) | 0
10.13 | Track: Vibration and noise dampening | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  | 136781.3446
20.01 | At-grade station, stop, shelter, mall, terminal, platform | 136781.3446
20.02 | Aerial station, stop, shelter, mall, terminal, platform | 0
20.03 | Underground station, stop, shelter, mall, terminal, platform | 0
20.04 | Other stations, landings, terminals: Intermodal, ferry, trolley, etc. | 0
20.05 | Joint development | 0
20.06 | Automobile parking multi-story structure | 0
20.07 | Elevators, escalators | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  | 13859.3239
30.01 | Administration Building: Office, sales, storage, revenue counting | 0
30.02 | Light Maintenance Facility | 13859.3239
30.03 | Heavy Maintenance Facility | 0
30.04 | Storage or Maintenance of Way Building | 0
30.05 | Yard and Yard Track | 0
40 SITEWORK & SPECIAL CONDITIONS |  | 25937.7469
40.01 | Demolition, Clearing, Earthwork | 1092.3411
40.02 | Site Utilities, Utility Relocation | 6425.536
40.03 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | 0
40.04 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | 4497.8752
40.05 | Site structures including retaining walls, sound walls | 0
40.06 | Pedestrian / bike access and accommodation, landscaping | 13921.9946
40.07 | Automobile, bus, van accessways including roads, parking lots | 0
40.08 | Temporary Facilities and other indirect costs during construction | 0
50 SYSTEMS |  | 33543.087
50.01 | Train control and signals | 11491.2939
50.02 | Traffic signals and crossing protection | 3447.3882
50.03 | Traction power supply: substations | 9193.0352
50.04 | Traction power distribution: catenary and third rail | 6894.7764
50.05 | Communications | 1264.0423
50.06 | Fare collection system and equipment | 1252.551
50.07 | Central Control | 0
Construction Subtotal (10 - 50) |  | 335880.8258
60 ROW, LAND, EXISTING IMPROVEMENTS |  | 23582.1369
60.01 | Purchase or lease of real estate | 23582.1369
60.02 | Relocation of existing households and businesses | 0
70 VEHICLES (number) |  | 37880.9088
70.01 | Light Rail | 37880.9088
70.02 | Heavy Rail | 0
70.03 | Commuter Rail | 0
70.04 | Bus | 0
70.05 | Other | 0
70.06 | Non-revenue vehicles | 0
70.07 | Spare parts | 0
80 PROFESSIONAL SERVICES |  | 90199.8485
80.01 | Preliminary Engineering | 15937.3076
80.02 | Final Design | 21669.4259
80.03 | Project Management for Design and Construction | 12749.8461
80.04 | Construction Administration & Management | 12749.8461
80.05 | Insurance | 4781.1923
80.06 | Legal; Permits; Review Fees by other agencies, cities, etc. | 4249.9487
80.07 | Surveys, Testing, Investigation, Inspection | 4249.9487
80.08 | Start up | 13812.3332
Subtotal (10 - 80) |  | 487543.7201
90 UNALLOCATED CONTINGENCY |  | 24559.0492
Subtotal (10 - 90) |  | 512102.7693
100 FINANCE CHARGES |  | 500
Total Project Cost (10 - 100) |  | 512602.7693

## A3T2
Table 2 - Inflated Cost to Year of Expenditure
| Base Year Dollars w/o Contingency (X000) | Base Year Dollars Allocated Contingency (X000) | Base Year Dollars TOTAL (X000) | Inflation Factor | YOE Dollars Total (X000)
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 100000 | 12000 | 112000 | 1.1229 | 125759.3234
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 100000 | 20000 | 120000 | 1.1398 | 136781.3446
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10000 | 2000 | 12000 | 1.1549 | 13859.3239
40 SITEWORK & SPECIAL CONDITIONS | 21420 | 2800 | 24220 | 1.0709 | 25937.7469
50 SYSTEMS | 25490 | 3700 | 29190 | 1.1491 | 33543.087
60 ROW, LAND, EXISTING IMPROVEMENTS | 17000 | 4000 | 21000 | 1.123 | 23582.1369
70 VEHICLES (number) | 25404 | 8000 | 33404 | 1.134 | 37880.9088
80 PROFESSIONAL SERVICES | 65895 | 19000 | 84895 | 1.0625 | 90199.8485
90 UNALLOCATED CONTINGENCY |  |  | 21971 | 1.1178 | 24559.0492
100 FINANCE CHARGES |  |  | 454.7199 | 1.0996 | 500
Total Project Cost (10 - 100) |  |  | 459134.7199 | 1.1165 | 512602.7693

## A3T3
Table 3 - BCE by Source of Funding
| Total Project Cost in YOE Dollars (X000) | Double Check Total (X000) | Federal 5309 New Starts | Federal Other | Local
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 125759.3234 | 125759 | 759 | 100000 | 25000
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 136781.3446 | 136781 | 70000 | 0 | 66781
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 13859.3239 | 13859 | 7000 | 0 | 6859
40 SITEWORK & SPECIAL CONDITIONS | 25937.7469 | 25938 | 15000 | 0 | 10938
50 SYSTEMS | 33543.087 | 33543 | 18000 | 0 | 15543
60 ROW, LAND, EXISTING IMPROVEMENTS | 23582.1369 | 23582 | 10000 | 0 | 13582
70 VEHICLES (number) | 37880.9088 | 37881 | 15000 | 0 | 22881
80 PROFESSIONAL SERVICES | 90199.8485 | 90200 | 45000 |  | 45200
90 UNALLOCATED CONTINGENCY | 24559.0492 | 24559 | 4559 | 0 | 20000
100 FINANCE CHARGES | 500 | 500 | 250 | 0 | 250
Total Project Cost (10 - 100) | 512602.7693 | 512602 | 185568 | 100000 | 227034
Sources of Federal Funding and Matching Share Ratios
| Costs Attributed to Source of Funds (X000) | Federal/ Local Matching Ratio within Source | All Federal Funds (X000) | Local Funds (X000)
Federal 5309 New Starts | 372602 | 50/50 | 185568 | 187034
Federal Other (pls say what..) | 140000 | 71/29 | 100000 | 40000
Total | 512602 |  | 285568 | 227034
Overall Federal Share of Project |  |  | 55.71%
New Starts Share of Project |  |  | 36.2%
Note on F2: Add columns as required to show all federal funding.
Note on A19: Add rows are needed to show all federal funding.

## A3A
Scope and Activity Description
Scope Code | ALI Code | Scope and Activity Line Item Descriptions | Qty |  | Federal 5309 New Starts |  |  | Federal Other |  |  | Project Totals |  |  | Total Project Cost in YOE Dollars (X000)
|  |  |  | Total Federal % | Federal | Local | Total | Federal | Local | Total | Federal | Local | Total
14010 | 140110 | GUIDEWAY & TRACK ELEMENTS | 9 | 80.12% | 759 | 25000 | 25759 | 100000 | 0 | 100000 | 100759 | 25000 | 125759 | 125759.3234
14020 | 140220 | STATIONS, STOPS, TERMINALS, INTERMODAL | 18 | 51.18% | 70000 | 26781 | 96781 | 0 | 40000 | 40000 | 70000 | 66781 | 136781 | 136781.3446
14030 | 140330 | SUPPORT FACILITIES, YARDS, SHOPS, ADMIN. BLDGS. |  | 50.51% | 7000 | 6859 | 13859 | 0 | 0 | 0 | 7000 | 6859 | 13859 | 13859.3239
14040 | 140440 | SITEWORK & SPECIAL CONDITIONS |  | 57.83% | 15000 | 10938 | 25938 | 0 | 0 | 0 | 15000 | 10938 | 25938 | 25937.7469
14050 | 140550 | SYSTEMS |  | 53.66% | 18000 | 15543 | 33543 | 0 | 0 | 0 | 18000 | 15543 | 33543 | 33543.087
14060 | 140660 | ROW, LAND, EXISTING IMPROVEMENTS |  | 42.41% | 10000 | 13582 | 23582 | 0 | 0 | 0 | 10000 | 13582 | 23582 | 23582.1369
14070 |  | VEHICLES | 10 | 39.6% | 15000 | 22881 | 37881 | 0 | 0 | 0 | 15000 | 22881 | 37881 | 37880.9088
| 13.13.20 | Light Rail Cars | 10
13.__.__
14080 | 140880 | PROFESSIONAL SERVICES |  | 49.89% | 45000 | 45200 | 90200 | 0 | 0 | 0 | 45000 | 45200 | 90200 | 90199.8485
14090 | 140990 | UNALLOCATED CONTINGENCY |  | 18.56% | 4559 | 20000 | 24559 | 0 | 0 | 0 | 4559 | 20000 | 24559 | 24559.0492
14100 | 141010 | FINANCE CHARGES |  | 50% | 250 | 250 | 500 | 0 | 0 | 0 | 250 | 250 | 500 | 500
Total Project Cost (10 - 100) |  |  |  | 55.71% | 185568 | 187034 | 372602 | 100000 | 40000 | 140000 | 285568 | 227034 | 512602 | 512602.7693
Note on I2: Add more tri-columns as required to show all funding.

## A4
SCHEDULE | Start Date | End Date | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020
10 GUIDEWAY & TRACK ELEMENTS (route miles)
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number)
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS
40 SITEWORK & SPECIAL CONDITIONS
50 SYSTEMS
60 ROW, LAND, EXISTING IMPROVEMENTS
70 VEHICLES (number)
80 PROFESSIONAL SERVICES
90 UNALLOCATED CONTINGENCY
100 FINANCE CHARGES
Revenue Operations
Before and After Study: Two years post Rev Ops
Fulfillment of the New Starts funding commitment
Completion of project close-out, resolution of claims