## PFMEA
POTENTIAL FAILURE MODE AND EFFECTS ANALYSIS
PROCESS FMEA
FMEA Number:
[11 empty] | Page 1 of : | 2
Project No: | 30/30.8.2.06.2 | [9 empty] | Customer: | BD
Project Name: | Tev Dipole Reshimming (0234) |  | Project Engineer: |  |  |  | B. Robotham |  |  |  | Issue Date: | 2003-08-08
Process Name: |  |  | Traveler Coordinator: |  |  |  | B. Jensen |  |  |  | Revision Date:
Core Team: | J. Blowers, J. Carson, D. Harding, R. Hanft
Process | Potential | Potential |  |  | Potential |  | Current |  | R | Recommended | Responsibility |  | Action Results |  |  | R
Step | Failure | Effect(s) of |  |  | Cause(s) of |  | Process |  | P | Action(s) | & Target | Action(s) |  |  |  | P
| Mode | Failure | S | C | Failure | O | Controls | D | N |  | Completion Date | Taken | S | O | D | N
Identify magnets to be reshimmed | Wrong magnets identified | Documentation mismatch |  |  | Database not up to date |  | TD verified BD list
|  | Not all magnets reshimmed |  |  | Typographical error
Misread list
Create shim kits | Wrong thickness | Bad harmonics | 2 |  | Shims not measured |  | Every shim is being measured
|  | Put coils too far off center | 2 |  | Shims mismeasured |  | Measurer training
[5 empty] | Shims put into wrong bag |  | Measurer training
Collect historic data | Data not collected | No comparison can be made |  |  | Travelers/pages not available |  | None
| Wrong data collected | Comparison is incorrect |  |  | List is incomplete or misread |  | None |  |  | Compare dbs with lift list | J. Blowers
[5 empty] | Data entry error |  | Review data
Collect lift measurements | Gauge miscalibrated | Data incorrect, leading to wrong conclusions |  |  | Calibration not done |  | Training
| Gauge not in correct position for measurement |  |  |  | Improper calibration technique |  | Training
[5 empty] | Material on bolt surface |  | Cleaning of surface
[5 empty] | Gauge not placed flush on surface |  | Training
| PDA fails | Loss of data |  |  | Battery runs out |  | Charge batteries over lunch break |  |  | Save data to CF card | J. Blowers
Upload measurements to dbs | Software not working | Data cannot be directly uploaded |  |  | Computer malfunction |  | None
| Data not uploaded | Data loss, or data errors |  |  | Person or PC not available |  | Training of more than one person to do uploads
Review/compare data | Wrong data compared | Incorrect conclusions drawn |  |  | Wrong query used |  | Training
[5 empty] | Query code is incorrect |  | Previous validation of query
| Data erased | No conclusions can be drawn |  |  | Dbs corrupted |  | Backups
[5 empty] | Dbs erased |  | Backups
[5 empty] | Data erased |  | Backups
PROCESS FMEA
Part Name: | Tev Dipole Reshimming (0234) |  |  |  |  | PFMEA Number: | 0 |  |  |  | Page 2 of | 2
Process | Potential | Potential |  |  | Potential |  | Current |  | R | Recommended | Responsibility |  | Action Results |  |  | R
| Failure | Effect(s) of |  |  | Cause(s) of |  | Process |  | P | Action(s) | & Target | Action(s) |  |  |  | P
Purpose | Mode | Failure | S | C | Failure | O | Controls | D | N |  | Completion Date | Taken | S | O | D | N
Issue traveler and kits | Wrong traveler | Can't do work |  |  | Wrong spec issued |  | Verification of traveler
| Kit incorrect | Wrong shim applied |  |  | Mismeasure |  | Training
|  | Not enough shims |  |  | Incorrect shim count |  | Extra shims
Reshimming | Not all bolts reshimmed | Harmonics not corrected |  |  | Traveler not followed |  | Traveler/training; all magnets will be checked for sticker at end of project |  |  | Consider using toolmaker paint to identify shims and/or stickers applied to smart bolts | B. Robotham
[5 empty] | Not enough shims in kit |  | Traveler/training
| Too much shim added | Harmonics overcorrected |  |  | Shim packs incorrect |  | Training/lift inspections
[5 empty] | Two shims stuck together |  | Training
|  | Coils put too far off center |  |  | Poor measurements or production data |  | Training; review of old data
| Not enough shim added | Harmonics not corrected |  |  | Shim packs incorrect |  | Training/lift inspections
| Bolts undertightened | Cryostat too loose |  |  | Malfunctioning tool |  | None
[5 empty] | Torque not set properly |  | Training
| Bolts overtightened | None |  |  | Malfunctioning tool |  | None
[5 empty] | Torque not set properly |  | Training
| Debris put into magnet | None |  |  | Dropped shim |  | None |  |  | Tray/mat under magnet? | B. Robotham
[5 empty] | Failure to clean smart bolt well |  | Traveler/training
| Stripped threads | Replace bolt |  |  | Screwing in bolt at angle |  | Training |  |  | Spare parts ready to go in tunnel | B. Robotham
| Not all magnets reshimmed | Harmonics not corrected |  |  | Documentation mix up |  | Documentation verification
| Wrong shims added | Harmonics not corrected |  |  | Shim pask dropped, and shims lost |  | Training/lift inspections |  |  | Extract data as needed | J. Blowers
| Vertical plane changed too much | Magnet needs to be realigned |  |  | Effect of lossening and tightening bolts |  | Studies being done |  |  | Possible change the work pattern | J. Carson
| Tools fail/break | Down time |  |  | Mfg defect/misuse |  | Spare tooling
Radiation safety | Contamination | Overexposure |  |  | Not following procedure |  | Rad Worker training |  |  | RSO to speak with teams | J. Blowers
Ergonomics | Repetative strain | Injury |  |  | Work too strenuous |  | PPE/tooling/training |  |  | SSO speak with teams re ergonomics | J. Blowers
| Physical exhaustion | Poor work quality