D&D

“Final Tokamak Removal”

FAILURE MODES AND EFFECTS

ANALYSIS

(FMEA)

Rev.1 5/16/01

Prepared By: 	________________________	J. Chrzanowski (D&D Engineering Manager)

________________________	S. Raftopoulos (D&D Engineer)

________________________	R. Feder (D&D Engineer)

________________________	G. Gettelfinger (D&D Engineer)

________________________	R. Parsells (D&D Engineer)

Reviewed By:	________________________	J. Levine (Safety Engineer)

________________________	Mike Viola (D&D Construction Manager)

Approved By: 	________________________	E. Perry (D&D Project Manager)

## Table of Contents

PREFACE

SCOPE …………………………………………………………………………………………………………	5

SAFETY IMPLICATIONS ……………………………………………………………………………………	5

LIST OF ACRONYMS  ………………………………………………………………………………………………	4

- Concrete Filling of Vacuum Vessel…………………………………………………………………………… 	7

  - VV Ventilation system fails during concrete fill

  - VV window or component ruptures

  - Concrete overflows the vacuum vessel

  - Fill sight system fails

- Vacuum Vessel Support System……………………………………………………………………………….	8

  - Main Weight Bearing Rope Fails As System Is Adjusted to Full Design Tension

  - Main Weight Bearing Rope Fails As Vacuum Vessel Support Columns are Lowered

  - Horizontal Stop Wire Rope Fails At the Completion of Diamond Wire Cutting

- Diamond Wire Cutting (DWC)………………………………………………………………………………. 	10

  - Diamond Wire breaks during cutting operation

  - Diamond wire bead breaks off and becomes a projectile

  - Diamond wire gets bound in groove during cutting operation

  - Loss of liquid Nitrogen during cutting operation

  - Loss of liquid Nitrogen system during personnel entry into enclosure

  - Hydraulic system fails during DWC

  - Hydraulic fluid leak

  - Containment fails during DWC

  - HEPA filter system fails

  - HVAC (elephant trunk) System Fails during DWC

  - Following DWC large voids are found in the concrete exposing tiles

  - AC Power interrupted during DWC operations

  - Seismic Event during DWC operations

- Lifting of TF Coil/ Vacuum Vessel Segment ………………………………………………………………	12

  - TF nose surrogate fails during segment lift

  - Surrogate fails

  - Inboard lifting hardware failure during segment lift

  - Outboard lifting hardware during segment lift

  - Main hook fails to rotate

  - Main hook fails to move up/down

  - Trolley Drive Failure

  - Bridge Drive Failure

  - AC power interrupted

- TF/VV Disassembly Activities …………………………………………………………………………………	14

  - Segment does not fit fixture

  - Tritium Leak

  - Fixture fails to swing

  - Sector stand motion is abrupt

  - Cannot rotate components

  - Rigging components fail

  - Fixture fails to swing open

### LIST OF ACRONYMS

| AC | Alternating Current |  |  |
| --- | --- | --- | --- |
| D&D | Decontamination and Decommissioning |  |  |
| DWC | Diamond Wire Cutting |  |  |
| ERWM | Environmental Restoration & Waste Mgt |  |  |
| FMEA | Failure Modes & Effect Analysis |  |  |
| HEPA | High-Efficiency Particulate Air |  |  |
| HVAC | Heating/Ventilation/Air Conditioning |  |  |
| LOTO | Lock Out/Tag Out |  |  |
| MIE | Most Intense Earthquake |  |  |
| PPPL | Princeton Plasma Physics Laboratory |  |  |
| TF | Toroidal Field Coils |  |  |
| TFTR | Tokamak Fusion Test Reactor |  |  |
| VV | Vacuum Vessel |  |  |
| VVTSS | Vacuum Vessel Temporary Support System |  |  |

# SCOPE

This version of the D&D Final Tokamak Removal FMEA reflects the configuration of the vacuum vessel and facility as operations proceed in performing the filling and segmenting procedures. The failures have been identified to address the following.

1:	Load Line failures during lifts.

2:	Diagnostic & Control failures

3:	Component failures.

4:	Operational failures.

D&D will utilize the existing auxiliary systems of D-site.  The TFTR FSAR includes FMEA’s for these systems, including effects of failures on the auxiliary systems themselves.  For D&D this document only addresses failures that impact the D&D Final Tokamak Removal.  The TFTR FSAR covers effects of failures, on the auxiliary systems.

In general, single failure modes are addressed. In some cases, for failures that would have severe consequences in terms of damage to hardware or risk to personnel safety, multiple failures are addressed.

SAFETY IMPLICATIONS

Certain failures can increase the risk of injury to personnel.  For any particular failure, the level of risk of injury to personnel depends on several factors including:

- The nature of the failure

- The presence or absence of features that mitigate the effect of the failure (e.g. redundancy, energy isolating barriers, etc.)

- The presence or absence of personnel in the area where the failure has occurred

- The level of training of the personnel

The FMEA addresses the first two items.  The last two relate mainly to administrative procedures that aim to prevent access to hazardous areas or to limit access to personnel trained to conduct themselves safely in potentially hazardous areas.  This FMEA does not address administrative procedures.

This FMEA addresses new systems to support the Tokamak removal, as well as other D-site systems whose failure could cause damage during the operations.

This FMEA does not address safety issues related to the conduct of operations throughout the balance of the D-site facility.  Considering that the safety of operations of TFTR was documented and approved via the TFTR FSAR, and demonstrated to be effective for more than a decade, it would not add to the safety of D&D operations to repeat that analysis.

SUMMARY

The critical elements that draw the attention of the engineer include:

Load line failures have high impact.  Subsequently they have the most conservative margin.  The working load is the load indicating on the load line element.  The ultimate load is the load that accompanies failure.  The margin between the working load and the ultimate load is minimum factor of five.  The capacity for fabricated 304SS elements is based on yield and ultimate strength.  The minimum yield strength of 304SS is 30,000 psi.  The minimum tensile strength is 75,000 psi.  The allowable shear strength of welds per AWS/AISC is 30% of yield.  The allowable tensile strength of welds per AWS/AISC is 60% of yield.

Diagnostic and control failures have high impact during concrete fill operations.  This is the phase that can produce tritium release in the test cell.  This is a personnel hazard rather that a site release hazard.  Area and portable monitors will detect the presence of tritium.  Operations will be suspended and recovery procedures will be implemented.

Failures of Components share the same characteristic as control failures.  If a tritium boundary is ruptured, operations must be interrupted until components are restored.  Then the operations can be resumed.

Operations failures that involve personnel are mitigated by experience, training, walk-through, clear lines of responsibility, and written procedures.  Operations failures that involve equipment are mitigated by redundancy, work-a-rounds or emergency response procedures depending on the nature of the failure.

| Project | D&D | FAILURE MODES AND EFFECTS ANALYSIS |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| Element | 1.0 Concrete Filling of Vacuum Vessel | Performed By | Robert Parsells | Date | 1/25/01 |
| --- | --- | --- | --- | --- | --- |
|  |  | Reviewed By |  | Date |  |

| Operating Mode | Failure Mode/Cause | System Effect | Fault Detection/Isolation | Compensating provisions | Remarks |
| --- | --- | --- | --- | --- | --- |
| Concrete Filling | VV ventilation system fails during fill | Possible release of tritium in T/C | Air flow monitors or Area/Portable Monitors | Suspend operations, Isolate VV, Replace/repair ventilation system. Use bubble as req’d. |  |
| Concrete Filling | VV window or component ruptures | Concrete leak, Possible release of tritium in T/C | Visual Area/Portable Monitors | Suspend operations & cleanup. Replace/repair window & resume operations | All windows and fragile components covered with metal protective covers. |
| Concrete Filling | Concrete overflows the vacuum vessel | See previous | Visual | Let concrete set & resume operations |  |
| Concrete Filling | Fill level sight system fails | Suspend operations | Visual | Move sight system to alternate port. |  |

| Project | D&D | FAILURE MODES AND EFFECTS ANALYSIS |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| Element | 2.0 Vacuum Vessel Temporary Support System | Performed By | Russell Feder | Date | 1/25/01 |
| --- | --- | --- | --- | --- | --- |
|  |  | Reviewed By |  | Date |  |

| Operating Mode | Failure Mode/Cause | System Effect | Fault Detection/Isolation | Compensating provisions | Remarks |
| --- | --- | --- | --- | --- | --- |
| Set VVTSS To Full Design Tension | Main Weight Bearing Support Wire Rope Fails | No Effect on Load Safety Hazard to Personnel | Visual and audible | Vessel still resting on columns Tension can be easily relieved to fix problem | Safety Factor of 3 in design. Stored Energy in Wire Rope Horizontal stop ropes not effective at this stage because whole torus self-supports horizontal loading. Administrative controls will be placed in installation/testing procedure and warning will be noted of personnel hazard. |
| Lower/Remove Vacuum Vessel Columns | Main Weight Bearing Support Wire Rope Fails | Load from failed fixture distributed to other fixtures Belleville stack displacement results | Visual | Redundant design of fixtures and hardware 30 total fixtures to share load with more than adequate margin. | Safety Factor of 3 in design. Horizontal stop ropes not effective at this stage because whole torus self-supports horizontal loading |
| Diamond wire cutting of VV Or Lifting segment | Horizontal stop rope or hardware fails | Load Distributed to Other Fixtures, Bellevilles Displace | Visual | Redundant design of fixtures and hardware | Safety Factor of 3 in design. There is no additional loading on the main weight-bearing fixture in this step. In the instant that each segment is cut free, the Horizontal Stop Roped will load up for the first time. |
| Diamond wire cutting of VV Or Lifting segment R1 | Hard stop air bag develops leak | Ropes loose tension, vessel moves | Pressure indicator indicates loss of pressure, bevel washer stack will change displacement | Repair or replace air bag | Consequence of failure is minor. Loss of pressure will not lead to loss of control of segment. |

| Project | D&D | FAILURE MODES AND EFFECTS ANALYSIS |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| Element | 3.0 Diamond Wire Cutting of Vacuum Vessel (DWC) | Performed By | Robert Parsells | Date | 1/25/01 |
| --- | --- | --- | --- | --- | --- |
|  |  | Reviewed By |  | Date |  |

| Operating Mode | Failure Mode/Cause | System Effect | Fault Detection/Isolation | Compensating provisions | Remarks |
| --- | --- | --- | --- | --- | --- |
| Diamond wire cutting of VV | Diamond wire breaks during operation | Several beads will become projectiles. | Audio detection and movement of tensioning system. | The enclosure has been designed and prototyped to contain beads. | Analysis & field tests have been performed to verify integrity of enclosure |
| Diamond wire cutting of VV | Diamond wire bead breaks off and becomes projectile | Bead will become projectile, incremental diminution of saw cutting efficiency | Audio detection and movement of tensioning system. | The enclosure has been designed and prototyped to contain beads. | Analysis & field tests have been performed to verify integrity of enclosure |
| Diamond wire cutting of VV | Diamond wire becomes bound in groove | The wire slips on the drive wheel or separates at the coupling | Visual detection. | Suspend operation. Free wire or re-splice coupling if separated & resume operations. |  |
| Diamond wire cutting of VV | Loss of liquid nitrogen or CO2 coolant during DWC R1 | Heat build-up in wire | Visual detection | Suspend operation. Restore LN2 flow |  |
| Diamond wire cutting of VV | Liquid Nitrogen or CO2 leak while personnel are in enclosure R1 | Personnel hazard | Visual detection and O2 monitoring | Vacate personnel from enclosure. Close LN2 supply valve. | Administrative controls (LOTO) will exclude personnel from enclosure during cutting operation. Enclosure is treated as Possible O2/Confined space. Confined space permit and training required to enter. |
| Diamond wire cutting of VV | Hydraulic drive system fails during cutting | Suspend operations | Visual detection | Repair/replace unit & resume operations |  |
| Diamond wire cutting of VV | Hydraulic fluid leak | Suspend operations | Visual detection | Repair system, absorb & solidify oil; and resume operation |  |
| Diamond wire cutting of VV | Containment fails during DWC | Suspend operations | Loss of negative pressure | Repair system and resume operations |  |
| Diamond wire cutting of VV | HEPA filter system fails | Suspend operations | Visual detection & loss of delta-P | Repair system and resume operations |  |
| Diamond wire cutting of VV | HVAC (elephant trunk) System fails during DWC operations | Suspend operations | Loss of negative pressure | Repair system and resume operations |  |
| Diamond wire cutting of VV | Following DWC, large voids found in the concrete exposing carbon tiles | Suspend operations | Visual detection | Install end caps & bubbler. Foam fill voids & resume |  |
| Diamond wire cutting of VV | AC power interrupted during DWC operations | Shut down operations | Visual detection | Repair system and resume operations |  |
| Diamond wire cutting of VV | Seismic event occurs during the DWC operations | Shut down operations | Visual detection | Repair system and resume operations | All systems used for DWC of VV will be seismically qualified by PPPL’s Seismic Engineer before being placed in service. |

| Project | D&D | FAILURE MODES AND EFFECTS ANALYSIS |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

| Element | 4.0 Lifting of TF Coil/VV Segment | Performed By | Geoff Gettelfinger | Date | 1/25/01 |
| --- | --- | --- | --- | --- | --- |
|  |  | Reviewed By |  | Date |  |

| Operating Mode | Failure Mode/Cause | System Effect | Fault Detection/Isolation | Compensating provisions | Remarks |
| --- | --- | --- | --- | --- | --- |
| Lifting of TF Coil/VV Segment | Inter-TF coil nose surrogate fails during segment lift | Potentially increased loading on the vacuum vessel supports | Visual detection | Capacities of other supporting equipment will not be exceeded. |  |
| Lifting of TF Coil/VV Segment | Upper inter-TF coil outboard shear/compression surrogate fails during segment lift | Potentially increased loading on the vacuum vessel supports | Visual detection | Capacities of other supporting equipment will not be exceeded |  |
| Lifting of TF Coil/VV Segment | Catastrophic Failure of: Inboard Lifting Lug Bolt; Inboard Lifting Lug; Inboard Swivel Eye; Inboard Sling; Inboard Shackle; or Inboard Load Cell | Loss of load support | Visual detection or detection using load cells | Lift practices consistent with DOE Hoisting and Rigging Order | Safety Factor of 5 in rigging component design. Rigging components tested at manufacturer. |
| Lifting of TF Coil/VV Segment | Outboard Lifting Lug Bolt; Outboard Lifting Lug ; Outboard Swivel Eye; Outboard Sling; Outboard Shackle; Outboard Chain Hoist; or Outboard Load Cell | Shift of load. | Visual detection or detection using load cells | Lift practices consistent with DOE Hoisting and Rigging Order Capacities of other supporting equipment will not be exceeded | Safety Factor of 5 in rigging component design. Rigging components tested at manufacturer. |
| Lifting of TF Coil/VV Segment | Main hook fails to rotate | Loss of load orientation control | Visible detection by operator | Implement custom recovery procedure |  |
| Lifting of TF Coil/VV Segment | Main hook fails to move U/D | Loss of ability to change load elevation | Visible detection by operator | Implement custom recovery procedure | Main hoist drive de-energizes to “parked” mode (brakes held on by fail-safe mechanical springs) |
| Lifting of TF Coil/VV Segment | Trolley drive failure | Loss of ability to move load North/South | Visible detection by operator | Implement custom recovery procedure |  |
| Lifting of TF Coil/VV Segment | Bridge drive failure | Loss of ability to move load East/West | Visible detection by operator | Implement custom recovery procedure |  |
| Lifting of TF Coil/VV Segment | AC power is interrupted. | Interruption of crane service | Visible detection by operator | Suspend lift until power system restoration | Main hoist drive de-energizes to “parked” mode (brakes held on by fail-safe mechanical springs) |

| Project | D&D | FAILURE MODES AND EFFECTS ANALYSIS |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Element | 5.0 TF Coil/VV Disassembly Activities | Performed By | Steve Raftopoulos | Date | 1/25/01 |
|  |  | Reviewed By |  | Date |  |

| Operating Mode | Failure Mode/Cause | System Effect | Fault Detection/Isolation | Compensating provisions | Remarks |
| --- | --- | --- | --- | --- | --- |
| Placing segment into fixture | Segment does not bolt into fixture properly | Cannot secure segment and release from hook | Visual | Implement custom recovery procedure |  |
| Removing small component(s) from segment | Tritium Leak | T2 levels rise | Portable/Area monitors alarm | Use Elephant trunks/Bubblers as required. |  |
| Removing small component(s) from segment | Fixture fails to swing open/close | Cannot remove TF coils and/or VV Schedule Impact | Visual | Repair and proceed |  |
| Removing small component(s) from segment | Sector stand motion is abrupt | Coil(s) become unstable and fall over | Visual | Design of mechanism used to control motion will prohibit this. | Fixture will withstand MIE without failure. |
| Placing large components into shipping containers | Cannot rotate components into proper orientation | Cannot directly load into container | Visual | Lower to floor, re-rig and continue loading into container |  |
| Placing large components into shipping containers | Any rigging component fails | Possible loss of load support | Visual | Lift practices consistent with DOE Hoisting and Rigging Order |  |
| Remobilize fixture | Fixture fails to swing open/close | Cannot load next segment - resulting in schedule impact | Visual | Repair and proceed |  |