## OB8
|  |  |  | Personnel |  | Est LOE (m) |  | Release
ID | OSIP Number | Description | Area | Advocate or IWT Lead | Dev Org(s) | Op | Pes | 8.1 | 8.2 | 8.3 | OB9
Infrastructure
3 | BFR | Transition to RedHat Package Manager | Install | Stowe Davison | ENV | TBD | TBD | X | X | X
29 | 05-059 | Removing NGM LAMP | Model | Judy Ghirardelli | ASM | 0.8 | 1.3 | X
13 | BFR | Elimination of all use of "R" commands in AWIPS | Security | Stowe Davison | ASM, ENV | 1 | 1.5 | X
18 | RC | Workstations Upgrades | Hardware | Jami Casamento | SE | TBD | TBD | X
21 | RC | XYPLEX Upgrade | Hardware | Jami Casamento | SE | TBD | TBD | X
20 | RC9740 | SBN CP Servers and Comms Processor | Hardware | Jami Casamento | SE | TBD | TBD | X
22 | xx-xxx | Stack Tracing | General | Stowe Davison | GSD | 0.25 | 0.5 | X
32 | xx-xxx | Notification Server | Monitoring | Tim Hopkins | GSD | 3 | 5 | X
23 | 05-071 | Higher Resolution for Map backgrounds | General | Ira Graffman | ASM, MDL, OHD | 10 | 16 | X | X
41 | 06-040 | NWRWAVE Enhancements | Dissemination | P. Browning, J. Nathan | NWS CR | 4 | 6 | X
16 | 06-008 | Replace LDAD Servers | Hardware | Jami Casamento | SE | TBD | TBD |  | X
27 | xx-xxx | Transfer of RFC Precipitation Bias Info to RPG | Hydrology | Kevin Lynott | OHD, ASM | 4.5 | 7 |  | X
17 | 06-031 | Synchronize RFC Archive Database and IHFS Database Meta Data | Hydrology | Julian Meyer | OHD | 6 | 8 |  | X
2 | BFR | COTS Upgrades (Integration of Applications) | OSCOTS | Stowe Davison | ENV, OOS, NCEP, MDL | 9 | 16 | X | X | X
15 | 05-058 | AWIPS Evolution: Improve Installation time | Install | Thuy Tran | ENV, MDL | 16 | 30 |  |  | X
28 | 06-050 | Speed up DB I/O | Hardware | Stowe Davison | SE | TBD | TBD |  |  | X
25 | 06-050 | Redundancy for PostgreSQL | Data | Stowe Davison | SE | TBD | TBD |  |  | X
10 | n/a | TTAR: Radar Acquisition Improvements | Radar | Diane Deitz | ASM | 1 | 3 |  |  | X
24 | SON | PX1/PX2 Decommissioning | Hardware | Tim Hopkins | SE | TBD | TBD |  |  | X
5 | xx-xxx | Port to NCEP GRIB2 Decoder | Decoding | Brian Gockel | ASM, NCEP, MDL, OHD | 11 | 21 |  |  | X
[5 empty] | Total | 66.55 | 115.3
Strategic
6 | 05-068 | Graphical Products in AWIPS | Aviation | Beth McNulty | ASM | 8 | 12 | X | X
33 | 06-054 | Transition to GOES-N | Satillite | Jim Heil | ASM, NESDIS | 0.5 | 1 | X
39 | n/a | Support for CTR with Raytheon | Support | Raytheon | GSD | 3 | 5 | X
40 | n/a | Development Kit Evaluation | Support | Raytheon | GSD | 2 | 4 | X
13 | 06-014 | Complete Integration of RFC QPE Tools into a Common National QPE System (i.e., Daily QC) | Hydrology | Kevin Lynott | OHD | 20 | 24 | X | X | X
24 | 06-030 | Characterize Hydrologic Point Fcst within IHFS Database | Hydrology | Kevin Lynott | OHD | 3 | 5 | X
| n/a | AWIPS Evolution: Overall Task | Infrastructure | Jason Tuell | GSD | 4 | 6 | X | X | X
4 | 05-009 | Analysis of Record | Model | Lee Anderson | ASM, NCEP | 2.5 | 3.8 |  | X | X
3 | 05-007 | NCEP Short/Med Range Models | Model | Brian Gockel | ASM, NCEP | 1.1 | 1.7 |  | X | X
15 | 05-001 | Application of GFE for RFCs | GFE | Kevin Lynott | GSD | 2 | 4 |  | X
12 | 05-084 | 4-D StormCell Investigator | Decision Assist | Greg Stumpf | MDL | 4 | 6 |  | X
10 | 04-002 | Super Resolution 88D base products | Radar | Mike Istok | GSD | 1 | 3 |  | X
41 | 06-051 | GFE Performance Improvements | GFE | Mark Mathewson | GSD | 14 | 16 |  | X | X
16 | 05-060 | GIS for RFCs | Data | Frank Richards | ENV | TBD | TBD |  |  | X
34 | 05-078 | Next Generation Wind Profiler | Obs | Al Wissman (OOS) | ASM | TBD | TBD |  |  | X?
1 | 04-007 | Distributed Hydrologic Modeling | Hydrologic, GFE, Display | Lee Cajina | OHD, ASM | 25 | 29 | X | X | X
19 | 06-022 | Re-Implement/Modernize the NWSRFS Interactive Calibration Program (ICP) | Hydrology | Kevin Lynott | OHD | 24 | 28 |  |  | X
25 | 06-025 | Hydrologic Ensemble Forecast and Verification | Hydrology | Kevin Lynott | OHD | 11 | 13 |  |  | X
26 | 06-024 | Hydrologic Ensemble Hindcaster | Hydrology | Kevin Lynott | OHD | 15 | 18 |  |  | X
28 | 06-009 | Increase Spatial and Temporal resolution of MPE QPE Grids | Hydrology | Kevin Lynott | OHD | 12 | 15 |  |  | X
29 | 06-032 | Add Multisensor Preciptiation Nowcaster to MPE | Hydrology | Kevin Lynott | OHD | 8 | 10 |  |  | X
11 | xx-xxx | Ensembles | Model | OST - TBD | ASM, GSD, NCEP | 19 | 27 |  |  |  | X
5 | 05-081 | NWS AWIPS Software Training Capability | Training | Mike Magsig | ENV, GSD | 31 | 45 |  |  |  | X
17 | 05-021 | AWIPS Evolution: Visualization Techniques | Display | Mark McInerney | GSD | 7 | 8 |  |  |  | X
32 | 05-042 | AWIPS Evolution: Collaboration | Digital Services | Darien Davis | GSD | 7 | 8 |  |  |  | X
14 | xx-xxx | WHFS Site-Specific Hydrologic Prediction (SSHP) Model | Hydrology | Jeff Zimmerman | OHD | 12 | 16 |  |  |  | X
27 | 06-035 | Compute Probabilistic QPE from Radar Data | Hydrology | Kevin Lynott | OHD | 12 | 16 |  |  |  | X
30 | 06-015 | Provide DHM capability for Flash Flood Forecasting | Hydrology | Kevin Lynott | OHD | 27 | 30 |  |  |  | X
31 | 06-039 | NA Scale Remote Sensor Precipitation Estimation | Hydrology | Kevin Lynott | OHD | TBD | TBD |  |  |  | X
8 | 05-038 | 4D Weather Information | Aviation | Kevin Johnston | MDL | TBD | TBD |  |  |  | X
[5 empty] | Total | 275.1 | 354.5
Adaptive and Corrective Maintenance
1 | n/a | Backlog DRs (210 DRs) |  |  | ASM, OHD, GSD, MDL, OOS | 22 | 42 | X | X | X
55 | n/a | NMAP Integration |  | Steve Schotz | NCEP | 1 | 3 | X | X | X
42 | n/a | LAPS/MSAS Integration | Models | Linda Worthington | GSD | 0.5 | 1 | X | X | X
56 | 05-062 | Low Cloud Base Product | Aviation | Mike Graf | ASM, NESDIS | 2 | 3 | X |  | X
57 | 06-048 | Polar Microwave Products | Satillite | Jim Heil | ASM, NESDIS | 2 | 3 | X | X
40 | 06-017 | Hazcollect to call NWRWAVES vice NWEM CAFÉ | Dissemination | Tim Hopkins | GSD | 1 | 2 | X
58 | 05-080 | Warning by Polygon (NWS 10-511) | Directive | John Ferree | GSD | 3 | 5 | X | X
19 | 06-016 | Enhance NWSRFS Streamflow Regulation Accounting Tools | Hydrology | Kevin Lynott | OHD | 7 | 11 | X |  | X
33 | 06-037 | Enhance HydroGen to Pull Additional Data from IHFS | Hydrology | Frank Richard | OHD | 2 | 4 | X
39 | 06-011 | Guardian (Integration of Applications) | Decision Assist | Tom Filiaggi | MDL, ASM, OHD | 4 | 8 | X
46 | xx-xxx | Aviation Forecast Preparation System (AVNFPS) | Aviation | Mike Graf | MDL | TBD | TBD | X | X | X
27 | 06-007 | SAFESEAS: Add NOS tide gage water depth values | Decision Assist | Mike Churma | MDL | 3 | 4 | X
44 | 06-004 | Fog Monitor: Add statistical calculations for users | Decision Assist | Mike Churma | MDL | 5 | 6 | X
13 | 06-041 | Centrally produced 5 km NWP derived grids of sensible weather elements for AWIPS and GFE for CONUS and OCONUS | Model/GFE | Jeff Waldstreicher | ASM, NCEP | 6 | 12 |  | X | X | X
17 | 05-006 | Gridded MOS (add AK, Hawaii, PuertoRico) | Model | Ed Mandel | ASM | 2.25 | 3.4 |  | X | X | X
14 | 05-070 | Improved Medium-Range Model Guidance (e.g., ECMWF, NOGAPS) | Model | Mark Mollner | ASM, NCEP | 3.35 | 5.1 | X | X
45 | 06-021 | Segmentation of the Hurricane Local Statement | Decision Assist | Therese Pierce | ASM | 3 | 5 |  | X
47 | 06-020 | GFE Formatter & Smart Tools for WFO Tropical Cyclone Hazard Graphics | Marine | Tim Schott | ASM | 2 | 4 |  | X
48 | 06-019 | Incorporation of tropical cyclone conditional terms in selected public and marine products | Marine | Scott Kiser | ASM | 1 | 2 |  | X
49 | 06-033 | Automate insertion of Dam Break data into a FFW | Decision Assist | Tom Donaldson | ASM | 1 | 2 |  | X
50 | 06-026 | Headline Flexibility for Long Duration Products | GFE | Paul Stokols | ASM | 4 | 8 |  | X
51 | 06-027 | Need accurate cities list in the MND header for long-duration products | GFE | Paul Stokols | ASM | 2 | 4 |  | X
52 | 06-029 | Attribution phrase in long-duration products | GFE | Paul Stokols | ASM | 4 | 9 |  | X
54 | 06-042 | Add Lake Effect attribute to GFE | GFE | Paul Stokols | ASM | 2 | 4 |  | X
8 | 06-043 | Estimated Actual Velocity | Radar | SR | GSD | 1 | 2 |  | X
35 | 06-023 | Enhance NWSRFS Deterministic Verification Tools | Hydrology | Kevin Lynott | OHD | 5 | 7 |  | X
20 | 06-012 | FFMP: Advanced Design (e.g., Adjust Data Handling, Combine QPE and QPF, Ingest Grid precipitation, debris flow) | Decision Assist | Tom Filiaggi | MDL | 5.6 | 6.4 |  | X
4 | 05-066 | Additional TDWR products (e.g., storm track, mesocyclone, tornado, rainfall accumulation, VIL) | Radar | Pete Pickard | ASM | 2 | 4 |  |  | X
12 | xx-xxx | FNMOC Wave Watch Model Guidance | Model | Chris McAloon | ASM, NCEP | 3 | 5 |  |  | X
30 | 05-042 | Enhance Chat Server | General | Tim Hopkins | ASM | 3 | 5 |  |  | X
10 | 06-049 | Integrated Radar/Environmental Sampling | Radar | Mike Magsig | GSD | 3 | 5 |  |  | X
18 | 06-018 | Replace SACSMA Frozen Ground Algorithm | Hydrology | Kevin Lynott | OHD | 14 | 16 |  |  | X
36 | 06-038 | Automated Rain Gauge QC to MPE | Hydrology | Kevin Lynott | OHD | 6 | 8 |  |  | X
[5 empty] | Total | 125.7 | 208.9