## Current Tasks
Updated 11/20/07
Task | Subtask | Who | Start | End | Completed
KEY:
Red: Highest Priority; Blue: Completed; Black: Upcoming
Aura2 Combo DAS reruns with new spinup |  |  |  | 2008-01-21
Complete 2 year spinup with 2004 |  | Megan | 2007-10-23 | 2007-11-02 | 2007-11-05
Implement new MEGAN emissions code |  | Jules | 2007-09-04 | 2007-11-30
Obtain input files from Harvard |  | Jules | TBD | TBD
Perform an additional year spinup with merged code |  | Megan | 2007-11-30 | 2007-12-14
Add code to output cloud fractions in overpass files |  | Jules | 2007-11-28 | 2007-11-30
Add column diagnostics to proper files |  | Megan | 2007-11-26 | 2007-12-05
Perform reruns, 2004-2006 w/ new restart file& MEGAN Emissions |  | Megan | 2007-12-15 | 2008-01-21
Processing GEOS Met Fields |  |  |  | 2007-11-28
Test GFIO for 3D variables |  | Megan | 2007-10-01 | 2007-10-31 | 2007-11-01
Generate scripts to process GEOS5 fields |  | Megan | 2007-09-21 | 2007-11-28
GEOS-1/GISS runs |  |  |  | 2007-12-20
Find/investigate required metfields |  | Gary | 2007-11-26 | 2007-11-29
Generate namelist files/scripts |  | Gary | 2007-11-30 | 2007-12-03
Perform runs |  | Gary | 2007-12-04 | 2007-12-20
Lightning Runs |  |  |  | 2007-11-30
Test ap1.1 parameterizations |  | Megan | 2007-11-06 | 2007-11-30
Combo Integration with GEOS-5
Remove mcor inside emission component |  | Jules
Assist GMAO as needed |  | Jules
Add advecCore to the GMI code |  |  |  | 2008-01-15
Modify I/O to eliminate ESM framework |  | Jules | 2007-08-30 | 2007-12-15 | 2007-11-01
Add advecCore into code |  | Jules | TBD | 2008-01-15
Processing ECMWF Met Fields
Contact M. Prather about metfields with great vt extent |  | Gary/Jules | 2007-09-19 | 2007-09-19 | 2007-09-19
Process 2006 ECMWF fields from Michael Prather |  | Jules/Tom | TBD | TBD
Other Code Updates/Model Runs/Issues |  |  |  | Varies
Update production run spreadsheet |  | Megan | 2007-09-22
Merge code branches onto the trunk (aura/lightning) |  | Jules/Megan | 2007-11-09 | 2007-11-30
Calculate total column ozone for das and fvgcm runs |  | Gary/Megan | 2007-09-21 | 2007-11-16
Generate draft GMI User's Guide |  | Megan/Gary/Jules | 2007-06-26 | 2007-12-15
Generate self-contained/regression tests for code |  | Megan | 2007-09-12 | 2007-12-07
Add README to code with disclaimer |  | Jules | 2007-11-26 | 2007-11-26
Assist Debra Weisenstein as needed |  | Jules
Fix advec_opt bug |  | Jules | 2007-12-04 | 2007-12-05
Begin migrating from email groups to ModelingGuru |  | GMI Team | TBD | TBD
Fix date/met field bug |  | Jules/Megan | TBD | TBD
Fix leap year bug |  | Jules/Megan | TBD | TBD
Fix "no emission" bug |  | Jules | TBD | TBD
Introduce aerosol/gas phase coupling |  | Jules/Megan | TBD | TBD
Implement/test fastjx6.1 |  | Jules | TBD | TBD
Implement stratospheric water transport |  | TBD | TBD | TBD
Add Linoz to the model |  | Jules/Steve
Test Combo/strat code with GCR files |  | Jules/Steve
Baseline w/ new trop 124 sp, JPL06-2, H2 fix, fastjx53c |  | Gary
Diagnose strange "filename" problem (compiler?) |  | Jules et al.
Huisheng's problem with running multiple jobs |  | Jules/Hamid/Huisheng
Condense emissions variables into two variables |  | Jules
Continue code componentization
| Complete Metfields Componentization | Jules
| Remove default settings from code | Jules
Change netCDF data format |  | Jules
Help develop NCCS data-sharing for GMI data |  | Gary
Hindcast runs |  | Megan
Introduce mesospheric chemistry |  | Jules/Megan
Prepare ESMF Wrappers for GMI code |  | Jules

## Completed Tasks
Task | Subtask | Who | Start | End | Completed
GEOS4-DAS/GEOS4 Forecast Combo Runs (AGU) |  |  |  | 2006-12-08 | 2006-11-30
Fix Soil NOx Problem |  | Jules/Bryan | 2006-11-02 | 2006-11-09 | 2006-11-09
Prepare code and namelist file for runs |  | Bigyani/Jules | 2006-11-02 | 2006-11-16 | 2006-11-17
Obtain/implement new emissions inventory from Bryan |  | Bigyani | 2006-11-13 | 2006-11-16 | 2006-11-14
Run Combo with GEOS4-DAS and Forecast fields |  | Bigyani | 2006-11-13 | 2006-11-16 | 2006-11-22
Validate output of Combo DAS and Forecast runs |  | Bigyani/Jules/Gary | 2006-11-22 | 2006-11-24 | 2006-11-24
Run Combo GEOS4DAS w/Harvard 2005 emissions Feb-Apr 2005 runs |  | Bigyani | 2006-11-24 | 2006-11-27 | 2006-11-27
Run Combo GEOS4DAS and Forecast fields, no fire |  | Bigyani | 2006-11-27 | 2006-11-28 | 2006-11-30
Other Code Updates/Model Runs/Issues |  |  |  | Varies
Investigate microphysical aerosol INF/NaN value problem |  | Bhat/Bigyani | 2006-11-22 | 2006-12-01 | 2006-11-29
Add aerosol components to FASTJX-53c |  | Jules | 2006-11-17 | 2006-12-01 | 2006-12-07
Re-run pre-ind microphysical aerosol model w/o FF |  | Bigyani | 2006-12-08 | 2006-12-20 | 2006-12-22
Run pre-ind aerosol model w/ present oxidant fields |  | Bigyani | 2006-12-29 | 2007-01-03 | 2007-01-03
Add capability to read in monthly photolysis rates |  | Jules | 2006-12-15 | 2007-01-08 | 2007-01-08
Provide AEROCOM emissions at 4x5 to GA Tech |  | Bigyani | 2007-01-09 | 2007-01-11 | 2007-01-11
Assist with implementation of GOCART aersol code |  | Jules | 2007-01-16 | 2007-01-17 | 2007-01-17
Provide MicroPhysical Code to GA Tech |  | Gary | 2007-01-18 | 2007-01-22 | 2007-01-19
Update code for daily emissions |  | Jules | 2007-01-09 | 2007-01-19 | 2007-01-19
Update code for Aerosol Dust emissions |  | Jules | 2007-01-09 | 2007-01-19 | 2007-01-19
Change station "column" files to "profile" files |  | Bigyani | 2007-01-26 | 2007-01-29 | 2007-01-29
Add code to output surface aerosol emissions |  | Jules | 2007-01-19 | 2007-01-25 | 2007-01-22
Obtain online storage for GMI input/output data |  | Gary | 2007-01-18 | 2007-02-01 | 2007-02-06
Generate up to 9 preliminary GMI slides for MAP conference |  | Gary/Jules/Bigyani | 2007-01-23 | 2007-02-06 | 2007-02-08
Develop directory structure on discover |  | Gary | 2007-02-02 | 2007-02-06 | 2007-02-10
Finalize slides for MAP conference |  | Gary | 2007-02-07 | 2007-03-02 | 2007-03-04
Add H2 fix |  | Jules | 2007-02-09 | 2007-02-09 | 2007-02-09
Continue learning how to run GMI models |  | Gary/Megan | 2006-12-18 | 2007-03-15
Help Boeing with Combo code |  | Jules | 2007-03-05 | 2007-03-06 | 2007-03-06
Help Yasuko/Bryan with Combo on discover |  | Megan/Jules | 2007-01-22 | 2007-03-23 | 2007-03-30
Generate GMI model version numbers |  | Gary et al. | 2007-03-24 | 2007-04-06 | 2007-04-19
Reconfigure station profile input |  | Jules | 2007-04-10 | 2007-04-20 | 2007-04-23
Profile the GMI code |  | Jules/Hamid | 2007-04-05 | 2007-04-12 | 2007-04-05
Insert disclaimer into code |  | Jules | 2007-04-17 | 2007-04-20 | 2007-04-20
Investigate reasons output differences on halem/discover |  | Jules/Megan | 2007-05-15 | 2007-06-15 | 2007-05-18
Commit tagged CO and age of air code |  | Jules | 2007-05-16 | 2007-05-16 | 2007-05-16
Copy aura/tagged CO data to gmidata2 |  | Gary/Megan | 2007-04-30 | 2007-05-11 | 2007-05-17
Copy SR1 aerosol/full_chem data to gmidata2 |  | Gary | 2007-05-18 | 2007-05-21 | 2007-05-21
Assist AER (Weisenstein) with running code |  | Jules | 2007-05-24 | 2007-05-24 | 2007-05-24
Continue code componentization
| Replace species number with name | Jules/Tom | 2007-02-16 | 2007-03-23 | 2007-03-20
| Reorganize namelist file | Jules | 2007-02-16 | 2007-03-02 | 2007-03-04
| Complete species componentization | Jules | 2007-04-14 | 2007-05-02 | 2007-05-02
Locate data needed for Aerocom runs for Rafaella |  | Gary | 2007-05-30 | 2007-06-04 | 2007-06-08
Answer Jennifer's station profile questions |  | Gary/Jules | 2007-06-15 | 2007-06-22 | 2007-06-21
Recover files from discover disk problem |  | Megan/Gary | 2007-06-27 | 2007-06-29 | 2007-06-29
Update KMG package |  | Jules | 2007-07-02 | 2007-07-05 | 2007-07-05
Convert KMG codes to produce free format |  | Jules | 2007-07-05 | 2007-07-06 | 2007-07-06
Fix bug with col diag species |  | Jules/Megan | 2007-07-09 | 2007-07-10 | 2007-07-10
Rewrite lower level communication routines (TPCore related) |  | Jules | 2007-06-15 | 2007-07-20 | 2007-07-25
Fix daily ship emissions problem |  | Jules | 2007-06-22 | 2007-07-31 | 2007-07-19
Assist Huisheng with Michigan aerosol code on discover |  | Jules | 2007-08-10 | 2007-08-15 | 2007-08-15
Write modules to initialize model components |  | Jules | 2007-08-06 | 2007-08-24 | 2007-08-14
Implement new GA Tech aerosol/cloud code segments |  | Jules | 2007-08-24 | 2007-09-07 | 2007-08-30
Assist Yasuko with isoprene emissions |  | Jules | 2007-08-24 | 2007-08-31 | 2007-09-05
Allow surface output for station profiles |  | Jules | 2007-08-30 | 2007-09-07 | 2007-09-19
Process newly generated HTAP full_chem data |  | Gary | 2007-10-15 | 2007-10-19 | 2007-10-18
Re-establish QA/info system for model runs |  | Megan/Gary/Jules | 2007-09-17 | 2007-09-28 | 2007-10-10
Implement code to use hourly emissions |  | Jules | 2007-09-24 | 2007-09-28 | 2007-09-28
Assist Hiusheng with porting AOT code to NCCS |  | Jules | 2007-09-11 | 2007-09-25 | 2007-09-25
Determine timing/profiling info about GMI code |  | Jules | 2007-11-06 | 2007-11-07 | 2007-11-07
Implement biomass burning NO emissions |  | Jules | 2007-09-22 | 2007-11-09 | 2007-11-09
Add new column diagnostics |  | Jules | 2007-11-08 | 2007-11-13 | 2007-11-13
Rewrote the freq diagnostics |  | Jules | 2007-11-01 | 2007-11-16 | 2007-11-16
Implement standard column calculations in code |  | Megan/Jules | 2007-09-24 | 2007-11-16 | 2007-11-13
Update model version numbers |  | Gary/Megan/Jules | 2007-10-25 | 2007-10-31 | 2007-11-05
Propose New GMI Directory Structure |  |  |  | 2007-02-28 | 2007-03-07
Complete summary of directory structure on dirac and palm |  | Bigyani | 2006-11-08 | 2006-11-15 | 2006-11-14
Develop new input/output directory structures |  | Gary et al. | 2006-11-20 | 2006-12-20 | 2007-01-08
| Discuss first draft with SIVO | Gary et al. | 2007-01-18 | 2007-01-18 | 2007-01-18
| Edit new structure briefing | Gary | 2007-01-19 | 2007-01-25 | 2007-01-29
| Make final edits | Gary | 2007-01-31 | 2007-02-07 | 2007-02-08
Copy data to new directories and rename |  | Gary | 2007-02-07 | 2007-02-28 | 2007-03-07
GEOS4-DAS Combo (Aura) Re-runs
Update code to output potential vorticity |  | Jules | 2006-11-12 | 2006-11-15 | 2006-11-15
Fix truncated ozone profile problem |  | Bigyani | 2006-11-27 | 2006-12-13 | 2006-12-20
Generate Background Fields: 6 years spinup |  |  | 2006-11-24 | 2007-01-15
| Run 1998-2002 4x5 | Bigyani | 2006-11-29 | 2006-12-06 | 2006-12-04
| Regrid 2002 to 2x2.5 | Bigyani/Bhat | 2006-12-15 | 2006-12-18 | 2006-12-21
| Run 2003 2x2.5 | Bigyani | 2007-01-09 | 2007-01-15 | 2007-01-18
Complete evaluation of FASTJX-53c |  | Jules/others | 2006-11-09 | 2006-11-13 | 2006-11-13
Update code for new species output and output frequency |  | Jules | 2006-11-29 | 2006-12-05 | 2006-12-20
Update code for new noon_species (overpass1 and overpass2) |  | Jules | 2006-11-24 | 2006-11-29 | 2006-12-04
Update code to output cloud optical depth |  | Jules | 2006-12-04 | 2006-12-05 | 2006-12-05
Implement new qj_update.F |  | Jules | 2006-12-01 | 2006-12-04 | 2006-12-18
Add D. Considine's strat chem fix |  | Jules | 2006-12-13 | 2006-12-13 | 2006-12-13
Update code for new vort/trop pressure calc |  | Jules | 2006-11-20 | 2006-12-15 | 2006-12-18
Add code to fix shallow convection problem |  | Jules | 2006-12-14 | 2006-12-15 | 2006-12-18
Put flux diagnostics code in trunk version |  | Jules | 2006-12-11 | 2006-12-15 | 2006-12-18
Implement ozone column diagnostic from photolysis |  | Jules | 2006-12-13 | 2006-12-15 | 2006-12-18
Implement surface ozone output code |  | Bigyani | 2006-12-14 | 2006-12-15 | 2006-12-21
Generate output file names for Aura runs |  | Gary/Bigyani | 2007-01-04 | 2007-01-04 | 2007-01-08
Add code to output freq1 at specified time |  | Bigyani | 2007-01-18 | 2007-01-18 | 2007-01-18
Test emission code with ship emissions |  | Jules | 2007-01-23 | 2007-01-24 | 2007-01-24
Add code to read daily ship emissions |  | Jules | 2007-01-25 | 2007-01-26 | 2007-01-25
Output additional ship emissions diagnostics |  | Jules | 2007-01-25 | 2007-01-29 | 2007-01-29
Allow output of grid variables in necessary output files |  | Jules/Bigyani | 2007-01-29 | 2007-01-29 | 2007-01-29
Investigate array bounds problem in advection code |  | Jules | 2007-03-12 | 2007-04-12 | 2007-05-01
Investigate floating point problem in convection |  | Jules/Steve | 2007-03-12 | 2007-03-19 | 2007-03-19
Complete Aura re-run 2004-5 2x2.5 |  | Gary/Megan | 2007-03-19 | 2007-03-31 | 2007-03-25
Validate Aura re-run data |  | Gary | 2007-03-19 | 2007-03-31 | 2007-03-25
Perform Aura runs for 2006 |  | Gary/Jules | 2007-04-02 | 2007-04-16 | 2007-04-16
Incremental 1 year 4x5 FVGCM Combo Code Tests
Perform Baseline run |  | Bigyani | 2007-02-21 | 2007-02-24 | 2007-02-24
Baseline with new tropopause definition |  | Bigyani | 2007-02-24 | 2007-02-26 | 2007-02-28
Baseline w/ new trop, 124 species |  | Bigyani | 2007-02-26 | 2007-02-28 | 2007-03-01
Baseline w/new trop 124 sp & JPL06-2 |  | Bigyani | 2007-03-01 | 2007-03-02 | 2007-03-02
Baseline w/new trop 124 sp & JPL06-2 & H2 fix |  | Bigyani | 2007-03-03 | 2007-03-03 | 2007-03-05
Test #3 but with a het rxn=0 |  | Gary | 2007-03-15 | 2007-03-17 | 2007-03-23
HTAP simulations
Meet with GMI Scientists to determine requirements |  | Gary | week of 1/15/07 | week of 1/15/07 | 2007-01-18
Add code for new emissions diagnostics |  | Jules | 2007-02-08 | 2007-02-16 | 2007-02-15
Help with code for regional emissions experiments |  | Jules | 2007-02-16 | 2007-02-16 | 2007-02-16
Assist Huisheng with runs |  | Jules | 2007-02-21 | 2007-03-01 | 2007-03-05
Convert GMI aerosol output to HTAP format |  | Gary/Jules | 2007-03-12 | 2007-04-04 | 2007-04-05
Complete conversion of SR1 data into HTAP format |  | Gary/Jules
| Generate tracerm file | Gary/Jules | 2007-05-09 | 2007-05-18 | 2007-05-18
| Generate depm file | Gary/Jules | 2007-05-09 | 2007-05-18 | 2007-05-18
| Generate emim file | Gary/Jules | 2007-05-09 | 2007-05-18 | 2007-05-18
Convert new GMI aerosol output to HTAP format |  | Gary | 2007-06-26 | 2007-06-30 | 2007-07-05
Reprocess SR1 full chem output into HTAP format |  | Gary | 2007-07-16 | 2007-07-23 | 2007-07-24
Process data for other full chem experiments |  | Gary | 2007-08-01 | 2007-08-30 | 2007-09-07
Lightning Algorithm Runs (Trop Model 2x2.5)
Determine which algorithm to use |  | Gary | 2007-01-19 | 2007-01-19 | 2007-01-19
Generate namelist files |  | Gary/Megan | 2007-03-01 | 2007-03-05 | 2007-03-12
Edit aura2 restart file for troposphere run |  | Bryan | 2007-02-23 | 2007-03-01 | 2007-03-01
Perform 1 month test run and deliver to scientists |  | Megan | 2007-03-15 | 2007-03-22 | 2007-03-26
Identify cause of emission problem in lightning run |  | Megan/Gary/Jules | 2007-04-04 | 2007-04-13 | 2007-04-06
Investigate problem with flashrates in new algorithm |  | Megan | 2007-04-04 | 2007-06-01 | 2007-06-01
Run 2 13-month runs, DAS, new and old algorithm |  | Megan | 2007-06-01 | 2007-06-08 | 2007-06-07
FVGCM 1994-96 default lightning |  | Megan | 2007-06-08 | 2007-06-30 | 2007-07-05
FVGCM 1994-96 new lightning |  | Megan | 2007-06-08 | 2007-06-30 | 2007-07-05
GEOS4DAS 2004,2004-5 default lightning |  | Megan | 2007-06-08 | 2007-06-30 | 2007-06-19
GEOS4DAS 2004,2004-5 new lightning |  | Megan | 2007-06-08 | 2007-06-30 | 2007-06-19
Re-do runs as requested |  | Megan | 2007-07-10 | 2007-07-12 | 2007-07-12
Processing GEOS Met Fields
Modify scripts to process data in near-realtime |  | Megan | 2006-11-02 | 2006-11-29 | 2006-12-08
Test operationally modified scripts for 2x2.5 |  | Megan | 2006-12-09 | 2007-01-18 | 2007-01-10
Fix slp problem in near realtime script |  | Megan | 2007-02-09 | 2007-02-16 | 2007-02-16
Fix tropopause units |  | Megan | 2007-02-20 | 2007-02-26 | 2007-03-05
Reprocess fields for slp (Jul-Dec 2006) and tropopause pressure |  | Megan | 2007-02-27 | 2007-03-15 | 2007-03-09
Process archived 2006 met fields |  | Megan | 2007-01-11 | 2007-03-20 | 2007-03-09
Investigate potential problems in 4x5 polar regions |  | Megan | 2007-03-27 | 2007-04-20 | 2007-04-05
Reprocess G4 4x5 fields for vt coord. Jan-Jun 2006 |  | Megan | 2007-06-01 | 2007-07-02 | 2007-07-02
Compare G4DAS and G5DAS variables |  | Megan | 2007-07-02 | 2007-07-11 | 2007-07-11
Compile complete list of G5DAS variables for GMI use |  | Megan/Steve | 2007-07-12 | 2007-07-18 | 2007-07-20
Gather comments on G5 variable list from GMI community |  | Megan/Gary/Susan | 2007-08-02 | 2007-08-30 | 2007-09-17
Test GFIO for 2D variables |  | Megan | 2007-08-15 | 2007-09-03 | 2007-08-31
Forecast Combo (Aura) runs
Prepare namelist files |  | Gary | 2007-05-07 | 2007-05-15 | 2007-05-25
Perform requested runs
| 24h forecast | Gary | 2007-05-07 | 2007-06-13 | 2007-05-29
| 12h forecast | Gary | 2007-05-07 | 2007-06-13 | 2007-05-29
Determine which emissions were used vs aura2 |  | Gary | 2007-06-25 | 2007-06-26 | 2007-06-26
Perform additional runs if necessary |  | Gary | 2007-06-26 | 2007-07-12 | 2007-07-12
2001 and 2006 Aura Combo Runs (w/o HO2 uptake) |  |  |  | 2007-08-06
Complete 2001 runs |  | Gary | 2007-08-01 | 2007-08-06 | 2007-08-14
Complete 2006 runs (with 2006 emissions) |  | Megan | 2007-08-01 | 2007-08-06 | 2007-08-14
Combo Integration with GEOS-5
Create I/O wrappers for Emissions and Chemistry |  | Jules | 2007-05-31 | 2007-06-22 | 2007-06-22
Make test program to validate code changes |  | Jules | 2007-07-12 | 2007-07-17 | 2007-07-17
Resolution Doubling Experiments
Contact M. Prather for background info |  | Gary | 2007-07-10 | 2007-07-10 | 2007-07-10
Perform 1 month test runs |  | Gary | 2007-08-10 | 2007-08-30 | 2007-09-07
New 2004-6 Aura Combo runs (w/ HO2 uptake and lightning) |  |  |  | 2007-09-17
Generate namelist files |  | Megan/Gary | 2007-08-01 | 2007-08-07 | 2007-08-07
Implement level-specific output code |  | Jules | 2007-08-31 | 2007-09-06 | 2007-08-31
Add capability to output subdomains only |  | Jules | 2007-09-07 | 2007-09-14 | 2007-09-12
Complete runs starting at June 2005 |  | Megan | 2007-09-06 | 2007-09-17 | 2007-09-15
Resolution Doubling Experiments |  |  |  | 2007-10-22
Perform short tests as needed |  | Susan/Steve | TBD | TBD
Perform 10 year runs |  | Susan/Steve | TBD | TBD
5yr FVGCM Aura Combo runs |  |  |  | 2007-10-03
Generate namelist files |  | Megan | 2007-08-30 | 2007-08-30 | 2007-08-30
Perform runs |  | Megan | 2007-08-30 | 2007-10-19 | 2007-10-03
Add advecCore to the GMI code
Meet with TransCore developers |  | Jules/Megan | 2007-09-14 | 2007-09-14 | 2007-09-14
Determine input requirements of TPCore |  | Jules | 2007-09-20 | 2007-09-24 | 2007-10-02
Determine input requirements of advecCore |  | Jules | 2007-09-24 | 2007-09-27 | 2007-10-02
Lightning Runs |  |  |  | 2007-11-30
Obtain and Implement new NOx distribution and factors |  | Megan | 2007-09-21 | 2007-09-28 | 2007-10-01
Perform runs | DAS 2004-5, new lightning | Megan | 2007-10-09 | 2007-11-09 | 2007-11-09
| FVGCM 1994-6, new lightning | Megan | 2007-10-09 | 2007-11-09 | 2007-11-09
| DAS 2004-5, Nox from file | Megan | 2007-10-09 | 2007-11-09 | 2007-11-09
| FVGCM 1994-6, Nox from file | Megan | 2007-10-09 | 2007-11-09 | 2007-11-09
| DAS 2004-5, no NO from lightning | Megan | 2007-10-09 | 2007-11-09 | 2007-11-09
| Forecast runs, new lightning | Megan | 2007-10-25 | 2007-11-09 | 2007-11-09