## CDFI
CDFI
FY 2006 YEAR END SCHEDULE
CDFI
RESPONSIBILITY | CDFI | Completed Date | Due Date | Responsible Party | Responsible Entity | Completed Date
4TH QUARTER / YEAR END:
Coordinate Y/E due dates with customers | Matt |  | 2006-08-18 | Mat | ARC
Request imputed audit cost from AIC. | CDFI-Valencia |  | 2006-08-28 | CDF | CDFI
Last date to submit Travel authorizations through Gov Trip for travel prior to 9/30/06. | CDFI |  | 2006-08-31 | CDF | CDFI
Provide the Department with completed updated imputed cost forms - Appendix A. | Peggy |  | 2006-09-01 | Peg | ARC
Request year end fieldwork PBC list from client/auditors (should include ALL known year end audit needs). | CDF-Valencia/ Peggy |  | 2006-09-05 | CDF | CDFI
Close Oracle accounting period 13 06 (AUG/06-06). | SSB |  | 2006-09-05 | SSB | ARC
Submit TIER period 11. | Joy |  | 2006-09-06 | Joy | ARC
Notify customers that preliminary open items adjustments and certifications are due on 9/13 | Matt |  | 2006-09-06 | Mat | ARC
ARC provides draft text of financial statement footnotes to customer for review and comment (comments are due 9/20). | Peggy |  | 2006-09-06 | Peg | ARC
Department updates TIER Master Appropriation File (MAF) for bureau review - due 9/12 | Dept |  | 2006-09-06 | Dep | Department
Final FY2005 subsidy reestimate and SF-132s are due today so that entries can be posted in Oracle and ARC can begin the interest expense calculation | CDF-Larry |  | 2006-09-07 | CDF | CDFI
IPIA - Provide draft report of the annual amount of high-risk erroneous payments in activities and programs, reduction targets, and progress made in reducing them during FY 2006 (as of 8/31/06) per the final instructions to bureaus and offices for conducting the assessment of and reporting on Improper Payments for FY 2006 to Treasury/AIC | FMB Processing |  | 2006-09-08 | FMB | ARC
Recovery Act - Provide draft report of Recovery Audit Program activity for FY 2006 (as of 8/31/06) to Treasury/AIC per the final instructions to bureaus and offices for establishing and maintaining a Recovery Audit Program and reporting requirements for FY 2006. | FMB Processing |  | 2006-09-08 | FMB | ARC
Bureaus submit draft FMFIA, FFMIA and A-123, Appendix A, Controls over Financial Reporting, Annual Assurance Statements to Treasury | CDFI |  | 2006-09-08 | CDF | CDFI
ARC provides capitalized asset report and capitalization policy for customer review. Comments on capitalization report are due by 9/25. | Bob |  | 2006-09-08 | Bob | ARC
Department posts updated imputed cost information from Appendix A forms on the DCFO Arena. | Dept |  | 2006-09-08 | Dep | Department
Post PAD collections via AR collection Interface. | Peggy |  | 2006-09-12 | Peg | ARC
Bureaus review TIER Master Appropriation File (MAF) and report (e-mail) any needed revisions to AIC - Joe McAndrew (202) 622-0807. | Dana |  | 2006-09-12 | Dan | ARC
Preliminary open items adjustments and certifications due including perliminary FY 06 operating plans, if applicable | CDFI |  | 2006-09-13 | CDF | CDFI
Prepare and review PAD for 9/29 generation. | Bob |  | 2006-09-15 | Bob | ARC
Monthly EFT Report due to Brian Lee | FMB Processing |  | 2006-09-15 | FMB | ARC
Monthly Prompt Pay Report due to Phil Howland | FMB Processing |  | 2006-09-15 | FMB | ARC
Monthly Reconciled/Unreconciled Cash Report due to Dan Waugh | Bob |  | 2006-09-15 | Bob | ARC
Upload August 2006 Statement of Financing to TIER repository. | Joy |  | 2006-09-15 | Joy | ARC
Bureaus submit the completed updated omitted imputed cost forms (AIC Acctg. Policy Memo 05-01 - Appendix B) via TIER | Peggy |  | 2006-09-15 | Peg | ARC
Email CDFI about lease (GSA Rent & Copier) and investment footnotes. | Joy |  | 2006-09-15 | Joy | ARC
Last date to submit year end payroll awards through HRD (after this date, awards may be included in September expense accruals) | CDFI |  | 2006-09-15 | CDF | CDFI
Department distributes OPM cost factors to bureaus | Dept |  | 2006-09-18 | Dep | Department
Begin preparing the OPEB calculations to impute costs of FEHB, FEGLI and FERS/CSRS pension expense (estimate 2 PP based on PP17). Post OPEB by 9/27. | Joy |  | 2006-09-18 | Joy | ARC
Inquire of Phil Howland if our DO bureau customers will receive an allocation of FECA liability (workers' comp) from DO | Stacy |  | 2006-09-18 | Sta | ARC
Prepare preliminary Interest Calculations for CDFI year end. Use old year's rate until new rate is posted. See OMB Credit page for website ("FCRA06"). Due 9/28 | Peggy |  | 2006-09-20 | Peg | ARC
Update contact and Treasury Fund Symbol information for FACTS II. | Dana |  | 2006-09-20 | Dan | ARC
Confirm 162001 balance with CDFI. | Peggy |  | 2006-09-20 | Peg | ARC
Customer agency comments on draft footnotes are due to ARC. | CDFI |  | 2006-09-20 | CDF | CDFI
Monthly PAR meeting (10AM-noon) | Dana/Peggy |  | 2006-09-20 | Dan | ARC
Draft Shortfalls & Future Plans due in PRS | CDF |  | 2006-09-20 | CDF | CDFI
Special payroll accruals for performance and special act awards, and non-routine overtime | CDF |  | 2006-09-22 | CDF | CDFI
Last day to submit cancelling fund (00/01) disbursements (to avoid post month-end cancellation and reissuance of rejected ACHs). | CDFI |  | 2006-09-22 | CDF | CDFI
Any outstanding expiring fund commitments (i.e.single year - 06 or multi-year 05/06) must be obligated or decommitted. | CDFI |  | 2006-09-22 | CDF | CDFI
Monitor OPDA's website for updated credit reform rates. See the following site: (www.whitehouse.gov/omb/credit/c2.html) | Peggy |  | 2006-09-25 | Peg | ARC
FY 2006 capitalized hardware descriptions, useful lives, salvage values and dates placed in service (previously expensed) due to ARC (requested on 9/8). | CDF |  | 2006-09-25 | CDF | CDFI
CDFI provides GSA/FAA breakdown | CDF-Valencia |  | 2006-09-25 | CDF | CDFI
Manual obligations in expiring funds are due to ARC | CDFI |  | 2006-09-26 | CDF | CDFI
Accounts receivable and accounts payable invoices are due. After this date, any revenue or expenses must be included in accruals | CDF |  | 2006-09-26 | CDF | CDFI
Revenue and expense accruals are due including prior month expense accrual adjustments | CDF |  | 2006-09-27 | CDF | CDFI
Interest calculator is due today. | Peggy |  | 2006-09-27 | Peg | ARC
Book OPEB. | Joy |  | 2006-09-27 | Joy | ARC
Depreciation/amortization expense should be posted by today. | Bob |  | 2006-09-28 | Bob | ARC
Using year end interest calculator, prepare IPACs to receive interest revenue from FMS and to pay interest expense to OPDA, provide CDFI with SF-132 revision information and spreadsheet to borrow for interest shortfall. Post associated entries. | Peggy |  | 2006-09-28 | Peg | ARC
Input all repayments and borrowings for interest shortfall in GWA and obtain Larry's approval in GWA for the repayments. NOTE: Borrowing for interest shortfall cannot be approved/processed until 9/30. | CDF-Valencia/Larry |  | 2006-09-28 | CDF | CDFI
Final certification and adjustments to open items are due by noon. | CDFI |  | Noon 9/29/2006 | CDF | CDFI
Generate and transmit PAD between 11AM-11:30. | Peggy/Bob |  | 2006-09-29 | Peg | ARC
Obtain Larry's approval of borrowings for interest shortfall in GWA before 10AM . | CDF-Valencia/Larry |  | 2006-09-29 | CDF | CDFI
A-123, Appendix A - Report to Update Treasury DCFO on the final FY 2006 results and status of all Corrective Action Plans. | CDFI |  | 2006-09-29 | CDF | CDFI
Department conducts Bureau Heads meeting on critical PAR dates and deliverables. | CDFI |  | 2006-09-29 | CDF | CDFI
Close out cancelled year (JV to back out cash and equity). Factor upward and downward adjustments on deobligations. | Peggy |  | 2006-10-02 | Peg | ARC
Send notification to FMB, TSD, CAB, PSD employees not to post any September transactions after October 3, regardless of SEP/06-06's posting availability as trial balances will be considered final after COB 10/3/06. | Dana |  | 2006-10-02 | Dan | ARC
Department submits Financial Statement Templates to FMS based on closing package requirement. | Dept |  | 2006-10-03 | Dep | Department
Book imputed audit costs. | Joy |  | 2006-10-03 | Joy | ARC
Post all year end Financing fund entries (removing anticipated borrowing and zero out anticipated collections - 406001 & 407001). | Budget/Peggy |  | 2006-10-03 | Bud | ARC
Bureaus will provide final narratives for MD&A strategic goals | CDFI |  | 2006-10-03 | CDF | CDFI
Run preliminary Budgetary/Proprietary Reconciliation | Bob |  | 2006-10-03 | Bob | ARC
JE 2007 commitments out of 47**** and 461004. Reverse in OCT/06-07. | Peggy |  | 2006-10-03 | Peg | ARC
JE 2007 obligations out of 480*** and 461004. Reverse in OCT/06-07. | Peggy |  | 2006-10-03 | Peg | ARC
Close 298001 to 101024 for custodial activity. | Peggy |  | 2006-10-03 | Peg | ARC
Close accounting period 14 06 (SEP/06-06). | SSB |  | 2006-10-03 | SSB | ARC
On a daily basis, begin running GL posted Discoverer report to ensure no activity has been posted in SEP/06-06. | Dana |  | 2006-10-04 | Dan | ARC
Submit TIER period 12. AIC submission due date is 10/10. AIC approval is required for period 12 resubmissions between 10/11 - 10/13. | Peggy |  | 2006-10-04 | Peg | ARC
September SF-224 Transmission (3rd workday) | Bob |  | 2006-10-04 | Bob | ARC
Based on bureau's TIER submission, initial draft financial statements will be generated through CFOV based on this data, and posted to the DCFO Web Repository for bureau review as of 12 06. | Dept |  | 2006-10-05 | Dep | Department
Provide an e-mail to customers to let them know the FFMIA/FMFIA assurance has not changed | FMB |  | 2006-10-05 | FMB | ARC
Review GWA Account Summary Statement for other ALCs impact to our September transactions. | Bob |  | 2006-10-05 | Bob | ARC
Provide trial balance to auditors. | Peggy |  | 2006-10-06 | Peg | ARC
IPIA - Provide final report of the annual amount of high-risk erroneous payments in activities and programs, reduction targets, and progress made in reducing them during FY 2006 (as of 9/30/06) per the final instructions to bureaus and offices for conducting the assessment of and reporting on Improper Payments for FY 2006 to Treasury/AIC | FMB Processing |  | 2006-10-06 | FMB | ARC
Recovery Act - Provide final report of Recovery Audit Program activity for FY 2006 (as of 9/30/06) to Treasury/AIC per the final instructions to bureaus and offices for establishing and maintaining a Recovery Audit Program and reporting requirements for FY 2006. | FMB Processing |  | 2006-10-06 | FMB | ARC
Submit TIER period 12 revisions (with AIC approval) for FACTS II Submission (FACTS II Window = 10/6-10/26). Upon notification from Treasury that FACTS II submission was successful, login to FACTS II and run and print SF-133's, SF-2108 and ATB's. Send copies of reports and certification statement to customers - certification due to ARC on 10/24. ARC certification on FACTS II website due 10/26. | Peggy |  | 2006-10-10 | Peg | ARC
Run FACTS II cohort file and begin reviewing cohort information | Peggy |  | 2006-10-10 | Peg | ARC
DO/FMD will issue the 4th quarter Transactions by Fund and Vendor Report, which includes Working Capital Fund advance information. NOTE: Post in October if WCF liquidation is posted after 10/3. | Bob/Aaron |  | 2006-10-10 | Bob | ARC
Final report on actions taken to address FY 2005 Management Challenges/High-Risk Areas to be e-mailed to I-Ming Clark. | CDFI |  | 2006-10-11 | CDF | CDFI
Final performance data and explanations of shortfalls due into Performance Reporting System (PRS) | CDFI |  | 2006-10-12 | CDF | CDFI
Check "Judgment Fund" website for claims (http://www.fms.treas.gov/judgefund/) | Joy |  | 2006-10-12 | Joy | ARC
FMS 6652,6653,6654 &6655 Available - Prepare cash rec and determine if TIER needs to be resubmitted due to cash outlays. | Bob/Peggy |  | 2006-10-12 | Bob | ARC
Contact Phil Howland to determine amount (if applicable, based on 9/16 response) that our DO bureau customers will receive of FECA liability (workers comp) allocation from DO (NOTE: See 9/16) | Peggy |  | 2006-10-12 | Peg | ARC
Prepare draft OMB 01-09 (and GAAP) statements, footnotes and supplementary information and compare the 01-09 statements to FARS statements. Note any AIC crosswalk differences. | Peggy |  | 2006-10-13 | Peg | ARC
Drafts due for: 1) Statement of Financing (if not fully automated); 2) Notes to the financial statements; 3) MD&A (future effects); and 4) Required Supplemental Information and Other Accompanying Information. | CDFI/ARC |  | 2006-10-13 | CDF | CDFI
Annual Assurance - Unaudited Bureau and Offices submit FINAL FMFIA, FFMIA, and A-123, Appendix A, Controls Over Financial Reporting, Annual Assurance Statement to Treasury (A-123 section only required if bureau or office is at the material 10% contribution level) | CDFI |  | 2006-10-13 | CDF | CDFI
Provide final OMB 01-09 (and GAAP) statements, footnotes and supplementary information to auditors and compare the 01-09 statements to FARS statements. Note any AIC crosswalk differences. | Peggy |  | 2006-10-13 | Peg | ARC
Final Performance in PRS and PRS locks down | CDFI |  | 2006-10-13 | CDF | CDFI
Monthly EFT Report due to Brian Lee | FMB Processing |  | 2006-10-13 | FMB | ARC
Monthly Prompt Pay Report due to Phil Howland | FMB Processing |  | 2006-10-13 | FMB | ARC
Monthly Reconciled/Unreconciled Cash Report due to Dan Waugh | Bob |  | 2006-10-13 | Bob | ARC
Quarterly suspense clearing due to Dan W. | Bob |  | 2006-10-13 | Bob | ARC
Submit 4th quarter admininistrative debt information in prescribed format to Brian Lee. (federal receivables/delinquencies) | Peggy |  | 2006-10-13 | Peg | ARC
Department verifies preparer/certifier and TAFS information for FACTS II | Dept |  | 2006-10-13 | Dep | Department
Department adds 6653 Data to the TIER budget edit checks. Note: FACTS II window opens this date; closes 10/26; We should have period 12 loaded into TIER | Dept/Peggy |  | 2006-10-13 | Dep | Department
Resubmit period 12 06 TIER file to include cohort data and/or adjustments for cash outlays. | Peggy |  | 2006-10-16 | Peg | ARC
Bureaus run WebTIER TEP and FAER reports, and begin elimination reconciliation processes (certification due 10/30/06). | Peggy |  | 2006-10-16 | Peg | ARC
Download and verify FACTS II accounts and balances (window open 10/13-10/26; certification is due on FACTS II website 10/26). Send FACTS II 133s and 2108s to customers. Customer certification due to ARC on 10/24. | Dana/Peggy |  | 2006-10-18 | Dan | ARC
Department will provide draft Performance and Accountability Report to OIG and Chief of Staff, and post on DCFO Web Repository for bureau review and comment. | Dept |  | 2006-10-18 | Dep | Department
Bureaus submit first update of the unasserted claim representation letters to AIC (as of 9/30/06, updated through 10/15/06). Note: A combined unasserted claim and legal representation response is not permissible. | CDFI |  | 2006-10-18 | CDF | CDFI
Bureaus submit variance analysis of quarterly financial statements. | Peggy |  | 2006-10-18 | Peg | ARC
Bureaus provide first update of the legal representation letter to OGC including bureau CFO & legal council contingent liability figure concurrence (as of 9/30/06, updated through 10/15/06). Note: A combined unasserted claim and legal representation response is not permissible. | CDFI |  | 2006-10-23 | CDF | CDFI
FACTS II certifications due from customers (requested on 10/18). | CDFI/Peggy |  | 2006-10-24 | CDF | CDFI
Bureaus provide final comments on draft Performance and Accountability Report. | CDFI |  | 2006-10-24 | CDF | CDFI
SF 220-9 Report on Receivables Due from the Public prepared and sent with certification statement to customer for review. See the following website: http://www.fms.treas.gov/debt/dmrpts.html Available between 10/13-11/15 (certification due to ARC by 11/10) | Peggy |  | 2006-10-25 | Peg | ARC
Auditors (OIG/GAO/IPA) complete field work on bureau audits and provide final audit adjustments. | KPMG |  | 2006-10-25 | KPM | Auditors
Provide elimination certification documentation to Customers for 10/30 department certification | Peggy |  | 2006-10-25 | Peg | ARC
Bureaus submit Adjusted Trial Balance (final period 12), which incorporates all final adjustments, to TIER for preparation of final Department-wide financial statements, including the Net Cost Percentage Calculator, which is applicable to bureaus that report multiple programs on the SONC. | Peggy |  | 2006-10-26 | Peg | ARC
Resubmissions of period 12 TIER data due for FACTS II submission. Note: FACTS II window officially closes on 10/26. | Peggy |  | 2006-10-26 | Peg | ARC
ARC Certification is due on FACTS II website. | Dana/Matt |  | 2006-10-26 | Dan | ARC
Department completes FACTS II submission to FMS | Dept |  | 2006-10-26 | Dep | Department
Finals due for: 1) Statement of Financing (if not fully automated); 2) Notes to the financial statements, Required Supplemental Information and Other Accompanying Information (Excel File.) This also includes submitting the Closing Package notes (filename: CP_Notes.xls) to WebTIER. | CDFI/Peggy |  | 2006-10-27 | CDF | CDFI
Notes and supplemental information for closing package due | Peggy |  | 2006-10-30 | Peg | ARC
Bureaus provide final certified Department-wide and Government-wide elimination entry data to the Department through WebTIER TEP and FAER reports [began elimination process 10/16/06); provided to Customers on October 25 | CDFI/Peggy |  | 2006-10-30 | CDF | CDFI
JE 1010** accounts to close to 101001 in OCT/ADJ/06-07. | Peggy |  | 2006-10-31 | Peg | ARC
JE 310*** accounts to close to 310001 in OCT/ADJ/06-07. | Peggy |  | 2006-10-31 | Peg | ARC
JE 461001 balances to 445001 in OCT/ADJ/06-07 since 461001 balances cannot exist in FY 2007 beginning balances for funds that are subject to reapportionment in the new year. | Peggy |  | 2006-10-31 | Peg | ARC
JE all outstanding FY 2006 commitment balances in OCT/ADJ/06-07 (DR 47*001; CR 46*004 - using AF details); Reverse in OCT/06-07. | Peggy |  | 2006-10-31 | Peg | ARC
JE 46100* net balance in expired funds in OCT/ADJ/06-07 (DR 461006; CR 465001) to show 4650 in FY 2007 beginning balance | Peggy |  | 2006-10-31 | Peg | ARC
In OCT/06-07, reverse commitment JEs posted in SEP/06-06 and OCT/ADJ/06-07 that closed commitment balances. This reestablishes the activity in the new fiscal year, which is in agreement with PRISM. | Peggy |  | 2006-10-31 | Peg | ARC
In OCT/06-07, reverse obligation JE posted in SEP/06-06 that backed off FY 2007 obligations. This reestablishes the activity in the new fiscal year, which is in agreement with PRISM. | Peggy |  | 2006-10-31 | Peg | ARC
Bureau auditors issue draft audit report and agreed upon procedures. | KPMG |  | 2006-10-31 | KPM | Auditors
Audited Bureaus provide management representation letters to AIC | CDFI |  | 2006-11-01 | CDF | CDFI
Annual Assurance - Audited Bureau and Offices submit final FMFIA, FFMIA, and A-123 Controls Over Financial Reporting Annual Assurance Statement to Treasury (A-123 section only required if at the material 10% contribution level) | CDFI |  | 2006-11-01 | CDF | CDFI
Bureaus e-mail update of the unasserted claim representation letters to AIC (as of 9/30/06, updated through 11/3/06). Note: A combined unasserted claim and legal representation response is not permissible. | CDFI |  | 2006-11-03 | CDF | CDFI
Bureaus email legal representation update to OGC thru November 3rd timeframe. Note: A combined unasserted claim and legal representation response is not permissible. | CDFI |  | 2006-11-03 | CDF | CDFI
Certification for SF 220-9 (Report on Receivables) provided by ARC on 10/25 is due. Also, submit Report on Receivables. Reporting window closes 11/15/06. | CDF/Peggy |  | 2006-11-10 | CDF | CDFI
Provide 4th quarter TIER/TROR reconcilation and FMS certification to Brian Lee | Peggy |  | 2006-11-14 | Peg | ARC
Department submits FACTS I ATB and Notes to FMS through GFRS | Dept |  | 2006-11-14 | Dep | Department
Perform preliminary year end close review. | Peggy |  | 2006-11-15 | Peg | ARC
Close accounting period 15 - Postclosing TB (Annual close creates beginning balances in AP 00 - Oracle) | SSB |  | TBD | SSB | ARC
Close accounting period 02 07 | SSB |  | 2006-12-04 | SSB | ARC
TIER period 00 and 02 2007 transmission. | Peggy |  | 2006-12-06 | Peg | ARC
Bureau auditors issue final audit report and agreed upon procedures. | KPMG |  | 2006-12-15 | KPM | Auditors