## CDR
FAA System Engineering & Development
Critical Design Review | [6 empty] | Program:
Program Risk Assessment Checklist (1 May 2006 version) | [6 empty] | Date:
Legend: | R | Y | G | U | NA
Instructions: Type the appropriate risk character in the space to the right of each question. The risk characters {R,Y,G,U or NA} are not case sensitive. The total number of each character will be displayed in the summary status at the beginning of each section. See SEM Appendix C for selection criteria. | R = Red
Y = Yellow
G = Green
U = Unknown
NA = Not Applicable
Indicates Lower level of entries
[6 empty] | Item | Comments/Mitigation
1. Timing / Entry Criteria | 0 | 0 | 0 | 0 | 0 | 1
a. Has a Preliminary Design Review (PDR) been successfully completed? | [5 empty] | 1.a
b. Is the program ready to conduct an CDR based upon CDR entry criteria vice a pre-determined schedule date? | [5 empty] | 1.b
c. Have all prior technical review RFAs been properly dispositioned, and closed? | [5 empty] | 1.c
d. Is the program using an effective Integrated Data Environment (IDE) to store data? | [5 empty] | 1.d
e. If an incremental CDR approach is being used (see 2.k below), have all incremental reviews been completed and the results and open action items documented? | [5 empty] | 1.e
2. CDR Planning | 0 | 0 | 0 | 0 | 0 | 2 | See 2.c & 2.g for issues.
a. Was a chairperson assigned in coordination with ATO-P System Engineering? | [5 empty] | 2.a
b. Has the date, location, participants, and scope been established and agreed to by all stakeholders? | [5 empty] | 2.b
c. Was the Systems Engineering Review Board (SERB) properly staffed, and did the appropriate competencies participate in the review? | [5 empty] | 2.c | A SERB (or TRB) is used to provide process consistency across an organization. Do we plan on using this concept and what would the SEC's role in this be?
d. Was a Systems Engineering Management Plan (SEMP)) developed and implemented on this program? | [5 empty] | 2.d
e. Was the Acquisition Strategy developed and documented through JRC? | [5 empty] | 2.e
f. Has the set of CIs to be reviewed been identified and correlated to the product WBS? | [5 empty] | 2.f
g. Does the review agenda address all applicable CDR Review Elements per paragraph C3.6 of the FAA SEM V3.1? | [5 empty] | 2.g
h. Has a Responsibility Assignment Matrix been established for all reviews and parties involved? | [5 empty] | 2.h
i. Has a requirements compliance matrix been developed for each CI being reviewed? | [5 empty] | 2.i
j. Have all prior review RFAs been properly dispositioned, and closed? | [5 empty] | 2.j
k. Is an incremental approach to CDR being used on this program? (If "yes", then continue below. If "no", proceed to question 2.l) | [5 empty] | 2.k
(1) Have all incremental reviews been scheduled to support the Sytem level review | [5 empty] | 2.k (1)
(2) Have incremental review scope & RAA been established and agreed to? | [5 empty] | 2.k (2)
(3) Has the corrective action process for the incremental reviews and RAA been established? | [5 empty] | 2.k (3)
(4) Have all RFAs for the incremental reviews been generated and dispositioned?
l. Have supportability analysis products from the system integration work effort been made available to the cognizant CDR participants prior to the review? | [5 empty] | 2.l
m. Are the current logistics documents available for review based on the Life Cycle Plan (LCP)? | [5 empty] | 2.m
3. Program Resources | 0 | 0 | 0 | 0 | 0 | 3
a. Does the Program have an updated schedule with sufficient detail to support development? Are the tasks linked? | [5 empty] | 3.a
(1) Has the software schedule been updated based upon the detailed software design? | [5 empty] | 3.a.(1)
(2) Has the software schedule been updated based upon actual measured project software development performance and productivity to date? | [5 empty] | 3.a.(2)
(3) Has the software schedule changed since the beginning of the project? What were the causes of these changes? | [5 empty] | 3.a.(3)
(4) Were any problems that caused schedule slips identified as risks prior to their occurrence? If not why not? If yes, why didn’t the associated mitigation plan succeed? | [5 empty] | 3.a. (4)
b. Is the schedule built upon “bottom-up” task planning? | [5 empty] | 3.b
c. Is the schedule reflective of available resources? | [5 empty] | 3.c
d. Does the program schedule have an identified critical path and is that critical path consistent with overall technical risk? | [5 empty] | 3.d
(1) Are any components of the software on the projects critical path? What are those components? | [5 empty] | 3.d.(1)
(2) If software is not currently on the project critical path, how much must the software development slip before it is on the critical path? | [5 empty] | 3.d.(2)
(3) What is the critical path for the software development aspect of the project only? | [5 empty] | 3.d.(3)
(4) Are there any hardware (COTS, GOTS or project specific) deliverables on the software development critical path? | [5 empty] | 3.d.(4)
(5) Are there any software deliverables from outside sources (COTS, GOTS on the software development critical path? | [5 empty] | 3.d.(5)
e. What is the Program schedule status versus Critical Path? | [5 empty] | 3.e
f. Latest cost estimate – Is the cost estimate consistent with the technical risk of the program, the critical path plan and available resources? | [5 empty] | 3.f
(1) Has the software estimate been updated based upon the detailed software design? | [5 empty] | 3.f (1)
(2) Has the software estimate been updated based upon actual measured project software development performance and productivity to date? | [5 empty] | 3.f (2)
(3) Are adequate resources and schedule provided for the development and or modification of any special purpose test, simulation and/or data analysis software for use during software development? | [5 empty] | 3.f (3)
(4) Has cost of acquiring, licensing and configuring COTS and/or GOTS computer hardware and software been considered? | [5 empty] | 3.f (4)
(5) Has COTS and/or GOTS computer hardware and software obsolescence and upgrade impacts been considered as part of the estimate? | [5 empty] | 3.f (5)
(6) Has the software cost changed since the beginning of the project? What were the causes of these changes? | [5 empty] | 3.f (6)
(7) Were any problems that caused schedule slips identified as risks prior to their occurrence? If not why not? If yes, why didn’t the associated mitigation plan succeed? | [5 empty] | 3.f (7)
g. Funding – Is the necessary funding been identiifed and in place to complete the system development? | [5 empty] | 3.g
h. Estimate of production costs – Is the estimate for production costs consistent with the detailed design as disclosed? Are all elements of production cost addressed? | [5 empty] | 3.h
i. Estimate of Operations & Support (O&S) Costs – Is the estimate for O&S costs consistent with the detailed design as disclosed? Are all elements of O & S cost addressed? | [5 empty] | 3.i
4. Management Metrics | 0 | 0 | 0 | 0 | 0 | 4 | See 4.g & 4.k for issues.
a. Does the SOW require the contractor to define, establish, and operate a metrics data collection, analysis, and reporting system that provides quantitative information on key program management issues? | [5 empty] | 4.a
b. Work Breakdown Structure (WBS) review | [5 empty] | 4.b
(1) Is the WBS consistent with the technical risks of the program? | [5 empty] | 4.b (1)
(2) Is the WBS broken down to an appropriately detailed level to address all technical tasks? | [5 empty] | 4.b (2)
(3) Are all CIs (including software) addressed in the WBS and identified in the detailed design? | [5 empty] | 4.b (3)
(4) Are the requirements tracked, traced, and modeled using an automated tool? | [5 empty] | 4.b (4)
c. Cost / Schedule / Performance / Technical Performance Parameters (TPP) – Status versus Plan: Is the latest revised estimate of each TPP in accordance with the Program Baseline? Are the TPPs reflective of program risks and technical results? | [5 empty] | 4.c
d. Earned Value Management (EVM) | [5 empty] | 4.d
(1) Is the EVM data up-to-date? | [5 empty] | 4.d (1)
(2) Is the EVM baseline being used as a program execution tool (i.e. by management and at the working level?) | [5 empty] | 4.d (2)
(3) Are the work packages based on earned value vice level of effort? | [5 empty] | 4.d (3)
(4) Is the EVM data consistent with known technical risks and challenges in the program? | [5 empty] | 4.d (4)
(5) Are the EVM data being used to adjust program resources to address risk issues? | [5 empty] | 4.d (5)
(6) Have the metrics to track EVM been clearly articulated and have sufficient fidelity to understand the status of the product development? | [5 empty] | 4.d (6)
e. Software metrics – Has a software metrics program been implemented to a recognized standard? What metrics standard is being used? | [5 empty] | 4.e | Do we use a recognized standard at the FAA for software metrics? If so, please add to the description for this entry. If not, what is recommended wording for the question?
(1) Are adequate software metrics in place and being used to manage the software effort? | [5 empty] | 4.e (1)
(2) Do the metrics indicate status versus plan? What level of risk do the metrics indicate? | [5 empty] | 4.e (2)
(3) Staffing level metrics – Is the software staffing adequate for the magnitude/complexity of the software and the level of software risk? | [5 empty] | 4.e (3)
(4) Size metrics – Are the software sizing metrics adequate and consistent with the detailed design? Do they indicate readiness for coding/testing? | [5 empty] | 4.e (4)
(5) Are Computer resource utilization metrics and/or Technical Performance Measures (TPM) known and allocated to individual processors, IO, RAM, ROM and other storage media to the extent appropriate for measurement? | [5 empty] | 4.e (5)
(6) Are other software complexity metrics being used and do these metrics indicate adequate understanding of complexity versus resources (schedule, funding, staff) available to ensure coding/testing success? | [5 empty] | 4.e (6)
(7) Are appropriate metrics in place to allow the tracking, management, and mitigation of significant software risks? | [5 empty] | 4.e (7)
(8) Are metrics used to track and manage the software requirements changes, deletions and additions (software requirements volatility)? | [5 empty] | 4.e (8)
(9) Are metrics used to manage the implementation of software requirements in accordance with the program cost and schedule plan? Note: If EVM is identified as the metric for managing and insuring that software requirements are being implemented in accordance with the project cost and schedule plan, allocation of earned value must be tied directly to the correct implementation of software requirements. | [5 empty] | 4.e (9)
(10) Are metrics used to insure that quality is designed and built into the software rather than attempting to test it in? What metrics have been used to track quality during the software requirements and software design phase? | [5 empty] | 4.e (10)
5. Program Staffing | 0 | 0 | 0 | 0 | 0 | 5
a. Is there a complete organization structure shown and is the organization consistent with the technical challenges/risks of the program? | [5 empty] | 5.a
b. Are key government / contractor interfaces identified and are these consistent with program risks? | [5 empty] | 5.b
c. Is adequate staffing (required expertise and quantity of expertise for both the contractor and the government) available to execute the schedule? If certification is a consideration, is there confidence that all required certification stakeholders are involved and do they concur with the detailed design? | [5 empty] | 5.c
d. Are there up to date viable succession plans in place for all management and key technical positions in the program structure for both the government and contractor teams? Have the respective parent organizations committed resources to execute these plans? | [5 empty] | 5.d
(e) Is the development team familiar with and/or trained in the use of the COTS, GOTS or reused software? If not, is documentation readily available? Is training readily available and has it been scheduled and budgeted for? | [5 empty] | 5.e
6. Process Review | 0 | 0 | 0 | 0 | 0 | 6 | See yellow cells for issues.
a. Program Management processes as detailed in the Program Management Plan – Are the program management processes that are in place adequate to address the technical challenges of the program and adequate to address program risks? | [5 empty] | 6.a | What plan spells out the PM processes in the FAA system in the same way that the SEMP does for SE processes?
(1) Is there an updated System Engineering Management Plan (SEMP) that is reflective of the emergent technical issues and risks? | [5 empty] | 6.a (1)
(2) Are there Program Management processes in place to properly manage the detailed design, prototype fabrication, testing, and attendant technical emphasis areas? | [5 empty] | 6.a (2)
(3) Is the program being managed to adjust resources to address issues in the detailed design, prototype fabrication and testing? | [5 empty] | 6.a (3)
b. Configuration Management processes as detailed in the Configuration Management Plan | [5 empty] | 6.b
(1) Is the CM plan in place and up-to-date? | [5 empty] | 6.b (1)
(2) Is the detailed design (each CI) documented and being managed in accordance with the CM Plan? | [5 empty] | 6.b (2)
(3) Are changes to the managed CI configurations controlled and tracked to higher level (System Specification and fPR Document), and lower level (detailed design) documents? | [5 empty] | 6.b (3)
c. Systems Engineering processes (FAA Systems Engineering Manual) as detailed in the Systems Engineering Management Plan (SEMP) | [5 empty] | 6.c
(1) Is there a defined system engineering process? Is it in accordance with the FAA System Engineering Manual? | [5 empty] | 6.c (1)
(2) Are the processes shared by the government and contractor team? | [5 empty] | 6.c (2)
(3) Are the SE processes for design development and system trades in place and being used? | [5 empty] | 6.c (3)
(4) Are the planned technical reviews in place and properly placed (event driven vice schedule driven)? | [5 empty] | 6.c (4)
(5) Are the SE processes adequate to support the technical requirements of the technical reviews? Are the technical teams working against a defined technical baseline? | [5 empty] | 6.c (5)
(6) Is there a process in place for requirements management and is it being applied to properly address this stage of the program? | [5 empty] | 6.c (6)
(7) Are there plans in place to ensure test requirements are addressed and documented to the same level of detail as functional requirements (operation and suitability)? | [5 empty] | 6.c (7)
(8) Is the program using a SE automated tool (i.e. DOORS, CORE, SLATE etc.) to manage traceability of each Configuration Item (CI)? | [5 empty] | 6.c (8)
d. Acquisition Logistics Support Management & Staffing | [5 empty] | 6.d | Need the proper terminology for this section - present terms are from DOD.
(1) Has the ALSP been updated to reflect the maintenance and support concepts at both the system and major hardware configuration item levels? | [5 empty] | 6.d (1) | Need the proper terminology for this section - present terms are from DOD.
(2) Have Alternative Logistics Concepts been adequately considered and preliminary cost-benefit trades conducted to justify the product support strategy in the ALSP? | [5 empty] | 6.d (2) | Need the proper terminology for this section - present terms are from DOD.
(3) Does the ALSP reflect user performance agreements pertaining to logistics (if any)? At minimum, xxx reviews and comments concerning maintenance planning and support concepts should be appropriately considered. | [5 empty] | 6.d (3) | Need the proper terminology for this section - present terms are from DOD.
(4) Does the Service Organization have regional or other operational site representation? | [5 empty] | 6.d (4) | Need the proper terminology for this section - present terms are from DOD.
e. Risk Management processes as detailed in the Risk Management Plan | [5 empty] | 6.e
(1) Is there a defined Risk Management process? Is the Risk Management Plan up to date and being used? | [5 empty] | 6.e (1)
(2) Is the risk management process shared by the government and contractor team? | [5 empty] | 6.e (2)
(3) Does the risk management process properly track ALL risks on a continuous basis and provide for update of the mitigation approaches? | [5 empty] | 6.e (3)
(4) Is there a risk database established to track all risks and mitigation approaches? | [5 empty] | 6.e (4)
(5) Is there a risk manager identified in the SEMP for the government and contractor efforts? | [5 empty] | 6.e (5)
(6) Is there a Program Risk Board established to review and adjudicate risks for the entire program? | [5 empty] | 6.e (6)
(7) Are mitigation approaches in place for all “yellow” and “red” risks? Are risk mitigations resourced? | [5 empty] | 6.e (7)
(8) Does the risk management process provide for risk updates to support the technical reviews and program management (acquisition) reviews? | [5 empty] | 6.e (8)
(9) Are the system’s INFOSEC Risk mitigation plans being managed by the program Risk Management Board? | [5 empty] | 6.e (9)
(10) Are the system’s safety Risk mitigation plans being managed by the program Risk Management Board? | [5 empty] | 6.e (10)
f. Logistics Budgeting | [5 empty] | 6.f
(1) Has the program office prepared Logistics Requirements and included them in the Program Requirements documentation? | [5 empty] | 6.f (1)
(2) Is there adequate documentation to support the lifecycle requirements identified for the program? | [5 empty] | 6.f (2)
(3) Do the lifecycle funding requirements coincide with the support requirements in the program requirements and other planning documents? | [5 empty] | 6.f (3)
(4) Are the impacts of funding shortfalls understood and plans in place to mitigate risk? | [5 empty] | 6.f (4)
(5) Has the Life Cycle plan been staffed and approved? | [5 empty] | 6.f (5)
g. Test processes as detailed in the V&V Master Plan and the contractor's overarching V&V Strategy. | [5 empty] | 6.g
(1) Has the V&V Master Plan been updated to reflect the required detail for the PDR timeframe? Does the plan address all required resources? | [5 empty] | 6.g (1)
(2) Does the contractor's T&E Strategy meet the program V&V requirements? | [5 empty] | 6.g.(2)
(3) Has detailed verification planning been initiated? Are test plans for the first six months of testing in a Draft status? | [5 empty] | 6.g(3)
(4) Is there a clear understanding of the FAA's deficiency documentation process and is there plan for a deficiency documentation and tracking system? | [5 empty] | 6.g (4) | What is the FAA approach to deficiency documentation? Is this a relevant question?
(5) Are test requirements tied to verification requirements? Is there a method to ensure traceability of test requirements to the verification requirements? | [5 empty] | 6.g (5)
(6) Have metrics been established to track the test program? | [5 empty] | 6.g.(6)
(7) Does the V&V plan reflect any relevant network-centric requirements? | [5 empty] | 6.g(7)
(8) Does the V&V Master Plan address metrics and test procedures to ensure that Human Integration requirements for each domain are delivered and satisfy the specification requirements? | [5 empty] | 6.g (8) | Terminology
(9) Have facilities/test resources (contractor and government) been defined and included in the test planning? | [5 empty] | 6.g (9)
(10) Is there User “buy-in” to the above test planning? Are there provisions for User participation? | [5 empty] | 6.g.(10)
(11) Has OT&E been involved with all aspects of test planning? Are OT&E requirements considered as a part of DT planning? | [5 empty] | 6.g.(11) | Terminology
(12) Is the certification process established to include definitions of the levels of certification authority? | [5 empty] | 6.g.(12)
h. Production | [5 empty] | 6.h
(1) Have production processes been considered in the detailed design? | [5 empty] | 6.h (1)
(2) Have production requirements been properly captured and addressed in the risk assessment? | [5 empty] | 6.h (2)
(3) Have long-lead items been identified and are production processes sufficiently mature for this phase of the program? | [5 empty] | 6.h (3)
(4) Where applicable, have Unique Identification (UID) requirements been incorporated? (e.g., FAA-G-2100) | [5 empty] | 6.h (4)
i. Program utilization of lessons learned - Have the lessons learned by other programs been utilized to reduce risk? | [5 empty] | 6.i
j. Software | [5 empty] | 6.j
(1) Is the software development lifecycle appropriate to the development? Does the software lifecycle being used contribute to reducing overall software development risk? | [5 empty] | 6.j (1)
(2) Are peer reviews of the software requirements and software detailed design part of exit criteria for determining if they are complete and placing them under configuration control? | [5 empty] | 6.j (2)
(3) Is the software development lifecycle appropriate to the development? Does the software lifecycle being used contribute to reducing overall software development risk? | [5 empty] | 6.j (3)
(Note: If the contract has a Capability and/or Maturity Level requirement, continue. If there is no contract requirement, proceed to the next section.)
(4) Is the software developer performing at a SW-CMM or CMMI level III as required by xxx? | [5 empty] | 6.j (4) | Are we using SW CMMI in our acquisitions? Have we imposed a requirement for a maturity level? If so, to what standard?
(5) If the software developer is performing at below a SW-CMM or CMMI Level III, what mitigating action is being taken to reduce the increased risk of cost, schedule and quality deficiencies? | [5 empty] | 6.j (5) | Are we using SW CMMI in our acquisitions? Have we imposed a requirement for a maturity level? If so, to what standard?
(6) If the software developer is performing at below the SW-CMM or CMMI Level they proposed during source selection, why is this the case and what corrective action is being taken? | [5 empty] | 6.j (6) | Are we using SW CMMI in our acquisitions? Have we imposed a requirement for a maturity level? If so, to what standard?
7. NAS Enterprise Architecture (NAS EA) | 0 | 0 | 0 | 0 | 0 | 7
a. Does the detail design comply with EA Operational Requirements and views? | [5 empty] | 7.a
b. Does the detail design comply with EA System/Technical Requirements and Systems views? | [5 empty] | 7.b
c. Does the detail design comply with EA Implementation Requirements and Timeframes? | [5 empty] | 7.c
d. Does the software detailed design and project plan provide for the implementation of any FAA NAS EA software architecture requirements and or standards? | [5 empty] | 7.d
8. System Detailed Design - Performance For the overall system (AND each Configuration Item) the following requirements should be assessed, as applicable: | 0 | 0 | 0 | 0 | 0 | 8 | See marked rows for issues/questions to be addressed
a. Requirements Compliance | [5 empty] | 8.a
(1) Are Subsystem requirements traced to system requirements (and subsequently up to the fPR)? | [5 empty] | 8.a (1)
(2) Is the Subsystem detailed design traced to subsystem requirements? | [5 empty] | 8.a (2)
(3) Have the TPPs and other performance requirements, both explicit and derived been defined, quantified and documented? | [5 empty] | 8.a (3)
(4) Have all functional requirements in the functional baseline been allocated to a CI and are these documented in the detailed design and allocated baseline? | [5 empty] | 8.a (4)
(5) Have Functional Interface Requirements been defined and included in the detailed design? | [5 empty] | 8.a (5)
(6) Are the functional Interface requirements aligned with the NAS EA? | [5 empty] | 8.a (6)
(7) Are the functional Interface requirements aligned with the net-centric functionality of the NAS (SWIM)? | [5 empty] | 8.a (7)
(8) Is full traceability from systems requirements allocated to software provided through: software requirements, software design, interface requirements, interface design, source code and test procedures? | [5 empty] | 8.a (8)
(9) Are any COTS, GOTS or reused software traced to: systems requirements, software requirements, interface requirements, interface design, software design, and test procedures? | [5 empty] | 8.a (9)
(10) Are software requirements allocated to COTS, GOTS and reused software appropriate? | [5 empty] | 8.a (10)
(11) Does the COTS, GOTS and/or reused software’s implementation meet the software requirements allocated to it? | [5 empty] | 8.a (11)
(12) Does the contract specification contain Human Integration requirements for each domain and are they traced back to fPR requirements? | [5 empty] | 8.a (12)
b. Design Interface | [5 empty] | 8.b
(1) Have testability, maintainability and supportability requirements been defined and adequately considered in the preliminary design? | [5 empty] | 8.b (1)
(2) Have the results of FMECA been integrated with the Supportability Analysis program? | [5 empty] | 8.b (2)
(3) Do design processes include adherence to specific derating guidelines, particularly for electronic and electrical components? | [5 empty] | 8.b (3)
(4) Is qualification testing planned to support design limit/life testing during System Demonstration? | [5 empty] | 8.b (4)
(5) Do the parts and material selection processes ensure items are qualified to the worst case Design Reference Mission Profile and design environment? | [5 empty] | 8.b (5)
c. Are trade studies complete, documented, approved, and implemented where applicable? | [5 empty] | 8.c
d. Have lessons learned been addressed, and implemented where applicable? | [5 empty] | 8.d
e. System and CI constraints (system budgets) | [5 empty] | 8.e
(1) Have Physical Interface requirements been considered in the detailed design? Have proper tradeoffs been made? | [5 empty] | 8.e (1)
(2) Has CI weight and its impact of overall system weight been considered and properly traded? Have weight budgets been establish for all CIs? | [5 empty] | 8.e (2)
(3) Has a System (and/or CI) Volume budget been established? Has the volume impact from each CI been considered at the system level? | [5 empty] | 8.e (3)
(4) Has a System (and/or CI) Power budget been established? Has the power impact from each CI been considered at the system level? | [5 empty] | 8.e (4)
(5) Has a System (and/or CI) Cooling (liquid and/or air) budget been established? Has the cooling impact from each CI been considered at the system level? | [5 empty] | 8.e (5)
(6) Available technology / system growth – Have the requirements for technology insertion and system growth been allocated to the CIs and reflected in the detailed design? | [5 empty] | 8.e (6)
(7) Have growth budgets been established for the TPPs at the System level? Have these budgets been allocated to individual Cis? | [5 empty] | 8.e (7)
(8) Do plans describe decision support analysis concerning system modernization, technology insertion, block upgrades, etc? | [5 empty] | 8.e (8)
(9) Are physical security and software security implementations consistent with the security level of the software and/or any data encrypted and managed by the software (both during development and operational use)? | [5 empty] | 8.e (9)
f. Have the above requirements and constraints been captured in the product baseline (approved product specifications) and traceable back through the updated allocated baseline and functional baselines to the system specification, fPR, and SLMN? | [5 empty] | 8.f
g. For Computer/Software CIs, is there sufficient detail to enable coding and testing to begin? | [5 empty] | 8.g
h. Structures | [5 empty] | 8.h
i. Materials | [5 empty] | 8.i
j. Mass properties | [5 empty] | 8.j
k. Reliability and Maintainability (R&M) | [5 empty] | 8.k
(1) Have Reliability and Maintainability and Built-In-Test (BIT) requirements been addressed in the system detailed designs? | [5 empty] | 8.k (1)
(2) Is the final mission profile definition complete and does it accurately define the expected Fleet operational environment? | [5 empty] | 8.k (2)
(3) Are the final R&M block diagrams and math models complete, accurate, and do they meet the required mission reliability performance requirements? | [5 empty] | 8.k (3)
(4) Is the final FMECA complete and accurate with specific examples of design changes implemented to eliminate single point failure modes and/or improve overall system reliability? | [5 empty] | 8.k (4)
(5) Have all critical safety items and critical application items been identified? Are the lists accurate and all inclusive? Do drawings and associated technical data confirm that critical safety items are clearly identified, along with critical and major characteristics, tolerances, critical processes and inspection, and other quality assurance requirements? | [5 empty] | 8.k (5)
(6) Are R&M allocations complete and accurate? | [5 empty] | 8.k (6)
(7) Are the final Reliability predictions using piece part stress technique complete, and do they meet all specified Reliability performance requirements in accordance with xxx guidelines? | [5 empty] | 8.k (7) | Need appropriate FAA Standard cited
(8) Are the final Maintainability predictions complete, and do they meet all specified Maintainability performance requirements in accordance with xxx guidelines? | [5 empty] | 8.k (8) | Need appropriate FAA Standard cited
(9) If applicable, are the final BIT and/or diagnostics assessments complete, and do they meet all specified performance requirements in accordance with xxx guidelines? | [5 empty] | 8.k (9) | Need appropriate FAA Standard cited
(10) Are the final Thermal, Vibration, and Shock analyses complete, and do they accurately reflect the anticipated operational environment? | [5 empty] | 8.k (10)
(11) Is the final derating analysis complete, and does it eliminate overstressed components? | [5 empty] | 8.k (11)
l. Electromagnetic Environmental Effects (E3) and Spectrum Supportability | [5 empty] | 8.l
(1) Does the specification address spectrum certification compliance, spectrum supportability, host nation approval, the control of electromagnetic environmental effects (E3), and safety issues regarding the hazards of electromagnetic radiation to personnel and equipment? | [5 empty] | 8.l (1)
(2) Have all of the E3 interface specifications of MIL-STD-461E and MIL-STD-464A been adequately verified and addressed prior to production drawing release ? (NOTE: This includes electrical bonding, precipitation static (P-static), electrostatic discharge (ESD), subsystem EMI (including COTS and NDI), intra-system EMC, lightening effects (direct and indirect), radiation hazards (HERP and HERF), and life-cycle E3 hardening to the extent specified in the System Specification.) | [5 empty] | 8.l (2)
(3) Does the program schedule allow adequate time to correct EMI deficiencies prior to production start ? | [5 empty] | 8.l (3)
m. Survivability - Have survivability requirements and program established goals been successfully met and incorporated into the system design? | [5 empty] | 8.m
n. Producibility- Have producibility requirements and program established goals been successfully met and incorporated into the system design? | [5 empty] | 8.n
0. System Safety - Have program systems safety requirements and goals been successfully achieved and have program hazards identified through the systems safety initiatives been mitigated or actions to eliminate been put in place? | [5 empty] | 8.o
p. Human Systems Engineering | [5 empty] | 8.p
(1) Have Human Integration design issues been addressed and implemented as part of the current design? | [5 empty] | 8.p (1)
(2) Has the program adequately identified, analyzed and integrated Human Interface requirements? | [5 empty] | 8.p (2)
(3) Does the system design meet or exceed the Human Systems engineering requirements appropriate for the system? | [5 empty] | 8.p (3)
(4) Do the human interfaces minimize or eliminate systems characteristics that require excessive cognitive, physical or sensory skills? | [5 empty] | 8.p (4)
(5) Does the program human-machine-interface concepts conform to HFE standards in HF-STD-001 (FAA Human Factors Design Standard). | [5 empty] | 8.p (5)
(6) Has the program developed a training systems design to maximize use of new learning techniques, modeling and simulation technology, embedded training, and instrumentation systems that provide anytime, anyplace training and reduce the demand on the training establishment? | [5 empty] | 8.p (6)
(7) Does the training system design conform to the Training System Requirements? | [5 empty] | 8.p (7)
(8) Does the design include embedded training capabilities if required? | [5 empty] | 8.p (8)
q. Environmental - Have all of the environmental program requirements been achieved or risks mitigated, and solutions integrated into the complete system design? | [5 empty] | 8.q
r. Obsolescence | [5 empty] | 8.r
s. Interoperability | [5 empty] | 8.s
9. System Detailed Design - Life Cycle For the overall system (AND each Configuration Item) the following requirements should be assessed, as applicable: | 0 | 0 | 0 | 0 | 0 | 9
a. Software | [5 empty] | 9.a
(1) If COTS or GOTS computer hardware and/or software is being used, has COTS and/or GOTS obsolescence issues been considered? | [5 empty] | 9.a (1)
(2) Has the long term viability of the COTS and/or GOTS product provider been considered for the program life-cycle? | [5 empty] | 9.a (2)
(3) Are COTS and/or GOTS software and computer hardware upgrades caused by COTS and/or GOTS obsolescence considered for both the software development and the remainder of the software lifecycle? | [5 empty] | 9.a (3)
(4) Has the likely impact of updating a component of COTS and/or GOTS computer hardware or software been considered in respect to how it may force other COTS and/or GOTS upgrades? | [5 empty] | 9.a (4)
(5) Has the impact on the projects custom software of COTS and/or GOTS computer hardware and/or software upgrades been considered? | [5 empty] | 9.a (5)
(6) Are the impacts of COTS and/or GOTS software and computer hardware obsolescence and upgrades on the software development and integration environment considered? | [5 empty] | 9.a (6)
b. Maintenance Planning | [5 empty] | 9.b
(1) Has preliminary Maintenance Planning been developed? | [5 empty] | 9.b (1)
(2) Has it been updated to reflect the results of systems engineering and supportability analysis conducted during the Systems Integration work effort? | [5 empty] | 9.b (2)
(3) Do the R&M thresholds used in establishing the maintenance concept support the system availability and performance requirements in the SLMN? | [5 empty] | 9.b (3)
(4) Does the program's approach to evolving the maintenance and support concepts captured in the approved Lifecycle Plan? | [5 empty] | 9.b (4)
(5) Has sufficient F&E and Operations funding for interim support, transition planning, and establishment of organic capability been identified and documented in the current program baseline? | [5 empty] | 9.b (5)
(6) Has 2nd level engineering capability/capacity and resource requirements been identified and documented? | [5 empty] | 9.b (6)
(7) Has 3rd level support (depot level) and resource requirements been identified and documented? | [5 empty] | 9.b (7)
c. Manpower & Personnel | [5 empty] | 9.c
(1) Have current operating procedures been reviewed and all required changes been identified with a plan for implementation to support system deployment? | [5 empty] | 9.c (1)
(2) Is there a clear plan on which operational skill classifications and number of personnel will be trained? | [5 empty] | 9.c (2)
(3) Is there a clear plan on how courses and related materials and devices will be developed for training at each required level of maintenance? | [5 empty] | 9.c (3)
(4) Is there a plan for the validating and verifying training materials? | [5 empty] | 9.c (4)
(5) Have training requirements been coordinated with the operating organization(s)? | [5 empty] | 9.c (5)
(6) Does deployment planning adequately sequence tasks and events to assure personnel are trained to operate and maintain the system during IOT&E? | [5 empty] | 9.c (6)
(7) Does deployment planning adequately sequence tasks and events to assure personnel are trained to operate and maintain the system at key site(s) prior to IOC? | [5 empty] | 9.c (7)
(8) Are training requirements reflected in the contract SOW for course and materials development, factory training, training devices and equipment? | [5 empty] | 9.c (8)
d. Supportability | [5 empty] | 9.d
(1) Does the sequencing and timing of events in the Supply Support planning logically support planned IOC? | [5 empty] | 9.d (1)
(2) Is the Provisioning Technical Documentation being procured adequate to support end items that have parts subject to failure/replacement and require maintenance at any level? | [5 empty] | 9.d (2)
(3) Are accepted sparing analysis and modeling tools being utilized and are the assumptions consistent with the supportability analysis and the prescribed maintenance concept? | [5 empty] | 9.d (3)
(4) Are supply support funding requirements reflected in the current program baseline? | [5 empty] | 9.d (4)
e. Support Equipment | [5 empty] | 9.e
(1) Are the support equipment strategies and diagnostics concepts defined in the preliminary Maintenance planning consistent with NAILS organic repair/contractor support and sparing strategies? | [5 empty] | 9.e (1)
(2) Is there a clear process by which the contractor will validate and demonstrate compliance with fault detection and isolation requirements? | [5 empty] | 9.e (2)
f. Facilities | [5 empty] | 9.f
(1) Does the LCP include analysis conducted to determine facility requirements? | [5 empty] | 9.f (1)
(2) Is there Facilities requirements documentation and a schedule to conduct Site Surveys? | [5 empty] | 9.f (2)
(3) Is the facilities requirement development process integrated with the Supportability Analysis process? | [5 empty] | 9.f (3)
g. Packaging, Handling, Storage & Transportation (PHS&T) | [5 empty] | 9.g
(1) Have potential PHS&T related problems been identified and are risk mitigation plans in place? | [5 empty] | 9.g (1)
(2) If new hazardous materials are being introduced, are PHS&T plans adequate to meet statutory and regulatory requirements? | [5 empty] | 9.g (2)
(3) Does the LCP identify PHS&T requirements with matching funding in the program baseline? | [5 empty] | 9.g (3)
10. Program Risk Assessment | 0 | 0 | 0 | 0 | 0 | 10
a. Have risk items in the detailed design been defined and analyzed? | [5 empty] | 10.a
b. Has Risk been considered at the CI level as well as at the system level? | [5 empty] | 10.b
c. Is the risk assessment process tightly coupled with the technical effort and reflective of the technical risks inherent in the detailed design? | [5 empty] | 10.c
d. Has the risk assessment addressed downstream risks to developmental test, operational test, training, and production/fielding of the system? | [5 empty] | 10.d
e. Is there adequate buy-in among the technical team as to risks and mitigations? | [5 empty] | 10.e
f. Is the technical risk assessment being shared at all levels of the Program Team? | [5 empty] | 10.f
g. Have supportability and logistics risk items been defined, analyzed, and included in the Program Risk Assessment? | [5 empty] | 10.g
h. Have R&M Risk Assessment questions been completed, and potential mitigation provided? | [5 empty] | 10.h
i. Have cost and schedule impacts for supportability and logistics risk mitigation been documented and identified? | [5 empty] | 10.i
11. Configuration Management | 0 | 0 | 0 | 0 | 0 | 11
a. For CDR, has an initial version of the Product Baseline, or equivalent, been established? Are the appropriate elements of this baseline under CM control? | [5 empty] | 11.a
b. Has software configuration management been included in the program CM plan? | [5 empty] | 11.b
c. Are all elements of the functional baseline for the system (and each CI) current? | [5 empty] | 11.c
d. Has the functional baseline for software been established and is it current? | [5 empty] | 11.d
e. Are the software detailed design documents complete and under configuration control? | [5 empty] | 11.e
f. Are the verification fixtures, tooling, and jigs being configuration managed in accordance with the program CM plan? | [5 empty] | 11.f
g. Technical Data | [5 empty] | 11.g
(1) Has a designated Government technical data review authority been established? | [5 empty] | 11.g (1)
(2) Has an IDE implementation plan been identified as a contract deliverable? | [5 empty] | 11.g (2)
(3) Is there a clear plan for the integration of contractor technical information systems and processes for engineering, manufacturing, and logistics support? | [5 empty] | 11.g (3)
(4) Is the government authorized access to contractor databases necessary to support Systems Verification? | [5 empty] | 11.g (4)
(5) Have requirements for system firmware and software documentation been identified and procured? | [5 empty] | 11.g (5)
(6) What software data rights have been procured by the Government and are they consistent with the Governments plans for maintenance and upgrade of the software over its lifecycle? | [5 empty] | 11.g (6)
h. Are the interface design doc uments complete and under configuration control? | [5 empty] | 11.h
i. Have all CI and TPP impacts from design changes been considered, documented, and controlled? | [5 empty] | 11.i
j. Are growth budgets formally managed and controlled as part of the program CM process? | [5 empty] | 11.j
12. System Verification | 0 | 0 | 0 | 0 | 0 | 12
a. Does the Requirements Verification Matrix exist and does it accurately reflect the fPR/System Specification requirements? | [5 empty] | 12.a
b. Is the detailed design of each CI consistent with the subsystem test planning and approach? | [5 empty] | 12.b
c. Is the detailed design of each CI consistent with the system test planning and approach? | [5 empty] | 12.c
d. Have test methodologies and metrics for R&M requirements been defined? Is there concurrence on the methodology/metrics from the verification organization(s)? | [5 empty] | 12.d
e. Is the detailed design testable? Are there plans in place to cover verification via other means as required (analysis, simulation, etc.)? Is there buy-in among all stakeholders as to these approaches? | [5 empty] | 12.e
f. Have adequate hardware, software, personnel, and spares been allocated to both laboratory, ground and flight testing to achieve the program schedule? | [5 empty] | 12.f
g. Does the program place an excessive and or unreasonable emphasis on ground, flight, or laboratory testing? Is the appropriate and most cost effective means of testing utilized for different testing phases? | [5 empty] | 12.g
h. Test and Evaluation equipment | [5 empty] | 12.h
(1) Has test unique equipment for each test article been identified? Is the mechanical and electrical design sufficiently mature for this phase of the Program? | [5 empty] | 12.h (1)
(2) Has the instrumentation design installation been coordinated with the appropriate system design groups? | [5 empty] | 12.h (2)
(3) Has the data processing system design and facility requirements been finalized? | [5 empty] | 12.h (3)
(4) Are all vendors for instrumentation and data processing hardware and software under contract? | [5 empty] | 12.h (4)
i. Software Integration and Test | [5 empty] | 12.i
(1) Are facilities and resources available or in development to support: software integration testing, formal qualification testing, systems testing, DT, and OT? | [5 empty] | 12.i (1)
(2) If the systems and software integration laboratory resources are planned to be used for spares for testing, have the impact on the testing schedule of the laboratory(s) being unavailable been considered? | [5 empty] | 12.i (2)
(3) Are there any test environment resource limitations that may result in a bottleneck or chokepoint in testing? What actions have been taken to mitigate these bottlenecks or chokepoints? | [5 empty] | 12.i (3)
(4) Is the COTS, GOTS or reused software fully tested and reliable? If not has adequate schedule and resources been included to test and rework it? Also if not, why is it being used? | [5 empty] | 12.i (4)
(5) Have software quality criteria for entrance into OT been identified? | [5 empty] | 12.i (5) | Is this a FAA practice?
13. Completion/Exit Criteria | 0 | 0 | 0 | 0 | 0 | 13
a. Have all Requirements compliance matrices been completed and signed by all parties? | [5 empty] | 13.a
b. Have all draft RFAs been signed off, corrective action plans in place, and an acceptable level of program risk achieved? | [5 empty] | 13.b
c. Have all CDR action plans been resourced and agreed schedules established? | [5 empty] | 13.c
d. Have all exit criteria in SEM App C3.g been satisfied? | [5 empty] | 13.d
e. Does the status of the technical effort and design indicate OPEVAL success (operationally suitable and effective)? | [5 empty] | 13.e
f. Can the detailed design, as disclosed, satisfy the System Specification and fPR? | [5 empty] | 13.f
g. Are adequate processes and metrics in place for the program to succeed? | [5 empty] | 13.g
h. Are the risks known and manageable for the verification program? | [5 empty] | 13.h
i. Is the program schedule executable within the anticipated cost and technical risks? | [5 empty] | 13.i
j. Are the system requirements understood to the level appropriate for this review? | [5 empty] | 13.j
k. Is the program properly staffed? | [5 empty] | 13.k
l. Is the program Non Recurring Engineering requirement executable with the existing budget? | [5 empty] | 13.l
m. Is the detailed design producible within the production budget? | [5 empty] | 13.m
n. Have all contract scope issues coming out of the CDR been resolved? | [5 empty] | 13.n
o. Were the proper FAA competencies represented at the review? If applicable, were all required certification performance monitors involved and do they concur with the detailed design? | [5 empty] | 13.o
p. Has all CDR related documentation been completed and issued? | [5 empty] | 13.p