## READ ME !!!!!
This cost estimate template has been provided to aid you in creating a cost estimate. This should save everyone time by having a workbook which is fully loaded with all formulas needed, and when everyone works with the same format, piecing together information from different estimators is simple.
The template contains ten level 2 WBS sections, each of which shows the recommended way to display the WBS down to level 5. If the need arises to take the task detail to level 6, do not provide any WBS numbers for them, simply indent the item one cell to the right of the level 5 item preceding it, and list each item with the relevant cost info.
We realize your estimate will likely contain many more items at levels 3, 4 and 5 than we have created in this template. You may insert rows, and either copy or AutoFill the formulas as needed.
Subtotals should only be provided at level 2. When not using a line to provide detailed cost information, delete the formulas/info on that particular line.
The cost summary is also fully loaded with formulas, which will reference the info you provide in the estimate. This will provide a concise way to look at the overall costs of the project. Again, you may need to add more rows to incorporate all the level 2 items in your estimate.
Specific Column Info:
"Cost Basis" options: ose = outside shop estimate cp = catalog price se = shop 77 estimate
vq = vendor quote eu = estimate undocumented pe = previous experience
"Unit Cost" - This column should have the estimated $ amount listed. (Not in $K)
"Craft Code" - By entering the craft code of the correct labor type required for a task (found on the "Rates Updated 1-26-00" worksheet in this workbook) the appropriate labor rate will be filled in for you.
"Overhead Total" - The overhead will be calculated automatically, and should only be done at level 2. The rates used are 11.3% for materials and 20.5% for labor.
"Contng %" - The contingency percentage should be filled in at level 2. The cells are already formatted as a percentage. The total project contingency percentage (level 1) will self-calculate.
"Notes" - This column should be used to note any information critical to understanding the estimate, for example, important underlying assumptions. Enter a number in the cell and provide a corresponding number with the information you wish to provide in the note section provided at the bottom of the spread sheet.
Read Me!!!!!!

## Cost Summary
BL 6.0 Femtosecond Cost Estimate Summary
[13 empty] | BEAMLINE(2135) | FRONTEND (507) | ENDSTATION (437)
| Total Material K$ |  | Total Labor K$ |  | Total Labor + Material K$ |  | Overhead Total K$ |  | Sub Total K$ |  | Contingency K$ |  | Total K$
1.0 BL 6.0 Femtosecond | 1741.47 | 0 | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 0 | #VALUE! | 523.862 | 234.7354
1.1 Project Management | 0 |  | 122.7915 |  | 122.7915 |  | 25.1723 |  | 147.9638 |  | 36.9909 |  | 184.9547
1.2 Front End | 272.7 |  | 121.162 |  | 393.862 |  | 43.8454 |  | 437.7074 |  | 86.1546 |  |  | 523.862
1.3 M1 Mirror | 116.5 |  | 40.1662 |  | 156.6662 |  | 16.3541 |  | 173.0203 |  | 31.4349 |  | 204.4552
1.4 Chopper | 129 |  | 30.9378 |  | 159.9378 |  | 15.3336 |  | 175.2714 |  | 30.0187 |  | 205.2901
1.5 Aperture Assy | 64 |  | 9.2549 |  | 73.2549 |  | 6.358 |  | 79.6129 |  | 13.0571 |  | 92.6701
1.6 Soft X-Ray Sample holder | 110 |  | 33.4809 |  | 143.4809 |  | 14.5306 |  | 158.0115 |  | 39.5029 |  |  |  | 197.5144
1.7 HUTCH | 70.5 |  | 33.0366 |  | 103.5366 |  | 11.6864 |  | 115.2229 |  | 19.4069 |  | 134.6299
1.8 Hard X-ray Mono | 121.57 |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A |  | #N/A
1.9 M4 Mirror | 95 |  | 36.812 |  | 131.812 |  | 14.168 |  | 145.98 |  | 31.4139 |  | 177.3939
1.10 Endstation 2 Dispersive | 12 |  | 14.0585 |  | 26.0585 |  | 3.7184 |  | 29.7768 |  | 7.4442 |  |  |  | 37.2211
1.11 VLS Grating Mono | 457.5 |  | 50.217 |  | 507.717 |  | 42.1822 |  | 549.8992 |  | 137.4748 |  | 687.374
1.12 M6 Mirror | 95.5 |  | 29.1677 |  | 124.6677 |  | 12.6357 |  | 137.3034 |  | 29.2448 |  | 166.5482
1.13 Detector Sample | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
1.14 Misc. Beamline | 70.3 |  | 37.0469 |  | 107.3469 |  | 12.4945 |  | 119.8414 |  | 25.9963 |  | 145.8376
1.15 Electrical | 80.7 |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE!
1.16 Computer Controls | 46.2 |  | 34.8142 |  | 81.0142 |  | 10.3571 |  | 91.3713 |  | 15.4298 |  | 106.8011

## Cost Template
[8 empty] | MATERIAL | [6 empty] | LABOR | [5 empty] | TOTALS
[7 empty] | Unit | Material | Cost | Unit | Total | Labor | Labor | Labor | Craft | Labor | Total | Total | Overhead | Sub | Cntng | Cntng | Totals
Description | [6 empty] | Meas | No. | Basis | Cost | Material | No. | Unit | Total | Code | Rate | Labor | Labor + | Total | Total | % | K$ | K$ | Notes
[8 empty] | Units |  |  | K$ | Units | Hours | Hours |  | $/Hr. | K$ | Material
1 | [5 empty] | BL 6.0 Femtosecond |  |  |  |  | 1741.47 | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
1.1 | [5 empty] | Project Management |  |  |  |  | 0 | [5 empty] | 122.7915 | 122.7915 | 25.1723 | 147.9638 | 25% | 36.9909 | 184.9547
| 1.1.1 |  | Engineering Oversight |  |  |  | ea | 0 | eu | 0 | 0 | 1 | 1384 | 1384 | me | 76.4428 | 105.7969
| 1.1.2 |  | General Design Support |  |  |  | ea | 0 | eu | 0 | 0 | 1 | 280 | 280 | md | 60.6952 | 16.9947
1.2 | [5 empty] | Front End |  |  |  |  | 272.7 | [5 empty] | 121.162 | 393.862 | 43.8454 | 437.7074 | 19.68% | 86.1546 | 523.862
| 1.2.1.0 |  | EDI | [7 empty] | 0 |  | 1160 | 1160 |  |  | 70.3187 | 70.3187 | 14.4153 | 84.734 | 25% | 21.1835 | 105.9175
|  | 1.2.1.1 |  |  | Mechcanical
|  |  | 1.2.1.1.1 |  |  | Design and Detail |  | 0 | eu | 0 | 0 | 1 | 200 | 200 | md | 60.6952 | 12.139 | 12.139
|  |  | 1.2.1.1.2 |  |  | Bremsstrahlung Dwgs |  | 0 | eu | 0 | 0 | 1 | 80 | 80 | md | 60.6952 | 4.8556 | 4.8556
|  |  | 1.2.1.1.3 |  |  | PS/PSS Specification |  | 0 | eu | 0 | 0 | 1 | 80 | 80 | me | 76.4428 | 6.1154 | 6.1154
|  |  | 1.2.1.1.4 |  |  | Documentation For PSS/PS |  | 0 | eu | 0 | 0 | 1 | 240 | 240 | md | 60.6952 | 14.5668 | 14.5668
|  |  | 1.2.1.1.5 |  |  | Procurment |  | 0 | eu | 0 | 0 | 1 | 40 | 40 | li | 52.7724 | 2.1109 | 2.1109
|  | 1.2.1.2 |  |  | Electrical
|  |  | 1.2.1.2.1 |  |  | EC- Hardware |  | 0 | eu | 0 | 0 | 1 | 180 | 180 | ec | 58.7065 | 10.5672 | 10.5672
|  |  | 1.2.1.2.2 |  |  | EC- Software |  | 0 | eu | 0 | 0 | 1 | 180 | 180 | ec | 58.7065 | 10.5672 | 10.5672
|  |  | 1.2.1.2.3 |  |  | EC- Electrical |  | 0 | eu | 0 | 0 | 1 | 80 | 80 | ec | 58.7065 | 4.6965 | 4.6965
|  |  | 1.2.1.2.4 |  |  | EC-RSS |  | 0 | eu | 0 | 0 | 1 | 80 | 80 | ec | 58.7065 | 4.7 | 4.7
| 1.2.2.0 |  | VVR1 Assy | [7 empty] | 39.8 |  |  | 48 |  |  | 2.0325 | 41.8325 | 3.1907 | 45.0232 | 15% | 6.7535 | 51.7767
|  | 1.2.2.1 |  |  | Valve
|  |  | 1.2.2.1.1 |  |  | Bellows #1 & #2 | ea | 2 | pe | 1500 | 3 |  |  | 0 |  |  | 0 | 3
|  |  | 1.2.2.1.2 |  |  | Vat Valve | ea | 1 | eu | 20000 | 20 |  |  | 0 |  |  | 0 | 20
|  |  | 1.2.2.1.3 |  |  | Roughing Tree | ea | 1 | pe | 1500 | 1.5 |  |  | 0 |  |  | 0 | 1.5
|  |  | 1.2.2.1.4 |  |  | SR Adaptor Spool | ea | 1 |  | 8000 | 8 |  |  | 0 |  |  | 0 | 8
|  | 1.2.2.2 |  |  | Valve Support
|  |  | 1.2.2.2.1 |  |  | Stand | ea | 1 | pe | 1650 | 1.65 |  |  | 0 |  |  | 0 | 1.65
|  |  | 1.2.2.2.2 |  |  | Table | ea | 1 | eu | 1750 | 1.75 |  |  | 0 |  |  | 0 | 1.75
|  |  | 1.2.2.2.3 |  |  | Support Hardware | ea | 1 |  | 2500 | 2.5 | [5 empty] | 0 | 2.5
|  |  | 1.2.2.2.4 |  |  | Strut assys | ea | 6 | pe | 200 | 1.2 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 1.5388
|  | 1.2.2.3 |  |  | Assemble and UHV Quaify |  | ea | 1 |  | 200 | 0.2 | 1 | 40 | 40 | mu | 42.344 | 1.6938 | 1.8938
| 1.2.3 |  | PS/PSS Assy | [7 empty] | 152 |  |  | 40 |  |  | 3.0577 | 155.0577 | 11.2212 | 166.2789 | 15% | 24.9418 | 191.2208
|  |  | 1.2.3.1 |  | Vendor PO |  | ea | 1 | eu | 125000 | 125 | 1 | 0 | 0 | md | 60.6952 | 0 | 125
|  |  | 1.2.3.2 |  | LBNL Cost |  | ea | 1 | eu | 20000 | 20 | 1 | 0 | 0 | md | 60.6952 | 0 | 20
|  |  | 1.2.3.3 |  | Receival and QA (mech,vac,rad,flow,survey} |  | ea | 2 | eu | 3500 | 7 | 1 | 40 | 40 | me | 76.4428 | 3.0577 | 10.0577
| 1.2.4 |  | VVR2/FV Assy | [7 empty] | 37.3 |  |  | 56 |  |  | 2.4399 | 39.7399 | 3.1 | 42.8399 | 20% | 8.568 | 51.4079
|  | 1.2.4.1 |  |  | Valve
|  |  | 1.2.4.1.1 |  |  | VVR2 Vat Valve | ea | 1 |  | 10000 | 10 |  |  | 0 |  |  | 0 | 10
|  |  | 1.2.4.1.2 |  |  | Fast Valve | ea | 1 |  | 15000 | 15 |  |  | 0 |  |  | 0 | 15
|  |  | 1.2.4.1.3 |  |  | Bellows | ea | 2 |  | 500 | 1 |  |  | 0 |  |  | 0 | 1
|  |  | 1.2.4.1.4 |  |  | Support Hardware | ea | 1 |  | 2500 | 2.5 | [5 empty] | 0 | 2.5
|  |  | 1.2.4.1.5 |  |  | Roughing Tree | ea | 1 | pe | 1500 | 1.5 |  |  | 0 |  |  | 0 | 1.5
|  | 1.2.4.2 |  |  | Valve Support
|  |  | 1.2.4.2.1 |  |  | Stand | ea | 1 | pe | 1650 | 1.65 |  |  | 0 |  |  | 0 | 1.65
|  |  | 1.2.4.2.2 |  |  | Table | ea | 1 | eu | 1750 | 1.75 |  |  | 0 |  |  | 0 | 1.75
|  |  | 1.2.4.2.3 |  |  | Support Hardware | ea | 1 |  | 2500 | 2.5 | [5 empty] | 0 | 2.5
|  |  | 1.2.4.2.4 |  |  | Strut assys | ea | 6 | pe | 200 | 1.2 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 1.5388
|  | 1.2.4.3 |  |  | Assemble and UHV Quaify |  |  | 1 |  | 200 | 0.2 | 1 | 40 | 40 | mu | 42.344 | 1.6938 | 1.8938
|  | 1.2.4.4 |  |  | Fiducialize | [5 empty] | 0 | 2 | 4 | 8 | mus | 50.9292 | 0.40743 | 0.40743
| 1.2.5 |  | Installation | [7 empty] | 1.5 |  |  | 216 |  |  | 9.8331 | 11.3331 | 2.1203 | 13.4535 | 25% | 3.3634 | 16.8168
|  | 1.2.5.1 |  |  | Stands
|  |  | 1.2.5.1.1 |  |  | Spot | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  |  | 1.2.5.1.2 |  |  | Drill | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  |  | 1.2.5.1.3 |  |  | Survey | ea | 0 | eu | 0 | 0 | 2 | 16 | 32 | mus | 50.9292 | 1.6297 | 1.6297
|  |  | 1.2.5.1.4 |  |  | Grout | ea | 1 | eu | 500 | 0.5 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 1.1775
|  | 1.2.5.2 |  |  | VVR1 |  | ea | 0 | eu | 0 | 0 | 0 | 0 | 0 | mu | 42.344 | 0 | 0
|  |  | 1.2.5.2.1 |  |  | Survey | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mus | 50.9292 | 0.40743 | 0.40743
|  |  | 1.2.5.2.2 |  |  | Connect | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  | 1.2.5.3 |  |  | PS/PSS Assy |  | ea | 0 | eu | 0 | 0 | 0 | 0 | 0 | mu | 42.344 | 0 | 0
|  |  | 1.2.5.3.1 |  |  | 1 Survey | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mus | 50.9292 | 0.40743 | 0.40743
|  |  | 1.2.5.3.2 |  |  | 2 Connect | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  |  | 1.2.5.3.3 |  |  | 3 Water | ea | 1 | eu | 500 | 0.5 | 1 | 16 | 16 | mu | 42.344 | 0.6775 | 1.1775
|  | 1.2.5.4 |  |  | VVR2/FV |  | ea | 0 | eu | 0 | 0 | 0 | 0 | 0 | mu | 42.344 | 0 | 0
|  |  | 1.2.5.4.1 |  |  | Survey | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mus | 50.9292 | 0.40743 | 0.40743
|  |  | 1.2.5.4.2 |  |  | Connect | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  | 1.2.5.5 |  |  | Shield Wall |  | ea | 0 | eu | 0 | 0 | 0 | 0 | 0 | mu | 42.344 | 0 | 0
|  |  | 1.2.5.5.1 |  |  | Survey | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mus | 50.9292 | 0.40743 | 0.40743
|  |  | 1.2.5.5.2 |  |  | Connect | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mu | 42.344 | 0.33875 | 0.33875
|  |  | 1.2.5.5.3 |  |  | Pb/Poly | ea | 1 | eu | 500 | 0.5 | 2 | 16 | 32 | mu | 42.344 | 1.355 | 1.855
| 1.2.6 |  | Electrical | [7 empty] | 42.1 |  |  | 780 |  |  | 33.48 | 75.58 | 9.7978 | 85.3778 | 25% | 21.3444 | 106.7222 |  | Woolfe and Mueller need to review
|  | 1.2.6.1 |  |  | Power Distribution and Wireway |  |  | 1 | eu | 1000 | 1 | 2 | 40 | 80 | el | 55.4077 | 4.4326 | 5.4326
|  | 1.2.6.2 |  |  | EPS Front End | [10 empty] | #N/A
|  |  | 1.2.6.2.1 |  |  | XC blocks |  | 1 | eu | 500 | 0.5 | 1 | 5 | 5 | ei | 37.4128 | 0.18706 | 0.68706
|  |  | 1.2.6.2.2 |  |  | PLC I/O modules |  | 10 | eu | 200 | 2 | 7 | 5 | 35 | ei | 37.4128 | 1.3094 | 3.3094
|  |  | 1.2.6.2.3 |  |  | Rack Loading - IG, IP (SR & Fac) |  | 0 | eu | 0 | 0 | 2 | 20 | 40 | ei | 37.4128 | 1.4965 | 1.4965
|  |  | 1.2.6.2.4 |  |  | Device Cable Pulls -IG, IP, FV |  | 2 | eu | 1000 | 2 | 2 | 30 | 60 | el | 55.4077 | 3.3245 | 5.3245
|  |  | 1.2.6.2.5 |  |  | IG controller w/tube - purchase |  | 3 | eu | 3000 | 9 | 0 | 0 | 0 | ei | 37.4128 | 0 | 9
|  |  | 1.2.6.2.6 |  |  | IG proc ctl. cables |  | 3 | eu | 0 | 0 | 4 | 4 | 16 | ei | 37.4128 | 0.5986 | 0.5986
|  |  | 1.2.6.2.7 |  |  | Device Cable Term.-IG, IP, FV, VVR, Jbox |  | 0 | eu | 0 | 0 | 1 | 40 | 40 | ei | 37.4128 | 1.4965 | 1.4965
|  |  | 1.2.6.2.8 |  |  | XC jumpers |  | 0 | eu | 0 | 0 | 2 | 10 | 20 | ei | 37.4128 | 0.74826 | 0.74826
|  |  | 1.2.6.2.9 |  |  | TSP cabling |  | 1 | eu | 300 | 0.3 | 1 | 5 | 5 | ei | 37.4128 | 0.18706 | 0.48706
|  |  | 1.2.6.2.10 |  |  | Misc EI time |  | 0 | eu | 0 | 0 | 1 | 40 | 40 | ei | 37.4128 | 1.4965 | 1.4965
|  |  | 1.2.6.2.11 |  |  | Flow Switches -Purchase, Add Connector |  | 6 | eu | 200 | 1.2 | 3 | 1 | 3 | ei | 37.4128 | 0.11224 | 1.3122
|  |  | 1.2.6.2.12 |  |  | IP Controller Purchase |  | 1 | eu | 6000 | 6 | 4 | 4 | 16 | ei | 37.4128 | 0.5986 | 6.5986
|  | 1.2.6.3 |  |  | EPS Fast Valve
|  |  | 1.2.6.3.1 |  |  | FV Basic Controller | ea | 2 | eu | 3300 | 6.6 | 0 | 0 | 0 | ei | 37.4128 | 0 | 6.6
|  |  | 1.2.6.3.2 |  |  | FV Control Module (not used w/ALS bds.) | ea | 0 | eu | 740 | 0 | 0 | 0 | 0 | ei | 37.4128 | 0 | 0
|  |  | 1.2.6.3.3 |  |  | FV Upgrade Boards (ALS design) | ea | 0 | eu | 1500 | 0 | 0 | 0 | 0 | ei | 37.4128 | 0 | 0
|  |  | 1.2.6.3.4 |  |  | FV Valve Module | ea | 1 | eu | 1300 | 1.3 | 0 | 0 | 0 | ei | 37.4128 | 0 | 1.3
|  |  | 1.2.6.3.5 |  |  | FV HV Sensor Module | ea | 2 | eu | 2000 | 4 | 0 | 0 | 0 | ei | 37.4128 | 0 | 4
|  |  | 1.2.6.3.6 |  |  | FV HV Sensor Unit | ea | 2 | eu | 1800 | 3.6 | 0 | 0 | 0 | ei | 37.4128 | 0 | 3.6
|  |  | 1.2.6.3.7 |  |  | FV installation & cabling | ea | 0 | eu | 0 | 0 | 2 | 10 | 20 | ei | 37.4128 | 0.74826 | 0.74826
|  | 1.2.6.4 |  |  | RSS | [11 empty] | 0
|  |  | 1.2.6.4.1 |  |  | Shutter Control Chassis | ea | 2 | pe | 1250 | 2.5 | 2 | 80 | 160 | ei | 37.4128 | 5.986 | 8.63
|  |  | 1.2.6.4.2 |  |  | Wire Check Shutter Control Chassis |  |  | pe |  |  | 2 | 8 | 16 | em | 42.0691 | 0.67311 | 0.6
|  |  | 1.2.6.4.3 |  |  | Rack Wiring-Shutter | ea | 2 | pe | 300 | 0.6 | 2 | 16 | 32 | ei | 37.4128 | 1.1972 | 1.8
|  |  | 1.2.6.4.4 |  |  | Wire Check Rack Wiring | ea |  | pe |  |  | 2 | 16 | 32 | em | 42.0691 | 1.3462 | 1.2
|  |  | 1.2.6.4.5 |  |  | Pull Shutter Cables | ea | 2 | pe | 600 | 1.2 | 2 | 16 | 32 | el | 55.4077 | 1.773 | 2.5
|  |  | 1.2.6.4.6 |  |  | Terminate Shutter Cables | ea | 2 | pe | 150 | 0.3 | 2 | 16 | 32 | ei | 37.4128 | 1.1972 | 1.5
|  |  | 1.2.6.4.7 |  |  | Wire Check Shutter Cables | ea | 2 | pe |  |  | 2 | 16 | 32 | em | 42.0691 | 1.3462 | 1.2
|  |  | 1.2.6.4.8 |  |  | Write Test Procedure | ea | 2 | pe |  |  | 2 | 16 | 32 | ec | 58.7065 | 1.8786 | 1.9
|  |  | 1.2.6.4.9 |  |  | Test Shutter System | ea | 2 | pe |  |  | 2 | 16 | 32 | em | 42.0691 | 1.3462 | 1.2
1.3 | [5 empty] | M1 Mirror |  |  |  |  | 116.5 | [5 empty] | 40.1662 | 156.6662 | 16.3541 | 173.0203 | 18.17% | 31.4349 | 204.4552 |  | Updated using Kurtis and Troy numbers
| 1.3.1 |  | EDI | [7 empty] | 0 | [5 empty] | 24.5727 | 24.5727 | 5.0374 | 29.6101 | 25% | 7.4025 | 37.0126
|  | 1.3.1.2 |  |  | Specification For PO /Optic |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | me | 76.4428 | 0.61154 | 0.61154
|  | 1.3.1.3 |  |  | Design and Detailing |  | ea | 0 | eu | 0 | 0 | 1 | 320 | 320 | md | 60.6952 | 19.4225 | 19.4225
|  | 1.3.1.4 |  |  | Assy/Install Documentation /Ordering |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | md | 60.6952 | 2.4278 | 2.4278
|  | 1.3.1.5 |  |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | li | 52.7724 | 2.1109 | 2.1109
| 1.3.2 |  | Mirror | [7 empty] | 110.5 | [5 empty] | 0 | 110.5 | 7.7019 | 118.2018 | 15% | 17.7303 | 135.9321
|  | 1.3.2.1 |  |  | Stand and Supports |  | ea | 1 | eu | 5000 | 5 | 0 | 0 | 0 | md | 60.6952 | 0 | 5
|  | 1.3.2.2 |  |  | Vacuum Vessel |  | ea | 1 | eu | 10000 | 10 | 0 | 0 | 0 | md | 60.6952 | 0 | 10
|  | 1.3.2.3 |  |  | Ion Pump |  | ea | 1 | eu | 7500 | 7.5 | 0 | 0 | 0 | md | 60.6952 | 0 | 7.5
|  | 1.3.2.4 |  |  | Stages for positioning |  | ea | 1 | eu | 6500 | 6.5 | 0 | 0 | 0 | md | 60.6952 | 0 | 6.5
|  | 1.3.2.5 |  |  | Mechanical Components |  | ea | 1 | eu | 25000 | 25 | 0 | 0 | 0 | me | 76.4428 | 0 | 25
|  | 1.3.2.6 |  |  | Mirror |  | ea | 1 | eu | 50000 | 50 | 0 | 0 | 0 | ee | 83.0394 | 0 | 50
|  | 1.3.2.7 |  |  | Stages for Bending |  | ea | 1 | eu | 6500 | 6.5 | 0 | 0 | 0 | md | 60.6952 | 0 | 6.5
| 1.3.3 |  | Assy | [7 empty] | 0.5 | [5 empty] | 13.0848 | 13.5848 | 2.7172 | 16.3021 | 25% | 4.0755 | 20.3776
|  | 1.3.3.1 |  |  | First Assy |  | ea | 0 | eu | 0 | 0 | 2 | 40 | 80 | mu | 42.344 | 3.3875 | 3.3875
|  | 1.3.3.2 |  |  | Inspect Mirror |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | me | 76.4428 | 1.2231 | 1.2231
|  | 1.3.3.3 |  |  | UHV Clean |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | mu | 42.344 | 1.6938 | 1.6938
|  | 1.3.3.4 |  |  | Second Assy |  | ea | 0 | eu | 0 | 0 | 2 | 40 | 80 | mu | 42.344 | 3.3875 | 3.3875
|  | 1.3.3.5 |  |  | Install Mirror |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  | 1.3.3.6 |  |  | Set Mirror |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | me | 76.4428 | 1.2231 | 1.2231
|  | 1.3.3.7 |  |  | Fiducialize |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  | 1.3.3.8 |  |  | Bake Prep |  | ea | 1 | eu | 500 | 0.5 | 1 | 16 | 16 | mu | 42.344 | 0.6775 | 1.1775
| 1.3.4 |  | Installation | [7 empty] | 5.5 | [5 empty] | 2.5086 | 8.0086 | 0.89762 | 8.9062 | 25% | 2.2266 | 11.1328
|  | 1.3.3.1 |  |  | Stand |  | ea | 1 | eu | 500 | 0.5 | 2 | 4 | 8 | mu | 42.344 | 0.33875 | 0.83875
|  | 1.3.3.2 |  |  | Survey |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  | 1.3.3.3 |  |  | Vacuum Connect |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  | 1.3.3.4 |  |  | Water /Chiller |  | ea | 1 | eu | 5000 | 5 | 1 | 16 | 16 | mu | 42.344 | 0.6775 | 5.6775
1.4 | [5 empty] | Chopper |  |  |  |  | 129 | [5 empty] | 30.9378 | 159.9378 | 15.3336 | 175.2714 | 17.13% | 30.0187 | 205.2901 |  | Waiting for Nord Update 1/28
| 1.4.1 |  | EDI | [7 empty] | 0 |  |  | 316 |  |  | 18.7978 | 18.7978 | 3.8536 | 22.6514 | 25% | 5.6628 | 28.3142
|  | 1.4.1.2 |  |  | Layout |  | ea | 0 | eu | 0 | 0 | 1 | 20 | 20 | md | 60.6952 | 1.2139 | 1.2139
|  | 1.4.1.4 |  |  | Detail |  | ea | 0 | eu | 0 | 0 | 1 | 120 | 120 | md | 60.6952 | 7.2834 | 7.2834
|  | 1.4.1.5 |  |  | Drive Specification |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | me | 76.4428 | 1.2231 | 1.2231
|  | 1.4.1.6 |  |  | Assy/Install |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | md | 60.6952 | 4.8556 | 4.8556
|  | 1.4.1.7 |  |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | li | 52.7724 | 4.2218 | 4.2218
| 1.4.2 |  | Fab/Procurement | [7 empty] | 129 | [5 empty] | 0 | 129 | 8.9913 | 137.9913 | 15% | 20.6987 | 158.69
|  | 1.4.2.1 |  |  | Fe Feed-Through/Drive/Disk Assy |  | ea | 2 | eu | 48500 | 97 | 0 | 0 | 0 | ee | 83.0394 | 0 | 97
|  | 1.4.2.2 |  |  | Vacuum Chamber |  | ea | 1 | eu | 15000 | 15 | 0 | 0 | 0 | ee | 83.0394 | 0 | 15
|  | 1.4.2.4 |  |  | Stand/Support |  | ea | 1 | eu | 5000 | 5 | 0 | 0 | 0 | ee | 83.0394 | 0 | 5
|  | 1.4.2.5 |  |  | Turbo Pump |  | ea | 1 | eu | 12000 | 12 | 0 | 0 | 0 | ee | 83.0394 | 0 | 12
| 1.4.3 |  | Assy | [7 empty] | 0 | [5 empty] | 9.6314 | 9.6314 | 1.9744 | 11.6058 | 25% | 2.9014 | 14.5072
|  | 1.4.3.1 |  |  | First Assy |  | ea | 0 | eu | 0 | 0 | 2 | 40 | 80 | mu | 42.344 | 3.3875 | 3.3875
|  | 1.4.3.2 |  |  | Test |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | me | 76.4428 | 3.0577 | 3.0577
|  | 1.4.3.3 |  |  | UHV Clean |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  | 1.4.3.4 |  |  | Second Assy |  | ea | 0 | eu | 0 | 0 | 1 | 24 | 24 | mu | 42.344 | 1.0163 | 1.0163
|  | 1.4.3.5 |  |  | Fiducialize |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  | 1.4.3.6 |  |  | Bake Prep |  | ea | 1 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
|  | 1.4.3.7 |  |  | UHV Qualify |  | ea | 1 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
| 1.4.4 |  | Installation | [7 empty] | 0 | [5 empty] | 2.5086 | 2.5086 | 0.51427 | 3.0229 | 25% | 0.75572 | 3.7786
|  | 1.4.3.1 |  |  | Stand |  | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mui | 42.344 | 0.33875 | 0.33875
|  | 1.4.3.2 |  |  | Survey |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  | 1.4.3.3 |  |  | Connect |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  | 1.4.3.4 |  |  | Water |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | mu | 42.344 | 0.6775 | 0.6775
#N/A
1.5 | [5 empty] | Aperture |  |  |  |  | 64 | [5 empty] | 9.2549 | 73.2549 | 6.358 | 79.6129 | 16.4% | 13.0571 | 92.6701
| 1.5.1 |  | EDI | [7 empty] | 0 | [5 empty] | 6.0687 | 6.0687 | 1.2441 | 7.3128 | 25% | 1.8282 | 9.141
|  | 1.5.1.1 |  |  | Layout |  | ea | 0 | eu | 0 | 0 | 1 | 20 | 20 | md | 60.6952 | 1.2139 | 1.2139
|  | 1.5.1.2 |  |  | Detail |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | md | 60.6952 | 2.4278 | 2.4278
|  | 1.5.1.2 |  |  | Specification |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | me | 76.4428 | 0.61154 | 0.61154
|  | 1.5.1.3 |  |  | Assy/Install |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | md | 60.6952 | 0.97112 | 0.97112
|  | 1.5.1.4 |  |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | li | 52.7724 | 0.84436 | 0.84436
| 1.5.2 |  | Fab/Procurement | [7 empty] | 64 | [5 empty] | 0 | 64 | 4.4608 | 68.4608 | 15% | 10.2691 | 78.7299
|  | 1.5.2.1 |  |  | 4 Jaw Aperture |  | ea | 1 | eu | 60000 | 60 | 0 | 0 | 0 | ee | 83.0394 | 0 | 60
|  | 1.5.2.2 |  |  | Support |  | ea | 1 | eu | 4000 | 4 | 0 | 0 | 0 | ee | 83.0394 | 0 | 4
| 1.5.3 |  | Assy | [7 empty] | 0 | [5 empty] | 1.355 | 1.355 | 0.27778 | 1.6328 | 25% | 0.4082 | 2.041
|  | 1.5.3.1 |  |  | Leak Test |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
|  | 1.5.3.2 |  |  | RGA |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  | 1.5.3.2 |  |  | Assemble Support |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
| 1.5.4 |  | Installation | [7 empty] | 0 | [5 empty] | 1.8311 | 1.8311 | 0.37538 | 2.2065 | 25% | 0.55163 | 2.7581
|  | 1.5.4.1 |  |  | Support |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
|  | 1.5.4.2 |  |  | Survey |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  | 1.5.4.3 |  |  | Vacuum Connect |  | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mu | 42.344 | 0.33875 | 0.33875
|  | 1.5.4.4 |  |  | Water |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
1.6 | [5 empty] | Soft X-Ray Sample Holder |  |  |  |  | 110 | [5 empty] | 33.4809 | 143.4809 | 14.5306 | 158.0115 | 25% | 39.5029 | 197.5144 |  | Not Updating Orginal Estimate
From Comins
| 1.6.1 |  | EDI | [7 empty] | 0 | [5 empty] | 26.7059 | 26.7059 | 5.4747 | 32.1806 | 25% | 8.0451 | 40.2257
|  | 1.6.1.1 |  |  | Layout |  | ea | 0 | eu | 0 | 0 | 1 | 120 | 120 | md | 60.6952 | 7.2834 | 7.2834
|  | 1.6.1.2 |  |  | Detail |  | ea | 0 | eu | 0 | 0 | 1 | 240 | 240 | md | 60.6952 | 14.5668 | 14.5668
|  | 1.6.1.3 |  |  | Assy/Install |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | md | 60.6952 | 2.4278 | 2.4278
|  | 1.6.1.4 |  |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | md | 60.6952 | 2.4278 | 2.4278
| 1.6.2 |  | Fab/Procurement | [7 empty] | 110 | [5 empty] | 0 | 110 | 7.667 | 117.667 | 25% | 29.4168 | 147.0838
|  | 1.6.2.1 |  |  | Sample Manipulator |  | ea | 1 | eu | 30000 | 30 | 0 | 0 | 0 | ee | 83.0394 | 0 | 30
|  | 1.6.2.2 |  |  | Differential Pump |  | ea | 2 | eu | 18000 | 36 | 0 | 0 | 0 | ee | 83.0394 | 0 | 36
|  | 1.6.2.3 |  |  | Vacuum Chamber |  | ea | 1 | eu | 20000 | 20 | 0 | 0 | 0 | ee | 83.0394 | 0 | 20
|  | 1.6.2.4 |  |  | Miscellaneous Hdwr. |  | ea | 1 | eu | 5000 | 5 | 0 | 0 | 0 | ee | 83.0394 | 0 | 5
|  | 1.6.2.5 |  |  | Optical Table |  | ea | 1 | eu | 4000 | 4 | 0 | 0 | 0 | ee | 83.0394 | 0 | 4
|  | 1.6.2.6 |  |  | Miscellaneous Vacuum |  | ea | 1 | eu | 5000 | 5 | 0 | 0 | 0 | ee | 83.0394 | 0 | 5
|  | 1.6.2.7 |  |  | Turbo Pump |  | ea | 1 | eu | 10000 | 10 | 0 | 0 | 0 | ee | 83.0394 | 0 | 10
| 1.6.3 |  | Assy | [7 empty] | 0 | [5 empty] | 3.3875 | 3.3875 | 0.69444 | 4.082 | 25% | 1.0205 | 5.1025
|  | 1.6.3.1 |  |  |  |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | mu | 42.344 | 3.3875 | 3.3875
| 1.6.4 |  | Installation | [7 empty] | 0 | [5 empty] | 3.3875 | 3.3875 | 0.69444 | 4.082 | 25% | 1.0205 | 5.1025
|  | 1.6.4.1 |  |  |  |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | mu | 42.344 | 3.3875 | 3.3875
1.7 | [5 empty] | Hutch |  |  |  |  | 70.5 | [5 empty] | 33.0366 | 103.5366 | 11.6864 | 115.2229 | 16.84% | 19.4069 | 134.6299 |  | Based on 3.2 Hutch
Needs updating current Layout
| 1.7.1 |  | EDI | [7 empty] | 0 | [5 empty] | 8.7052 | 8.7052 | 1.7846 | 10.4898 | 25% | 2.6225 | 13.1123 |  | Air Handeling Unit ?????
|  | 1.7.1.1 |  |  | Layout |  | ea | 0 | pe | 0 | 0 | 1 | 30 | 30 | md | 60.6952 | 1.8209 | 1.8209
|  | 1.7.1.2 |  |  | Detail |  | ea | 0 | pe | 0 | 0 | 1 | 80 | 80 | md | 60.6952 | 4.8556 | 4.8556
|  | 1.7.1.2 |  |  | Specification |  | ea | 0 | pe | 0 | 0 | 1 | 20 | 20 | md | 60.6952 | 1.2139 | 1.2139
|  | 1.7.1.3 |  |  | Survey and tape flr |  | ea | 0 | pe | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
| 1.7.2 |  | Electricial | [7 empty] | 25 | [5 empty] | 15.7781 | 40.7781 | 4.977 | 45.7551 | 25% | 11.4388 | 57.1938
|  | 1.7.2.2 |  |  | EDI |  | ea |  | pe |  | 0 | 1 | 80 | 80 | ec | 58.7065 | 4.6965 | 4.6965
|  | 1.7.2.3 |  |  | Electrical Installation and Distribution |  | ea |  | pe |  | 0 | 1 | 80 | 80 | el | 55.4077 | 4.4326 | 4.4326
|  | 1.7.2.4 |  |  | RSS |  | ea | 1 | pe | 25000 | 25 | 1 | 120 | 120 | el | 55.4077 | 6.6489 | 31.6489
| 1.7.3 |  | Procurement | [7 empty] | 29.5 | [5 empty] | 3.3875 | 32.8875 | 2.7506 | 35.6381 | 15% | 5.3457 | 40.9838
|  | 1.7.3.1 |  |  | Vendor Procument |  | ea | 1 | pe | 27000 | 27 | 0 | 0 | 0 | md | 60.6952 | 0 | 27
|  | 1.7.3.2 |  |  | Assy/Install |  | ea | 1 | pe | 500 | 0.5 | 2 | 40 | 80 | mu | 42.344 | 3.3875 | 3.8875
|  | 1.7.3.3 |  |  | Pb Windows |  | ea | 4 | pe | 500 | 2 | 0 | 0 | 0 | mu | 42.344 | 0 | 2
| 1.7.4 |  | Utilities | [7 empty] | 16 | [5 empty] | 5.1658 | 21.1658 | 2.1742 | 23.3399 | 25% | 5.835 | 29.1749
|  | 1.7.4.1 |  |  | Air, Vacuum, Water |  | ea | 1 | pe | 500 | 0.5 | 1 | 40 | 40 | mui | 42.344 | 1.6938 | 2.1938
|  | 1.7.4.2 |  |  | Fire Protection |  | ea | 1 | pe | 500 | 0.5 | 2 | 40 | 80 | pb | 43.4 | 3.472 | 3.972
|  | 1.7.4.3 |  |  | Air Handling tie to Facilities |  | ea | 1 | pe | 15000 | 15 | 0 | 40 | 0 | pb | 43.4 | 0 | 15
1.8 | [5 empty] | M2-MONO-M3 COMPONENT |  |  |  |  | 121.57 |  |  | 1216 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | TIG Estimate with ALS EDI
| 1.8.1.0 |  | EDI | [7 empty] | 0 |  |  | 1016 |  |  | 60.4507 | 60.4507 | 12.3924 | 72.8431 | 35% | 25.4951 | 98.3382
|  | 1.8.1.1 |  |  | Layout |  | ea | 0 |  | 0 | 0 | 1 | 160 | 160 | me | 76.4428 | 12.2309 | 12.2309
|  | 1.8.1.2 |  |  | Designer |  | ea | 0 |  | 0 | 0 | 1 | 600 | 600 | md | 60.6952 | 36.4171 | 36.4171 | [5 empty] | Designer time is based on the assumption they've no familiarity with the components and they have an average skill set.
|  | 1.8.1.3 |  |  | Technician for pre Assembly |  | ea | 0 |  | 0 | 0 | 1 | 200 | 200 | mu | 42.344 | 8.4688 | 8.4688 | [5 empty] | Mirror glueup, Assembly, Arrange metrology & wiring
|  | 1.8.1.4 |  |  | Metrology |  | ea | 0 |  | 0 | 0 | 1 | 16 | 16 | me | 76.4428 | 1.2231 | 1.2231 | [5 empty] | Experimental Systems Group Metrology effort.
|  | 1.8.1.5 |  |  | Procument |  | ea | 0 |  | 0 | 0 | 1 | 40 | 40 | li | 52.7724 | 2.1109 | 2.1109
| 1.8.2.0 |  | Internal Optic Mounting Hardware & Optics |  |  |  | ea | 0 |  | 0 | 92.57 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | 20% | #N/A | #N/A
|  | 1.8.2.1 |  |  | Picomotors |  | ea | 10 | cp | 0.65 | 6.5 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.2 |  |  | LVDT |  | ea | 10 | cp | 0.13 | 1.3 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.3 |  |  | Linear Slides Mirror Mechanism |  | ea | 4 | pe | 0.25 | 1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.4 |  |  | Newport Slide |  | ea | 3 | cp | 0.7 | 2.1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.5 |  |  | Fabrication Items |  | ea | 1 | eu | 40 | 40 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.6 |  |  | Huber 410 |  | ea | 1 | cp | 4.5 | 4.5 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.7 |  |  | Huber Motor (Pittman) |  | ea | 1 | eu | 1 | 1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.8 |  |  | Heidenhain #RON806 |  | ea | 1 | cp | 5.6 | 5.6 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.9 |  |  | Teflon Seals |  | ea | 2 | cp | 0.035 | 0.07 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.10 |  |  | Electrical Feedthrus |  | ea | 2 | cp | 0.25 | 0.5 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.11 |  |  | Huber Slit Support Mount |  | ea | 1 | eu | 0.5 | 0.5 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.12 |  |  | Huber Slit |  | ea | 1 | cp | 3.5 | 3.5 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.2.13 |  |  | Optics |  | ea | 1 | cp | 26 | 26 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
| 1.8.3.0 |  | Vac Chamber | [7 empty] | 11 |  |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | 20% | #N/A | #N/A
|  | 1.8.3.1 |  |  | Water Cooling Flange |  | ea | 1 | eu | 1 | 1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.3.2 |  |  | Electrical Feedthru Slits |  | ea | 1 | eu | 1 | 1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.3.3 |  |  | Electrical Feedthru M2 & M3 |  | ea | 1 | eu | 1 | 1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.3.4 |  |  | Chamber Fabrication |  | ea | 1 | eu | 8 | 8 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
| 1.8.4.0 |  | Stand and Supports |  |  |  | ea | 1 |  | 0 | 10 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | 20% | #N/A | #N/A
|  | 1.8.4.1 |  |  | Hardware |  | ea | 1 |  | 2 | 2 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.4.2 |  |  | Stand Fabrication |  | ea | 1 | eu | 5 | 5 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | [5 empty] | Epozy Concrete filled?
|  | 1.8.4.3 |  |  | 3/4" Struts |  | ea | 6 | eu | 0.5 | 3 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
| 1.8.5.0 |  | Linear Stage |  |  |  | ea | 1 |  | 0 | 6 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A | #N/A | #N/A | 20% | #N/A | #N/A
|  | 1.8.5.1 |  |  | Linear Rails |  | ea | 1 | eu | 1 | 1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.5.2 |  |  | Leadscrew |  | ea | 1 | eu | 0.5 | 0.5 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.5.3 |  |  | Leadscrew Motor |  | ea | 1 | eu | 1 | 1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.5.4 |  |  | Stage Fabrication |  | ea | 1 | eu | 3 | 3 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
|  | 1.8.5.5 |  |  | Stage Travel Stops & Limits |  | ea | 1 | eu | 0.5 | 0.5 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
#N/A
| 1.8.6.0 |  | System Assembly | [7 empty] | 1 |  |  | 120 |  | #N/A | #N/A | #N/A | #N/A | #N/A | 25% | #N/A | #N/A
|  | 1.8.6.1 |  |  | Designer |  | ea | 0 |  | 0 | 0 | 1 | 24 | 24 | md | 60.6952 | 1.4567 | 1.4567
|  | 1.8.6.2 |  |  | Assemble and align |  | ea | 0 |  | 0 | 0 | 1 | 80 | 80 | me | 76.4428 | 6.1154 | 6.1154 | [5 empty] | Completely assembled package ready for installation.
|  | 1.8.6.3 |  |  | Fiducialize |  | ea | 0 |  | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487 | [5 empty] | Designer time is based on the assumption they've no familiarity with the components and they have an average skill set.
|  | 1.8.6.4 |  |  | Hardware |  | ea | 1 |  | 1 | 1 | 0 | 0 | 0 |  | #N/A | #N/A | #N/A
| 1.8.7.0 |  | Installation | [7 empty] | 1 |  |  | 80 |  | #N/A | 4.001 | 5.001 | 0.8899 | 5.8909 | 20% | 1.1782 | 7.0691
|  | 1.8.7.1 |  |  | Spot Floor |  | ea | 0 |  | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  | 1.8.7.2 |  |  | Drill and Mount |  | ea | 0 |  | 0 | 0 | 2 | 16 | 32 | mui | 42.344 | 1.355 | 1.355
|  | 1.8.7.3 |  |  | Survey and Align |  | ea | 0 |  | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  | 1.8.7.4 |  |  | Vacuum connect and bake |  | ea | 1 |  | 1 | 0.5 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 1.1775
|  | 1.8.7.5 |  |  | Hook up Utlities |  | ea | 1 |  | 1 | 0.5 | 1 | 8 | 8 | mui | 42.344 | 0.33875 | 0.83875
Notes
Assumes that the mirror design is a copy of the BL_10.3.2 type but can be scaled larger easliy.
Air guard must be added to the water cooling circuit of the crystal. This may not be straight forward.
Experimental Systems Group Metrology effort.
Mirror glueup, Assembly, Arrange metrology & wiring
Epozy Concrete filled?
| Completely assembled package ready for installation. | [6 empty] | Less alignment, wiring, electronics systems, software, and general ALS support
Designer time is based on the assumption they've no familiarity with the components and they have an average skill set.
Rich Celestre says these slits are no longer in favor.
1.9 | [5 empty] | M4 Mirror |  |  |  |  | 95 | [5 empty] | 36.812 | 131.812 | 14.168 | 145.98 | 21.52% | 31.4139 | 177.3939 |  | Similar to M-1 Design
Waiting for Quotation and
| 1.9.1 |  | EDI | [7 empty] | 0 | [5 empty] | 27.1841 | 27.1841 | 5.5727 | 32.7569 | 25% | 8.1892 | 40.9461 |  | futher info from Oxfor/SESO
|  |  | 1.9.1.1 |  | Layout |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | me | 76.4428 | 6.1154 | 6.1154
|  |  | 1.9.1.2 |  | Detail |  | ea | 0 | eu | 0 | 0 | 1 | 200 | 200 | me | 76.4428 | 15.2886 | 15.2886
|  |  | 1.9.1.3 |  | Specification for Optic |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | me | 76.4428 | 0.61154 | 0.61154
|  |  | 1.9.1.4 |  | Assy/Install |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | me | 76.4428 | 3.0577 | 3.0577
|  |  | 1.9.1.5 |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | li | 52.7724 | 2.1109 | 2.1109
| 1.9.2 |  | Fab/Procure | [7 empty] | 95 | [5 empty] | 0 | 95 | 6.6215 | 101.6215 | 20% | 20.3243 | 121.9458
|  |  | 1.9.2.1 |  | Mechanical Components |  | ea | 1 | eu | 60000 | 60 | 0 | 0 | 0 | ee | 83.0394 | 0 | 60
|  |  | 1.9.2.2 |  | Mirror |  | ea | 1 | eu | 35000 | 35 | 0 | 0 | 0 | ee | 83.0394 | 0 | 35
| 1.9.3 |  | Assy | [7 empty] | 0 | [5 empty] | 8.1355 | 8.1355 | 1.6678 | 9.8033 | 25% | 2.4508 | 12.2541
|  |  | 1.9.3.1 |  | First Assy |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | mu | 42.344 | 1.6938 | 1.6938
|  |  | 1.9.3.2 |  | Inspect Optic |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | me | 76.4428 | 1.2231 | 1.2231
|  |  | 1.9.3.3 |  | UHV Clean |  | ea | 0 | eu | 0 | 0 | 1 | 24 | 24 | mu | 42.344 | 1.0163 | 1.0163
|  |  | 1.9.3.4 |  | Second Assy |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | mu | 42.344 | 1.6938 | 1.6938
|  |  | 1.9.3.5 |  | Install Optic |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  |  | 1.9.3.6 |  | Bend Optic |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  |  | 1.9.3.7 |  | Fiducialize |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  |  | 1.9.3.8 |  | Bake Prep |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
| 1.9.4 |  | Installation | [7 empty] | 0 | [5 empty] | 1.4924 | 1.4924 | 0.30594 | 1.7983 | 25% | 0.44958 | 2.2479
|  |  | 1.9.4.1 |  | Stand |  | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mu | 42.344 | 0.33875 | 0.33875
|  |  | 1.9.4.2 |  | Survey |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  |  | 1.9.4.3 |  | Vacuum Connect |  | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mu | 42.344 | 0.33875 | 0.33875
1.1 | [5 empty] | Endstation 2 Dispersive |  |  |  |  | 12 | [5 empty] | 14.0585 | 26.0585 | 3.7184 | 29.7768 | 25% | 7.4442 | 37.2211 |  | Not Updating Orginal Estimate
From Comins
| 1.10.1 |  | EDI | [7 empty] | 0 | [5 empty] | 7.2834 | 7.2834 | 1.4931 | 8.7765 | 25% | 2.1941 | 10.9707
|  |  | 1.10.1.1 |  | Layout |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | md | 60.6952 | 4.8556 | 4.8556
|  |  | 1.10.1.2 |  | Detail |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | md | 60.6952 | 2.4278 | 2.4278
|  |  | 1.10.1.3 |  | Assy/Install |  | ea | 0 | eu | 0 | 0 | 1 | 0 | 0 | md | 60.6952 | 0 | 0
|  |  | 1.10.1.4 |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 0 | 0 | li | 52.7724 | 0 | 0
| 1.10.2 |  | Fab/Procurement | [7 empty] | 12 | [5 empty] | 0 | 12 | 0.8364 | 12.8364 | 25% | 3.2091 | 16.0455
|  |  | 1.10.2.2 |  | Bellows | nce | ea | 1 | eu | 2000 | 2 | 0 | 0 | 0 | ee | 83.0394 | 0 | 2
|  |  | 1.10.2.3 |  | Six Way Cube |  | ea | 1 | eu | 6000 | 6 | 0 | 0 | 0 | ee | 83.0394 | 0 | 6
|  |  | 1.10.2.4 |  | Vacuum Chamber |  | ea | 1 | eu | 0 | 0 | 0 | 0 | 0 | ee | 83.0394 | 0 | 0
|  |  | 1.10.2.5 |  | Miscellaneous Hdwr. |  | ea | 1 | eu | 0 | 0 | 0 | 0 | 0 | ee | 83.0394 | 0 | 0
|  |  | 1.10.2.6 |  | Optical Table |  | ea | 1 | eu | 4000 | 4 | 0 | 0 | 0 | ee | 83.0394 | 0 | 4
|  |  | 1.10.2.7 |  | Miscellaneous Vacuum |  | ea | 1 | eu | 0 | 0 | 0 | 0 | 0 | ee | 83.0394 | 0 | 0
|  |  | 1.10.2.8 |  | Turbo Pump |  | ea | 1 | eu | 0 | 0 | 0 | 0 | 0 | ee | 83.0394 | 0 | 0
| 1.10.3 |  | Assy | [7 empty] | 0 | [5 empty] | 3.3875 | 3.3875 | 0.69444 | 4.082 | 25% | 1.0205 | 5.1025
|  |  | 1.10.3.1 |  |  |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | mu | 42.344 | 3.3875 | 3.3875
| 1.10.4 |  | Installation | [7 empty] | 0 | [5 empty] | 3.3875 | 3.3875 | 0.69444 | 4.082 | 25% | 1.0205 | 5.1025
[7 empty] | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | mu | 42.344 | 3.3875 | 3.3875
1.11 | [5 empty] | VLS Grating Monochromator |  |  |  |  | 457.5 | [5 empty] | 50.217 | 507.717 | 42.1822 | 549.8992 | 25% | 137.4748 | 687.374 |  | Similar to Comins PEEM 3 11/18/02
Need to check Optics $'s
| 1.11.1 |  | EDI | [7 empty] | 0 | [5 empty] | 28.6835 | 28.6835 | 5.8801 | 34.5636 | 25% | 8.6409 | 43.2045
|  |  | 1.11.1.1 |  | Layout |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | me | 76.4428 | 3.0577 | 3.0577
|  |  | 1.11.1.2 |  | Detail |  | ea | 0 | eu | 0 | 0 | 1 | 160 | 160 | me | 76.4428 | 12.2309 | 12.2309
|  |  | 1.11.1.3 |  | Specification for Outside Purchase |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | me | 76.4428 | 3.0577 | 3.0577
|  |  | 1.11.1.4 |  | Assy/Install |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | me | 76.4428 | 6.1154 | 6.1154
|  |  | 1.11.1.5 |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | li | 52.7724 | 4.2218 | 4.2218
| 1.11.2 |  | Fab/Procure | [7 empty] | 457.5 | [5 empty] | 0 | 457.5 | 31.8878 | 489.3877 | 25% | 122.3469 | 611.7347
|  |  | 1.11.2.1 |  | Mechanical Components /Vendor |  | ea | 1 | eu | 225000 | 225 | 0 | 0 | 0 | ee | 83.0394 | 0 | 225
|  |  | 1.11.2.2 |  | Mechanical Components Job Shops |  | ea | 1 | eu | 50000 | 50 | 0 | 0 | 0 | ee | 83.0394 | 0 | 50
|  |  | 1.11.2.3 |  | Optical Components |  | ea | 0 | eu | 0 | 0 | 0 | 0 | 0 | ee | 83.0394 | 0 | 0
|  |  |  | 1 |  | Grating | ea | 1 | eu | 100000 | 100 | 0 | 0 | 0 | ee | 83.0394 | 0 | 100
|  |  |  | 2 |  | Si Mirrors | ea | 3 | eu | 27500 | 82.5 | 0 | 0 | 0 | ee | 83.0394 | 0 | 82.5
| 1.11.3 |  | Sub- Assy | [7 empty] | 0 | [5 empty] | 17.1937 | 17.1937 | 3.5247 | 20.7184 | 25% | 5.1796 | 25.8981
|  |  | 1.11.3.1 |  | First Assy |  | ea | 0 | eu | 0 | 0 | 1 | 120 | 120 | mu | 42.344 | 5.0813 | 5.0813
|  |  | 1.11.3.2 |  | Inspect Optics |  | ea | 0 | eu | 0 | 0 | 1 | 60 | 60 | me | 76.4428 | 4.5866 | 4.5866
|  |  | 1.11.3.3 |  | UHV Clean |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | mu | 42.344 | 1.6938 | 1.6938
|  |  | 1.11.3.4 |  | Second Assy |  | ea | 0 | eu | 0 | 0 | 1 | 32 | 32 | mu | 42.344 | 1.355 | 1.355
|  |  | 1.11.3.5 |  | Install Optics |  | ea | 0 | eu | 0 | 0 | 1 | 32 | 32 | mu | 42.344 | 1.355 | 1.355
|  |  | 1.11.3.6 |  | Fiducialize |  | ea | 0 | eu | 0 | 0 | 2 | 24 | 48 | mus | 50.9292 | 2.4446 | 2.4446
|  |  | 1.11.3.7 |  | Bake Prep |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | mu | 42.344 | 0.6775 | 0.6775
| 1.11.4 |  | Installation | [7 empty] | 0 | [5 empty] | 4.3397 | 4.3397 | 0.88965 | 5.2294 | 25% | 1.3073 | 6.5367
|  |  | 1.11.4.1 |  | Stand |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  |  | 1.11.4.2 |  | Survey |  | ea | 0 | eu | 0 | 0 | 2 | 16 | 32 | mus | 50.9292 | 1.6297 | 1.6297
|  |  | 1.11.4.3 |  | Table |  | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mu | 42.344 | 0.33875 | 0.33875
|  |  | 1.11.4.4 |  | Mono |  | ea | 0 | eu | 0 | 0 | 1 | 32 | 32 | mu | 42.344 | 1.355 | 1.355
|  |  | 1.11.4.5 |  | Installation- Water |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
1.12 | [5 empty] | M6 Mirror |  |  |  |  | 95.5 | [5 empty] | 29.1677 | 124.6677 | 12.6357 | 137.3034 | 21.3% | 29.2448 | 166.5482 |  | Same as M-4
| 1.12.1 |  | EDI | [7 empty] | 0 | [5 empty] | 19.5399 | 19.5399 | 4.0057 | 23.5455 | 25% | 5.8864 | 29.4319
|  |  | 1.12.1.1 |  | Layout |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | me | 76.4428 | 6.1154 | 6.1154
|  |  | 1.12.1.2 |  | Detail |  | ea | 0 | eu | 0 | 0 | 1 | 100 | 100 | me | 76.4428 | 7.6443 | 7.6443
|  |  | 1.12.1.3 |  | Specification for Optic |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | me | 76.4428 | 0.61154 | 0.61154
|  |  | 1.12.1.4 |  | Assy/Install |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | me | 76.4428 | 3.0577 | 3.0577
|  |  | 1.12.1.5 |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | li | 52.7724 | 2.1109 | 2.1109
#N/A
| 1.12.2 |  | Fab/Procure | [7 empty] | 95 | [5 empty] | 0 | 95 | 6.6215 | 101.6215 | 20% | 20.3243 | 121.9458
|  |  | 1.12.2.1 |  | Mechanical Components |  | ea | 1 | eu | 60000 | 60 | 0 | 0 | 0 | ee | 83.0394 | 0 | 60
|  |  | 1.12.2.2 |  | Mirror |  | ea | 1 | eu | 35000 | 35 | 0 | 0 | 0 | ee | 83.0394 | 0 | 35
| 1.12.3 |  | Assy | [7 empty] | 0 | [5 empty] | 8.1355 | 8.1355 | 1.6678 | 9.8033 | 25% | 2.4508 | 12.2541
|  |  | 1.12.3.1 |  | First Assy |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | mu | 42.344 | 1.6938 | 1.6938
|  |  | 1.12.3.2 |  | Inspect Optic |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | me | 76.4428 | 1.2231 | 1.2231
|  |  | 1.12.3.3 |  | UHV Clean |  | ea | 0 | eu | 0 | 0 | 1 | 24 | 24 | mu | 42.344 | 1.0163 | 1.0163
|  |  | 1.12.3.4 |  | Second Assy |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | mu | 42.344 | 1.6938 | 1.6938
|  |  | 1.12.3.5 |  | Install Optic |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  |  | 1.12.3.6 |  | Bend Optic |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | mu | 42.344 | 0.6775 | 0.6775
|  |  | 1.12.3.7 |  | Fiducialize |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  |  | 1.12.3.8 |  | Bake Prep |  | ea | 0 | eu | 0 | 0 | 1 | 8 | 8 | mu | 42.344 | 0.33875 | 0.33875
| 1.12.4 |  | Installation | [7 empty] | 0.5 | [5 empty] | 1.4924 | 1.9924 | 0.34079 | 2.3332 | 25% | 0.58329 | 2.9164
|  |  | 1.12.4.1 |  | Stand |  | ea | 1 | eu | 500 | 0.5 | 2 | 4 | 8 | mu | 42.344 | 0.33875 | 0.83875
|  |  | 1.12.4.2 |  | Survey |  | ea | 0 | eu | 0 | 0 | 2 | 8 | 16 | mus | 50.9292 | 0.81487 | 0.81487
|  |  | 1.12.4.3 |  | Vacuum Connect |  | ea | 0 | eu | 0 | 0 | 2 | 4 | 8 | mu | 42.344 | 0.33875 | 0.33875
1.13 | [5 empty] | Detector Sample |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | Not Updating Orginal Estimate
From Comins
| 1.13.1 |  | EDI | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0% | 0 | 0
|  |  | 1.13.1.1 |  | Layout |  | ea | 0 | eu | 0 | 0 | 0 | 0 | 0 | md | 60.6952 | 0 | 0
|  |  | 1.13.1.2 |  | Detail |  | ea | 0 | eu | 0 | 0 | 0 | 0 | 0 | md | 60.6952 | 0 | 0
|  |  | 1.13.1.3 |  | Procurement |  | ea | 0 | eu | 0 | 0 | 0 | 0 | 0 | md | 60.6952 | 0 | 0
| 1.13.2 |  | Fab/Procurement | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0% | 0 | 0
[7 empty] | ea | 1 | eu | 0 | 0 | 0 | 0 | 0 | ee | 83.0394 | 0 | 0
| 1.13.3 |  | Assy | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0% | 0 | 0
[7 empty] | ea | 0 | eu | 0 | 0 | 0 | 80 | 0 | mu | 42.344 | 0 | 0
| 1.13.4 |  | Installation | [7 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 25% | 0 | 0
[7 empty] | ea | 0 | eu | 0 | 0 | 0 | 40 | 0 | mu | 42.344 | 0 | 0
1.14 | [5 empty] | Miscellaneous Beamline |  |  |  |  | 70.3 | [5 empty] | 37.0469 | 107.3469 | 12.4945 | 119.8414 | 21.69% | 25.9963 | 145.8376
| 1.14.1 |  | EDI | [7 empty] | 0 | [5 empty] | 19.4225 | 19.4225 | 3.9816 | 23.4041 | 25% | 5.851 | 29.2551
|  |  | 1.14.1.1 |  | Layout |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | md | 60.6952 | 4.8556 | 4.8556
|  |  | 1.14.1.2 |  | Detail |  | ea | 0 | eu | 0 | 0 | 1 | 120 | 120 | md | 60.6952 | 7.2834 | 7.2834
|  |  | 1.14.1.3 |  | Assy/Install |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | md | 60.6952 | 4.8556 | 4.8556
|  |  | 1.14.1.4 |  | Procurement |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | md | 60.6952 | 2.4278 | 2.4278
| 1.14.2 |  | Fab/Procurement | [7 empty] | 70.3 | [5 empty] | 3.3875 | 73.6875 | 5.5944 | 79.2819 | 20% | 15.8564 | 95.1382
|  |  | 1.14.2.1 |  | Differential Ion Pump |  | ea | 1 | eu | 18000 | 18 | 1 | 0 | 0 | md | 60.6952 | 0 | 18
|  |  | 1.14.2.2 |  | 2-1/2" Vat Valve No. 10 |  | ea | 4 | eu | 1700 | 6.8 | 1 | 0 | 0 | md | 60.6952 | 0 | 6.8
|  |  | 1.14.2.3 |  | 4" Vat Valve No. 10 |  | ea | 3 | eu | 2200 | 6.6 | 1 | 0 | 0 | md | 60.6952 | 0 | 6.6
|  |  | 1.14.2.4 |  | Ion Pump 240 L/s |  | ea | 1 | eu | 5500 | 5.5 | 1 | 0 | 0 | md | 60.6952 | 0 | 5.5
|  |  | 1.14.2.5 |  | Beam Pipe |  | ea | 5 | eu | 1000 | 5 | 1 | 0 | 0 | md | 60.6952 | 0 | 5
|  |  | 1.14.2.6 |  | Bellows |  | ea | 5 | eu | 1000 | 5 | 1 | 0 | 0 | md | 60.6952 | 0 | 5
|  |  | 1.14.2.7 |  | Stands |  | ea | 2 | eu | 2500 | 5 | 1 | 0 | 0 | md | 60.6952 | 0 | 5
|  |  | 1.14.2.8 |  | Diagnostic Chamber |  | ea | 1 | eu | 1400 | 1.4 | 1 | 0 | 0 | md | 60.6952 | 0 | 1.4
|  |  | 1.14.2.9 |  | Diagnostic Components |  | ea | 1 | eu | 4000 | 4 | 1 | 0 | 0 | md | 60.6952 | 0 | 4
|  |  | 1.14.2.10 |  | Miscellaneous |  | ea | 1 | eu | 5000 | 5 | 1 | 0 | 0 | md | 60.6952 | 0 | 5
|  |  | 1.14.2.11 |  | Brems Rad Shielding |  | ea | 1 | eu | 2000 | 2 | 1 | 80 | 80 | mu | 42.344 | 3.3875 | 5.3875
|  |  | 1.14.2.12 |  | Rough Trees |  | ea | 6 | eu | 1000 | 6 | 1 | 0 | 0 | mu | 42.344 | 0 | 6
| 1.14.3 |  | Assy/Installation | [7 empty] | 0 | [5 empty] | 14.2369 | 14.2369 | 2.9186 | 17.1555 | 25% | 4.2889 | 21.4443
|  |  | 1.14.3.1 |  | Assemble, Bake, Vacuum Qualify |  | ea | 0 | eu | 0 | 0 | 1 | 240 | 240 | mu | 42.344 | 10.1626 | 10.1626
|  |  | 1.14.3.2 |  | Misc. Survey Tasks |  | ea | 0 | eu | 0 | 0 | 1 | 80 | 80 | mus | 50.9292 | 4.0743 | 4.0743
1.15 | [5 empty] | Electrical |  |  |  |  | 80.7 | [5 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| 1.15.1 |  | Racks/Wireways Branchline | [7 empty] | 19.3 |  |  | 1002 |  |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 25% | #VALUE! | #VALUE!
|  |  | 1.15.1.1 |  | BR Racks -EPS Racks above beamline |  | ea | 2 | eu | 2850 | 5.7 | 5 | 6 | 30 | ei | #VALUE! | #VALUE! | #VALUE!
|  |  | 1.15.1.2 |  | BR Rack AC outlets + Subpanel |  | ea | 1 | eu | 3000 | 3 | 1 | 80 | 80 | el | 55.4077 | 4.4326 | 7.4326
|  |  | 1.15.1.3 |  | Wireway - along beamline |  | ea | 1 | eu | 4000 | 4 | 1 | 320 | 320 | el | 55.4077 | 17.7305 | 21.7305
|  |  | 1.15.1.4 |  | Wireway lampost supports |  | ea | 2 | eu | 1000 | 2 | 2 | 4 | 8 | mui | 42.344 | 0.33875 | 2.3388
|  |  | 1.15.1.5 |  | AC power along beamline |  | ea | 1 | eu | 1000 | 1 | 1 | 60 | 60 | el | 55.4077 | 3.3245 | 4.3245
|  |  | 1.15.1.6 |  | Cable pulls - Motor cables |  | ea | 1 | eu | 1600 | 1.6 | 2 | 32 | 64 | el | 55.4077 | 3.5461 | 5.1461
|  |  | 1.15.1.7 |  | Cable Terminations / Motor controls |  | ea | 1 | eu | 1000 | 1 | 1 | 80 | 80 | ei | 37.4128 | 2.993 | 3.993
|  |  | 1.15.1.8 |  | EC- Electrical |  | ea | 1 | eu | 0 | 0 | 1 | 80 | 80 | ec | 58.7065 | 4.6965 | 4.6965
|  |  | 1.15.1.9 |  | EC- Motor Controls |  | ea | 1 | eu | 0 | 0 | 1 | 120 | 120 | ec | 58.7065 | 7.0448 | 7.0448
|  |  | 1.15.1.10 |  | Existing Wireway Modifications |  |  | 1 | eu | 0 | 1 | 2 | 80 | 160 | el | 55.41 | 8.9 | 9.9
| 1.15.2 |  | RSS | [7 empty] | 2 | [5 empty] | 5.8508 | 7.8508 | 1.3388 | 9.1897 | 25% | 2.2974 | 11.4871
|  |  | 1.15.2.1 |  | Hutchless Control Chassis |  | ea | 1 | eu | 1500 | 1.5 | 1 | 40 | 40 | ei | 37.4128 | 1.4965 | 2.9965
|  |  | 1.15.2.2 |  | Cable Pull To PSS |  | ea | 1 | eu | 300 | 0.3 | 1 | 20 | 20 | el | 55.4077 | 1.1082 | 1.4082
|  |  | 1.15.2.3 |  | Cable Termination/Installation |  | ea | 1 | eu | 200 | 0.2 | 1 | 24 | 24 | ei | 37.4128 | 0.89791 | 1.0979
|  |  | 1.15.2.4 |  | Design/Documentation |  | ea | 0 | eu | 0 | 0 | 1 | 40 | 40 | ec | 58.7065 | 2.3483 | 2.3483
| 1.15.3 |  | EPS Branchline | [7 empty] | 58.9 | [5 empty] | 43.8465 | 102.7465 | 13.0939 | 115.8404 | 25% | 28.9601 | 144.8005
|  |  | 1.15.3.1 |  | 24v power supplies - inst & cable |  | ea | 1 | eu | 1300 | 1.3 | 1 | 6 | 6 | ei | 37.4128 | 0.22448 | 1.5245
|  |  | 1.15.3.2 |  | 24v power distribution - inst & cable |  | ea | 1 | eu | 2000 | 2 | 1 | 6 | 6 | ei | 37.4128 | 0.22448 | 2.2245
|  |  | 1.15.3.3 |  | XC blocks |  | ea | 2 | eu | 500 | 1 | 2 | 5 | 10 | ei | 37.4128 | 0.37413 | 1.3741
|  |  | 1.15.3.4 |  | PLC mtg panel - fab & inst. |  | ea | 1 | eu | 100 | 0.1 | 1 | 6 | 6 | ei | 37.4128 | 0.22448 | 0.32448
|  |  | 1.15.3.5 |  | PLC backplane, CPU & I/O mod. |  | ea | 1 | eu | 3500 | 3.5 | 1 | 40 | 40 | ei | 37.4128 | 1.4965 | 4.9965
|  |  | 1.15.3.6 |  | PanelMate display & shelf |  | ea | 1 | cp | 5000 | 5 | 1 | 10 | 10 | ei | 37.4128 | 0.37413 | 5.3741
|  |  | 1.15.3.7 |  | Rack Loading - IG, IP |  | ea | 10 | eu | 0 | 0 | 10 | 2 | 20 | ei | 37.4128 | 0.74826 | 0.74826
|  |  | 1.15.3.8 |  | device cable pulls - IG, IP, VVR, WFS, FVS |  | lot | 1 | eu | 2000 | 2 | 1 | 40 | 40 | el | 55.4077 | 2.2163 | 4.2163
|  |  | 1.15.3.9 |  | Cable term. |  | ea | 0 | eu | 0 | 0 | 2 | 40 | 80 | ei | 37.4128 | 2.993 | 2.993
|  |  | 1.15.3.10 |  | XC jumpers |  | ea | 0 | eu | 0 | 0 | 1 | 16 | 16 | ei | 37.4128 | 0.5986 | 0.5986
|  |  | 1.15.3.11 |  | IG controller w/tube - purchase |  | ea | 8 | A99 | 3000 | 24 | 0 | 0 | 0 | ei | 37.4128 | 0 | 24
|  |  | 1.15.3.12 |  | Mirror limit sw, other misc ei time |  | ea |  | eu |  | 0 | 1 | 40 | 40 | ei | 37.4128 | 1.4965 | 1.4965
|  |  | 1.15.3.13 |  | IP controller purchase |  | ea | 3 | eu | 5000 | 15 | 0 | 0 | 0 | ei | 37.4128 | 0 | 15
|  |  | 1.15.3.14 |  | Digipak 270 |  | ea | 2 | eu | 1500 | 3 | 0 | 0 | 0 | ei | 37.4128 | 0 | 3
|  |  | 1.15.3.15 |  | Turbo Interface Module to EPS |  | ea | 1 | eu | 2000 | 2 | 0 | 0 | 0 | ei | 37.4128 | 0 | 2
|  |  | 1.15.3.16 |  | EC- EPS Racks Loading & Cable Pull |  | ea | 1 | eu | 0 | 0 | 1 | 160 | 160 | ec | 58.7065 | 9.393 | 9.393
|  |  | 1.15.3.17 |  | EC- EPS XC, Wiretables |  | ea | 1 | eu | 0 | 0 | 1 | 160 | 160 | ec | 58.7065 | 9.393 | 9.393
|  |  | 1.15.3.18 |  | EC- EPS Software |  | ea | 1 | eu | 0 | 0 | 1 | 240 | 240 | ec | 58.7065 | 14.0896 | 14.0896
| 1.15.4 |  | Network Branchline | [7 empty] | 0.5 | [5 empty] | 0.5986 | 1.0986 | 0.15756 | 1.2562 | 25% | 0.31404 | 1.5702
|  |  | 1.15.4.1 |  | Network Drop |  | ea | 1 | eu | 500 | 0.5 | 1 | 16 | 16 | ei | 37.4128 | 0.5986 | 1.0986
1.16 | [5 empty] | Computer Controls |  |  |  |  | 46.2 | [5 empty] | 34.8142 | 81.0142 | 10.3571 | 91.3713 | 16.89% | 15.4298 | 106.8011
| 1.16.1 |  | Motor Contol Hardware | [7 empty] | 46.2 | [5 empty] | 34.8142 | 81.0142
|  |  | 1.16.1.1 |  | Controls/Motors Hardware (see Sheet) |  | ea | 1 | eu | 46200 | 46.2 | 0 | 0 | 0 | ei | 37.4128 | 0 | 46.2 | 3.2201 | 49.4201 | 20% | 9.884 | 59.3042
|  |  | 1.16.1.2 |  | Programming /Testing |  | ea | 0 | eu | 0 | 0 | 1 | 480 | 480 | cp | 72.5296 | 34.8142 | 34.8142 | 7.1369 | 41.9511 | 50% | 20.9756 | 62.9267

## FY03 Craft Code
| Code | Base Hourly w/ Payroll Burden (37.6%) | Plus 17.5% EG/FA Bdn | CAD/Shop Charges | Burdened Rate
ALS Computer Programmer 9133 | CP | 61.7274 | 72.5296 |  | 72.5296
ALS Electronic Coordination 9141 | EC | 46.729 | 54.9065 | 3.8 | 58.7065
ALS Electronic Engineering 9131 | EE | 67.4378 | 79.2394 | 3.8 | 83.0394
ALS Senior Electronic Engineering 9131 | SEE | 71.0429 | 83.4754 | 3.8 | 87.2754
ALS Electronic Installation 9148 | EI | 31.8406 | 37.4128 |  | 37.4128
Electrician (Plant Engineer/PE for KW) | EL | 47.1555 | 55.4077 |  | 55.4077
ALS Electronic Maintenance 9148 | EM | 35.8035 | 42.0691 |  | 42.0691
M.E. Liason 9140 | LI | 44.9126 | 52.7724 |  | 52.7724
Bldg. 77 Assembly Shop 9160's | MA | 39.8902 | 46.871 | 14.9 | 61.771
Mechanical Technician-Brazing 9160's | MB | 39.8902 | 46.871 | 14.9 | 61.771
ALS Mechanical Designer/Drafter 9145 | MD | 48.4214 | 56.8952 | 3.8 | 60.6952
ALS Mechanical Engineer 9135 | ME | 61.8237 | 72.6428 | 3.8 | 76.4428
UHV Cleaning & Plating Shop 9160's | MP | 39.8902 | 46.871 | 14.9 | 61.771
Mechanical Shops 9160's | MS | 39.8902 | 46.871 | 14.9 | 61.771
ALS Mechanical Technician 9148 | MU | 36.0374 | 42.344 |  | 42.344
ALS Mech. Tech/Assembly (Bldg. 80) 9148 | MUA | 36.0374 | 42.344 |  | 42.344
ALS Mech. Tech./Installation 9148 | MUI | 36.0374 | 42.344 |  | 42.344
ALS Mech. Tech./Machine Shop 9148 | MUM | 36.0374 | 42.344 |  | 42.344
ALS Mech. Tech./Survey & Alignment 9148 | MUS | 43.344 | 50.9292 |  | 50.9292
Mech. Shops NC Tool 9160's | NC | 36.0374 | 42.344 | 14.9 | 57.244
Student 9151 | ST | 14.8095 | 17.4012 | 3.8 | 21.2012
Post Doc | PD | 39.4362 | 46.3375 |  | 46.3375
Carpenter Shop | CS | 36.3126 | 42.6674 |  | 42.6674
Paint Shop | PS | 34.7302 | 40.808 |  | 40.808
Senior Mech engineer | SME | 79.9869 | 93.9846 | 3.8 | 97.7846
Riggers | RG | 37.0419 | 43.5243 |  | 40.49
Laborers | LBR | 28.3869 | 33.3546 |  | 32.5
Plumbers | PB | 46.2886 | 54.3892 |  | 43.4
| 0 |  |  |  | 0

## FY02 Craft Code
| Code | Base Hourly | Plus 17.5% Engr Bdn | CAD/Shop Charges | Burdened Rate
ALS Computer Programmer 9133 | CP | 58.05 | 68.2087 |  | 68.2087
ALS Electronic Coordination 9141 | EC | 46.93 | 55.1427 | 3.8 | 58.9427
ALS Electronic Engineering 9131 | EE | 63.91 | 75.0943 |  | 75.0943
ALS Senior Electronic Engineering 9131 | SEE | 70.72 | 83.096 |  | 83.096
ALS Electronic Installation 9148 | EI | 35.72 | 41.971 |  | 41.971
Electrician (Plant Engineer/PE for KW) | EL | 40.04 | 47.047 |  | 47.047
ALS Electronic Maintenance 9148 | EM | 36.35 | 42.7112 |  | 42.7112
M.E. Liason 9140 | LI | 41.85 | 49.1737 |  | 49.1737
Bldg. 77 Assembly Shop 9160's | MA | 44.23 | 51.9703 | 9.75 | 61.7203
Mechanical Technician-Brazing 9160's | MB | 44.23 | 51.9703 | 9.75 | 61.7203
ALS Mechanical Designer/Drafter 9145 | MD | 47.27 | 55.5423 | 3.8 | 59.3422
ALS Mechanical Engineer 9135 | ME | 63.87 | 75.0473 | 3.8 | 78.8473
UHV Cleaning & Plating Shop 9160's | MP | 44.23 | 51.9703 | 9.75 | 61.7203
Mechanical Shops 9160's | MS | 44.23 | 51.9703 | 9.75 | 61.7203
ALS Mechanical Technician 9148 | MU | 36.38 | 42.7465 |  | 42.7465
ALS Mech. Tech/Assembly (Bldg. 80) 9148 | MUA | 36.38 | 42.7465 |  | 42.7465
ALS Mech. Tech./Installation 9148 | MUI | 36.38 | 42.7465 |  | 42.7465
ALS Mech. Tech./Machine Shop 9148 | MUM | 36.38 | 42.7465 |  | 42.7465
ALS Mech. Tech./Survey & Alignment 9148 | MUS | 40.97 | 48.1397 |  | 48.1397
Mech. Shops NC Tool 9160's | NC | 44.23 | 51.9703 | 9.75 | 61.7203
Student 9151 | ST | 14.26 | 16.7555 | 3.8 | 20.5555
Post Doc | PD | 38.84 | 45.637 |  | 45.637
Carpenter Shop | CS | 37.61 | 44.1917 |  | 44.1917
Paint Shop | PS | 36.43 | 42.8053 |  | 42.8053
Senior Mech engineer | SME | 74.88 | 87.984 | 3.8 | 91.784
Riggers | RG | 37.36 | 43.898 |  | 40.49
Laborers | LBR | 29.99 | 35.2383 |  | 32.5
Plumbers | PB | 40.04 | 47.047 |  | 43.4
| 0 |  |  |  | 0

## Motors
Cost of Equipment |  |  |  |  | Cost for Engineering Time | Time (Weeks) | Type | Element | Motor | Pico | Stepper | Servo | Feedback | Current
Item | Part Number | Number | Cost | Total | Installation of Code | 1 | Motor | M1
Boxx Computer | 3DBOXX E2 | 1 | 1493 | 1493 | Testing of Motors and Wiring | 3 |  |  | Pitch |  |  | x | Encoder
17" Flat Panel Monitor | VG175 | 1 | 679 | 679 | Interface to Superconducting Undulator | 1 |  |  | Bend 1 |  | x |  | Encoder
LabVIEW | 776670-03 | 1 | 1995 | 1995 | Programming for Monochromators | 1 |  |  | Bend 2 |  | x |  | Encoder
MXI 3 Kit | 777942-01 | 1 | 1495 | 1495 | Programming for Picomotor Controls | 3 |  |  | Roll |  |  | x | Encoder
PXI Crate 8 Slot NI-PXI-1006 | 777551-01 | 1 | 1975 | 1975 | Integration | 1 |  |  | Yaw |  |  | x | Encoder
PXI Crate Rack Mount Kit | 778302-01 | 1 | 150 | 150 | Time for tracking unforseen bugs | 2 |  | Entrance Slit
PXI-7334 | 778444-01 | 4 | 1045 | 4180 |  |  |  |  | Horz Width |  | x |  | Encoder
PXI-7334 Cables | 186381-02 | 4 | 150 | 600 | Total (Weeks) | 12 |  |  | Horz Position |  | x |  | Encoder
60M-50F Cable Adaptor | 185630-01 | 4 | 25 | 100 |  |  |  |  | Vert Width |  | x |  | Encoder
NuDrive 4SX-411 Stepper Amp | 777669-01 | 4 | 2750 | 11000 | Please Add 50% Contingency |  |  |  | Horz Position |  | x |  | Encoder
PXI-7344 | 777935-01 | 1 | 1695 | 1695 |  |  |  | M2
PXI-7344 Cables | 186380-02 | 1 | 150 | 150 |  |  |  |  | Bend 1 | x |  |  | LVDT
MID 7654 Servo Amp | 778005-01 | 1 | 2850 | 2850 |  |  |  |  | Bend 2 | x |  |  | LVDT
PCI-1407 | 777852-01 | 1 | 695 | 695 |  |  |  |  | Pitch | x |  |  | LVDT
PXI 6052E | 777962-01 | 1 | 1995 | 1995 |  |  |  |  | Translation | x |  |  | LVDT
SCXI 1540 8 Chan LVDT Module | 777966-40 | 2 | 1395 | 2790 |  |  |  | X1
SCXI Kit | 777687-15 | 2 | 150 | 300 |  |  |  |  | Rotation |  |  | x | Encoder
SCXI Chassis | 776570-01 | 1 | 695 | 695 |  |  |  | X2
SCXI Rack Mount Kit | 776577-71 | 1 | 60 | 60 |  |  |  |  | Translation | x |  |  | LVDT
SCXI 1349 Cable | 776574-492 | 1 | 175 | 175 |  |  |  |  | Pitch | x |  |  | LVDT
iPico network controller (serial) | Model 8750 | 1 | 343 | 343 |  |  |  |  | Roll | x |  |  | LVDT
iPico Intelligent Driver | Model 8753 | 4 | 485 | 1940 |  |  |  | M3
iPico Serial Com adaptor | Model 8761 | 1 | 50 | 50 |  |  |  |  | Bend 1 | x |  |  | LVDT
iPico Power Supply | Model 8755 | 1 | 47 | 47 |  |  |  |  | Bend 2 | x |  |  | LVDT
iPico Power Cables Short | Model 8727 | 3 | 7 | 21 |  |  |  |  | Pitch | x |  |  | LVDT
iPico Com Extender Short | Model 8724 | 3 | 5 | 15 |  |  |  |  | Translation | x |  |  | LVDT
HH Digitizing Box | EXE 660B | 1 | 780 | 780 |  |  |  | Crystal Mono
HH Cable from encoder to 660B |  | 1 | 66 | 66 |  |  |  |  | Insertion |  | x |  | Encoder
HH Pigtail Cable from 660B |  | 1 | 150 | 150 |  |  |  | M4
Compumotor Stepper w/ Enc | OS21A-DNFLY-RE | 16 | 327 | 5232 |  |  |  |  | Bend 1 |  | x |  | Encoder
HD Systems Servo Motor for M1 | RH14C-3002-E100AL | 1 | 916 | 916 |  |  |  |  | Bend 2 |  | x |  | Encoder
HD Systems Servo Motor for M1 | RH-11C-3001-E100AL | 2 | 827 | 1654 |  |  |  |  | Pitch |  | x |  | Encoder
|  |  |  | 46286 |  |  |  | M5
Please Add a 20% Contingency | [8 empty] | Rotation |  | x |  | Encoder
Grating
[9 empty] | Rotation |  | x |  | HH Encoder
Grating Mono
[9 empty] | Translation |  | x |  | Encoder
M6
[9 empty] | Bend 1 |  | x |  | Encoder
[9 empty] | Bend 2 |  | x |  | Encoder
[9 empty] | Pitch |  | x |  | Encoder
[8 empty] | Totals |  | 11 | 16 | 4
Video
[8 empty] | Yag Crystal |  |  |  |  | NTSC