## Main
Station Name | Site ID | Region | Legacy System | Target install date (D-Day | Site receives and installs RWS | Site receives and installs Operator Training Material | Initial telecon briefing to provide overview | WFO receives Site Installation Plan, Deployment Plan & Disposal Plan | Site returns Ops Immediate data via FAX | Site provides comments against SIP | Second telecon briefing to review SIP comments | Site receives GPS repeater FMK | Site receives final SIP | Final telecon briefing | GPS repeater FMK installed | AWIPS Admin Note 15 completed | Training Telecon | Operators complete computer based training material | El Tech completes RRS Maint. Couse at NWSTC | Site MIC proposes tentative decommis-sioning date | Site Receives NLSC shipments | Site receives required permits | Required electrical and ground work completed | Final Site Readiness Telecon | Operator Training Cert signed | ART decommissioning checklist signed | Site completes and returns Facilities Readiness Cert | Site receives TRS | Site disassembles ART
[5 empty] | 115 | 115 | 110 | 105 | 100 | 90 | 85 | 85 | 80 | 70 | 45 | 45 | 45 | 30 | 30 | 30 | 25 | 25 | 25 | 20 | 20 | 15 | 15 | 7 | 3
FY 2007 2 QTR
Jacksonville, FL | JAX | SR | ART-2 | 2007-01-08 | 2006-09-15 | 2006-09-15 | 2006-09-20 | 2006-09-25 | 2006-09-29 | 2006-10-10 | 2006-10-16 | 2006-10-16 | 2006-10-20 | 2006-10-30 | 2006-11-24 | 2006-11-24 | 2006-11-24 | 2006-12-08 | 2006-12-08 | 2006-12-08 | 2006-12-14 | 2006-12-14 | 2006-12-14 | 2006-12-19 | 2006-12-19 | 2006-12-25 | 2006-12-25 | 2007-01-01 | 2007-01-05
Morehead Cty.,NC | MHX | ER | ART-1 | 2007-01-22 | 2006-09-29 | 2006-09-29 | 2006-10-04 | 2006-10-09 | 2006-10-13 | 2006-10-24 | 2006-10-30 | 2006-10-30 | 2006-11-03 | 2006-11-13 | 2006-12-08 | 2006-12-08 | 2006-12-08 | 2006-12-22 | 2006-12-22 | 2006-12-22 | 2006-12-28 | 2006-12-28 | 2006-12-28 | 2007-01-02 | 2007-01-02 | 2007-01-08 | 2007-01-08 | 2007-01-15 | 2007-01-19
Greensboro, NC | GSO | ER | ART-2 | 2007-02-05 | 2006-10-13 | 2006-10-13 | 2006-10-18 | 2006-10-23 | 2006-10-27 | 2006-11-07 | 2006-11-13 | 2006-11-13 | 2006-11-17 | 2006-11-27 | 2006-12-22 | 2006-12-22 | 2006-12-22 | 2007-01-05 | 2007-01-05 | 2007-01-05 | 2007-01-11 | 2007-01-11 | 2007-01-11 | 2007-01-16 | 2007-01-16 | 2007-01-22 | 2007-01-22 | 2007-01-29 | 2007-02-02
Blacksburg, VA | RNK | ER | ART-2 | 2007-02-20 | 2006-10-27 | 2006-10-27 | 2006-11-02 | 2006-11-07 | 2006-11-13 | 2006-11-22 | 2006-11-27 | 2006-11-27 | 2006-12-01 | 2006-12-12 | 2007-01-05 | 2007-01-05 | 2007-01-05 | 2007-01-22 | 2007-01-22 | 2007-01-22 | 2007-01-26 | 2007-01-26 | 2007-01-26 | 2007-01-31 | 2007-01-31 | 2007-02-05 | 2007-02-05 | 2007-02-13 | 2007-02-16
Birmingham, AL | BMX | SR | ART-2 | 2007-03-05 | 2006-11-10 | 2006-11-10 | 2006-11-15 | 2006-11-20 | 2006-11-24 | 2006-12-05 | 2006-12-11 | 2006-12-11 | 2006-12-15 | 2006-12-25 | 2007-01-19 | 2007-01-19 | 2007-01-19 | 2007-02-02 | 2007-02-02 | 2007-02-02 | 2007-02-08 | 2007-02-08 | 2007-02-08 | 2007-02-13 | 2007-02-13 | 2007-02-19 | 2007-02-19 | 2007-02-26 | 2007-03-02
Tampa Bay, FL | TBW | SR | ART-1 | 2007-03-19 | 2006-11-24 | 2006-11-24 | 2006-11-29 | 2006-12-04 | 2006-12-08 | 2006-12-19 | 2006-12-25 | 2006-12-25 | 2006-12-29 | 2007-01-08 | 2007-02-02 | 2007-02-02 | 2007-02-02 | 2007-02-16 | 2007-02-16 | 2007-02-16 | 2007-02-22 | 2007-02-22 | 2007-02-22 | 2007-02-27 | 2007-02-27 | 2007-03-05 | 2007-03-05 | 2007-03-12 | 2007-03-16
FY 2007 3 QTR
Wilmington, OH | ILN | ER | ART-1 | 2007-04-02 | 2006-12-08 | 2006-12-08 | 2006-12-13 | 2006-12-18 | 2006-12-22 | 2007-01-02 | 2007-01-08 | 2007-01-08 | 2007-01-12 | 2007-01-22 | 2007-02-16 | 2007-02-16 | 2007-02-16 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-08 | 2007-03-08 | 2007-03-08 | 2007-03-13 | 2007-03-13 | 2007-03-19 | 2007-03-19 | 2007-03-26 | 2007-03-30
Charleston, SD | CHS | ER | W9000 | 2007-04-16 | 2006-12-22 | 2006-12-22 | 2006-12-27 | 2007-01-01 | 2007-01-05 | 2007-01-16 | 2007-01-22 | 2007-01-22 | 2007-01-26 | 2007-02-05 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-16 | 2007-03-16 | 2007-03-16 | 2007-03-22 | 2007-03-22 | 2007-03-22 | 2007-03-27 | 2007-03-27 | 2007-04-02 | 2007-04-02 | 2007-04-09 | 2007-04-13
Miami, FL | MFL | SR | ART-2 | 2007-04-30 | 2007-01-05 | 2007-01-05 | 2007-01-10 | 2007-01-15 | 2007-01-19 | 2007-01-30 | 2007-02-05 | 2007-02-05 | 2007-02-09 | 2007-02-19 | 2007-03-16 | 2007-03-16 | 2007-03-16 | 2007-03-30 | 2007-03-30 | 2007-03-30 | 2007-04-05 | 2007-04-05 | 2007-04-05 | 2007-04-10 | 2007-04-10 | 2007-04-16 | 2007-04-16 | 2007-04-23 | 2007-04-27
Nashville, TN | OHX | SR | ART-2 | 2007-05-14 | 2007-01-19 | 2007-01-19 | 2007-01-24 | 2007-01-29 | 2007-02-02 | 2007-02-13 | 2007-02-19 | 2007-02-19 | 2007-02-23 | 2007-03-05 | 2007-03-30 | 2007-03-30 | 2007-03-30 | 2007-04-13 | 2007-04-13 | 2007-04-13 | 2007-04-19 | 2007-04-19 | 2007-04-19 | 2007-04-24 | 2007-04-24 | 2007-04-30 | 2007-04-30 | 2007-05-07 | 2007-05-11
Tuscon, AZ | TUS | WR | ART-1 | 2007-05-29 | 2007-02-02 | 2007-02-02 | 2007-02-08 | 2007-02-13 | 2007-02-19 | 2007-02-28 | 2007-03-05 | 2007-03-05 | 2007-03-09 | 2007-03-20 | 2007-04-13 | 2007-04-13 | 2007-04-13 | 2007-04-30 | 2007-04-30 | 2007-04-30 | 2007-05-04 | 2007-05-04 | 2007-05-04 | 2007-05-09 | 2007-05-09 | 2007-05-14 | 2007-05-14 | 2007-05-22 | 2007-05-25
Elko, NV | LKN | WR | ART-2 | 2007-06-11 | 2007-02-16 | 2007-02-16 | 2007-02-21 | 2007-02-26 | 2007-03-02 | 2007-03-13 | 2007-03-19 | 2007-03-19 | 2007-03-23 | 2007-04-02 | 2007-04-27 | 2007-04-27 | 2007-04-27 | 2007-05-11 | 2007-05-11 | 2007-05-11 | 2007-05-17 | 2007-05-17 | 2007-05-17 | 2007-05-22 | 2007-05-22 | 2007-05-28 | 2007-05-28 | 2007-06-04 | 2007-06-08
Salem, OR | SLE | WR | ART-2 | 2007-06-25 | 2007-03-02 | 2007-03-02 | 2007-03-07 | 2007-03-12 | 2007-03-16 | 2007-03-27 | 2007-04-02 | 2007-04-02 | 2007-04-06 | 2007-04-16 | 2007-05-11 | 2007-05-11 | 2007-05-11 | 2007-05-25 | 2007-05-25 | 2007-05-25 | 2007-05-31 | 2007-05-31 | 2007-05-31 | 2007-06-05 | 2007-06-05 | 2007-06-11 | 2007-06-11 | 2007-06-18 | 2007-06-22
FY 2007 4 QTR
Glasgow, MT | GGW | WR | ART-1 | 2007-07-09 | 2007-03-16 | 2007-03-16 | 2007-03-21 | 2007-03-26 | 2007-03-30 | 2007-04-10 | 2007-04-16 | 2007-04-16 | 2007-04-20 | 2007-04-30 | 2007-05-25 | 2007-05-25 | 2007-05-25 | 2007-06-08 | 2007-06-08 | 2007-06-08 | 2007-06-14 | 2007-06-14 | 2007-06-14 | 2007-06-19 | 2007-06-19 | 2007-06-25 | 2007-06-25 | 2007-07-02 | 2007-07-06
Lincoln IL | ILX | CR | ART-2 | 2007-07-23 | 2007-03-30 | 2007-03-30 | 2007-04-04 | 2007-04-09 | 2007-04-13 | 2007-04-24 | 2007-04-30 | 2007-04-30 | 2007-05-04 | 2007-05-14 | 2007-06-08 | 2007-06-08 | 2007-06-08 | 2007-06-22 | 2007-06-22 | 2007-06-22 | 2007-06-28 | 2007-06-28 | 2007-06-28 | 2007-07-03 | 2007-07-03 | 2007-07-09 | 2007-07-09 | 2007-07-16 | 2007-07-20
Springfield, MO | SGF | CR | ART-2 | 2007-08-06 | 2007-04-13 | 2007-04-13 | 2007-04-18 | 2007-04-23 | 2007-04-27 | 2007-05-08 | 2007-05-14 | 2007-05-14 | 2007-05-18 | 2007-05-28 | 2007-06-22 | 2007-06-22 | 2007-06-22 | 2007-07-06 | 2007-07-06 | 2007-07-06 | 2007-07-12 | 2007-07-12 | 2007-07-12 | 2007-07-17 | 2007-07-17 | 2007-07-23 | 2007-07-23 | 2007-07-30 | 2007-08-03
Gaylord, MI | APX | CR | ART-2 | 2007-08-20 | 2007-04-27 | 2007-04-27 | 2007-05-02 | 2007-05-07 | 2007-05-11 | 2007-05-22 | 2007-05-28 | 2007-05-28 | 2007-06-01 | 2007-06-11 | 2007-07-06 | 2007-07-06 | 2007-07-06 | 2007-07-20 | 2007-07-20 | 2007-07-20 | 2007-07-26 | 2007-07-26 | 2007-07-26 | 2007-07-31 | 2007-07-31 | 2007-08-06 | 2007-08-06 | 2007-08-13 | 2007-08-17
North Platte, NE | LBF | CR | ART-2 | 2007-09-04 | 2007-05-11 | 2007-05-11 | 2007-05-17 | 2007-05-22 | 2007-05-28 | 2007-06-06 | 2007-06-11 | 2007-06-11 | 2007-06-15 | 2007-06-26 | 2007-07-20 | 2007-07-20 | 2007-07-20 | 2007-08-06 | 2007-08-06 | 2007-08-06 | 2007-08-10 | 2007-08-10 | 2007-08-10 | 2007-08-15 | 2007-08-15 | 2007-08-20 | 2007-08-20 | 2007-08-28 | 2007-08-31
Valley, NE | OAX | CR | ART-2 | 2007-09-17 | 2007-05-25 | 2007-05-25 | 2007-05-30 | 2007-06-04 | 2007-06-08 | 2007-06-19 | 2007-06-25 | 2007-06-25 | 2007-06-29 | 2007-07-09 | 2007-08-03 | 2007-08-03 | 2007-08-03 | 2007-08-17 | 2007-08-17 | 2007-08-17 | 2007-08-23 | 2007-08-23 | 2007-08-23 | 2007-08-28 | 2007-08-28 | 2007-09-03 | 2007-09-03 | 2007-09-10 | 2007-09-14
FY 20008 1 QTR
Quillayute, WA | UIL | WR | ART-2 | 2007-10-15 | 2007-06-22 | 2007-06-22 | 2007-06-27 | 2007-07-02 | 2007-07-06 | 2007-07-17 | 2007-07-23 | 2007-07-23 | 2007-07-27 | 2007-08-06 | 2007-08-31 | 2007-08-31 | 2007-08-31 | 2007-09-14 | 2007-09-14 | 2007-09-14 | 2007-09-20 | 2007-09-20 | 2007-09-20 | 2007-09-25 | 2007-09-25 | 2007-10-01 | 2007-10-01 | 2007-10-08 | 2007-10-12
Davenport, IA | DVN | CR | ART-2 | 2007-10-29 | 2007-07-06 | 2007-07-06 | 2007-07-11 | 2007-07-16 | 2007-07-20 | 2007-07-31 | 2007-08-06 | 2007-08-06 | 2007-08-10 | 2007-08-20 | 2007-09-14 | 2007-09-14 | 2007-09-14 | 2007-09-28 | 2007-09-28 | 2007-09-28 | 2007-10-04 | 2007-10-04 | 2007-10-04 | 2007-10-09 | 2007-10-09 | 2007-10-15 | 2007-10-15 | 2007-10-22 | 2007-10-26
Fort Worth, TX | FWD | SR | ART-2 | 2007-12-03 | 2007-08-10 | 2007-08-10 | 2007-08-15 | 2007-08-20 | 2007-08-24 | 2007-09-04 | 2007-09-10 | 2007-09-10 | 2007-09-14 | 2007-09-24 | 2007-10-19 | 2007-10-19 | 2007-10-19 | 2007-11-02 | 2007-11-02 | 2007-11-02 | 2007-11-08 | 2007-11-08 | 2007-11-08 | 2007-11-13 | 2007-11-13 | 2007-11-19 | 2007-11-19 | 2007-11-26 | 2007-11-30
Formulas:
Site receives and installs RWS = IF(WEEKDAY([Target install date (D-Day]-F3)=1,([Target install date (D-Day]-F3+1),(IF(WEEKDAY([Target install date (D-Day]-F3)=7,([Target install date (D-Day]-F3-1),([Target install date (D-Day]-F3))))
Site returns Ops Immediate data via FAX = IF(WEEKDAY([Target install date (D-Day]-J3)=1,([Target install date (D-Day]-J3+1),(IF(WEEKDAY([Target install date (D-Day]-J3)=7,([Target install date (D-Day]-J3-1),([Target install date (D-Day]-J3))))
Site provides comments against SIP = IF(WEEKDAY([Target install date (D-Day]-K3)=1,([Target install date (D-Day]-K3+1),(IF(WEEKDAY([Target install date (D-Day]-K3)=7,([Target install date (D-Day]-K3-1),([Target install date (D-Day]-K3))))
Site receives GPS repeater FMK = IF(WEEKDAY([Target install date (D-Day]-M3)=1,([Target install date (D-Day]-M3+1),(IF(WEEKDAY([Target install date (D-Day]-M3)=7,([Target install date (D-Day]-M3-1),([Target install date (D-Day]-M3))))
Site receives final SIP = IF(WEEKDAY([Target install date (D-Day]-N3)=1,([Target install date (D-Day]-N3+1),(IF(WEEKDAY([Target install date (D-Day]-N3)=7,([Target install date (D-Day]-N3-1),([Target install date (D-Day]-N3))))
Final telecon briefing = IF(WEEKDAY([Target install date (D-Day]-O3)=1,([Target install date (D-Day]-O3+1),(IF(WEEKDAY([Target install date (D-Day]-O3)=7,([Target install date (D-Day]-O3-1),([Target install date (D-Day]-O3))))
GPS repeater FMK installed = IF(WEEKDAY([Target install date (D-Day]-P3)=1,([Target install date (D-Day]-P3+1),(IF(WEEKDAY([Target install date (D-Day]-P3)=7,([Target install date (D-Day]-P3-1),([Target install date (D-Day]-P3))))
AWIPS Admin Note 15 completed = IF(WEEKDAY([Target install date (D-Day]-Q3)=1,([Target install date (D-Day]-Q3+1),(IF(WEEKDAY([Target install date (D-Day]-Q3)=7,([Target install date (D-Day]-Q3-1),([Target install date (D-Day]-Q3))))
Training Telecon = IF(WEEKDAY([Target install date (D-Day]-R3)=1,([Target install date (D-Day]-R3+1),(IF(WEEKDAY([Target install date (D-Day]-R3)=7,([Target install date (D-Day]-R3-1),([Target install date (D-Day]-R3))))
Site Receives NLSC shipments = IF(WEEKDAY([Target install date (D-Day]-V3)=1,([Target install date (D-Day]-V3+1),(IF(WEEKDAY([Target install date (D-Day]-V3)=7,([Target install date (D-Day]-V3-1),([Target install date (D-Day]-V3))))
Site receives required permits = IF(WEEKDAY([Target install date (D-Day]-W3)=1,([Target install date (D-Day]-W3+1),(IF(WEEKDAY([Target install date (D-Day]-W3)=7,([Target install date (D-Day]-W3-1),([Target install date (D-Day]-W3))))
Final Site Readiness Telecon = IF(WEEKDAY([Target install date (D-Day]-Y3)=1,([Target install date (D-Day]-Y3+1),(IF(WEEKDAY([Target install date (D-Day]-Y3)=7,([Target install date (D-Day]-Y3-1),([Target install date (D-Day]-Y3))))
Operator Training Cert signed = IF(WEEKDAY([Target install date (D-Day]-Z3)=1,([Target install date (D-Day]-Z3+1),(IF(WEEKDAY([Target install date (D-Day]-Z3)=7,([Target install date (D-Day]-Z3-1),([Target install date (D-Day]-Z3))))
ART decommissioning checklist signed = IF(WEEKDAY([Target install date (D-Day]-AA3)=1,([Target install date (D-Day]-AA3+1),(IF(WEEKDAY([Target install date (D-Day]-AA3)=7,([Target install date (D-Day]-AA3-1),([Target install date (D-Day]-AA3))))
Site receives TRS = IF(WEEKDAY([Target install date (D-Day]-AC3)=1,([Target install date (D-Day]-AC3+1),(IF(WEEKDAY([Target install date (D-Day]-AC3)=7,([Target install date (D-Day]-AC3-1),([Target install date (D-Day]-AC3))))
Site disassembles ART = IF(WEEKDAY([Target install date (D-Day]-AD3)=1,([Target install date (D-Day]-AD3+1),(IF(WEEKDAY([Target install date (D-Day]-AD3)=7,([Target install date (D-Day]-AD3-1),([Target install date (D-Day]-AD3))))

## HQ Dates
Station Name | Site ID | Target install date (D-Day | Ship Training Material and RWS and send first e-mail | Confirm Site Received RWS and Training Materials | Schedule First Telecon | Hold first Telecon and Ship Plans | Issue general info. Request e-mail | Ops-Immed Response Due | All Plan Comments Received and General Info/Photos received | Issue GPS repeater kit and Mounting Plate | Request 7460 | Send Ops Immed to IMET | Schedule Second Telecon | Hold Second Telecon | Send Final SIP | Schedule Final Telecon | Hold Final Telecon | Permit reminder | Notify Debbie Pickerign | Schedule Training Telecon | Hold Training Telecon | Prelim. Decomm. Date Due | All Gov Permits Due | Exchange encription Keys, Record PWs | Issue NLSC Kits (Tools, Radome GPS, Sondes, RWS Cables,SPS etc.) | Notify NLSC for LRU Containers | Notify target backup sites of pending installation and products | Schedule Site Readiness Telecon | Site Readiness Telecon | Facilities Checklist Due | Site Decomm. Checklist Due | Distance Learning Cert Due | Notify Maint and Logistics of pending Installation | Get current RRS Software & Ghost CD | Issue Hotline request to access FTP server | Notify NCDC and NCEP that RWS install is pending
|  |  | 120 | 115 | 115 | 110 | 105 | 100 | 90 | 90 | 90 | 90 | 90 | 85 | 75 | 75 | 70 | 60 | 60 | 50 | 45 | 30 | 30 | 30 | 30 | 21 | 21 | 20 | 15 | 15 | 15 | 15 | 10 | 10 | 5 | 5
FY 2007 2 QTR
Jacksonville, FL | JAX | 2007-01-08 | 2006-09-11 | 2006-09-15 | 2006-09-15 | 2006-09-20 | 2006-09-25 | 2006-09-29 | 2006-10-10 | 2006-10-10 | 2006-10-10 | 2006-10-10 | 2006-10-10 | 2006-10-16 | 2006-10-25 | 2006-10-25 | 2006-10-30 | 2006-11-09 | 2006-11-09 | 2006-11-20 | 2006-11-24 | 2006-12-08 | 2006-12-08 | 2006-12-08 | 2006-12-08 | 2006-12-18 | 2006-12-18 | 2006-12-19 | 2006-12-25 | 2006-12-25 | 2006-12-25 | 2006-12-25 | 2006-12-29 | 2006-12-29 | 2007-01-03 | 2007-01-03
Morehead Cty.,NC | MHX | 2007-01-22 | 2006-09-25 | 2006-09-29 | 2006-09-29 | 2006-10-04 | 2006-10-09 | 2006-10-13 | 2006-10-24 | 2006-10-24 | 2006-10-24 | 2006-10-24 | 2006-10-24 | 2006-10-30 | 2006-11-08 | 2006-11-08 | 2006-11-13 | 2006-11-23 | 2006-11-23 | 2006-12-04 | 2006-12-08 | 2006-12-22 | 2006-12-22 | 2006-12-22 | 2006-12-22 | 2007-01-01 | 2007-01-01 | 2007-01-02 | 2007-01-08 | 2007-01-08 | 2007-01-08 | 2007-01-08 | 2007-01-12 | 2007-01-12 | 2007-01-17 | 2007-01-17
Greensboro, NC | GSO | 2007-02-05 | 2006-10-09 | 2006-10-13 | 2006-10-13 | 2006-10-18 | 2006-10-23 | 2006-10-27 | 2006-11-07 | 2006-11-07 | 2006-11-07 | 2006-11-07 | 2006-11-07 | 2006-11-13 | 2006-11-22 | 2006-11-22 | 2006-11-27 | 2006-12-07 | 2006-12-07 | 2006-12-18 | 2006-12-22 | 2007-01-05 | 2007-01-05 | 2007-01-05 | 2007-01-05 | 2007-01-15 | 2007-01-15 | 2007-01-16 | 2007-01-22 | 2007-01-22 | 2007-01-22 | 2007-01-22 | 2007-01-26 | 2007-01-26 | 2007-01-31 | 2007-01-31
Blacksburg, VA | RNK | 2007-02-20 | 2006-10-23 | 2006-10-27 | 2006-10-27 | 2006-11-02 | 2006-11-07 | 2006-11-13 | 2006-11-22 | 2006-11-22 | 2006-11-22 | 2006-11-22 | 2006-11-22 | 2006-11-27 | 2006-12-07 | 2006-12-07 | 2006-12-12 | 2006-12-22 | 2006-12-22 | 2007-01-01 | 2007-01-05 | 2007-01-22 | 2007-01-22 | 2007-01-22 | 2007-01-22 | 2007-01-30 | 2007-01-30 | 2007-01-31 | 2007-02-05 | 2007-02-05 | 2007-02-05 | 2007-02-05 | 2007-02-09 | 2007-02-09 | 2007-02-15 | 2007-02-15
Birmingham, AL | BMX | 2007-03-05 | 2006-11-06 | 2006-11-10 | 2006-11-10 | 2006-11-15 | 2006-11-20 | 2006-11-24 | 2006-12-05 | 2006-12-05 | 2006-12-05 | 2006-12-05 | 2006-12-05 | 2006-12-11 | 2006-12-20 | 2006-12-20 | 2006-12-25 | 2007-01-04 | 2007-01-04 | 2007-01-15 | 2007-01-19 | 2007-02-02 | 2007-02-02 | 2007-02-02 | 2007-02-02 | 2007-02-12 | 2007-02-12 | 2007-02-13 | 2007-02-19 | 2007-02-19 | 2007-02-19 | 2007-02-19 | 2007-02-23 | 2007-02-23 | 2007-02-28 | 2007-02-28
Tampa Bay, FL | TBW | 2007-03-19 | 2006-11-20 | 2006-11-24 | 2006-11-24 | 2006-11-29 | 2006-12-04 | 2006-12-08 | 2006-12-19 | 2006-12-19 | 2006-12-19 | 2006-12-19 | 2006-12-19 | 2006-12-25 | 2007-01-03 | 2007-01-03 | 2007-01-08 | 2007-01-18 | 2007-01-18 | 2007-01-29 | 2007-02-02 | 2007-02-16 | 2007-02-16 | 2007-02-16 | 2007-02-16 | 2007-02-26 | 2007-02-26 | 2007-02-27 | 2007-03-05 | 2007-03-05 | 2007-03-05 | 2007-03-05 | 2007-03-09 | 2007-03-09 | 2007-03-14 | 2007-03-14
FY 2007 3 QTR
Wilmington, OH | ILN | 2007-04-02 | 2006-12-04 | 2006-12-08 | 2006-12-08 | 2006-12-13 | 2006-12-18 | 2006-12-22 | 2007-01-02 | 2007-01-02 | 2007-01-02 | 2007-01-02 | 2007-01-02 | 2007-01-08 | 2007-01-17 | 2007-01-17 | 2007-01-22 | 2007-02-01 | 2007-02-01 | 2007-02-12 | 2007-02-16 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-02 | 2007-03-12 | 2007-03-12 | 2007-03-13 | 2007-03-19 | 2007-03-19 | 2007-03-19 | 2007-03-19 | 2007-03-23 | 2007-03-23 | 2007-03-28 | 2007-03-28
Charleston, SD | CHS | 2007-04-16 | 2006-12-18 | 2006-12-22 | 2006-12-22 | 2006-12-27 | 2007-01-01 | 2007-01-05 | 2007-01-16 | 2007-01-16 | 2007-01-16 | 2007-01-16 | 2007-01-16 | 2007-01-22 | 2007-01-31 | 2007-01-31 | 2007-02-05 | 2007-02-15 | 2007-02-15 | 2007-02-26 | 2007-03-02 | 2007-03-16 | 2007-03-16 | 2007-03-16 | 2007-03-16 | 2007-03-26 | 2007-03-26 | 2007-03-27 | 2007-04-02 | 2007-04-02 | 2007-04-02 | 2007-04-02 | 2007-04-06 | 2007-04-06 | 2007-04-11 | 2007-04-11
Miami, FL | MFL | 2007-04-30 | 2007-01-01 | 2007-01-05 | 2007-01-05 | 2007-01-10 | 2007-01-15 | 2007-01-19 | 2007-01-30 | 2007-01-30 | 2007-01-30 | 2007-01-30 | 2007-01-30 | 2007-02-05 | 2007-02-14 | 2007-02-14 | 2007-02-19 | 2007-03-01 | 2007-03-01 | 2007-03-12 | 2007-03-16 | 2007-03-30 | 2007-03-30 | 2007-03-30 | 2007-03-30 | 2007-04-09 | 2007-04-09 | 2007-04-10 | 2007-04-16 | 2007-04-16 | 2007-04-16 | 2007-04-16 | 2007-04-20 | 2007-04-20 | 2007-04-25 | 2007-04-25
Nashville, TN | OHX | 2007-05-14 | 2007-01-15 | 2007-01-19 | 2007-01-19 | 2007-01-24 | 2007-01-29 | 2007-02-02 | 2007-02-13 | 2007-02-13 | 2007-02-13 | 2007-02-13 | 2007-02-13 | 2007-02-19 | 2007-02-28 | 2007-02-28 | 2007-03-05 | 2007-03-15 | 2007-03-15 | 2007-03-26 | 2007-03-30 | 2007-04-13 | 2007-04-13 | 2007-04-13 | 2007-04-13 | 2007-04-23 | 2007-04-23 | 2007-04-24 | 2007-04-30 | 2007-04-30 | 2007-04-30 | 2007-04-30 | 2007-05-04 | 2007-05-04 | 2007-05-09 | 2007-05-09
Tuscon, AZ | TUS | 2007-05-29 | 2007-01-29 | 2007-02-02 | 2007-02-02 | 2007-02-08 | 2007-02-13 | 2007-02-19 | 2007-02-28 | 2007-02-28 | 2007-02-28 | 2007-02-28 | 2007-02-28 | 2007-03-05 | 2007-03-15 | 2007-03-15 | 2007-03-20 | 2007-03-30 | 2007-03-30 | 2007-04-09 | 2007-04-13 | 2007-04-30 | 2007-04-30 | 2007-04-30 | 2007-04-30 | 2007-05-08 | 2007-05-08 | 2007-05-09 | 2007-05-14 | 2007-05-14 | 2007-05-14 | 2007-05-14 | 2007-05-18 | 2007-05-18 | 2007-05-24 | 2007-05-24
Elko, NV | LKN | 2007-06-11 | 2007-02-12 | 2007-02-16 | 2007-02-16 | 2007-02-21 | 2007-02-26 | 2007-03-02 | 2007-03-13 | 2007-03-13 | 2007-03-13 | 2007-03-13 | 2007-03-13 | 2007-03-19 | 2007-03-28 | 2007-03-28 | 2007-04-02 | 2007-04-12 | 2007-04-12 | 2007-04-23 | 2007-04-27 | 2007-05-11 | 2007-05-11 | 2007-05-11 | 2007-05-11 | 2007-05-21 | 2007-05-21 | 2007-05-22 | 2007-05-28 | 2007-05-28 | 2007-05-28 | 2007-05-28 | 2007-06-01 | 2007-06-01 | 2007-06-06 | 2007-06-06
Salem, OR | SLE | 2007-06-25 | 2007-02-26 | 2007-03-02 | 2007-03-02 | 2007-03-07 | 2007-03-12 | 2007-03-16 | 2007-03-27 | 2007-03-27 | 2007-03-27 | 2007-03-27 | 2007-03-27 | 2007-04-02 | 2007-04-11 | 2007-04-11 | 2007-04-16 | 2007-04-26 | 2007-04-26 | 2007-05-07 | 2007-05-11 | 2007-05-25 | 2007-05-25 | 2007-05-25 | 2007-05-25 | 2007-06-04 | 2007-06-04 | 2007-06-05 | 2007-06-11 | 2007-06-11 | 2007-06-11 | 2007-06-11 | 2007-06-15 | 2007-06-15 | 2007-06-20 | 2007-06-20
FY 2007 4 QTR
Glasgow, MT | GGW | 2007-07-09 | 2007-03-12 | 2007-03-16 | 2007-03-16 | 2007-03-21 | 2007-03-26 | 2007-03-30 | 2007-04-10 | 2007-04-10 | 2007-04-10 | 2007-04-10 | 2007-04-10 | 2007-04-16 | 2007-04-25 | 2007-04-25 | 2007-04-30 | 2007-05-10 | 2007-05-10 | 2007-05-21 | 2007-05-25 | 2007-06-08 | 2007-06-08 | 2007-06-08 | 2007-06-08 | 2007-06-18 | 2007-06-18 | 2007-06-19 | 2007-06-25 | 2007-06-25 | 2007-06-25 | 2007-06-25 | 2007-06-29 | 2007-06-29 | 2007-07-04 | 2007-07-04
Lincoln IL | ILX | 2007-07-23 | 2007-03-26 | 2007-03-30 | 2007-03-30 | 2007-04-04 | 2007-04-09 | 2007-04-13 | 2007-04-24 | 2007-04-24 | 2007-04-24 | 2007-04-24 | 2007-04-24 | 2007-04-30 | 2007-05-09 | 2007-05-09 | 2007-05-14 | 2007-05-24 | 2007-05-24 | 2007-06-04 | 2007-06-08 | 2007-06-22 | 2007-06-22 | 2007-06-22 | 2007-06-22 | 2007-07-02 | 2007-07-02 | 2007-07-03 | 2007-07-09 | 2007-07-09 | 2007-07-09 | 2007-07-09 | 2007-07-13 | 2007-07-13 | 2007-07-18 | 2007-07-18
Springfield, MO | SGF | 2007-08-06 | 2007-04-09 | 2007-04-13 | 2007-04-13 | 2007-04-18 | 2007-04-23 | 2007-04-27 | 2007-05-08 | 2007-05-08 | 2007-05-08 | 2007-05-08 | 2007-05-08 | 2007-05-14 | 2007-05-23 | 2007-05-23 | 2007-05-28 | 2007-06-07 | 2007-06-07 | 2007-06-18 | 2007-06-22 | 2007-07-06 | 2007-07-06 | 2007-07-06 | 2007-07-06 | 2007-07-16 | 2007-07-16 | 2007-07-17 | 2007-07-23 | 2007-07-23 | 2007-07-23 | 2007-07-23 | 2007-07-27 | 2007-07-27 | 2007-08-01 | 2007-08-01
Gaylord, MI | APX | 2007-08-20 | 2007-04-23 | 2007-04-27 | 2007-04-27 | 2007-05-02 | 2007-05-07 | 2007-05-11 | 2007-05-22 | 2007-05-22 | 2007-05-22 | 2007-05-22 | 2007-05-22 | 2007-05-28 | 2007-06-06 | 2007-06-06 | 2007-06-11 | 2007-06-21 | 2007-06-21 | 2007-07-02 | 2007-07-06 | 2007-07-20 | 2007-07-20 | 2007-07-20 | 2007-07-20 | 2007-07-30 | 2007-07-30 | 2007-07-31 | 2007-08-06 | 2007-08-06 | 2007-08-06 | 2007-08-06 | 2007-08-10 | 2007-08-10 | 2007-08-15 | 2007-08-15
North Platte, NE | LBF | 2007-09-04 | 2007-05-07 | 2007-05-11 | 2007-05-11 | 2007-05-17 | 2007-05-22 | 2007-05-28 | 2007-06-06 | 2007-06-06 | 2007-06-06 | 2007-06-06 | 2007-06-06 | 2007-06-11 | 2007-06-21 | 2007-06-21 | 2007-06-26 | 2007-07-06 | 2007-07-06 | 2007-07-16 | 2007-07-20 | 2007-08-06 | 2007-08-06 | 2007-08-06 | 2007-08-06 | 2007-08-14 | 2007-08-14 | 2007-08-15 | 2007-08-20 | 2007-08-20 | 2007-08-20 | 2007-08-20 | 2007-08-24 | 2007-08-24 | 2007-08-30 | 2007-08-30
Valley, NE | OAX | 2007-09-17 | 2007-05-21 | 2007-05-25 | 2007-05-25 | 2007-05-30 | 2007-06-04 | 2007-06-08 | 2007-06-19 | 2007-06-19 | 2007-06-19 | 2007-06-19 | 2007-06-19 | 2007-06-25 | 2007-07-04 | 2007-07-04 | 2007-07-09 | 2007-07-19 | 2007-07-19 | 2007-07-30 | 2007-08-03 | 2007-08-17 | 2007-08-17 | 2007-08-17 | 2007-08-17 | 2007-08-27 | 2007-08-27 | 2007-08-28 | 2007-09-03 | 2007-09-03 | 2007-09-03 | 2007-09-03 | 2007-09-07 | 2007-09-07 | 2007-09-12 | 2007-09-12
FY 2008 1 QTR
Quillayute, WA | UIL | 2007-10-15 | 2007-06-18 | 2007-06-22 | 2007-06-22 | 2007-06-27 | 2007-07-02 | 2007-07-06 | 2007-07-17 | 2007-07-17 | 2007-07-17 | 2007-07-17 | 2007-07-17 | 2007-07-23 | 2007-08-01 | 2007-08-01 | 2007-08-06 | 2007-08-16 | 2007-08-16 | 2007-08-27 | 2007-08-31 | 2007-09-14 | 2007-09-14 | 2007-09-14 | 2007-09-14 | 2007-09-24 | 2007-09-24 | 2007-09-25 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-01 | 2007-10-05 | 2007-10-05 | 2007-10-10 | 2007-10-10
Davenport, IA | DVN | 2007-10-29 | 2007-07-02 | 2007-07-06 | 2007-07-06 | 2007-07-11 | 2007-07-16 | 2007-07-20 | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-07-31 | 2007-08-06 | 2007-08-15 | 2007-08-15 | 2007-08-20 | 2007-08-30 | 2007-08-30 | 2007-09-10 | 2007-09-14 | 2007-09-28 | 2007-09-28 | 2007-09-28 | 2007-09-28 | 2007-10-08 | 2007-10-08 | 2007-10-09 | 2007-10-15 | 2007-10-15 | 2007-10-15 | 2007-10-15 | 2007-10-19 | 2007-10-19 | 2007-10-24 | 2007-10-24
Fort Worth, TX | FWD | 2007-12-03 | 2007-08-06 | 2007-08-10 | 2007-08-10 | 2007-08-15 | 2007-08-20 | 2007-08-24 | 2007-09-04 | 2007-09-04 | 2007-09-04 | 2007-09-04 | 2007-09-04 | 2007-09-10 | 2007-09-19 | 2007-09-19 | 2007-09-24 | 2007-10-04 | 2007-10-04 | 2007-10-15 | 2007-10-19 | 2007-11-02 | 2007-11-02 | 2007-11-02 | 2007-11-02 | 2007-11-12 | 2007-11-12 | 2007-11-13 | 2007-11-19 | 2007-11-19 | 2007-11-19 | 2007-11-19 | 2007-11-23 | 2007-11-23 | 2007-11-28 | 2007-11-28
Formulas:
Schedule First Telecon = IF(WEEKDAY([Target install date (D-Day]-F3)=1,([Target install date (D-Day]-F3+1),(IF(WEEKDAY([Target install date (D-Day]-F3)=7,([Target install date (D-Day]-F3-1),([Target install date (D-Day]-F3))))
Hold first Telecon and Ship Plans = IF(WEEKDAY([Target install date (D-Day]-G3)=1,([Target install date (D-Day]-G3+1),(IF(WEEKDAY([Target install date (D-Day]-G3)=7,([Target install date (D-Day]-G3-1),([Target install date (D-Day]-G3))))
Issue general info. Request e-mail = IF(WEEKDAY([Target install date (D-Day]-H3)=1,([Target install date (D-Day]-H3+1),(IF(WEEKDAY([Target install date (D-Day]-H3)=7,([Target install date (D-Day]-H3-1),([Target install date (D-Day]-H3))))
Ops-Immed Response Due = IF(WEEKDAY([Target install date (D-Day]-I3)=1,([Target install date (D-Day]-I3+1),(IF(WEEKDAY([Target install date (D-Day]-I3)=7,([Target install date (D-Day]-I3-1),([Target install date (D-Day]-I3))))
Request 7460 = IF(WEEKDAY([Target install date (D-Day]-L3)=1,([Target install date (D-Day]-L3+1),(IF(WEEKDAY([Target install date (D-Day]-L3)=7,([Target install date (D-Day]-L3-1),([Target install date (D-Day]-L3))))
Send Ops Immed to IMET = IF(WEEKDAY([Target install date (D-Day]-M3)=1,([Target install date (D-Day]-M3+1),(IF(WEEKDAY([Target install date (D-Day]-M3)=7,([Target install date (D-Day]-M3-1),([Target install date (D-Day]-M3))))
Schedule Second Telecon = IF(WEEKDAY([Target install date (D-Day]-N3)=1,([Target install date (D-Day]-N3+1),(IF(WEEKDAY([Target install date (D-Day]-N3)=7,([Target install date (D-Day]-N3-1),([Target install date (D-Day]-N3))))
Hold Second Telecon = IF(WEEKDAY([Target install date (D-Day]-O3)=1,([Target install date (D-Day]-O3+1),(IF(WEEKDAY([Target install date (D-Day]-O3)=7,([Target install date (D-Day]-O3-1),([Target install date (D-Day]-O3))))
Send Final SIP = IF(WEEKDAY([Target install date (D-Day]-P3)=1,([Target install date (D-Day]-P3+1),(IF(WEEKDAY([Target install date (D-Day]-P3)=7,([Target install date (D-Day]-P3-1),([Target install date (D-Day]-P3))))
Schedule Final Telecon = IF(WEEKDAY([Target install date (D-Day]-Q3)=1,([Target install date (D-Day]-Q3+1),(IF(WEEKDAY([Target install date (D-Day]-Q3)=7,([Target install date (D-Day]-Q3-1),([Target install date (D-Day]-Q3))))
Hold Final Telecon = IF(WEEKDAY([Target install date (D-Day]-R3)=1,([Target install date (D-Day]-R3+1),(IF(WEEKDAY([Target install date (D-Day]-R3)=7,([Target install date (D-Day]-R3-1),([Target install date (D-Day]-R3))))
Permit reminder = IF(WEEKDAY([Target install date (D-Day]-S3)=1,([Target install date (D-Day]-S3+1),(IF(WEEKDAY([Target install date (D-Day]-S3)=7,([Target install date (D-Day]-S3-1),([Target install date (D-Day]-S3))))
Notify Debbie Pickerign = IF(WEEKDAY([Target install date (D-Day]-T3)=1,([Target install date (D-Day]-T3+1),(IF(WEEKDAY([Target install date (D-Day]-T3)=7,([Target install date (D-Day]-T3-1),[Target install date (D-Day]-T3)))
Schedule Training Telecon = IF(WEEKDAY([Target install date (D-Day]-U3)=1,([Target install date (D-Day]-U3+1),(IF(WEEKDAY([Target install date (D-Day]-U3)=7,([Target install date (D-Day]-U3-1),([Target install date (D-Day]-U3))))
Hold Training Telecon = IF(WEEKDAY([Target install date (D-Day]-V3)=1,([Target install date (D-Day]-V3+1),(IF(WEEKDAY([Target install date (D-Day]-V3)=7,([Target install date (D-Day]-V3-1),([Target install date (D-Day]-V3))))
Prelim. Decomm. Date Due = IF(WEEKDAY([Target install date (D-Day]-W3)=1,([Target install date (D-Day]-W3+1),(IF(WEEKDAY([Target install date (D-Day]-W3)=7,([Target install date (D-Day]-W3-1),([Target install date (D-Day]-W3))))
All Gov Permits Due = IF(WEEKDAY([Target install date (D-Day]-X3)=1,([Target install date (D-Day]-X3+1),(IF(WEEKDAY([Target install date (D-Day]-X3)=7,([Target install date (D-Day]-X3-1),([Target install date (D-Day]-X3))))
Exchange encription Keys, Record PWs = IF(WEEKDAY([Target install date (D-Day]-Y3)=1,([Target install date (D-Day]-Y3+1),(IF(WEEKDAY([Target install date (D-Day]-Y3)=7,([Target install date (D-Day]-Y3-1),([Target install date (D-Day]-Y3))))
Notify NLSC for LRU Containers = IF(WEEKDAY([Target install date (D-Day]-AA3)=1,([Target install date (D-Day]-AA3+1),(IF(WEEKDAY([Target install date (D-Day]-AA3)=7,([Target install date (D-Day]-AA3-1),([Target install date (D-Day]-AA3))))
Schedule Site Readiness Telecon = IF(WEEKDAY([Target install date (D-Day]-AC3)=1,([Target install date (D-Day]-AC3+1),(IF(WEEKDAY([Target install date (D-Day]-AC3)=7,([Target install date (D-Day]-AC3-1),([Target install date (D-Day]-AC3))))
Site Readiness Telecon = IF(WEEKDAY([Target install date (D-Day]-AD3)=1,([Target install date (D-Day]-AD3+1),(IF(WEEKDAY([Target install date (D-Day]-AD3)=7,([Target install date (D-Day]-AD3-1),([Target install date (D-Day]-AD3))))
Facilities Checklist Due = IF(WEEKDAY([Target install date (D-Day]-AE3)=1,([Target install date (D-Day]-AE3+1),(IF(WEEKDAY([Target install date (D-Day]-AE3)=7,([Target install date (D-Day]-AE3-1),([Target install date (D-Day]-AE3))))
Site Decomm. Checklist Due = IF(WEEKDAY([Target install date (D-Day]-AF3)=1,([Target install date (D-Day]-AF3+1),(IF(WEEKDAY([Target install date (D-Day]-AF3)=7,([Target install date (D-Day]-AF3-1),([Target install date (D-Day]-AF3))))
Distance Learning Cert Due = IF(WEEKDAY([Target install date (D-Day]-AG3)=1,([Target install date (D-Day]-AG3+1),(IF(WEEKDAY([Target install date (D-Day]-AG3)=7,([Target install date (D-Day]-AG3-1),([Target install date (D-Day]-AG3))))
Get current RRS Software & Ghost CD = IF(WEEKDAY([Target install date (D-Day]-AI3)=1,([Target install date (D-Day]-AI3+1),(IF(WEEKDAY([Target install date (D-Day]-AI3)=7,([Target install date (D-Day]-AI3-1),([Target install date (D-Day]-AI3))))

## Per site
Enter the three character Site ID in Column B of this row | JAX
Enter the installation date in Column B of this row | 2007-01-08
JAX - Ship RWS & Tng. Mat. & Issue e-mail 1, Deployment Team Action, 09/11/2006 , 8:00 AM
JAX - Verify RWS received, Deployment Team Action, 09/15/2006 , 8:00 AM
JAX - Schedule first telecon & issue e-mail, Deployment Team Action, 09/15/2006 , 8:00 AM
JAX - First telecon, Proposed Telecon, 09/20/2006 , 8:00 AM
JAX - Request general data, Deployment Team Action, 09/25/2006 , 8:00 AM
JAX - Ops immediate data due, Forecast Office Action, 09/29/2006 , 8:00 AM
JAX - SIP comments and data due, Forecast Office Action, 10/10/2006 , 8:00 AM
JAX - Issue GPS repeater kit, Deployment Team Action, 10/10/2006 , 8:00 AM
JAX - Submit 7460 request, Deployment Team Action, 10/10/2006 , 8:00 AM
JAX - Send Ops Immed. To IMET, Deployment Team Action, 10/10/2006 , 8:00 AM
JAX - Schedule second telecon , Deployment Team Action, 10/10/2006 , 8:00 AM
JAX - Second telecon, Proposed Telecon, 10/16/2006 , 8:00 AM
JAX - Send final SIP, Deployment Team Action, 10/25/2006 , 8:00 AM
JAX - Schedule final telecon, Deployment Team Action, 10/25/2006 , 8:00 AM
JAX - Final telecon, Proposed Telecon, 10/30/2006 , 8:00 AM
JAX - Permit reminder call, Deployment Team Action, 11/09/2006 , 8:00 AM
JAX - Notify Debbie P, Deployment Team Action, 11/09/2006 , 8:00 AM
JAX - Schedule training telecon, Deployment Team Action, 11/20/2006 , 8:00 AM
JAX - Training telecon, Proposed Telecon, 11/24/2006 , 8:00 AM
JAX - Prelim. Decomm. Date due, Forecast Office Action, 12/08/2006 , 8:00 AM
JAX - Permits due, Deployment Team Action, 12/08/2006 , 8:00 AM
JAX - Exchange keys & PWs, Deployment Team Action, 12/08/2006 , 8:00 AM
JAX - Issue NLSC kits, Deployment Team Action, 12/08/2006 , 8:00 AM
JAX - Notify NLSC to ship crates, Deployment Team Action, 12/18/2006 , 8:00 AM
JAX - Notify BU sites, Deployment Team Action, 12/18/2006 , 8:00 AM
JAX - Schedule readiness telecon, Deployment Team Action, 12/19/2006 , 8:00 AM
JAX - Readiness telecon, Proposed Telecon, 12/25/2006 , 8:00 AM
JAX - Facilities checklist due, Forecast Office Action, 12/25/2006 , 8:00 AM
JAX - Decomm. Checklist due, Forecast Office Action, 12/25/2006 , 8:00 AM
JAX - Operator training cert due, Forecast Office Action, 12/25/2006 , 8:00 AM
JAX - Notify Maint & logistics, Deployment Team Action, 12/29/2006 , 8:00 AM
JAX - Get RRS SW, Deployment Team Action, 12/29/2006 , 8:00 AM
JAX - Notify Hotline, Deployment Team Action, 01/03/2007 , 8:00 AM
JAX - Notify NDCD & NCEP, Deployment Team Action, 01/03/2007 , 8:00 AM
JAX - Issue final notification email, Deployment Team Action, 01/04/2007 , 8:00 AM
JAX - Installation, Installation Action, 01/08/2007 , 8:00 AM
JAX - Schedule Wrap up Meeting, Deployment Team Action, 01/16/2007 , 8:00 AM

## Dialed Backups
RRS COMMUNICATIONS PATHS
2005-05-24
UA OFC | OFC_NAME | PRIMARY COMMS | BACKUP 1 | BACKUP 2
CR
KABR | Aberdeen, SD | ABR | CRH | ERH
KAPX | North Central Lower Michigan, MI | APX | CRH | ERH
KBIS | Bismarck, ND | BIS | CRH | ERH
KDDC | Dodge City, KS | DDC | CRH | ERH
KDNR | Denver, CO | BOU | CRH | ERH
KDTX | Detroit, MI | DTX | CRH | ERH
KDVN | Quad Cities, IA | DVN | CRH | ERH
KGJT | Grand Junction, CO | GJT | CRH | ERH
KGRB | Green Bay, WI | GRB | CRH | ERH
KILX | Central Illinois, IL | ILX | CRH | ERH
KINL | International Falls, MN | INL | CRH | ERH
KLBF | North Platte, NE | LBF | CRH | ERH
KMPX | Minneapolis, MN | MPX | CRH | ERH
KOAX | Omaha, NE | OAX | CRH | ERH
KRIW | Riverton, WY | RIW | CRH | ERH
KSGF | Springfield, MO | SGF | CRH | ERH
KTOP | Topeka, KS | TOP | CRH | ERH
KUNR | Rapid City, SD | UNR | CRH | ERH
ER
KALY | Albany, NY | ALY | ERH | CRH
KBUF | Buffalo, NY | BUF | ERH | CRH
KCAR | Caribou, ME | CAR | ERH | CRH
KCHH | Chatham, MA | BOX | ERH | CRH
KCHS | Charleston, SC | CHS | ERH | CRH
KGSO | Greensboro, NC | RAH | ERH | CRH
KGYX | Portland, ME | GYX | ERH | CRH
KILN | Wilmington, OH | ILN | ERH | CRH
KLWX | Baltimore, MD/Washington, DC | LWX | ERH | CRH
KMHX | Morehead City, NC | MHX | ERH | CRH
KOKX | New York City, NY | OKX | ERH | CRH
KPBZ | Pittsburgh, PA | PBZ | ERH | CRH
KRNK | Blackburg, VA | RNK | ERH | CRH
KWAL | Wallops Island, VA | AKQ | ERH | CRH
PR
PGUM | Guam, GU | GUM
SR
KABQ | Albuquerque, NM | ABQ | SRH | WRH
KAMA | Amarillo, TX | AMA | SRH | WRH
KBMX | Birmingham, AL | BMX | SRH | WRH
KBRO | Brownsville, TX | BRO | SRH | WRH
KCRP | Corpus Christi, TX | CRP | SRH | WRH
KDRT | Del Rio, TX | MAF | SRH | WRH
KEPZ | El Paso, TX | EPZ | SRH | WRH
KEYW | Key West, FL | EYW | SRH | WRH
KFFC | Atlanta, GA | FFC | SRH | WRH
KFWD | Dallas/Fort Worth, TX | FWD | SRH | WRH
KJAN | Jackson, MS | JAN | SRH | WRH
KJAX | Jacksonville, FL | JAX | SRH | WRH
KLCH | Lake Charles, LA | LCH | SRH | WRH
KLIX | New Orleans/Baton Rouge, LA | LCH | SRH | WRH
KLZK | Little Rock, AR | LZK | SRH | WRH
KMAF | Midland/Odessa, TX | MAF | SRH | WRH
KMFL | Miami, FL | MFL | SRH | WRH
KOHX | Nashville, TN | OHX | SRH | WRH
KOUN | Oklahoma City, OK | OUN | SRH | WRH
KSHV | Shreveport, LA | SHV | SRH | WRH
KSJU | San Juan, PR | SJU | SRH | WRH
KTAE | Tallahassee, FL | TAE | SRH | WRH
KTBW | Tampa Bay Area, FL | TBW | SRH | WRH
WR
KBOI | Boise, ID | BOI | WRH | SRH
KDRA | Las Vegas, NV | VEF | WRH | SRH
KFGZ | Flagstaff, AZ | FGZ | WRH | SRH
KGGW | Glasgow, MT | GGW | WRH | SRH
KLKN | Elko, NV | LKN | WRH | SRH
KMFR | Medford, OR | MFR | WRH | SRH
KNKX | San Diego, CA | SGX | WRH | SRH
KOAK | Oakland, CA | STO | WRH | SRH
KOTX | Spokane, WA | OTX | WRH | SRH
KREV | Reno, NV | REV | WRH | SRH
KSLC | Salt Lake City, UT | SLC | WRH | SRH
KSLE | Salem, OR | MFR | WRH | SRH
KTFX | Great Falls, MT | TFX | WRH | SRH
KTUS | Tucson, AZ | TWC | WRH | SRH
KUIL | Quillayute, WA | SEW | WRH | SRH
71
CRH Dialup # 816-891-6324
ERH Dialup # 631-589-7236
SRH Dialup # 817-978-0045
WRH Dialup # 801-524-5119