## Forecast <= 45 Days from TARGET
MS Project Row ID | Outline Level | Summary Task? | Site Code | Name | Goal (in SPIRE or Waterfall) | Goal Alert (Forecast is 45 days or less before GOAL date) | % Comp | Current Forecast Date | Calendar Days Before (or After if negative) the GOAL in Col F
1 | 1 | Yes |  | ASR-11 Integrated Program Schedule |  |  | 58% | 1999-07-20 08:00
4 | 2 | No | 000 | Last Operational Readiness Date (ORD) | 2009-09-30 17:00 | Yes | 0% | 2010-06-30 17:00 | -273
130 | 2 | Yes | ABI | Abilene, TX (ABI) |  |  | 74% | 2005-10-07 08:00
141 | 3 | No | ABI | ABI Operational Readiness Date (ORD)/Commissioning | 2007-09-30 17:00 | Yes | 0% | 2007-10-30 17:00 | -30
146 | 2 | Yes | FAR | Fargo, ND (FAR) |  |  | 64% | 2005-11-16 08:00
159 | 3 | No | FAR | FAR Start Dismantle/Deactivation | 2007-08-31 17:00 | Yes | 0% | 2007-09-26 17:00 | -26
194 | 2 | Yes | MYR | Myrtle Beach, SC (MYR) |  |  | 62% | 2006-01-03 08:00
205 | 3 | No | MYR | MYR Operational Readiness Date (ORD)/Commissioning | 2007-07-31 17:00 | Yes | 0% | 2007-10-31 17:00 | -92
210 | 2 | Yes | AGS | Augusta, GA (AGS) |  |  | 46% | 2006-01-17 08:00
221 | 3 | No | AGS | AGS Operational Readiness Date (ORD)/Commissioning | 2007-10-31 17:00 | Yes | 0% | 2007-09-30 17:00 | 31
243 | 2 | Yes | CMI | Champaign, IL (CMI) |  |  | 38% | 2006-03-13 08:00
254 | 3 | No | CMI | CMI Operational Readiness Date (ORD)/Commissioning | 2007-10-31 17:00 | Yes | 0% | 2008-03-05 17:00 | -126
256 | 3 | No | CMI | CMI Start Dismantle/Deactivate | 2007-11-30 17:00 | Yes | 0% | 2008-09-08 17:00 | -283
259 | 2 | Yes | YNG | Youngstown, OH (YNG) |  |  | 62% | 2003-03-27 08:00
271 | 3 | No | YNG | YNG Initial Operating Capability (IOC) | 2007-09-30 17:00 | Yes | 0% | 2007-09-28 17:00 | 2
278 | 2 | Yes | LEX | Lexington, KY (LEX) |  |  | 55% | 2006-02-22 08:00
290 | 3 | No | LEX | LEX Operational Readiness Date (ORD)/Commissioning | 2007-11-30 17:00 | Yes | 0% | 2008-03-28 17:00 | -119
295 | 2 | Yes | MBS | Saginaw, MI (MBS) |  |  | 56% | 2006-05-10 08:00
306 | 3 | No | MBS | MBS Operational Readiness Date (ORD)/Commissioning | 2007-11-11 17:00 | Yes | 0% | 2007-10-13 17:00 | 29
308 | 3 | No | MBS | MBS Start Dismantle/Deactivate | 2007-12-31 17:00 | Yes | 0% | 2008-08-29 17:00 | -242
311 | 2 | Yes | LIT | Little Rock, AR (LIT) |  |  | 64% | 2006-03-14 08:00
323 | 3 | No | LIT | LIT Operational Readiness Date (ORD)/Commissioning | 2007-11-30 17:00 | Yes | 0% | 2007-11-02 17:00 | 28
328 | 2 | Yes | AMA | Amarillo, TX (AMA) |  |  | 31% | 2006-03-22 08:00
338 | 3 | No | AMA | AMA Initial Operating Capability (IOC) | 2007-11-30 17:00 | Yes | 0% | 2008-09-08 17:00 | -283
340 | 3 | No | AMA | AMA Operational Readiness Date (ORD)/Commissioning | 2008-01-31 17:00 | Yes | 0% | 2008-10-08 17:00 | -251
345 | 2 | Yes | MAF | Midland, TX (MAF) |  |  | 50% | 2005-10-24 08:00
355 | 3 | No | MAF | MAF Initial Operating Capability (IOC) | 2007-12-31 17:00 | Yes | 0% | 2008-04-10 17:00 | -101
380 | 2 | Yes | RDG | Reading, PA (RDG) |  |  | 35% | 2006-03-31 08:00
391 | 3 | No | RDG | RDG Initial Operating Capability (IOC) | 2008-02-29 17:00 | Yes | 0% | 2008-04-25 17:00 | -56
393 | 3 | No | RDG | RDG Operational Readiness Date (ORD)/Commissioning | 2008-04-30 17:00 | Yes | 0% | 2008-05-25 17:00 | -25
398 | 2 | Yes | SUX | Sioux City, IA (SUX) |  |  | 41% | 2006-04-13 08:00
409 | 3 | No | SUX | SUX Initial Operating Capability (IOC) | 2008-03-31 17:00 | Yes | 0% | 2008-06-02 17:00 | -63
411 | 3 | No | SUX | SUX Operational Readiness Date (ORD)/Commissioning | 2008-05-31 17:00 | Yes | 0% | 2008-07-02 17:00 | -32
416 | 2 | Yes | GPT | Gulfport, MS (GPT) |  |  | 44% | 2006-03-28 08:00
423 | 3 | No | GPT | GPT CAI/DD250 Signed | 2007-10-31 17:00 | Yes | 0% | 2008-02-11 17:00 | -103
427 | 3 | No | GPT | GPT Initial Operating Capability (IOC) | 2008-01-31 17:00 | Yes | 0% | 2008-08-04 17:00 | -186
429 | 3 | No | GPT | GPT Operational Readiness Date (ORD)/Commissioning | 2008-03-31 17:00 | Yes | 0% | 2008-09-03 17:00 | -156
434 | 2 | Yes | SPI | Springfield, IL (SPI) |  |  | 34% | 2006-06-22 08:00
445 | 3 | No | SPI | SPI Initial Operating Capability (IOC) | 2008-05-31 17:00 | Yes | 0% | 2008-06-16 17:00 | -16
447 | 3 | No | SPI | SPI Operational Readiness Date (ORD)/Commissioning | 2008-07-31 17:00 | Yes | 0% | 2008-07-16 17:00 | 15
452 | 2 | Yes | CRP | Corpus Christi, TX (CRP) |  |  | 36% | 2005-07-21 08:00
460 | 3 | No | CRP | CRP CAI/DD250 Signed | 2007-12-31 17:00 | Yes | 0% | 2008-02-09 17:00 | -40
464 | 3 | No | CRP | CRP Initial Operating Capability (IOC) | 2008-04-30 17:00 | Yes | 0% | 2009-01-30 17:00 | -275
466 | 3 | No | CRP | CRP Operational Readiness Date (ORD)/Commissioning | 2008-06-30 17:00 | Yes | 0% | 2009-03-01 17:00 | -244
471 | 2 | Yes | BTR | Baton Rouge, LA (BTR) |  |  | 57% | 2002-02-19 08:00
483 | 3 | No | BTR | BTR Initial Operating Capability (IOC) | 2008-06-30 17:00 | Yes | 0% | 2009-02-20 17:00 | -235
485 | 3 | No | BTR | BTR Operational Readiness Date (ORD)/Commissioning | 2008-08-31 17:00 | Yes | 0% | 2009-03-22 17:00 | -203
511 | 2 | Yes | OGG | Kahului, HI (OGG) |  |  | 67% | 1999-07-20 08:00
515 | 3 | No | OGG | OGG Equipment Delivered to Site | 2007-09-30 17:00 | Yes | 0% | 2008-02-28 17:00 | -151
519 | 3 | No | OGG | OGG CAI/DD250 Signed | 2007-11-30 17:00 | Yes | 0% | 2008-12-30 17:00 | -396
523 | 3 | No | OGG | OGG Initial Operating Capability (IOC) | 2008-02-29 17:00 | Yes | 0% | 2009-05-06 17:00 | -432
525 | 3 | No | OGG | OGG Operational Readiness Date (ORD)/Commissioning | 2008-04-30 17:00 | Yes | 0% | 2009-06-05 17:00 | -401
530 | 2 | Yes | MRY | Monterey, CA (MRY) |  |  | 63% | 2003-04-08 08:00
542 | 3 | No | MRY | MRY Initial Operating Capability (IOC) | 2008-06-30 17:00 | Yes | 0% | 2008-07-18 17:00 | -18
544 | 3 | No | MRY | MRY Operational Readiness Date (ORD)/Commissioning | 2008-08-31 17:00 | Yes | 0% | 2008-08-17 17:00 | 14
549 | 2 | Yes | BGM | Binghamton, NY (BGM) |  |  | 25% | 2005-10-03 08:00
557 | 3 | No | BGM | BGM CAI/DD250 Signed | 2008-06-30 17:00 | Yes | 0% | 2008-08-03 17:00 | -34
561 | 3 | No | BGM | BGM Initial Operating Capability (IOC) | 2008-09-30 17:00 | Yes | 0% | 2008-12-08 17:00 | -69
563 | 3 | No | BGM | BGM Operational Readiness Date (ORD)/Commissioning | 2008-11-30 17:00 | Yes | 0% | 2009-01-07 17:00 | -38
568 | 2 | Yes | GRB | Green Bay, WI (GRB) |  |  | 55% | 2002-07-23 08:00
573 | 3 | No | GRB | GRB Equipment Delivered to Site | 2008-07-31 17:00 | Yes | 0% | 2008-08-27 17:00 | -27
577 | 3 | No | GRB | GRB CAI/DD250 Signed | 2009-03-31 17:00 | Yes | 0% | 2009-09-30 17:00 | -183
581 | 3 | No | GRB | GRB Initial Operating Capability (IOC) | 2009-06-30 17:00 | Yes | 0% | 2010-02-07 17:00 | -222
583 | 3 | No | GRB | GRB Operational Readiness Date (ORD)/Commissioning | 2009-08-31 17:00 | Yes | 0% | 2010-03-07 17:00 | -188
588 | 2 | Yes | MLI | Moline, IL (MLI) |  |  | 19% | 2006-02-01 08:00
591 | 3 | No | MLI | MLI Start Site Construction | 2007-05-31 17:00 | Yes | 0% | 2007-10-30 17:00 | -152
593 | 3 | No | MLI | MLI Equipment Delivered to Site | 2008-05-31 17:00 | Yes | 0% | 2008-07-03 17:00 | -33
597 | 3 | No | MLI | MLI CAI/DD250 Signed | 2009-01-31 17:00 | Yes | 0% | 2009-03-31 17:00 | -59
601 | 3 | No | MLI | MLI Initial Operating Capability (IOC) | 2009-04-30 17:00 | Yes | 0% | 2009-07-31 17:00 | -92
603 | 3 | No | MLI | MLI Operational Readiness Date (ORD)/Commissioning | 2009-06-30 17:00 | Yes | 0% | 2009-09-30 17:00 | -92
608 | 2 | Yes | MLB | Melbourne, FL (MLB) |  |  | 37% | 2005-12-01 08:00
616 | 3 | No | MLB | MLB CAI/DD250 Signed | 2008-10-31 17:00 | Yes | 0% | 2008-10-30 17:00 | 1
646 | 2 | Yes | FSD | Sioux Falls, SD (FSD) |  |  | 35% | 2005-04-12 08:00
650 | 3 | No | FSD | FSD Equipment Delivered to Site | 2008-03-30 17:00 | Yes | 0% | 2008-03-30 17:00 | 0
665 | 2 | Yes | ABE | Allentown, PA (ABE) |  |  | 56% | 2002-10-22 08:00
669 | 3 | No | ABE | ABE Equipment Delivered to Site | 2007-11-30 17:00 | Yes | 0% | 2007-10-30 17:00 | 31
673 | 3 | No | ABE | ABE CAI/DD250 Signed | 2008-10-31 17:00 | Yes | 0% | 2008-09-30 17:00 | 31
677 | 3 | No | ABE | ABE Initial Operating Capability (IOC) | 2009-01-31 17:00 | Yes | 0% | 2009-02-04 17:00 | -4
679 | 3 | No | ABE | ABE Operational Readiness Date (ORD)/Commissioning | 2009-03-31 17:00 | Yes | 0% | 2009-04-06 17:00 | -6
684 | 2 | Yes | PIA | Peoria, IL (PIA) |  |  | 52% | 2000-05-09 08:00
689 | 3 | No | PIA | PIA Equipment Delivered to Site | 2008-08-30 17:00 | Yes | 0% | 2008-09-10 17:00 | -11
693 | 3 | No | PIA | PIA CAI/DD250 Signed | 2009-04-30 17:00 | Yes | 0% | 2009-12-09 17:00 | -223
697 | 3 | No | PIA | PIA Initial Operating Capability (IOC) | 2009-07-31 17:00 | Yes | 0% | 2010-04-30 17:00 | -273
699 | 3 | No | PIA | PIA Operational Readiness Date (ORD)/Commissioning | 2009-09-30 17:00 | Yes | 0% | 2010-06-30 17:00 | -273

## Forecast is Past TARGET Date
MS Project Row ID | Outline Level | Summary Task? | Site Code | Name | Goal (in SPIRE or Waterfall) | Goal Alert (Forecast is 45 days or less before GOAL date) | % Comp | Current Forecast Date | Calendar Days Before (or After if negative) the GOAL in Col F
1 | 1 | Yes |  | ASR-11 Integrated Program Schedule | NA | No | 58% | 1999-07-20 08:00
4 | 2 | No | 000 | Last Operational Readiness Date (ORD) | 2009-09-30 17:00 | Yes | 0% | 2010-06-30 17:00 | -273
130 | 2 | Yes | ABI | Abilene, TX (ABI) | NA | No | 74% | 2005-10-07 08:00
141 | 3 | No | ABI | ABI Operational Readiness Date (ORD)/Commissioning | 2007-09-30 17:00 | Yes | 0% | 2007-10-30 17:00 | -30
146 | 2 | Yes | FAR | Fargo, ND (FAR) | NA | No | 64% | 2005-11-16 08:00
159 | 3 | No | FAR | FAR Start Dismantle/Deactivation | 2007-08-31 17:00 | Yes | 0% | 2007-09-26 17:00 | -26
194 | 2 | Yes | MYR | Myrtle Beach, SC (MYR) | NA | No | 62% | 2006-01-03 08:00
205 | 3 | No | MYR | MYR Operational Readiness Date (ORD)/Commissioning | 2007-07-31 17:00 | Yes | 0% | 2007-10-31 17:00 | -92
243 | 2 | Yes | CMI | Champaign, IL (CMI) | NA | No | 38% | 2006-03-13 08:00
254 | 3 | No | CMI | CMI Operational Readiness Date (ORD)/Commissioning | 2007-10-31 17:00 | Yes | 0% | 2008-03-05 17:00 | -126
256 | 3 | No | CMI | CMI Start Dismantle/Deactivate | 2007-11-30 17:00 | Yes | 0% | 2008-09-08 17:00 | -283
278 | 2 | Yes | LEX | Lexington, KY (LEX) | NA | No | 55% | 2006-02-22 08:00
290 | 3 | No | LEX | LEX Operational Readiness Date (ORD)/Commissioning | 2007-11-30 17:00 | Yes | 0% | 2008-03-28 17:00 | -119
295 | 2 | Yes | MBS | Saginaw, MI (MBS) | NA | No | 56% | 2006-05-10 08:00
308 | 3 | No | MBS | MBS Start Dismantle/Deactivate | 2007-12-31 17:00 | Yes | 0% | 2008-08-29 17:00 | -242
328 | 2 | Yes | AMA | Amarillo, TX (AMA) | NA | No | 31% | 2006-03-22 08:00
338 | 3 | No | AMA | AMA Initial Operating Capability (IOC) | 2007-11-30 17:00 | Yes | 0% | 2008-09-08 17:00 | -283
340 | 3 | No | AMA | AMA Operational Readiness Date (ORD)/Commissioning | 2008-01-31 17:00 | Yes | 0% | 2008-10-08 17:00 | -251
345 | 2 | Yes | MAF | Midland, TX (MAF) | NA | No | 50% | 2005-10-24 08:00
355 | 3 | No | MAF | MAF Initial Operating Capability (IOC) | 2007-12-31 17:00 | Yes | 0% | 2008-04-10 17:00 | -101
380 | 2 | Yes | RDG | Reading, PA (RDG) | NA | No | 35% | 2006-03-31 08:00
391 | 3 | No | RDG | RDG Initial Operating Capability (IOC) | 2008-02-29 17:00 | Yes | 0% | 2008-04-25 17:00 | -56
393 | 3 | No | RDG | RDG Operational Readiness Date (ORD)/Commissioning | 2008-04-30 17:00 | Yes | 0% | 2008-05-25 17:00 | -25
398 | 2 | Yes | SUX | Sioux City, IA (SUX) | NA | No | 41% | 2006-04-13 08:00
409 | 3 | No | SUX | SUX Initial Operating Capability (IOC) | 2008-03-31 17:00 | Yes | 0% | 2008-06-02 17:00 | -63
411 | 3 | No | SUX | SUX Operational Readiness Date (ORD)/Commissioning | 2008-05-31 17:00 | Yes | 0% | 2008-07-02 17:00 | -32
416 | 2 | Yes | GPT | Gulfport, MS (GPT) | NA | No | 44% | 2006-03-28 08:00
423 | 3 | No | GPT | GPT CAI/DD250 Signed | 2007-10-31 17:00 | Yes | 0% | 2008-02-11 17:00 | -103
427 | 3 | No | GPT | GPT Initial Operating Capability (IOC) | 2008-01-31 17:00 | Yes | 0% | 2008-08-04 17:00 | -186
429 | 3 | No | GPT | GPT Operational Readiness Date (ORD)/Commissioning | 2008-03-31 17:00 | Yes | 0% | 2008-09-03 17:00 | -156
434 | 2 | Yes | SPI | Springfield, IL (SPI) | NA | No | 34% | 2006-06-22 08:00
445 | 3 | No | SPI | SPI Initial Operating Capability (IOC) | 2008-05-31 17:00 | Yes | 0% | 2008-06-16 17:00 | -16
452 | 2 | Yes | CRP | Corpus Christi, TX (CRP) | NA | No | 36% | 2005-07-21 08:00
460 | 3 | No | CRP | CRP CAI/DD250 Signed | 2007-12-31 17:00 | Yes | 0% | 2008-02-09 17:00 | -40
464 | 3 | No | CRP | CRP Initial Operating Capability (IOC) | 2008-04-30 17:00 | Yes | 0% | 2009-01-30 17:00 | -275
466 | 3 | No | CRP | CRP Operational Readiness Date (ORD)/Commissioning | 2008-06-30 17:00 | Yes | 0% | 2009-03-01 17:00 | -244
471 | 2 | Yes | BTR | Baton Rouge, LA (BTR) | NA | No | 57% | 2002-02-19 08:00
483 | 3 | No | BTR | BTR Initial Operating Capability (IOC) | 2008-06-30 17:00 | Yes | 0% | 2009-02-20 17:00 | -235
485 | 3 | No | BTR | BTR Operational Readiness Date (ORD)/Commissioning | 2008-08-31 17:00 | Yes | 0% | 2009-03-22 17:00 | -203
511 | 2 | Yes | OGG | Kahului, HI (OGG) | NA | No | 67% | 1999-07-20 08:00
515 | 3 | No | OGG | OGG Equipment Delivered to Site | 2007-09-30 17:00 | Yes | 0% | 2008-02-28 17:00 | -151
519 | 3 | No | OGG | OGG CAI/DD250 Signed | 2007-11-30 17:00 | Yes | 0% | 2008-12-30 17:00 | -396
523 | 3 | No | OGG | OGG Initial Operating Capability (IOC) | 2008-02-29 17:00 | Yes | 0% | 2009-05-06 17:00 | -432
525 | 3 | No | OGG | OGG Operational Readiness Date (ORD)/Commissioning | 2008-04-30 17:00 | Yes | 0% | 2009-06-05 17:00 | -401
530 | 2 | Yes | MRY | Monterey, CA (MRY) | NA | No | 63% | 2003-04-08 08:00
542 | 3 | No | MRY | MRY Initial Operating Capability (IOC) | 2008-06-30 17:00 | Yes | 0% | 2008-07-18 17:00 | -18
549 | 2 | Yes | BGM | Binghamton, NY (BGM) | NA | No | 25% | 2005-10-03 08:00
557 | 3 | No | BGM | BGM CAI/DD250 Signed | 2008-06-30 17:00 | Yes | 0% | 2008-08-03 17:00 | -34
561 | 3 | No | BGM | BGM Initial Operating Capability (IOC) | 2008-09-30 17:00 | Yes | 0% | 2008-12-08 17:00 | -69
563 | 3 | No | BGM | BGM Operational Readiness Date (ORD)/Commissioning | 2008-11-30 17:00 | Yes | 0% | 2009-01-07 17:00 | -38
568 | 2 | Yes | GRB | Green Bay, WI (GRB) | NA | No | 55% | 2002-07-23 08:00
573 | 3 | No | GRB | GRB Equipment Delivered to Site | 2008-07-31 17:00 | Yes | 0% | 2008-08-27 17:00 | -27
577 | 3 | No | GRB | GRB CAI/DD250 Signed | 2009-03-31 17:00 | Yes | 0% | 2009-09-30 17:00 | -183
581 | 3 | No | GRB | GRB Initial Operating Capability (IOC) | 2009-06-30 17:00 | Yes | 0% | 2010-02-07 17:00 | -222
583 | 3 | No | GRB | GRB Operational Readiness Date (ORD)/Commissioning | 2009-08-31 17:00 | Yes | 0% | 2010-03-07 17:00 | -188
588 | 2 | Yes | MLI | Moline, IL (MLI) | NA | No | 19% | 2006-02-01 08:00
591 | 3 | No | MLI | MLI Start Site Construction | 2007-05-31 17:00 | Yes | 0% | 2007-10-30 17:00 | -152
593 | 3 | No | MLI | MLI Equipment Delivered to Site | 2008-05-31 17:00 | Yes | 0% | 2008-07-03 17:00 | -33
597 | 3 | No | MLI | MLI CAI/DD250 Signed | 2009-01-31 17:00 | Yes | 0% | 2009-03-31 17:00 | -59
601 | 3 | No | MLI | MLI Initial Operating Capability (IOC) | 2009-04-30 17:00 | Yes | 0% | 2009-07-31 17:00 | -92
603 | 3 | No | MLI | MLI Operational Readiness Date (ORD)/Commissioning | 2009-06-30 17:00 | Yes | 0% | 2009-09-30 17:00 | -92
665 | 2 | Yes | ABE | Allentown, PA (ABE) | NA | No | 56% | 2002-10-22 08:00
677 | 3 | No | ABE | ABE Initial Operating Capability (IOC) | 2009-01-31 17:00 | Yes | 0% | 2009-02-04 17:00 | -4
679 | 3 | No | ABE | ABE Operational Readiness Date (ORD)/Commissioning | 2009-03-31 17:00 | Yes | 0% | 2009-04-06 17:00 | -6
684 | 2 | Yes | PIA | Peoria, IL (PIA) | NA | No | 52% | 2000-05-09 08:00
689 | 3 | No | PIA | PIA Equipment Delivered to Site | 2008-08-30 17:00 | Yes | 0% | 2008-09-10 17:00 | -11
693 | 3 | No | PIA | PIA CAI/DD250 Signed | 2009-04-30 17:00 | Yes | 0% | 2009-12-09 17:00 | -223
697 | 3 | No | PIA | PIA Initial Operating Capability (IOC) | 2009-07-31 17:00 | Yes | 0% | 2010-04-30 17:00 | -273
699 | 3 | No | PIA | PIA Operational Readiness Date (ORD)/Commissioning | 2009-09-30 17:00 | Yes | 0% | 2010-06-30 17:00 | -273