## GOAL <=45 Days from TARGET
MS Project Row ID | Outline Level | Summary Task? | Site Code | Name | Goal (in SPIRE or Waterfall) | Goal Alert (Forecast is 45 days or less before GOAL date) | % Comp | Current Forecast Date | Calendar Days Before (or After if negative) the GOAL in Col F
1 | 1 | Yes |  | ASR-11 Integrated Program Schedule
4 | 2 | No | 000 | Last Operational Readiness Date (ORD) | 2009-09-30 17:00 | Yes | 0% | 2010-03-22 17:00 | -173
184 | 2 | Yes | MCN | Macon, GA (MCN)
195 | 3 | No | MCN | MCN Start Dismantle/Deactivate | 2008-01-31 17:00 | Yes | 0% | 2008-01-16 17:00 | 15
199 | 2 | Yes | MBS | Saginaw, MI (MBS)
212 | 3 | No | MBS | MBS Start Dismantle/Deactivate | 2008-03-31 17:00 | Yes | 0% | 2008-03-31 17:00 | 0
233 | 2 | Yes | MYR | Myrtle Beach, SC (MYR)
246 | 3 | No | MYR | MYR Start Dismantle/Deactivate | 2008-05-31 17:00 | Yes | 0% | 2008-05-31 17:00 | 0
263 | 2 | Yes | BPT | Beaumont, TX (BPT)
273 | 3 | No | BPT | BPT Start Dismantle/Deactivate | 2008-08-31 17:00 | Yes | 0% | 2008-08-31 17:00 | 0
316 | 2 | Yes | LIT | Little Rock, AR (LIT)
329 | 3 | No | LIT | LIT Operational Readiness Date (ORD)/Commissioning | 2008-01-31 17:00 | Yes | 0% | 2008-01-31 17:00 | 0
511 | 2 | Yes | BGM | Binghamton, NY (BGM)
528 | 3 | No | BGM | BGM Start Dismantle/Deactivate | 2010-05-31 17:00 | Yes | 0% | 2010-04-30 17:00 | 31
532 | 2 | Yes | ABE | Allentown, PA (ABE)
549 | 3 | No | ABE | ABE Start Dismantle/Deactivate | 2009-09-30 17:00 | Yes | 0% | 2009-08-30 17:00 | 31
553 | 2 | Yes | FSD | Sioux Falls, SD (FSD)
570 | 3 | No | FSD | FSD Start Dismantle/Deactivate | 2010-06-30 17:00 | Yes | 0% | 2010-05-30 17:00 | 31
658 | 2 | Yes | OGG | Kahului, HI (OGG)
675 | 3 | No | OGG | OGG Start Dismantle/Deactivate | 2009-11-30 17:00 | Yes | 0% | 2009-11-30 17:00 | 0
679 | 2 | Yes | MLI | Moline, IL (MLI)
697 | 3 | No | MLI | MLI Start Dismantle/Deactivate | 2010-01-31 17:00 | Yes | 0% | 2010-06-30 17:00 | -150
701 | 2 | Yes | GRB | Green Bay, WI (GRB)
720 | 3 | No | GRB | GRB Start Dismantle/Deactivate | 2010-08-31 17:00 | Yes | 0% | 2010-07-30 17:00 | 32

## GOAL is Past TARGET Date
MS Project Row ID | Outline Level | Summary Task? | Site Code | Name | Goal (in SPIRE or Waterfall) | Goal Alert (Forecast is 45 days or less before GOAL date) | % Comp | Current Forecast Date | Calendar Days Before (or After if negative) the GOAL in Col F
1 | 1 | Yes |  | ASR-11 Integrated Program Schedule
4 | 2 | No | 000 | Last Operational Readiness Date (ORD) | 2009-09-30 17:00 | Yes | 0 | 2010-03-22 17:00 | -173
679 | 2 | Yes | MLI | Moline, IL (MLI)
697 | 3 | No | MLI | MLI Start Dismantle/Deactivate | 2010-01-31 17:00 | Yes | 0 | 2010-06-30 17:00 | -150

## MILESTONE <=15 Days from TARGET
MS Project Row ID | Outline Level | Summary Task? | Site Code | Name | Deployment Milestone | Milestone Alert (15 d) | % Comp | Current Forecast Date | Calendar Days Before (or After if negative) the MILESTONE in Col F
1 | 1 | Yes |  | ASR-11 Integrated Program Schedule
199 | 2 | Yes | MBS | Saginaw, MI (MBS)
212 | 3 | No | MBS | MBS Start Dismantle/Deactivate | 2008-03-31 17:00 | Yes | 0% | 2008-03-31 17:00 | 0
216 | 2 | Yes | AGS | Augusta, GA (AGS)
229 | 3 | No | AGS | AGS Start Dismantle/Deactivate | 2008-05-31 08:00 | Yes | 0% | 2008-05-31 17:00 | -0.375
233 | 2 | Yes | MYR | Myrtle Beach, SC (MYR)
246 | 3 | No | MYR | MYR Start Dismantle/Deactivate | 2008-05-31 17:00 | Yes | 0% | 2008-05-31 17:00 | 0
250 | 2 | Yes | ANC | Anchorage, AK (ANC)
257 | 3 | No | ANC | ANC Operational Readiness Date (ORD)/Commissioning | 2008-06-30 08:00 | Yes | 0% | 2008-06-30 17:00 | -0.375
259 | 3 | No | ANC | ANC Start Dismantle/Deactivate | 2008-06-30 08:00 | Yes | 0% | 2008-06-30 17:00 | -0.375
263 | 2 | Yes | BPT | Beaumont, TX (BPT)
271 | 3 | No | BPT | BPT Operational Readiness Date (ORD)/Commissioning | 2008-06-30 08:00 | Yes | 0% | 2008-06-30 17:00 | -0.375
273 | 3 | No | BPT | BPT Start Dismantle/Deactivate | 2008-08-31 17:00 | Yes | 0% | 2008-08-31 17:00 | 0
295 | 2 | Yes | YNG | Youngstown, OH (YNG)
308 | 3 | No | YNG | YNG Initial Operating Capability (IOC) | 2008-01-31 08:00 | Yes | 0% | 2008-01-19 17:00 | 11.625
310 | 3 | No | YNG | YNG Operational Readiness Date (ORD)/Commissioning | 2008-02-29 08:00 | Yes | 0% | 2008-02-28 17:00 | 0.625
316 | 2 | Yes | LIT | Little Rock, AR (LIT)
329 | 3 | No | LIT | LIT Operational Readiness Date (ORD)/Commissioning | 2007-11-30 08:00 | Yes | 0% | 2008-01-31 17:00 | -62.375
331 | 3 | No | LIT | LIT Start Dismantle/Deactivate | 2008-04-30 08:00 | Yes | 0% | 2008-04-30 17:00 | -0.375
335 | 2 | Yes | CMI | Champaign, IL (CMI)
345 | 3 | No | CMI | CMI Initial Operating Capability (IOC) | 2008-01-31 08:00 | Yes | 0% | 2008-02-06 17:00 | -6.375
349 | 3 | No | CMI | CMI Start Dismantle/Deactivate | 2008-09-30 08:00 | Yes | 0% | 2008-09-30 17:00 | -0.375
491 | 2 | Yes | GPT | Gulfport, MS (GPT)
498 | 3 | No | GPT | GPT CAI/DD250 Signed | 2008-02-29 08:00 | Yes | 0% | 2008-02-28 17:00 | 0.625
595 | 2 | Yes | BTR | Baton Rouge, LA (BTR)
603 | 3 | No | BTR | BTR CAI/DD250 Signed | 2008-03-31 08:00 | Yes | 0% | 2008-04-01 17:00 | -1.375
637 | 2 | Yes | MLB | Melbourne, FL (MLB)
641 | 3 | No | MLB | MLB Equipment Delivered to Site | 2008-06-30 08:00 | Yes | 0% | 2008-06-30 17:00 | -0.375
701 | 2 | Yes | GRB | Green Bay, WI (GRB)
704 | 3 | No | GRB | GRB Real Estate Acquisition Complete | 2008-02-29 08:00 | Yes | 0% | 2008-02-28 17:00 | 0.625
705 | 3 | No | GRB | GRB Start Site Construction | 2008-03-31 08:00 | Yes | 0% | 2008-03-30 17:00 | 0.625

## MILESTONE is Past TARGET Date
MS Project Row ID | Outline Level | Summary Task? | Site Code | Name | Deployment Milestone | Milestone Alert (15 d) | % Comp | Current Forecast Date | Calendar Days Before (or After if negative) the MILESTONE in Col F
1 | 1 | Yes |  | ASR-11 Integrated Program Schedule
316 | 2 | Yes | LIT | Little Rock, AR (LIT)
329 | 3 | No | LIT | LIT Operational Readiness Date (ORD)/Commissioning | 2007-11-30 08:00 | Yes | 0 | 2008-01-31 17:00 | -62.375
335 | 2 | Yes | CMI | Champaign, IL (CMI)
345 | 3 | No | CMI | CMI Initial Operating Capability (IOC) | 2008-01-31 08:00 | Yes | 0 | 2008-02-06 17:00 | -6.375
595 | 2 | Yes | BTR | Baton Rouge, LA (BTR)
603 | 3 | No | BTR | BTR CAI/DD250 Signed | 2008-03-31 08:00 | Yes | 0 | 2008-04-01 17:00 | -1.375