## LBNL
LBNL Resource Requirements |  |  |  |  | DRAFT 2a
June 6, 2002 rev. June 10
$ in Millions
Project/Activity |  | GSF New Const. | GSF Removed | Net New GSF | Vision/ Goal | TEC | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 |  | Simple Payback * | TEC ($ / gsf) | Const. Cost ($ /gsf ) **
REAL PROPERTY MAINTENANCE
| Real Property Maintenance *** | [5 empty] | 7.53 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255
| % of Replacement Plant Value (RPV) | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
FY 2002 $1.253B total SC and all other inc. EM, Leased and Campus / $1.07B if only SC included.
GENERAL PLANT PROJECTS AND EQUIPMENT
General Plant Projects (GPP):
| Bldg. 6 Second Floor Office and Lab Space (FY 2000 start) |  |  |  | M, O, W | 4.99 | 1.26
| Bldg. 77 142C Clean Room |  |  |  | M, O, W | 1.35 | 1.35
| Bldg. 2 Ventilation Upgrade |  |  |  | E, M, W | 0.6 | 0.35 | 0.15
| Radio Communication System |  |  |  | E, M, O, W | 0.85 | 0.08 | 0.57 | 0.2
| Bldg. 83 Remodel Culture Room (PGPP) |  |  |  | E, M, O, W | 0.2 |  | 0.2
| Bldg. 74 Renovate Animal Area |  |  |  | M, O, W | 0.07 |  | 0.07
| Bldg. 71 Modify Caves L & M and Seismically Upgrade |  |  |  | M, O, W | 1.25 |  | 1.25
| Bldg. 2 Laboratory Upgrade |  |  |  | M, O, W | 0.9 |  | 0.9
| Bldg. 77 Install Sump Pump |  |  |  | M, O, W | 0.035 |  | 0.035
| Bldg. 6 Rm. 2145 Install Ventilation |  |  |  | E, M, O, W | 0.025 |  | 0.025
| Bldg. 90 HVAC System Upgrade |  |  |  | E, M, O, W | 0.77 |  | 0.2 | 0.57
| Bldg. 76 Dust Collection System Upgrade |  |  |  | E, M, W | 0.2 |  | 0.13 | 0.07
| Bldg. 6 Enclose Offices |  |  |  | M, W | 0.35 |  |  | 0.35
| Bldg. 58 Expansion | 500 | 0 | 500 | M, O, W | 0.75 |  |  | 0.75 | [12 empty] | 1500
| Bldg. 50 Rm 2265 Convert to Office Space |  |  |  | M, W | 0.25 |  |  | 0.25
| Bldg. 70A Rm 2245 Convert to Wet Lab |  |  |  | E, M, O, W | 0.5 |  |  | 0.5
| Bldg. 70A Rm 2253 Convert to Cell Culture Lab |  |  |  | M, O, W | 0.25 |  |  | 0.25
| Bldg. 64 Rm 163 Upgrade High Bay Heating |  |  |  | M, O, W | 0.07 |  |  | 0.07
| Bldg. 73 Rm 001 Convert to NMR Lab |  |  |  | M, O, W | 0.375 |  |  | 0.375
| Bldg. 64 Rm 150 Create Lab and Office Space |  |  |  | M, O, W | 1.4 |  |  | 0.9 | 0.6
| Bldg. 70A Superconducting Detector Array Laboratory |  |  |  | E, M, O, W | 2 |  |  | 0.5 | 1.5
| Bldg. 6 Rm 1000 Electrical Power Upgrade |  |  |  | M, O, W | 0.08 |  |  |  | 0.08
| Bldg. 50 - Construct Communication Grid Center |  |  |  | M, O, W | 1.5 |  |  |  | 1.5
| Bldg. 37 Install New Low Conductivity Water Cooling Tower |  |  |  | M, O, W | 1.5 |  |  |  | 1.5
| Bldg. 58A Extension | 1950 | 0 | 1950 | E, M, O, W | 2.95 |  |  |  | 2.95 | [11 empty] | 1500
| Bldg. 10 Improve Staging And Vacuum Assembly Facility |  |  |  | E, M, O, W | 1 |  |  |  | 1
| Bldg. 70 Improve And Expand Existing Vacuum System |  |  |  | E, M, W | 0.214 |  |  |  | 0.214
| Upgrade 2MW Standby Generator Connection to Electrical Distribution System |  |  |  | E, M, O, W | 0.75 |  |  |  | 0.75
| Bldg. 88 Area - Create Parking Lot on Fill Site |  |  |  | M, W | 0.7 |  |  |  | 0.7
| Construct Sensitive Instrument Facility |  |  |  | M, O, W | 3 |  |  |  | 3
| Bldg. 62 Highbay Conversion to Laboratory |  |  |  | M, O, W | 3 |  |  |  | 3
| Construct Isolation Kennel | 400 | 0 | 400 | M, O, W | 0.4 |  |  |  | 0.4 | [11 empty] | 1000
| Blackberry Canyon - Create Fill Site to Expand Parking Lot |  |  |  | M, O, W | 0.5 |  |  |  | 0.5
| Expand Cooling Tower Capacity Lee Road Area |  |  |  | M, O, W | 1.5 |  |  |  |  | 1.5
| Bldg. 71 Highbay Improvements |  |  |  | M, O, W | 3.7 |  |  |  |  | 3.7
| Construct Medium Height Bay Research Bldg. | 10000 | 0 | 10000 | M, O, W | 4.5 |  |  |  |  | 4.5 | [10 empty] | 450
| Upgrade Intersection of Lawrence Road, Glaser Road and Road "S" |  |  |  | E, M, O, W | 0.7 |  |  |  |  | 0.7
| Bldgs. 62/66 - Conversion of Support Space to Wet Lab |  |  |  | E, M, O, W | 2 |  |  |  |  | 2
| Bldg. 50 Office Reconfiguration |  |  |  | M, O, W | 4 |  |  |  |  | 2 | 2
| Realignment of Grizzly Gate Road |  |  |  | E, M, O, W | 3.7 | [5 empty] | 3.7
| Completion of Storm Drain Piping Upgrade |  |  |  | E, M, O | 2.16 | [5 empty] | 2.16
| Construct SNAP Control Room and Support Facilities |  |  |  | M, O, W | 0.8 | [5 empty] | 0.8
| NCEM Addition | 5000 | 0 | 5000 | M, O, W | 4 | [5 empty] | 4 | [9 empty] | 800
| Improve Access Road on West and South sides of Bldg. 70A |  |  |  | E, M, O, W | 1 | [6 empty] | 1
| Upgrade Laboratories in Bldg. 70 |  |  |  | M, O, W | 1.5 | [6 empty] | 1.5
| Upgrade Laboratories in Bldg. 70A |  |  |  | M, O, W | 1.5 | [6 empty] | 1.5
| Bldg. 88 - Upgrade Electrical Systems |  |  |  | E, M, O, W | 1.7 | [6 empty] | 1.7
| Fill Draw to Southwest of Bldg. 70A |  |  |  | M, O, W | 0.8 | [6 empty] | 0.8
| Upgrade of ALS Access - Convert Pathway to Roadway |  |  |  | E, M, O, W | 1.5 | [6 empty] | 1.5
| Construct Parking Area on Fill Site between Operations and Engineering Areas |  |  |  | E, M, O, W | 1 | [6 empty] | 1
| Upgrade Unit Substations |  |  |  | M, O, W | 1.1 | [6 empty] | 0.54 | 0.56
| Realign McMillan Road Intersection at Chamberlain Road |  |  |  | E, M, O, W | 1.2 | [7 empty] | 1.2
| Improve Ventilation in 50/50A |  |  |  | E, M, O, W | 4.8 | [7 empty] | 4.8
| Storm Drain Upgrades |  |  |  | E, M, O, W | 2.5 | [7 empty] | 2.5
| Upgrade Civic Center Assembly Area |  |  |  | M, O, W | 0.5 | [8 empty] | 0.5
| Addition to Cafeteria | 8000 | 0 | 8000 | E, M, O, W | 4.5 | [8 empty] | 4.5 | [6 empty] | 562
| Construct Primary Shuttle Bus Transfer Station in Civic Center |  |  |  | M, O, W | 0.5 | [8 empty] | 0.5
| Widen and Straighten Cyclotron Road at Main Entrance |  |  |  | E, M, O, W | 3.7 | [8 empty] | 3.7
| Complete Office Addition at Bldg. 88 | 4600 | 0 | 4600 | E, M, O, W | 2 | [9 empty] | 2 | [5 empty] | 435
| Bldg. 70 Rm 108 Fumehood Exhaust Fan Upgrade |  |  |  | E, M, O, W | 0.012 | [9 empty] | 0.012
| Bldg. 70 Improve and Expand Vacuum System |  |  |  | M, O, W | 0.214 | [9 empty] | 0.214
| Extend Sanitary Sewer Line between Chicken Creek and Centennial Drive |  |  |  | E, M, O, W | 1.5 | [9 empty] | 1.5
| Road and Utility Corridor Improvements in Chicken Creek |  |  |  | E, M, O, W | 1.5 | [9 empty] | 1.5
| Bldg. 90 - Construct Large Communication Grid Space |  |  |  | M, O, W | 3.1 | [9 empty] | 3.1
| Construct Large Vehicle Wash Facility | 2000 | 0 | 2000 | E, M, O, W | 0.93 | [9 empty] | 0.93 | [5 empty] | 465
| Compressed Air Distribution System Upgrade |  |  |  | M, O, W | 0.18 | [9 empty] | 0.18
| Bldg. 80 Provide Process Cooling Water Backup |  |  |  | M, O, W | 0.025 | [10 empty] | 0.025
| Bldg. 34 Add Chilled Water Expansion Tank |  |  |  | M, O, W | 0.024 | [10 empty] | 0.024
| Bldg. 55 Area Office/Lab Expansion |  |  |  | M, W | 4.9 | [10 empty] | 4.9
| Upgrade Upper East Canyon Egress Roadway |  |  |  | M, O, W | 1.5 | [10 empty] | 1.5
| Bldg. 70 Upgrade Bldg. Exhaust System |  |  |  | E, M, O, W | 2.5 | [10 empty] | 2.5
| Bldg. 70A Upgrade Bldg. Exhaust System |  |  |  | E, M, O, W | 2.8 | [11 empty] | 2.8
| Bldg. 72 Add Two Chilled Water Storage Tanks |  |  |  | M, O, W | 0.017 | [11 empty] | 0.017
| Natural Gas Distribution System Upgrade |  |  |  | E, M, O, W | 1.1 | [11 empty] | 1.1
| Create Corridor Connecting the Main Floors of Bldgs. 66 and 62 |  |  |  | E, M, O, W | 1 | [11 empty] | 1
| Upgrade HVAC System in Bldgs. 50B, 50E and 50F |  |  |  | E, M, O, W | 4.6 | [11 empty] | 4.6
| Bldg. 54 - Upgrade Mechanical Systems |  |  |  | M, O, W | 2.3 | [12 empty] | 2.3
| Low Conductivity Water System Upgrade |  |  |  | E, M, O, W | 4.3 | [12 empty] | 4.3
| Lawrence Road Sightline Improvements |  |  |  | E, M, O, W | 2.8 | [12 empty] | 2.8
| Other GPP Priorities | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.96 | 1.44 | 1.3 | 1.064 | 1.551 | 0.983 | 1.1 | 8.398
| Total GPP: | 32450 | 0 | 32450 |  |  | 3.04 | 3.53 | 4.785 | 17.694 | 14.4 | 12.66 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5
General Plant Equipment (GPE):
| Information Technology: Conferencing and Collaboration Equipment |  |  |  | M, O, W |  |  |  | 0.3 | 0.2 | 0.3 | 0.2 | 0.3 | 0.1 |  | 0.1 |  |  | 0.1
| Information Technology: Digital Libraries and Information Management |  |  |  | M, O, W |  |  |  | 0.2 | 0.2 | 0.2 | 0.1 |  |  | 0.1 |  |  | 0.1
| Information Technology: "Network Smart" Equipment Infrastructure |  |  |  | E, M, O, W |  |  |  | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| Information Technology: Networking Facilities Needs |  |  |  | E, M, O, W |  | 0.8 | 1.1 |  |  | 8 | 8 | 8 | 8 | 8
| Other GPE Priorities | [5 empty] | 1.3 | 0.8 | 11.8 | 9.4 | 2.2 | 2.4 | 2.4 | 2.6 | 3.1 | 11.1 | 11.2 | 11.1 | 11.1
| Total GPE: | [5 empty] | 2.1 | 1.9 | 12.6 | 10.1 | 11 | 11 | 11 | 11 | 11.5 | 11.5 | 11.5 | 11.5 | 11.5
LINE ITEM CONSTRUCTION:
Program Related Projects:
| Molecular Foundry | 94500 | 0 | 94500 | M, O, W | 83.7 |  |  | 83.7 | [12 empty] | 886
| E-Lab | 29000 | 0 | 29000 | E, M, O, W | 19 |  |  |  | 19 | [11 empty] | 655
| Proteomics and Computational Biology Facility | 50000 | 0 | 50000 | E, M, O, W | 45 |  |  |  |  | 45 | [10 empty] | 900
| Femtosecond Structural Dynamics User Facility | TBD |  |  | E, M, O, W | TBD | [5 empty] | TBD
| Center for Atomic, Molecular & Chemical Science | 33000 | 15173 | 17827 | M, O, W | 30 | [5 empty] | 30 | [9 empty] | 909
| Stable Beam Facility | TBD |  |  | M, O, W | TBD | [5 empty] | TBD
| Biosciences Research Bldg. | 50000 | 7533 | 42467 | E, M, O, W | 50 | [6 empty] | 50 | [8 empty] | 1000
| Energy Sciences Bldg. | 30000 |  | 30000 | E, M, O, W | 18 | [7 empty] | 18 | [7 empty] | 600
| Computational Sciences Research Facility | 50000 |  | 50000 | E, M, O, W | 25 | [8 empty] | 25 | [6 empty] | 500
| Accelerator Research Support Bldg. | 25000 | 5168 | 19832 | E, M, O, W | 25 | [9 empty] | 25 | [5 empty] | 1000
| Astrophysics Research Facility | 40000 |  | 40000 | M, O, W | 40 | [10 empty] | 40 |  |  |  |  | 1000
| Earth Sciences Center | 30000 |  | 30000 | E, M, O, W | 20 | [11 empty] | 20 |  |  |  | 667
| Total Programmatic Line Item Projects: | 431500 | 27874 | 403626 |  |  | 0 | 0 | 83.7 | 19 | 45 | 30 | 50 | 18 | 25 | 25 | 40 | 20 | 0
Science Lab Infrastructure (SLI) Projects:
| Bldg. 77 Rehabilitation, Phs. 1 (FY 1999 start) |  |  |  | E, M, O, W | 8 | 1.113
| Sitewide Water Distribution Upgrade, Phase 1 |  |  |  | E, M, O, W | 8.3 | 1 | 4.4 | 2.9
| Bldg. 77 Rehabilitation of Bldg. Structure & Systems, Phs 2 |  |  |  | E, M, O, W | 13.36 |  |  | 13.36
| Research Support Bldg. | 25000 | 15475 | 9525 | M, O, W | 15 |  |  |  | 15 |  |  |  | 0 | 0 | 0 |  |  |  |  | 6.8 | 600
| Bldg. 62 & 74- Upgrade of Bldg. Operating Systems |  |  |  | E, M, O, W | 19.5 |  |  |  |  | 19.5
| User Support Building | 30000 | 21459 | 8541 | E, M, O, W | 20 |  |  |  |  | 20 | [10 empty] | 400
| Operations Bldg. | 25000 | 16975 | 8025 | M, O, W | 15 |  |  |  | 0 |  | 15 | 0 | 0 | 0 | 0 |  |  |  |  | 5.7 | 600
| Engineering Support Facility | 19000 | 0 | 19000 | M, O, W | 15.3 |  |  | 0 | 0 | 0 |  | 15.3 | 0 | 0 | 0 | [5 empty] | 805
| Replace Bldg. 25 (Seismic Stability) | 25000 | 27975 | -2975 | E, M, O, W | 20.2 |  |  | 0 | 0 | 0 |  | 20.2 | 0 | 0 | 0 | [5 empty] | 800
| Environmental, Health and Safety Support Facility | 21000 | 3603 | 17397 | M, O, W | 16.4 |  |  | 0 | 0 | 0 | 0 |  | 16.4 | 0 | 0 | [5 empty] | 781
| Training Center and Auditorium | 14000 | 0 | 14000 | M, O, W | 16 |  |  | 0 | 0 | 0 | 0 | 0 |  | 16 | 0 | [5 empty] | 1100
| Site Support Services Facility | 13000 | 4000 | 9000 | E, M, O, W | 9.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 9.5 | [5 empty] | 731
| Replace Bldg. 73 | 19000 | 4631 | 14369 | E, M, O, W | 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 14 |  |  |  |  | 737
| Rehabilitation of Bldg. 90 Operating Systems |  |  |  | E, M, O, W | 18 | [11 empty] | 18
| Rehabilitation of Bldg. 72 Operating Systems |  |  |  | E, M, O, W | 12 | [12 empty] | 12
| Total SLI Line Item Projects: | 191000 | 94118 | 96882 |  |  | 2.113 | 4.4 | 16.26 | 15 | 39.5 | 15 | 35.5 | 16.4 | 16 | 9.5 | 14 | 18 | 12 |  | 190.9
THIRD PARTY FUNDED BUILDINGS:
| 50X **** | 60000 | 0 | 60000 | M, O, W | TBD
| Total Third Party Projects: | 60000 | 0 | 60000
OPERATING FUNDING NEEDED FOR REMOVAL OF RETIRED FACILITIES:
| Removal of Bldg. 51 Bevatron Complex | 0 | 164000 | -164000 | E, M, O, W | 74.45 |  | 2.5 | 0.95 | 10 | 10 | 10 | 10 | 10 | 10 | 11
| Total Operating Funded Removal of Retired Facilities: | 0 | 164000 | -164000 |  |  |  | 2.5 | 0.95 | 10 | 10 | 10 | 10 | 10 | 10 | 11
Sub-Totals By Category: |  | GSF New Const. | GSF Removed | Net New GSF
Total Change in Gross Square Feet of DOE Assets (GSF): |  | 654950 | 285992 | 368958
Total GPP/GPE/GPF ($M): | [6 empty] | 7.253 | 9.83 | 33.645 | 42.794 | 64.9 | 38.66 | 57 | 37.9 | 38 | 31.5 | 36 | 40 | 34
Total Operating Funding Needed for Removal of Retired Facilities ($M): | [6 empty] | 0 | 2.5 | 0.95 | 10 | 10 | 10 | 10 | 10 | 10 | 11 | 0 | 0 | 0
Total Operating Funding for Real Property Maintenance ($M): | [6 empty] | 7.53 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255 | 7.255
Programmatic Modernization Projects ($M) | [6 empty] | 0 | 0 | 83.7 | 19 | 45 | 30 | 50 | 18 | 25 | 25 | 40 | 20 | 0
Third Party Funding ($M) | [5 empty] | TBD
Information Technology (IT) Needs Crosscut ($M)
| Operating Funds: Networking Facilities Needs (GPE) | [7 empty] | 0.3 | 0.2 | 0.3 | 0.2 | 0.3 | 0.1 |  | 0.1 |  |  | 0.1
| Information Technology: Conferencing and Collaboration Equipment (GPE) | [7 empty] | 0.2 | 0.2 | 0.2 | 0.1 |  |  | 0.1 |  |  | 0.1
| Information Technology: Digital Libraries and Information Management (GPE) | [7 empty] | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
| Information Technology: "Network Smart" Equipment Infrastructure (GPE) | [5 empty] | 0.8 | 1.1 |  |  | 8 | 8 | 8 | 8 | 8
| Total IT: | [5 empty] | 0.8 | 1.1 | 0.8 | 0.7 | 8.8 | 8.6 | 8.6 | 8.4 | 8.4 | 0.4 | 0.3 | 0.4 | 0.4
| KEY to Vision/Goals : E = Environmental Health & Safety |  | Footnotes:
| M = Mission |  | * = Payback has been calculated for both the Operations Bldg. and the Research Support Bldg..
| O = Maintenance & Operations |  | Based on these calculations, we anticipate that other building projects will also have simple paybacks in the 5 to 10 year range
| W = Working Environment |  | **= Construction Cost is being calculated.
***= Per DOE budget definition, these figures do not include grounds, pest control etc. The FY 2001 figure including these activities is 7.97M.
| Note: GSF = Gross Square Feet |  | The FY 2002 - 2013 figures are consistent with the budget forecast submittal of FY 2002, these figures are flat as LBNL is
| TBD = To Be Determined |  | evaluating maintenance activities and SAFA 6 guidelines; it is anticipated that this section of the table will be modified in the 2003 SFP.
| $M = Million Dollars |  | The FIMS RPV figure ( $1.253B in FY 2002 ) is similarly held constant pending conclusion of this evaluation.
| $B = Billion Dollars |  | **** = Request for Qualifications review completed in FY 2002. Request for Proposals to be issued in FY 2002.