## KA00; 165e, 180
NOAA SHIP KA'IMIMOANA
KA-03-04
11 JULY - 8 AUGUST 2003
165E & 180
TAO: GP4-03-KA
| Activity |  | Latitude |  |  | Longitude |  | Deployed | Distance | Speed | Transit | On Sta. | Arrive | Depart | CUMULATIVE |  |  |  |  | SWAP | DEPLOY | LAT | LONG
|  | Deg. | Minutes |  | Deg. | Minutes |  | (mos) | (nmi) | (kts) | (hrs) | (hrs) | Date / Time | Date / Time | (hrs) | (days) | RECOVER | VISIT | REPAIR | OUT | ONLY | CORR | CORR |  |  |  |  | AT SITE | LAST RECOV | DIFFERENCE
| KWAJALEIN ATOLL, REPUBLIC OF MARSHALL ISLANDS | 8 | 43 | N | 167 | 44 | E | [6 empty] | 2003-07-11 14:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 8 | N | 167 | 0 | 0 |  | 0
R | ECOVER/DEPLOY TAUT-NG (Picklefork) & CTD | 8 | 0 | N | 165 | 0 | E | 12.1744 | 167.8577 | 9.5 | 17.6692 | 15 | 2003-07-12 07:40 | 2003-07-12 22:40 | 32.6692 | 1.3612 | 1 | 0 | 0 | 0 | 0 | 1 | -1 | 8 | N | 165 | R | 36352.3196 | 2002-07-06 | 12.1744
| CTD | 7 | 0 | N | 165 | 0 | E |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-13 04:59 | 2003-07-13 05:59 | 39.985 | 1.666 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 7 | N | 165 | 0 | 0 |  | 0
| CTD | 6 | 0 | N | 165 | 0 | E |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-13 12:18 | 2003-07-13 13:18 | 47.3008 | 1.9709 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 6 | N | 165 | 0 | 0 |  | 0
R E | EPAIR, Swap SWR, dump RAM | 5 | 0 | N | 165 | 0 | E | 8.2563 | 60 | 9.5 | 6.3158 | 6 | 2003-07-13 19:37 | 2003-07-14 01:37 | 59.6166 | 2.484 | 0 | 0 | 1 | 0 | 0 | 1 | -1 | 5 | N | 165 | 0 | 36353.8174 | 2002-11-04 | 8.2563
| CTD | 4 | 0 | N | 165 | 0 | E |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-14 07:56 | 2003-07-14 08:56 | 66.9324 | 2.7888 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 4 | N | 165 | 0 | 0 |  | 0
| CTD | 3 | 0 | N | 165 | 0 | E |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-14 15:15 | 2003-07-14 16:15 | 74.2482 | 3.0937 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 3 | N | 165 | 0 | 0 |  | 0
| CTD | 2 | 30 | N | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-14 19:24 | 2003-07-14 20:24 | 78.4061 | 3.2669 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 2 | N | 165 | 0 | 0 |  | 0
R | ECOVER/DEPLOY TAUT-NG (RAD) & CTD | 2 | 0 | N | 165 | 0 | E | 12.1961 | 30 | 9.5 | 3.1579 | 18 | 2003-07-14 23:34 | 2003-07-15 17:34 | 99.564 | 4.1485 | 1 | 0 | 0 | 0 | 0 | 1 | -1 | 2 | N | 165 | R | 36354.9818 | 2002-07-08 | 12.1961
| CTD | 1 | 30 | N | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-15 20:43 | 2003-07-15 21:43 | 103.7219 | 4.3217 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 1 | N | 165 | 0 | 0 |  | 0
| CTD | 1 | 0 | N | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-16 00:53 | 2003-07-16 01:53 | 107.8798 | 4.495 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 1 | N | 165 | 0 | 0 |  | 0
| CTD | 0 | 30 | N | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-16 05:02 | 2003-07-16 06:02 | 112.0377 | 4.6682 | 0 | 0 | 0 | 0 | 0 | 1 | -1 | 0 | N | 165 | 0 | 0 |  | 0
R | DEPLOY TAUT-NG CM (INSERT, FAIRED 0-250m) & CTD | 0 | 0 |  | 165 | 0 | E | 12.2093 | 30 | 9.5 | 3.1579 | 12 | 2003-07-16 09:12 | 2003-07-16 21:12 | 127.1955 | 5.2998 | 1 | 0 | 0 | 0 | 0 | -1 | -1 | 0 |  | 165 | R | 36356.3831 | 2002-07-09 | 12.2093
| SS ADCP (NO RECOVERY) | 0 | 0 |  | 165 | 0 | E |  | 0 | 9.5 | 0 | 0 | 2003-07-16 21:12 | 2003-07-16 21:12 | 127.1955 | 5.2998 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 0 | 0 | 165 | 0 | 0 |  | 0
| CTD | 0 | 30 | S | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-17 00:21 | 2003-07-17 01:21 | 131.3534 | 5.4731 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 0 | S | 165 | 0 | 0 |  | 0
| CTD | 1 | 0 | S | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-17 04:31 | 2003-07-17 05:31 | 135.5113 | 5.6463 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 1 | S | 165 | 0 | 0 |  | 0
| CTD | 1 | 30 | S | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-17 08:40 | 2003-07-17 09:40 | 139.6692 | 5.8196 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 1 | S | 165 | 0 | 0 |  | 0
R E | EPAIR TAUT-NG (Swap anemometer, dump RAM) & CTD | 2 | 0 | S | 165 | 0 | E | 8.3126 | 30 | 9.5 | 3.1579 | 6 | 2003-07-17 12:50 | 2003-07-17 18:50 | 148.8271 | 6.2011 | 0 | 0 | 1 | 0 | 0 | -1 | -1 | 2 | S | 165 | 0 | 36357.5345 | 2002-11-06 | 8.3126
| CTD | 2 | 30 | S | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-17 21:59 | 2003-07-17 22:59 | 152.985 | 6.3744 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 2 | S | 165 | 0 | 0 |  | 0
| CTD | 3 | 0 | S | 165 | 0 | E |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-18 02:09 | 2003-07-18 03:09 | 157.1429 | 6.5476 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 3 | S | 165 | 0 | 0 |  | 0
| CTD | 4 | 0 | S | 165 | 0 | E |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-18 09:28 | 2003-07-18 10:28 | 164.4587 | 6.8524 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 4 | S | 165 | 0 | 0 |  | 0
R E | EPAIR (Swap SWR, dump RAM) TAUT-NG & CTD | 5 | 0 | S | 165 | 0 | E | 8.2852 | 60 | 9.5 | 6.3158 | 6 | 2003-07-18 16:46 | 2003-07-18 22:46 | 176.7745 | 7.3656 | 0 | 0 | 1 | 0 | 0 | -1 | -1 | 5 | S | 165 | 0 | 36358.6989 | 2002-11-08 | 8.2852
| CTD | 6 | 0 | S | 165 | 0 | E |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-19 05:05 | 2003-07-19 06:05 | 184.0903 | 7.6704 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 6 | S | 165 | 0 | 0 |  | 0
| CTD | 7 | 0 | S | 165 | 0 | E |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-19 12:24 | 2003-07-19 13:24 | 191.4061 | 7.9753 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | 7 | S | 165 | 0 | 0 |  | 0
R | ECOVER/DEPLOY TAUT-NG & CTD | 8 | 0 | S | 165 | 0 | E | 12.1909 | 60 | 9.5 | 6.3158 | 18 | 2003-07-19 19:43 | 2003-07-20 13:43 | 215.7219 | 8.9884 | 1 | 0 | 0 | 0 | 0 | -1 | -1 | 8 | S | 165 | R | 36359.8217 | 2002-07-13 | 12.1909
9.5
V | ISIT TAUT-NG & CTD | 8 | 0 | S | 180 | 0 | W | 8.3108 | 891.1916 | 9.5 | 93.8096 | 4 | 2003-07-24 11:32 | 2003-07-24 15:32 | 313.5315 | 13.0638 | 0 | 1 | 0 | 0 | 0 | -1 | 1 | 8 | S | 180 | V | 36364.4805 | 2002-11-13 | 8.3108
| CTD | 7 | 0 | S | 180 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-24 21:51 | 2003-07-24 22:51 | 320.8473 | 13.3686 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 7 | S | 180 | 0 | 0 |  | 0
| CTD | 6 | 0 | S | 180 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-25 05:10 | 2003-07-25 06:10 | 328.1631 | 13.6735 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 6 | S | 180 | 0 | 0 |  | 0
R | ECOVER DEPLOY TAUT-NG & CTD | 5 | 0 | S | 180 | 0 | W | 12.2138 | 60 | 9.5 | 6.3158 | 12 | 2003-07-25 12:29 | 2003-07-26 00:29 | 346.4789 | 14.4366 | 1 | 0 | 0 | 0 | 0 | -1 | 1 | 5 | S | 180 | R | 36365.52 | 2002-07-18 | 12.2138
| CTD | 4 | 0 | S | 180 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-26 06:48 | 2003-07-26 07:48 | 353.7947 | 14.7414 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 4 | S | 180 | 0 | 0 |  | 0
| CTD | 3 | 0 | S | 180 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-26 14:07 | 2003-07-26 15:07 | 361.1105 | 15.0463 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 3 | S | 180 | 0 | 0 |  | 0
| CTD | 2 | 30 | S | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-26 18:16 | 2003-07-26 19:16 | 365.2683 | 15.2195 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | S | 180 | 0 | 0 |  | 0
V | ISIT TAUT-NG, & CTD | 2 | 0 | S | 180 | 0 | W | 8.3257 | 30 | 9.5 | 3.1579 | 4 | 2003-07-26 22:26 | 2003-07-27 02:26 | 372.4262 | 15.5178 | 0 | 1 | 0 | 0 | 0 | -1 | 1 | 2 | S | 180 | V | 36366.9344 | 2002-11-15 | 8.3257
| CTD | 1 | 30 | S | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-27 05:35 | 2003-07-27 06:35 | 376.5841 | 15.691 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 180 | 0 | 0 |  | 0
| CTD | 1 | 0 | S | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-27 09:45 | 2003-07-27 10:45 | 380.742 | 15.8643 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 180 | 0 | 0 |  | 0
| CTD | 0 | 30 | S | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-27 13:54 | 2003-07-27 14:54 | 384.8999 | 16.0375 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | S | 180 | 0 | 0 |  | 0
V | ISIT TAUT-NG & CTD | 0 | 0 |  | 180 | 0 | W | 8.3198 | 30 | 9.5 | 3.1579 | 4 | 2003-07-27 18:03 | 2003-07-27 22:03 | 392.0578 | 16.3357 | 0 | 1 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 180 | V | 36367.7524 | 2002-11-16 | 8.3198
| CTD | 0 | 30 | N | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-28 01:13 | 2003-07-28 02:13 | 396.2157 | 16.509 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | N | 180 | 0 | 0 |  | 0
| CTD | 1 | 0 | N | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-28 05:22 | 2003-07-28 06:22 | 400.3736 | 16.6822 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 180 | 0 | 0 |  | 0
| CTD | 1 | 30 | N | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-28 09:32 | 2003-07-28 10:32 | 404.5315 | 16.8555 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 180 | 0 | 0 |  | 0
R | ECOVER/DEPLY TAUT-NG, CTD | 2 | 0 | N | 180 | 0 | W | 12.2154 | 30 | 9.5 | 3.1579 | 12 | 2003-07-28 13:41 | 2003-07-29 01:41 | 419.6894 | 17.4871 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 180 | R | 36368.5704 | 2002-07-21 | 12.2154
| CTD | 2 | 30 | N | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-29 04:51 | 2003-07-29 05:51 | 423.8473 | 17.6603 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 180 | 0 | 0 |  | 0
| CTD | 3 | 0 | N | 180 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-07-29 09:00 | 2003-07-29 10:00 | 428.0052 | 17.8335 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | N | 180 | 0 | 0 |  | 0
| CTD | 4 | 0 | N | 180 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-29 16:19 | 2003-07-29 17:19 | 435.321 | 18.1384 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | N | 180 | 0 | 0 |  | 0
R | ECOVER/DEPLOY, CTD | 5 | 0 | N | 180 | 0 | W | 12.229 | 60 | 9.5 | 6.3158 | 18 | 2003-07-29 23:38 | 2003-07-30 17:38 | 459.6368 | 19.1515 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 5 | N | 180 | R | 36369.9849 | 2002-07-22 | 12.229
| CTD | 6 | 0 | N | 180 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-30 23:57 | 2003-07-31 00:57 | 466.9526 | 19.4564 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6 | N | 180 | 0 | 0 |  | 0
| CTD | 7 | 0 | N | 180 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-07-31 07:16 | 2003-07-31 08:16 | 474.2683 | 19.7612 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | N | 180 | 0 | 0 |  | 0
R | ECOVER/DEPLOY TAUT-NG, CTD | 8 | 0 | N | 180 | 0 | W | 12.9052 | 60 | 9.5 | 6.3158 | 12 | 2003-07-31 14:35 | 2003-08-01 02:35 | 492.5841 | 20.5243 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 8 | N | 180 | R | 36371.6077 | 2002-07-03 | 12.9052
| NMFS BIGEYE MOORING DEPLOY | 20 | 36 | N | 161 | 24.2 | W |  | 1316.9311 | 9.5 | 138.6243 | 19 | 2003-08-06 21:13 | 2003-08-07 16:13 | 650.2085 | 27.092 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 20 | N | 161 | 0 | 0 | 1999-12-12 | -1148.9836
| HONOLULU, OAHU | 21 | 18 | N | 157 | 52 | W |  | 202.5682 | 9.5 | 21.323 |  | 2003-08-08 13:32 |  | 671.5314 | 27.9805 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 21 | N | 157 | 0 | 0 |  | 0
[17 empty] | 8 | 3 | 3 | 0 | 0
RECOVER TAUT-NEXGEN = |  | 7 | [6 empty] | Transit | On Sta
DEPLOY TAUT-NEXGEN = |  | 8 | [6 empty] | hrs | hrs
|  |  |  | Nautical Miles |  |  |  |  | 473.5314 | 198
DEPLOY BIGEYE TAUTLINE SURFACE MOORING = |  | 1 |  | Kwaj - 8N/165E = |  |  | 167.8577 | [5 empty] | 165E: DAS = | 8.2522
|  |  |  | 165E - 180W = |  |  | 2811.1916 | [5 empty] | 180W: DAS = | 8.6272
REPAIR (BUOY RIDE) TAUT-NEXGEN = |  | 3 |  | 8N/180W - Hono = |  |  | 1519.4993 | [5 empty] | TRANSIT: DAS = | 12.1011
DEPLOY SUBSURFACE ADCP (NO SS ADCP RECOVERY) = |  | 0 |  | Total Distance (nmi) = |  |  | 4498.5486 | [5 empty] | TOTAL: DAS = | 28.9805
VISIT STD ATLAS (3) & TAUT-NEXGEN (1) = |  | 3 |  | ** ALL TIMES ARE HAWAIIAN STANDARD TIME (HST). NOT ADJUSTED FOR DATELINE CROSSING **
6-HOURS ON STATION TIME: ADDED FOR 4-CTD's BETWEEN 9N-12N ALONG TRANSIT TO HONOLULU
Formulas:
Arrive = [Depart, row above]+[Transit]/24
Arrive = O34+[Transit]/24
Depart = [Arrive]+[On Sta.]/24