## ProposalSummary
Experiment Number | Name | Rating | #Shifts allocated | # Shifts scheduled | Difference | Comments | Shifts Requested | Impossible Dates
2476R | Yang | 1.96 | 6 | 6 | 0 |  | 6 | April ideal, not before April, not > June 15
2688R | Daraio | 1.98 | 12 | 12 | 0 |  | 15
2911 | Gruber | 2.03 | 15 | 15 | 0 |  | 15 | January 15 - February 8, Febrary 15 - February 19, After April 4
2666R | Johnson | 2.07 | 15 | 15 | 0 |  | 15
2542R | Lau | 2.15 | 15 | 14 | 1 |  | 15 | not before June
2870 | Chen | 2.27 | 15 | 15 | 0 |  | 15
2725R | Sciau | 2.28 | 18 | 17 | 1 |  | 18 | 12/02, du 21/02 au 07/03, du 16 au 27/03 et du 4 au 7/05
2626R | Baerlocher | 2.33 | 21 | 20 | 1 |  | 21 | before mid April
3001 | Hanan | 2.36 | 18 | 18 | 0 |  | 18 | June
2387R | Zhang | 2.38 | 12 | 12 | 0 |  | 12 | as late as possible
2955 | Koo | 2.4 | 15 | 15 | 0 |  | 15 | before April
2286R | Spiecker | 2.48 | 15 | 14 | 1 |  | 16 | CAN: 8. März - 14. März / 26. März - 2. April / 26. Juli - 31. Juli
2306R | Wan | 2.59 | 15 | 15 | 0 |  | 15 | Not before May
2894 | Perroud | 2.6 | 15 | 15 | 0 |  | 15
2684R | Courtin-Nomade | 2.65 | 15 | 15 | 0 |  | 15 | Not early in the year. March 15 - April 15
2895 | Courtin-Nomade | 2.68 | 30 | 29 | 1 |  | 30 | Before March 20, April 20 - April 26
2385R | Chen | 2.74 | 15 | 15 | 0 |  | 15
2384R | Chen | 2.94 | 15 | 15 | 0 |  | 15
Total |  |  | 282 | 277 | 5 | Total requested | 286
Commissioning 5 % |  |  | 18 | 21 | -3
In house Research 10% |  |  | 35 | 34 | 1 | Oversubscription factor | 1.0142
Directors Discretion 5 % |  |  | 17 | 18 | -1
Total number of 1.9 GeV Shifts available: |  |  | 350 | 350 | 2
0

## For Distribution
10/26//2008
ALS-12.3.2
January 2009 - June 2009 Final
[33 empty] | Shifts |  | shifts
2009-01-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 46 |  |  | January
| Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | AP/MS | 6
0000-0800 | H | IT | I | I | I | I | I | I | I | S/T | S/T | AP | S.O. | [5 empty] | H | S/T | MS | Chen 2870 |  |  |  |  | S.O. | Hanan 3001 |  |  |  | M/I/IT | 23
0800-1600 | Th: H; F: M; S: I; Su: I; M: I; T: I; W: I; Th: I; F: S/T; S: S/T; Su: S/T; M: AP; T: Comm; F: IHR; M: H; T: AP; M: M | S/T,I/S/T,BLC | 10
1600-2400 | Th: H; F: I; S: I; Su: I; M: I; T: I; W: I; Th: I; F: S/T; S: S/T; Su: S/T; M: AP; M: H; T: AP; M: S/T | Hol/X | 6
[32 empty] | Spec. Ops. | 2
[32 empty] | Total NonU | 47 |  | 93
2009-02-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 |  |  |  | 1.9 GeV User/U7 | 62 |  |  | February
| Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S |  |  |  | AP/MS | 9
0000-0800 | Su: 3001; T: AP; Th: Perroud 2894; T: I; W: S.O.; Th: IHR; M: H; T: IT; W: MS; Th: Daraio 2688; M: AP; T: S.O.; Th: Courtin-Nomade 2684 |  |  |  | M/I/IT | 6
0800-1600 | M: AP; T: Comm; M: M; T: I; M: H; T: AP; Su: AP; M: M; T: DD |  |  |  | S/T,I/S/T,BLC | 2
1600-2400 | M: AP; M: I; T: S/T; M: H; T: AP; Su: AP; M: S/T |  |  |  | Hol/X | 3
[32 empty] | Spec. Ops. | 2
[32 empty] | Total NonU | 22 |  | 84
2009-03-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 69 |  |  | March
| Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | AP/MS | 12
0000-0800 | Su: 2684; T: AP; W: 2-bunch; T: MS; W: 2-bunch; M: IT; T: I; W: S.O.; T: AP; M: AP; T: S.O. | M/I/IT | 7
0800-1600 | M: AP; T: M; M: AP; M: M; T: I; W: Comm; F: Gruber 2911; M: AP; T: 2911; Th: Spiecker 2286; Su: AP; M: M | S/T,I/S/T,BLC | 3
1600-2400 | M: AP; T: S/T; M: AP; M: I; T: S/T; M: AP; Su: AP; M: S/T | 2-bunch | 0
[32 empty] | Spec. Ops. | 2
[32 empty] | Total NonU | 24 |  | 93
2009-04-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | User/U7 | 70 |  |  | April
| W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | Tu | W | Th |  | AP/MS | 9
0000-0800 | W: S.O.; F: IHR; T: MS; W: Sciau 2725; M: IT; T: I; W: S.O.; Th: Koo 2955; T: AP; W: Johnson 2666; M: AP; Tu: S.O. |  | M/I/IT | 6
0800-1600 | M: AP; M: M; T: I; M: AP; Su: AP; M: M; Tu: Yang 2476; Th: DD |  | S/T,I/S/T,BLC | 2
1600-2400 | M: AP; M: I; T: S/T; M: AP; Su: AP; M: S/T |  | Hol/X | 0
[32 empty] | Spec. Ops. | 3
[32 empty] | Total NonU | 20 |  | 90
2009-05-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 71 |  |  | May
| F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | AP/MS | 9
0000-0800 | F: Directors Discretion; T: MS; Th: Chen 2384; T: I; W: S.O.; Th: Courtin-Nomade 2895; T: AP; W: Courtin-Nomade 2895; Su: AP; M: H; T: IT; W: S.O.; Th: Wan 2306 | M/I/IT | 6
0800-1600 | M: AP; T: Comm; M: M; T: I; M: AP; Su: AP; M: H; T: M | S/T,I/S/T,BLC | 2
1600-2400 | M: AP; M: I; T: S/T; M: AP; Su: AP; M: H; T: S/T | Hol/X | 3
[32 empty] | Spec. Ops. | 2
[32 empty] | Total NonU | 22 |  | 93
2009-06-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | User/U7 | 65 |  |  | June
| M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T |  | AP/MS | 12
0000-0800 | T: MS; W: DD; Th: Lau 2542; M: IT; T: SS; W: I; Th: S.O.; F: Zhang 2387; T: AP; W: Chen 2385; M: AP; T: S.O.; W: Baerlocher 2626; T: MS |  | M/I/IT | 6
0800-1600 | M: AP; T: DD; M: SS; T: M; W: I; M: AP; Su: AP; M: M; M: AP |  | S/T,I/S/T,BLC | 2
1600-2400 | M: AP; T: DD; M: SS; T: I; W: S/T; M: AP; Su: AP; M: S/T; M: AP |  | Hol/X | 0
[32 empty] | Spec. Ops. | 5
July is draft only | [31 empty] | Total NonU | 25 |  | 90
2009-07-01 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | Tu | W | Th | F
0000-0800 | F: H; S: X; Su: X; M: IT; T: I; T: AP; M: AP; Tu: MS
0800-1600 | F: H; S: X; Su: X; M: M; T: I; M: AP; Su: AP; M: M; M: AP
1600-2400 | Th: U7; F: H; S: X; Su: X; M: I; T: S/T; M: AP; Su: AP; M: S/T; M: AP
Previous
[32 empty] | Jan 2009 - June 2009 cycle |  |  |  |  | cycle
| Th: User Operations; M: U7; T: User Operations (7 hr shift); Th: Jan 2009 - June 2009 cycle; Su: Jul-Dec 08; W: Jan-June 08 | A.P. Off-Shifts |  | 0 |  | 0% | 52.6%
| Th: Total calendar shifts =; W: 543; Su: 552 shifts; W: 546 shifts | User Off-Shifts |  | 0 |  | 0% | 55.6%
|  | Special ops & scrubbing | [5 empty] | SS | Safety Standdown | [6 empty] | Total user shifts | [5 empty] | 383 |  | 70.53% |  | 54.7% |  |  | 61%
| Th: Special operations; W: 16; F: 2.947%; Su: 1.6%; W: 1.8% | Distribution:
| W: S/T; Th: Startup & Tune; M: M; T: Maintenance; F: IT; S: Interlock Tests; Th: Maint./inst./int. (M/I/IT); W: 54; F: 9.945%; Su: 21%; W: 19% | PX Group Leader
| Th: Acc physics and MS; W: 57; F: 10.5%; Su: 6.9%; W: 8.4% | CXRO Group leader
| W: AP; Th: Accelerator Physics; M: H; T: Holiday; F: I/S/T; S: Injection Startup; Th: Startup and Tune; W: 21; F: 3.867%; Su: 7.1%; W: 8.1% | Scientific Support Group Leader
| Th: Holiday/Off; W: 12; F: 2.21%; Su: 8.7%; W: 1.6% | Experimental Systems Group Leader
| W: MS; Th: Machine Setup; M: BLC; T: Beamline Commissioning | Accelerator Physics Group Leader
| Th: Jan 2009 - June 2009 cycle; Su: Jul-Dec 08; W: Jan-June 08 | Operations Manager
| W: X; Th: Off; Su: Note: All running is at 1.9 GeV; Th: 1.9 GeV shifts =; W: 351; F: 91.64%; Su: 91.7%; W: 89.5% | Division Deputy Director
[5 empty] | multibunch unless outherwise noted. | [10 empty] | 2-bunch shifts = | [5 empty] | 33 |  | 8.616% |  | 8.3% |  |  | 10.5%
| I | Installation |  |  | JULY is draft only.

## Jan 2009-June2009
10/26//2008
ALS-12.3.2
January 2009 - June 2009 1st Draft
[33 empty] | Shifts |  | shifts
2009-01-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 46 |  |  | January
| Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | AP/MS | 6
0000-0800 | H | IT | I | I | I | I | I | I | I | S/T | S/T | AP | S.O. | Comm | Comm | Comm | IHR | IHR | H | S/T | MS | 2870 | 2870 | 2870 | 2870 | 2870 | S.O. | 3001 | 3001 | 3001 | 3001 | M/I/IT | 23
0800-1600 | H | M | I | I | I | I | I | I | S/T | S/T | S/T | AP | Comm | Comm | Comm | IHR | IHR | IHR | H | AP | 2870 | 2870 | 2870 | 2870 | 2870 | M | 3001 | 3001 | 3001 | 3001 | 3001 | S/T,I/S/T,BLC | 10
1600-2400 | H | I | I | I | I | I | I | I | S/T | S/T | S/T | AP | Comm | Comm | Comm | IHR | IHR | IHR | H | AP | 2870 | 2870 | 2870 | 2870 | 2870 | S/T | 3001 | 3001 | 3001 | 3001 | 3001 | Hol/X | 6
[32 empty] | Spec. Ops. | 2
[32 empty] | Total NonU | 47 |  | 93
2009-02-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 |  |  |  | 1.9 GeV User/U7 | 62 |  |  | February
| Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S |  |  |  | AP/MS | 9
0000-0800 | 3001 | 3001 | AP | Comm | 2894 | 2894 | 2894 | 2894 | 2894 | I | S.O. | IHR | IHR | IHR | IHR | H | IT | MS | 2688 | 2688 | 2688 | 2688 | AP | S.O. | DD | 2684 | 2684 | 2684 |  |  |  | M/I/IT | 6
0800-1600 | 3001 | AP | Comm | 2894 | 2894 | 2894 | 2894 | 2894 | M | I | IHR | IHR | IHR | IHR | IHR | H | AP | 2688 | 2688 | 2688 | 2688 | AP | M | DD | 2684 | 2684 | 2684 | 2684 |  |  |  | S/T,I/S/T,BLC | 2
1600-2400 | 3001 | AP | Comm | 2894 | 2894 | 2894 | 2894 | 2894 | I | S/T | IHR | IHR | IHR | IHR | IHR | H | AP | 2688 | 2688 | 2688 | 2688 | AP | S/T | DD | 2684 | 2684 | 2684 | 2684 |  |  |  | Hol/X | 3
[32 empty] | Spec. Ops. | 2
[32 empty] | Total NonU | 22 |  | 84
2009-03-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 36 |  |  | March
| Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | AP/MS | 12
0000-0800 | 2684 | 2684 | AP | 2-b | 2-b | 2-b | 2-b | 2-b | 2-b | MS | 2-b | 2-b | 2-b | 2-b | 2-b | IT | I | S.O. | Comm | Comm | 2911 | 2911 | 2911 | AP | 2911 | 2911 | 2286R | 2286R | 2286R | AP | S.O. | M/I/IT | 7
0800-1600 | 2684 | AP | M | 2-b | 2-b | 2-b | 2-b | 2-b | AP | 2-b | 2-b | 2-b | 2-b | 2-b | 2-b | M | I | Comm | Comm | 2911 | 2911 | 2911 | AP | 2911 | 2911 | 2286R | 2286R | 2286R | AP | M | 2286R | S/T,I/S/T,BLC | 3
1600-2400 | 2684 | AP | S/T | 2-b | 2-b | 2-b | 2-b | 2-b | AP | 2-b | 2-b | 2-b | 2-b | 2-b | 2-b | I | S/T | Comm | Comm | 2911 | 2911 | 2911 | AP | 2911 | 2911 | 2286R | 2286R | 2286R | AP | S/T | 2286R | 2-bunch | 33
[32 empty] | Spec. Ops. | 2
[32 empty] | Total NonU | 57 |  | 93
2009-04-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | User/U7 | 70 |  |  | April
| W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | Tu | W | Th |  | AP/MS | 9
0000-0800 | S.O. | 2286R | IHR | IHR | IHR | IHR | MS | 2725 | 2725 | 2725 | 2725 | 2725 | IT | I | S.O. | 2955 | 2955 | 2955 | 2955 | 2955 | AP | 2666 | 2666 | 2666 | 2666 | 2666 | AP | S.O. | 2476 | 2476 |  | M/I/IT | 6
0800-1600 | 2286R | IHR | IHR | IHR | IHR | AP | 2725 | 2725 | 2725 | 2725 | 2725 | 2725 | M | I | 2955 | 2955 | 2955 | 2955 | 2955 | AP | 2666 | 2666 | 2666 | 2666 | 2666 | AP | M | 2476 | 2476 | DD |  | S/T,I/S/T,BLC | 2
1600-2400 | 2286R | IHR | IHR | IHR | IHR | AP | 2725 | 2725 | 2725 | 2725 | 2725 | 2725 | I | S/T | 2955 | 2955 | 2955 | 2955 | 2955 | AP | 2666 | 2666 | 2666 | 2666 | 2666 | AP | S/T | 2476 | 2476 | DD |  | Hol/X | 0
[32 empty] | Spec. Ops. | 3
[32 empty] | Total NonU | 20 |  | 90
2009-05-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 71 |  |  | May
| F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | AP/MS | 9
0000-0800 | DD | DD | DD | DD | MS | Comm | 2384 | 2384 | 2384 | 2384 | 2384 | I | S.O. | 2895 | 2895 | 2895 | 2895 | 2895 | AP | 2895 | 2895 | 2895 | 2895 | AP | H | IT | S.O. | 2306 | 2306 | 2306 | 2306 | M/I/IT | 6
0800-1600 | DD | DD | DD | AP | Comm | 2384 | 2384 | 2384 | 2384 | 2384 | M | I | 2895 | 2895 | 2895 | 2895 | 2895 | AP | 2895 | 2895 | 2895 | 2895 | 2895 | AP | H | M | 2306 | 2306 | 2306 | 2306 | 2306 | S/T,I/S/T,BLC | 2
1600-2400 | DD | DD | DD | AP | Comm | 2384 | 2384 | 2384 | 2384 | 2384 | I | S/T | 2895 | 2895 | 2895 | 2895 | 2895 | AP | 2895 | 2895 | 2895 | 2895 | 2895 | AP | H | S/T | 2306 | 2306 | 2306 | 2306 | 2306 | Hol/X | 3
[32 empty] | Spec. Ops. | 2
[32 empty] | Total NonU | 22 |  | 93
2009-06-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | User/U7 | 65 |  |  | June
| M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T |  | AP/MS | 12
0000-0800 | 2306 | MS | DD | 2542 | 2542 | 2542 | 2542 | IT | SS | I | S.O. | 2387 | 2387 | 2387 | 2387 | AP | 2385 | 2385 | 2385 | 2385 | 2385 | AP | S.O. | 2626 | 2626 | 2626 | 2626 | 2626 | 2626 | MS |  | M/I/IT | 6
0800-1600 | AP | DD | 2542 | 2542 | 2542 | 2542 | 2542 | SS | M | I | 2387 | 2387 | 2387 | 2387 | AP | 2385 | 2385 | 2385 | 2385 | 2385 | AP | M | 2626 | 2626 | 2626 | 2626 | 2626 | 2626 | AP | 2626 |  | S/T,I/S/T,BLC | 2
1600-2400 | AP | DD | 2542 | 2542 | 2542 | 2542 | 2542 | SS | I | S/T | 2387 | 2387 | 2387 | 2387 | AP | 2385 | 2385 | 2385 | 2385 | 2385 | AP | S/T | 2626 | 2626 | 2626 | 2626 | 2626 | 2626 | AP | 2626 |  | Hol/X | 0
[32 empty] | Spec. Ops. | 5
July is draft only | [31 empty] | Total NonU | 25 |  | 90
2009-07-01 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | Tu | W | Th | F
0000-0800 | W: 2626; F: H; S: X; Su: X; M: IT; T: I; T: AP; M: AP; Tu: MS
0800-1600 | F: H; S: X; Su: X; M: M; T: I; M: AP; Su: AP; M: M; M: AP
1600-2400 | Th: U7; F: H; S: X; Su: X; M: I; T: S/T; M: AP; Su: AP; M: S/T; M: AP
Previous
[32 empty] | Jan 2009 - June 2009 cycle |  |  |  |  | cycle
| Th: User Operations; M: U7; T: User Operations (7 hr shift); Th: Jan 2009 - June 2009 cycle; Su: Jul-Dec 08; W: Jan-June 08 | A.P. Off-Shifts |  | 0 |  | 0% | 52.6%
| Th: Total calendar shifts =; W: 543; Su: 552 shifts; W: 546 shifts | User Off-Shifts |  | 0 |  | 0% | 55.6%
|  | Special ops & scrubbing | [5 empty] | SS | Safety Standdown | [6 empty] | Total user shifts | [5 empty] | 350 |  | 64.46% |  | 54.7% |  |  | 61%
| Th: Special operations; W: 16; F: 2.947%; Su: 1.6%; W: 1.8% | Distribution:
| W: S/T; Th: Startup & Tune; M: M; T: Maintenance; F: IT; S: Interlock Tests; Th: Maint./inst./int. (M/I/IT); W: 54; F: 9.945%; Su: 21%; W: 19% | PX Group Leader
| Th: Acc physics and MS; W: 57; F: 10.5%; Su: 6.9%; W: 8.4% | CXRO Group leader
| W: AP; Th: Accelerator Physics; M: H; T: Holiday; F: I/S/T; S: Injection Startup; Th: Startup and Tune; W: 21; F: 3.867%; Su: 7.1%; W: 8.1% | Scientific Support Group Leader
| Th: Holiday/Off; W: 12; F: 2.21%; Su: 8.7%; W: 1.6% | Experimental Systems Group Leader
| W: MS; Th: Machine Setup; M: BLC; T: Beamline Commissioning | Accelerator Physics Group Leader
| Th: Jan 2009 - June 2009 cycle; Su: Jul-Dec 08; W: Jan-June 08 | Operations Manager
| W: X; Th: Off; Su: Note: All running is at 1.9 GeV; Th: 1.9 GeV shifts =; W: 351; F: 100.3%; Su: 91.7%; W: 89.5% | Division Deputy Director
[5 empty] | multibunch unless outherwise noted. | [10 empty] | 2-bunch shifts = | [5 empty] | 33 |  | 9.429% |  | 8.3% |  |  | 10.5%
| I | Installation |  |  | JULY is draft only.

## BackupSChedule
10/26//2008
ALS-12.3.2
January 2009 - June 2009 1st Draft
[33 empty] | Shifts |  | shifts | U.O.S.* | A.O.S.*
2009-01-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 65
| Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | AP/MS | 9
0000-0800 | Th: H; F: IT; S: I; Su: I; M: I; T: I; W: I; Th: I; F: I; S: S/T; Su: S/T; M: AP; M: H; T: S/T; W: MS | M/I/IT | 6
0800-1600 | Th: H; F: M; S: I; Su: I; M: I; T: I; W: I; Th: I; F: S/T; S: S/T; Su: S/T; M: AP; M: H; T: AP; M: M | S/T,I/S/T,BLC | 2
1600-2400 | Th: H; F: I; S: I; Su: I; M: I; T: I; W: I; Th: I; F: S/T; S: S/T; Su: S/T; M: AP; Su: U7; M: H; T: AP; M: S/T | Hol/X | 9
[32 empty] | Spec. Ops. | 2
[35 empty] | 93 | 35 | 3
2009-02-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 |  |  |  | 1.9 GeV User/U7 | 50
| Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S |  |  |  | AP/MS | 7
0000-0800 | T: AP; T: I; M: H; T: IT; W: MS; M: AP |  |  |  | M/I/IT | 6
0800-1600 | M: AP; M: M; T: I; M: H; T: AP; Su: AP; M: M |  |  |  | S/T,I/S/T,BLC | 2
1600-2400 | M: AP; M: I; T: S/T; Su: U7; M: H; T: AP; Su: AP; M: S/T |  |  |  | 2-bunch | 27
[32 empty] | Spec. Ops. | 1
[35 empty] | 93 | 43 | 7
2009-03-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 0
| Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | AP/MS | 0
0000-0800 | T: AP; T: MS; M: IT; T: I; T: AP; M: AP | M/I/IT | 87
0800-1600 | M: AP; T: M; Th: 2 bunch; M: AP; F: 2 bunch; M: M; T: I; M: AP; Su: AP; M: M | S/T,I/S/T,BLC | 0
1600-2400 | M: AP; T: S/T; M: AP; M: I; T: S/T; M: AP; Su: AP; M: S/T | Hol/X | 3
[32 empty] | Spec. Ops. | 0
[35 empty] | 90 | 0 | 0
2009-04-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | User/U7 | 50
| W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | Tu | W | Th |  | AP/MS | 5
0000-0800 | T: MS; M: IT; T: I; T: AP; M: AP |  | M/I/IT | 5
0800-1600 | M: AP; M: M; T: I; M: AP; Su: AP; M: M |  | S/T,I/S/T,BLC | 31
1600-2400 | M: AP; M: I; T: S/T; M: AP; Su: AP; M: S/T |  | Hol/X | 0
[32 empty] | Spec. Ops. | 2
[35 empty] | 93 | 28 | 3
2009-05-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | User/U7 | 57
| F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | AP/MS | 11
0000-0800 | T: MS; T: I; T: AP; Su: AP; M: H; T: IT | M/I/IT | 6
0800-1600 | M: AP; M: M; T: I; M: AP; Su: AP; M: H; T: M | S/T,I/S/T,BLC | 2
1600-2400 | M: AP; M: I; T: S/T; M: AP; Su: AP; M: H; T: S/T | Hol/X | 12
[32 empty] | Spec. Ops. | 2
[35 empty] | 90 | 33 | 7
2009-06-03 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | User/U7 | 53
| M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T |  | AP/MS | 6
0000-0800 | T: MS; M: IT; T: SS; W: I; T: AP; M: AP; T: MS |  | M/I/IT | 6
0800-1600 | M: AP; M: SS; T: M; W: I; M: AP; Su: AP; M: M; M: AP |  | S/T,I/S/T,BLC | 2
1600-2400 | M: AP; M: SS; T: I; W: S/T; M: AP; Su: AP; M: S/T; M: AP |  | Hol/X | 24
[32 empty] | Spec. Ops. | 2
July is draft only | [34 empty] | 93 | 29 | 4
2009-07-01 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
| W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | Tu | W | Th | F
0000-0800 | F: H; S: X; Su: X; M: IT; T: I; T: AP; M: AP; Tu: MS
0800-1600 | F: H; S: X; Su: X; M: M; T: I; M: AP; Su: AP; M: M; M: AP
1600-2400 | Th: U7; F: H; S: X; Su: X; M: I; T: S/T; M: AP; Su: AP; M: S/T; M: AP
Previous
[32 empty] | Jan 2009 - June 2009 cycle |  |  |  |  | cycle
| Th: User Operations; M: U7; T: User Operations (7 hr shift); Th: Jan 2009 - June 2009 cycle; Su: Jul-Dec 08; W: Jan-June 08 | A.P. Off-Shifts |  | 24 |  | 63.16% | 52.6%
| Th: Total calendar shifts =; W: 543; Su: 552 shifts; W: 546 shifts | User Off-Shifts |  | 168 |  | 61.09% | 55.6%
|  | Special ops & scrubbing | [5 empty] | SS | Safety Standdown | [6 empty] | Total user shifts | [5 empty] | 275 |  | 50.64% |  | 54.7% |  |  | 61%
| Th: Special operations; W: 9; F: 1.657%; Su: 1.6%; W: 1.8% | Distribution:
| W: S/T; Th: Startup & Tune; M: M; T: Maintenance; F: IT; S: Interlock Tests; Th: Maint./inst./int. (M/I/IT); W: 116; F: 21.36%; Su: 21%; W: 19% | PX Group Leader
| Th: Acc physics and MS; W: 38; F: 6.998%; Su: 6.9%; W: 8.4% | CXRO Group leader
| W: AP; Th: Accelerator Physics; M: H; T: Holiday; F: I/S/T; S: Injection Startup; Th: Startup and Tune; W: 39; F: 7.182%; Su: 7.1%; W: 8.1% | Scientific Support Group Leader
| Th: Holiday/Off; W: 75; F: 13.81%; Su: 8.7%; W: 1.6% | Experimental Systems Group Leader
| W: MS; Th: Machine Setup; M: BLC; T: Beamline Commissioning | Accelerator Physics Group Leader
| Th: Jan 2009 - June 2009 cycle; Su: Jul-Dec 08; W: Jan-June 08 | Operations Manager
| W: X; Th: Off; Su: Note: All running is at 1.9 GeV; Th: 1.9 GeV shifts =; W: 351; F: 127.6%; Su: 91.7%; W: 89.5% | Division Deputy Director
[5 empty] | multibunch unless outherwise noted. | [10 empty] | 2-bunch shifts = | [5 empty] | 33 |  | 12% |  | 8.3% |  |  | 10.5%
| I | Installation |  |  | JULY is draft only.