## Diagnostics
Diagnostics Beamline Vacuum Hardware Progress Schedule, 02/26/04
| QUANTITY |  |  |  | TOTAL | System Specialist | Vendor | Design | Design Room | RFQ | P.O./ILR | 1st Art | Del'vd | Production | Production | Shipped
Diagnostics |  | HEBT | RING | RTBT | DEVICES | [8 empty] | Total | Testing
BPM |  | 36 | 44 | 17 | 97 | Liaw/Dawson | BNL | X | X | X | X | X | X | 97 | 97 | 40
| TOTAL Beam Position Monitors |  |  |  | 97
IPM |  |  | 2 |  | 2 | Liaw/Connolly | BNL | X | X | X | X | N/A
| TOTAL Ionization Profile Monitors |  |  |  | 2
BCM |  | 5 | 1 | 5 | 11 | Liaw/Kesselman | BNL/Bergoz | X | X | X | X | X | X | 5 | 5 | 5
| TOTAL Beam Current Monitors |  |  |  | 11
IncoherentTune |  |  | 3 |  | 3 | Liaw/Russo | BNL | X | X | X | X | X
/ Damper / QMM
| TOTAL Incoherent Tune/Damper |  |  |  | 3
Wire Scanner Chmbrs |  | 11 | 0 | 8 | 19 | Liaw/Russo | BNL | X | X | X | X | X | X | 12 | 12 | 12
| TOTAL Wire Scanners |  |  |  | 19
Coherent tune - BIG |  |  | 1 |  | 1 | Liaw/Russo | BNL | X | X | X | X | N/A
| TOTAL CohTune/BIG |  |  |  | 1
VFM |  |  | 2 |  | 2 | Gassner | BNL | X | X | X | X | N/A
| TOTAL Video Foil Monitors |  |  |  | 2
Elec. Detector |  |  | 5 |  | 5 | Gulotta | BNL | X | X | X | X | X | X
| TOTAL Electron Detectors |  |  |  | 5
Halo Scrapers |  |  | 2 |  | 2 | Liaw/Russo | BNL | X | X | X | X | X
| TOTAL Halo Scrapers |  |  |  | 2
TOTAL -- ALL COMPONENTS |  | 52 | 60 | 30 | 142 | [8 empty] | 114 | 114 | 57
[8 empty] | X = work in progress |  |  | X = work complete