## Sheet1
CY 2008 LUF Approved Operating Schedule
| Jan |  |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  |  | Jul |  | Aug |  | Sep |  |  | Oct |  | Nov |  | Dec | Run period | 1 | 2 | 3 | 4 | 5 | 6
1 |  |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  | 1 |  | 1 |  | 1 |  |  | 1 |  | 1 |  | 1 |  |  | 1: days |  | hours
2 |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 2 |  | 2 |  | 2 |  |  | 2 |  | 2 |  | 2 |  | Lujan | 23 | 17.67 | 20.67 | 24 | 20.67 | 19.67 | 125.68 | 3016.32
3 |  |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  |  | 3 |  | 3 |  | 3 |  |  | 3 |  | 3 |  | 3 |  | pRad | 23 | 20.67 | 24.67 | 24 | 23.67 | 22.33 | 138.34 | 3320.16
4 |  |  | 4 |  | 4 |  | 4 |  | 4 |  | 4 |  |  | 4 |  | 4 |  | 4 |  |  | 4 |  | 4 |  | 4 |  | WNR Sole Use | 0 | 3 | 4 | 0 | 3 | 2.67 | 12.67 | 304.08
5 |  |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  |  | 5 |  | 5 |  | 5 |  |  | 5 |  | 5 |  | 5 |  | WNR Tgt-4 | 23 | 15.67 | 18.67 | 24 | 18.67 | 17.67 | 117.68 | 2824.32
6 |  |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  |  | 6 |  | 6 | Sec F | 6 |  |  | 6 |  | 6 |  | 6 |  | IPF | 25 | 22.67 | 24.67 | 25.67 | 25.67 | 22.33 | 146.01 | 3504.24
7 |  |  | 7 |  | 7 |  | 7 |  | 7 |  | 7 |  |  | 7 |  | 7 |  | 7 |  |  | 7 |  | 7 |  | 7 |  | Development | 2 | 2 | 0 | 1.67 | 2 | 0 | 7.67 | 184.08
8 |  |  | 8 |  | 8 |  | 8 |  | 8 |  | 8 |  |  | 8 |  | 8 |  | 8 |  |  | 8 |  | 8 |  | 8
9 |  |  | 9 |  | 9 |  | 9 |  | 9 |  | 9 |  |  | 9 |  | 9 |  | 9 | LSDS |  | 9 |  | 9 |  | 9
10 |  |  | 10 |  | 10 |  | 10 |  | 10 |  | 10 |  |  | 10 |  | 10 |  | 10 |  |  | 10 |  | 10 |  | 10
11 |  |  | 11 |  | 11 |  | 11 |  | 11 |  | 11 |  |  | 11 |  | 11 |  | 11 |  |  | 11 |  | 11 |  | 11
12 |  |  | 12 |  | 12 |  | 12 |  | 12 |  | 12 |  |  | 12 | ORNL | 12 |  | 12 |  |  | 12 |  | 12 |  | 12
13 |  |  | 13 |  | 13 |  | 13 |  | 13 |  | 13 |  |  | 13 |  | 13 |  | 13 |  |  | 13 |  | 13 |  | 13
14 |  |  | 14 |  | 14 |  | 14 |  | 14 |  | 14 |  |  | 14 |  | 14 |  | 14 |  |  | 14 |  | 14 |  | 14
15 |  |  | 15 |  | 15 |  | 15 |  | 15 |  | 15 |  |  | 15 |  | 15 |  | 15 |  |  | 15 |  | 15 |  | 15
16 |  |  | 16 |  | 16 |  | 16 |  | 16 |  | 16 |  |  | 16 |  | 16 |  | 16 |  |  | 16 |  | 16 |  | 16 | ORNL
17 |  |  | 17 |  | 17 |  | 17 |  | 17 |  | 17 |  |  | 17 |  | 17 |  | 17 |  |  | 17 |  | 17 |  | 17
18 |  |  | 18 |  | 18 |  | 18 |  | 18 |  | 18 |  |  | 18 |  | 18 |  | 18 |  |  | 18 |  | 18 |  | 18
19 |  |  | 19 |  | 19 |  | 19 |  | 19 |  | 19 |  |  | 19 |  | 19 |  | 19 |  |  | 19 |  | 19 |  | 19
20 |  |  | 20 |  | 20 |  | 20 |  | 20 |  | 20 |  |  | 20 |  | 20 |  | 20 |  |  | 20 |  | 20 |  | 20
21 |  |  | 21 |  | 21 |  | 21 |  | 21 |  | 21 |  |  | 21 |  | 21 |  | 21 |  |  | 21 |  | 21 |  | 21
22 |  |  | 22 |  | 22 |  | 22 |  | 22 |  | 22 |  |  | 22 |  | 22 |  | 22 |  |  | 22 | SNL | 22 |  | 22
23 |  |  | 23 |  | 23 |  | 23 |  | 23 |  | 23 |  |  | 23 |  | 23 |  | 23 |  |  | 23 |  | 23 |  | 23
24 |  |  | 24 |  | 24 |  | 24 |  | 24 |  | 24 |  |  | 24 |  | 24 |  | 24 |  |  | 24 |  | 24 |  | 24
25 |  |  | 25 |  | 25 |  | 25 |  | 25 |  | 25 |  |  | 25 |  | 25 |  | 25 |  |  | 25 |  | 25 |  | 25
26 |  |  | 26 |  | 26 |  | 26 |  | 26 |  | 26 |  |  | 26 |  | 26 |  | 26 |  |  | 26 |  | 26 |  | 26
27 |  |  | 27 |  | 27 |  | 27 |  | 27 |  | 27 |  |  | 27 |  | 27 |  | 27 |  |  | 27 |  | 27 |  | 27
28 |  |  | 28 |  | 28 |  | 28 |  | 28 |  | 28 |  |  | 28 |  | 28 |  | 28 |  |  | 28 |  | 28 |  | 28
29 |  |  | 29 |  | 29 |  | 29 |  | 29 |  | 29 | Sec J |  | 29 |  | 29 |  | 29 |  |  | 29 |  | 29 |  | 29
30 |  |  |  |  | 30 |  | 30 |  | 30 |  | 30 |  |  | 30 |  | 30 |  | 30 |  |  | 30 |  | 30 |  | 30
31 |  |  |  |  | 31 |  |  |  | 31 |  |  |  |  | 31 |  | 31 |  |  |  |  | 31 |  |  |  | 31
| Jan |  |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  |  | Jul |  | Aug |  | Sep |  |  | Oct |  | Nov |  | Dec
|  | Outage maintenance all areas | [7 empty] | Ion source recycle/scheduled maintenance | [8 empty] | # | Holiday and/or laboratory closure
|  | Scheduled maintenance all areas | [7 empty] | Tgt2 Setup, Production other areas | [8 empty] | # | Weekend
|  | Development | [7 empty] | Development, Documentation, and Shutdown
|  | Production to all areas | [7 empty] | WNR Sole Use
|  | Turn on all areas | [7 empty] | Maintenance and FIRP roofing project
"All areas" = IPF, Lujan, WNR T2 or
WNR T4, pRad, UCN
"800-MeV beam areas" = Lujan, WNR T2 or WNR T4, pRad, UCN