## Sheet1
| C56 | C78 | A78 | A12 | C12
2007-03-29 | Opto heater hookup, blankets, final opto test,continuity | IR top heaters | Bottom heat spreaders and heaters, blanket | Test top optoboards,invert
2007-03-30 |  | Blankets, opto heater hookup | Optocooling loop | Bottom optoboards and test
2007-03-31 | Buckets and can | Slack | Slack | Slack
2007-04-01 | Slack | Slack | Slack | Slack
2007-04-02 | Continuity/repair | Final opto test, continuity | ISP prep, bend, continuity | ISP continuity | Load top B boards
2007-04-03 | Final prep | Buckets and can | Attach ISPs, fiber routing, start ENV | Bottom heat spreaders, heaters,IR, blanket | Continue top opto
2007-04-04 | Box for shipping | Continuity/repair | Fiber routing, ENV routing | Optocooling loop | Finish top opto, invert
2007-04-05 |  | Final prep | ENV pictures, fiber PP1 can, upright | Attach ISPs, fiber routing, start ENV | Bottom opto
2007-04-06 |  | Holiday | Holiday | Holiday | Holiday
2007-04-07 |  | Slack | Slack | Slack | Slack
2007-04-08 |  | Slack | Slack | Slack | Slack
2007-04-09 |  | Holiday | Holiday | Holiday | Holiday
2007-04-10 |  | Box for shipping | Spreaders, top heaters, IR | Fiber routing, ENV routing | Bottom heat spreaders, IR,heaters,blankets
2007-04-11 |  | Deliver to SR1 | Blankets, opto heater hookup | ENV pictures, fiber PP1 can, upright | Finish bottom blankets, start opto cooling
2007-04-12 |  |  | Attach exhaust extensions | Top heaters, IR | Finish opto cooling
2007-04-13 |  |  | Final opto test, continuity | Blankets, opto heater hookup | ISP prep, bend, continuity
2007-04-14 |  |  | Slack | Slack | Slack
2007-04-15 |  |  | Slack | Slack | Slack
2007-04-16 |  |  | Buckets and can | Final opto test, continuity | Attach ISPs, fiber routing, start ENV
2007-04-17 |  |  | Continuity/repair | Buckets and can | Fiber routing, ENV routing
2007-04-18 |  |  | Final prep | Continuity/repair | ENV pictures, fiber PP1 can, upright
2007-04-19 |  |  | Box for shipping | Final prep | Top heat spreaders, heaters, IR, blankets
2007-04-20 |  |  |  | Box for shipping | Opto heater hookup
2007-04-21 |  |  |  | Slack | Slack
2007-04-22 |  |  |  | Slack | Slack
2007-04-23 |  |  |  |  | Final opto test, continuity
2007-04-24 |  |  |  |  | Buckets and can
2007-04-25 |  |  |  |  | Continuity/repair
2007-04-26 |  |  |  |  | Final prep
2007-04-27 |  |  |  |  | Box for shipping
2007-04-28 |  |  |  |  | Slack
2007-04-29 |  |  |  |  | Slack
2007-04-30
2007-05-01
2007-05-02