## PI Schedule
DRAFT PRODUCT IMPROVEMENT UPGRADE SCHEDULE (10/13/06)
FAA |  |  |  | RAYTHEON
SITE | STATE | START | FINISH | SITE | STATE | START | FINISH
ESA |  |  |  | TRAINING w/FAA
Citronelle | AL | 2006-02-08 | 2006-02-10 | Odessa | TX | 2006-01-24 | 2006-01-27
Clearfield | PA | 2006-02-07 | 2006-02-08 | Anson | TX | 2006-01-31 | 2006-02-03
CSA |  |  |  | Russelville | AR | 2006-02-15 | 2006-02-16
Odessa | TX | 2006-01-31 | 2006-02-01 | ESA
Anson | TX | 2006-02-02 | 2006-02-03 | Samburg | TN | 2006-03-07 | 2006-03-10
Silver City | NM | 2006-02-07 | 2006-02-10 | Byhalia | MS | 2006-03-15 | 2006-03-17
Chelsea | OK | 2006-02-14 | 2006-02-15 | Montgomery | AL | 2006-03-28 | 2006-03-31
West Mesa | NM | 2006-02-14 | 2006-02-17 | Haleyville | AL | 2006-04-04 | 2006-04-07
Russelville | AR | 2006-02-16 | 2006-02-17 | Joelton | TN | 2006-04-18 | 2006-04-21
Houston | TX | 2006-03-07 | 2006-03-10 | Crossville | TN | 2006-04-25 | 2006-04-28
Rogers | TX | 2006-03-14 | 2006-03-17 | Higby | WV | 2006-05-09 | 2006-05-12
Texarkana | AR | 2006-03-21 | 2006-03-24 | Maiden | NC | 2006-05-16 | 2006-05-19
Hutchinson | KS | 2006-03-28 | 2006-03-31 | Benton | PA | 2006-05-23 | 2006-05-26
La Grange | IN | 2006-04-04 | 2006-04-07 | Ashburn | GA | 2006-06-06 | 2006-06-09
Hanna City | IL | 2006-04-18 | 2006-04-21 | Cummington | MA | 2006-06-13 | 2006-06-16
Crocker | MO | 2006-04-25 | 2006-04-28 | Oakdale | PA | 2006-07-11 | 2006-07-14
Detroit (RMC Only) | MI | 2006-05-23 | 2006-05-24 | Skowegan | ME | 2006-07-18 | 2006-07-21
St Louis | MO | 2006-05-26 | 2006-05-27
Indianapolis | IN | 2006-05-31 | 2006-06-01
Huntingburg | IN | 2006-06-05 | 2006-06-06
Apple Valley | MN | 2006-06-13 | 2006-06-14 | *Grayed out sites are complete
Coopersville | MI | 2006-08-22 | 2006-08-23
Brecksville | OH | 2006-09-06 | 2006-09-07
Eagle River | WI | 2006-09-19 | 2006-09-20
Alexandria | LA
WSA
Phoenix (Humbolt) | AZ | 2006-06-06 | 2006-06-08
Boron | CA | 2006-06-13 | 2006-06-16
Middleton Island | AK | 2006-06-28 | 2006-07-05
Shemya(BI6 Only) | AK | 2006-07-19 | 2006-07-21
St. Paul Island | AK | 2006-07-24 | 2006-07-26
Deadhorse | AK | 2006-07-27 | 2006-07-29
Biorka Island | AK | 2006-07-31 | 2006-08-02
Red Table Mountain | CO | 2006-08-15 | 2006-08-16
Sacramento | CA | 2006-08-29 | 2006-08-30
Seattle (Ft Lawton) | WA | 2006-09-07 | 2006-09-08
Monroe | OR | 2006-09-11 | 2006-09-12
Battle Mountain | NV | 2006-09-12 | 2006-09-13
Pahoa | HI | 2006-10-17 | 2006-10-20
Maui | HI | 2006-10-24 | 2006-10-27
Formulas:
FINISH = [START]+3

## PI Status
PRODUCT IMPROVEMENT (10/4/06)
SITE | ST | REGION | LID | PRIMARY RADAR | BI-6 INSTALLED | COMMISSIONED | PI INSTALLED | DATE PI INSTALL COMPLETE | RMC UPGRADED | DATE RMC UPGRADE COMPLETE
TINKER AFB (Key Site) | OK | ASW | OKC | FPS-67B | X | X | X | 2005-08-22 | X | 2005-08-22
TECH CENTER (OT&E) | NJ | N/A | ACYT | SUPPORT | X | N/A | X | 2005-07-19 | X | 2005-07-19
PUTNAM | OK | ASW | QOT | BOS | X | X | X | 2005-09-14 | X | 2005-09-14
MONROE | OR | ANM | QMO | BOS | X | X | X | 2006-09-14 | X | 2006-09-14
PUU NIAUNIAU (MAUI) | HI | AWP | QPN | BOS | X | X
CHELSEA | OK | ASW | QAF | BOS | X | X | X | 2006-02-15 | X | 2006-02-15
HALEYVILLE | AL | ASO | QPC-E | FPS-67B | X | X | X | 2006-04-07 | X | 2006-04-07
ANSON | TX | ASW | QOO | BOS | X | X | X | 2006-02-03 | X | 2006-02-03
CROSSVILLE | TN | ASO | QRV | BOS | X | X | X | 2006-04-26 | X | 2006-04-26
RED TABLE MOUNTAIN | CO | ANM | DBL | BOS | X | X | X | 2006-08-16 | X | 2006-08-16
SEATTLE (FORT LAWTON) | WA | ANM | SEA-E | ARSR-1E | X | X | X | 2006-09-10 | X | 2006-09-10
OAKDALE (PITTSBURGH) | PA | AEA | PIT-E | FPS-67B | X | X | X | 2006-07-11 | X | 2006-07-11
BORON | CA | AWP | QSR | FPS-67B | X | X | X | 2006-06-14 | X | 2006-06-14
BRECKSVILLE (CLEVELAND) | OH | AGL | CLE-E | ARSR-1E | X | X | X | 2006-09-07 | X | 2006-09-07
FAA ACADEMY | OK | N/A | FAAAC | SUPPORT | X | N/A | X | 2005-11-15 | X
ALEXANDRIA (ENGLAND) | LA | ASW | AEX-E | FPS | X | X
ASHBURN | GA | ASO | QHN-E | ARSR-1E | X | X | X | 2006-06-06 | X | 2006-06-06
MARIETTA | GA | ASO | ATL-E | ARSR-1E | X | X | X | 2005-10-27 | X | 2005-10-31
HIGBY | WV | AEA | QHY | BOS | X | X | X | 2006-05-10 | X | 2006-05-10
TEXARKANA | AR | ASW | TXK-E | FPS-67 | X | X | X | 2006-03-24 | X | 2006-03-24
BIORKA ISLAND | AK | AAL | BKA | BOS | X | X | X | 2006-08-02 | X | 2006-08-02
HUNTINGBURG | IN | AGL | HNB | BOS | X | X | X | 2006-06-05 | X | 2006-06-05
KLAMATH FALLS (MIG) | OR | ANM | LMT | FPS | X | X | X | 2005-09-20 | X | 2005-09-20
SACRAMENTO | CA | AWP | SAC | BOS | X | X | X | 2006-08-30 | X | 2006-08-30
MONTGOMERY | AL | ASO | MGM-E | ARSR-1D | X | X | X | 2006-03-28 | X | 2006-03-28
PAHOA | HI | AWP | POA | BOS | X | X
BYHALIA (MEMPHIS) | MS | ASO | QYB-E | ARSR-1 | X | X | X | 2006-03-17 | X | 2006-03-17
DEAD HORSE | AK | AAL | SCC | BOS | X | X | X | 2006-07-29 | X | 2006-07-29
APPLE VALLEY | MN | AGL | QJE-E | ARSR-1E | X | X | X | 2006-06-13 | X | 2006-06-13
SKOWHEGAN | ME | ANE | QYC | BOS | X | X | X | 2006-07-18 | X | 2006-07-18
EAGLE RIVER | WI | AGL | EGV | BOS | X | X | X | 2006-09-19 | X | 2006-09-19
MAIDEN | NC | ASO | QRM-E | ARSR-1 | X | X | X | 2006-05-16 | X | 2006-05-16
ROGERS | TX | ASW | QYS-E | ARSR-1E | X | X | X | 2006-03-15 | X | 2006-03-15
CUMMINGTON | MA | ANE | QHA-E | FPS-67B | X | X | X | 2006-06-13 | X | 2006-06-13
LAGRANGE | IN | AGL | QTZ-E | ARSR-1E | X | X | X | 2006-04-07 | X | 2006-04-07
RUSSELLVILLE | AR | ASW | QXR-E | FPS-64A | X | X | X | 2006-02-16 | X | 2006-02-16
SAN PEDRO | CA | AWP | QLA-E | ARSR-1E | X | X | X | 2005-10-06 | X | 2005-10-06
CROCKER | MO | ACE | QJN | BOS | X | X | X | 2006-04-25 | X | 2006-04-25
JOELTON (NASHVILLE) | TN | ASO | QOJ-E | ARSR-1E | X | X | X | 2006-04-18 | X | 2006-04-21
WEST MESA | NM | ASW | QSA | FPS-66A | X | X | X | 2006-02-16 | X | 2006-02-16
LINCOLNTON | GA | ASO | QNK-E | ARSR-3 | X | X | X | 2005-09-07 | X | 2005-09-07
LONDON | OH | AGL | QWO-E | ARSR-1E | X | X | X | 2005-11-16 | X | 2005-11-16
HOUSTON (ELLINGTON) | TX | ASW | HOU-E | ARSR-1E | X | X | X | 2006-03-10 | X | 2006-03-10
MIDDLETON ISLAND | AK | AAL | MDO | BOS | X | X | X | 2006-06-30 | X | 2006-06-30
HANNA CITY | IL | AGL | QUZ-E | FPS-67B | X | X | X | 2006-04-18 | X | 2006-04-18
ODESSA | TX | ASW | QXS-E | ARSR-1E | X | X | X | 2006-02-01 | X | 2006-02-01
BENTON | PA | AEA | QRC-E | FPS-67B | X | X | X | 2006-05-23 | X | 2006-05-24
SILVER CITY | NM | ASW | SVC-E | ARSR-2 | X | X | X | 2006-02-08 | X | 2006-02-08
BATTLE MOUNTAIN | NV | AWP | BAM | ARSR-2 | X | X | X | 2006-09-12 | X | 2006-09-12
SAMBURG | TN | ASO | QPB | BOS | X | X | X | 2006-03-09 | X | 2006-03-09
COOPERSVILLE | MI | AGL | CPV-E | FPS-66A | X | X | X | 2006-08-23 | X | 2006-08-23
BINNS HALL | VA | AEA | QBN-E | ARSR-3 | X | X | X | 2005-10-17 | X | 2005-10-21
ST. PAUL ISLAND | AK | AAL | SNP | BOS | X | X | X | 2006-07-26 | X | 2006-07-26
INDIANAPOLIS | IN | AGL | INDA | ARSR-1E | X | X | X | 2006-05-31 | X | 2006-05-31
FOSSIL | OR | ANM | QVN-E | ARSR-3 | X | X | X | 2005-05-25 | X | 2005-05-26
DANSVILLE (MIG) | NY | AEA | DSV-E | ARSR-1E | X | X | X | 2005-04-26 | X | 2005-07-14
HUTCHINSON | KS | ACE | HTI-E | FPS-66A | X | X | X | 2006-03-31 | X | 2006-03-31
HORICON | WI | AGL | QHZ-E | ARSR-2 | X | X | X | 2005-05-01 | X | 2005-11-03
SELIGMAN | AZ | AWP | QXP-E | ARSR-3 | X | X | X | 2005-02-02 | X | 2006-03-02
CLEARFIELD | PA | AEA | QCF-E | ARSR-3 | X | X | X | 2006-02-08 | X | 2006-02-08
PHOENIX (HUMBOLT) | AZ | AWP | PHX-E | ARSR-1E | X | X | X | 2006-06-06 | X | 2006-06-06
ST. LOUIS | MO | ACE | STL-E | ARSR-1E | X | X | X | 2006-05-26 | X | 2006-05-26
DETROIT (MIG) | MI | AGL | QDT | ARSR-1E | X | X | X | 2005-02-01 | X | 2006-05-23
THE PLAINS | VA | AEA | QPL-E | ARSR-3 | X | X | X | 2005-09-13 | X | 2005-09-13
BENSON | NC | ASO | QRL-E | ARSR-1E | X | X | X | 2005-08-01 | X | 2005-09-01
NEWPORT | MS | ASO | QNM-E | ARSR-3 | X |  | X | 2006-05-01 | X | 2006-06-23
OMAHA | NE | ACE | QHO-E | FPS-66A | X | X | X | 2005-08-02 | X | 2005-08-02
CITRONELLE | AL | ASO | QRB-E | ARSR-2 | X | X | X | 2006-02-10 | X | 2006-02-10
KENAI | AK | AAL | ENA | ARSR-3 | X |  | X | 2006-09-15 | X | 2006-09-15
LYNCH | KY | ASO | QRI-E | ARSR-2 | X | X | X | 2005-06-01 | X | 2006-02-01
OSKALOOSA | KS | ACE | QBZ-E | ARSR-2 | X | X | X | 2005-08-16 | X | 2005-09-29
KELLER (FT. WORTH) | TX | ASW | FTW-E | ARSR-1D | X | X | X | 2005-05-01 | X | 2006-02-07
BEDFORD | VA | AEA | QBE-E | ARSR-3 | X | X | X | 2005-10-18 | X | 2006-01-26
ELWOOD (JOLIET) | IL | AGL | JLT-E | ARSR-3 | X |  | X | 2006-05-19 | X | 2006-05-19
KIRKSVILLE | MO | ACE | IRK-E | ARSR-3 | X |  | X | 2006-07-20 | X | 2006-08-03
SHEMYA | AK | AAL | SYA | BOS | X | X | X | 2006-07-20 | X | 2005-05-13
ARLINGTON | IA | ACE | QJO-E | ARSR-3 | X | X | X | 2005-10-26 | X | 2006-04-14
BOZEMAN | MT | ANM | BZN | BOS
EAGLE COUNTY | CO | ANM | EGE | BOS
PICO DEL ESTE | PR | ASO | QJQ-E | FPS-67
GRAND TURK | BW | ASO | GDT | BOS
FREEPORT | BW | ASO | BHF | BOS
GEORGETOWN | BW | ASO | FK7 | BOS
YAKUTAT | AK | AAL | YAK
EDWARDS AFB
NASSAU | BH | ASO | QJS | ASR-8
SAN ANTONIO | TX | ASW | SAT-E | BOS
TOTALS | [6 empty] | 74 |  | 74