## Sheet1
| Manhours (Budgeted) | Manhours (New) | completion
Update Structural and thermal models for the Ro=2.14m, Dec 4 2001 build | 160 |  | completed
Elbrodur R&D | 50
Plot of Flattop time vs. Nuclear Heat vs. peak TF field |  | 4 | 2002-11-22
Prepare TF elevation dwg. |  | 16 | 2002-12-10
TF envelope with scale-up
Include CS and PF
New manifold position
Coolant channel details
Insulation details
Criteria Document update for nuclear resistivity changes | 2 |  | 2002-12-10
Analyze H mode fiducial | 16 |  | Dec 10 2002
Analyze H mode Variants | 50 |  | 2003-02-01
Analyze AT fiducial | 16 |  | Dec 20 2002
Analyze AT Variants |  | 120 | May 1 2003
Evaluate resized PF 1, and 2 | 16 |  | Jan 1 2003
Develop options for extending AT pulse – e.g. Larger or SC PF1,2 |  | 140 | June 1 2003
ANS Fusion Topical Washington DC. Creep paper | 36 |  | Nov. 22 2002'
Re-run TF loads due to disruption with no vessel copper. | 16 |  | June 1 2003
Complete 2 sided cooldown, LN2 two phase flow simulation | 28 |  | May 1 2003
Run elastic-plastic inner leg with holes analysis. | 4 |  | Feb 1 2003
Analyse/Interact on insulation mechanical loading | 16
Outer TF joint analysis | 32 |  | March 1 2003
CS Joints and Leads | 72 |  | July 1 2003
Prepare new TF, CS, and cooldown sections of FY2003 report | 72 |  | June 1 2003
Prepare new TF, CS, and cooldown sections of FY2003 appendices | 72 |  | June 1 2003
| 658 | 280
Additional Cost, Fully Loaded ($) |  | 30000