## Sheet1
WBS No. |  |  | Title | Level of Estimate |  | Est. Cost | Comments
|  |  |  | Summary | Detail | FY-02 $K
1 - Fusion Core Systems | [5 empty] | 317105.6
1.1 | Plasma Facing Components - Ulrickson / Dreimeyer |  |  |  |  | 55814.4
1.1.1 |  | First Wall |  |  | X | 14623.2
1.1.2 |  | Outer Divertor Modules |  |  | X | 22360
1.1.3 |  | Baffle Structures |  |  | X | 7883.2
1.1.4 |  | Inner Divertor Plates |  |  | X | 4752
1.1.5 |  | Limiters & Armor |  |  | X | 1915.2
1.1.6 |  | Wall Conditioning Systems |  |  | X | 4280.8
1.1.7 |  | Plasma Facing Components Cooling Water (Inside Cryostat) |  |  |  |  | Already in Above Numbers
1.2 | Vacuum Vessel & In-Vessel Structures - Nelson |  |  |  |  | 119464
1.2.1 |  | Primary VV shell |  |  | X | 18288.8
1.2.2 |  | VV Port Extensions & Duct Shielding |  |  | X | 93520.8
1.2.3 |  | VV Port Closure Systems & Penetration Shielding |  |  | X | 5160
1.2.4 |  | VV Heating & Cooling Systems (Inside Cryostat) |  |  | X | 620
1.2.5 |  | VV Supports |  |  | X | 1449.6
1.2.6 |  | Local I&C and Sensors |  |  | X | 424.8
1.3 | Toroidal Field Magnets and Structures |  |  |  |  | 102600.8
1.3.1 |  | TF Winding Pack |  |  | X | 82868.8
1.3.2 |  | TF Cases & Support Structure |  | X |  | 4776
1.3.3 |  | TF Magnet Assembly (Winding Pack into Cases) |  |  | X | 2097.6
1.3.4 |  | TF Power & Cryogen Interfaces |  |  | X | 1563.2
1.3.5 |  | TF Magnets Engineering Design/Support |  |  | X | 11295.2
1.4 | Poloidal Field Magnets and Structures |  |  |  |  | 29776.8
1.4.1 |  | Central Solenoid and Inner Ring Coils (PF1/2 Upper & Lower) |  |  | X | 6847.2
| 1.4.1.1 |  | CS/Inner Ring Coils Winding Packs |  |  | 5370.4
| 1.4.1.2 |  | CS/Inner Ring Coils Cases and Support Structures |  |  | 917.6
| 1.4.1.3 |  | CS/Inner Ring Coils Assembly (Winding Pack into Cases) |  |  | 559.2
1.4.2 |  | Outer Ring Coils (PF3/4 Upper & Lower) |  |  | X | 12978.4
| 1.4.2.1 |  | Outer Ring Coils Winding Packs |  |  | 7554.4
| 1.4.2.2 |  | Outer Ring Coils Cases and Support Structures |  |  | 248.8
| 1.4.2.3 |  | Outer Ring Coils Shrouds & Assembly |  |  | 5175.2
1.4.3 |  | PF Power and Cryogen Interfaces |  |  |  | 1000
1.4.4 |  | Field Error Correction Coils |  |  | X | 1599.2
1.4.5 |  | Resistive Wall Mode Coils |  |  |  |  | Future Upgrade - WBS Placeholder Only
1.4.6 |  | PF Magnets Engineering Design/Support |  |  | X | 6367.2
1.4.7 |  | PF Coil R&D |  |  | X | 984.8
1.5 | Cryostat - Nelson |  |  |  |  | 1599.2
1.5.1 |  | Cryostat Shell & Structure |  |  | X | 1446.4
1.5.2 |  | Vaccum & Fluid Systems |  |  | X | 92
1.5.3 |  | Thermal Shields |  |  | X | 0
1.5.4 |  | Local I&C and Sensors |  |  | X | 60.8
1.6 | Tokamak Support Structure - Titus \ Heitzenroeder \ Waganer |  |  |  |  | 7850.4
1.6.1 |  | Main Assembly Support Ringf & Central Column Supports |  |  |  | 1320.8
| 1.6.1.1 |  | Central Column Supports |  | X | 841.6
| 1.6.1.2 |  | Main Assembly Support Ring |  | X | 479.2
1.6.2 |  | Gravity Supports |  |  | X | 922.4
1.6.3 |  | TF Coil Radial Compression |  |  |  | 5607.2
| 1.6.3.1 |  | Compression Rings |  | X | 3242.4
| 1.6.3.2 |  | Radial Compression Mechanism & Interface Elements |  | X | 2364.8
2 - Auxiliary Systems | [5 empty] | 74824
2.1 | Gas & Pellet Injection Fueling Systems - M. Gouge |  |  |  |  | 3974.4
2.1.1 |  | Fuel Storage System |  |  | X | 404
2.1.2 |  | Pellet Injector Fueling System |  |  | X | 1744
2.1.3 |  | Gas Fueling System |  |  | X | 818.4
2.1.4 |  | Disruption Control Systems |  |  | X | 1008
2.2 | Vacuum Pumping System - M. Gouge |  |  | X |  | 10537.6
2.2.1 |  | High Vacuum Pumping Systems |  |  |  | 6690.4
2.2.2 |  | Roughing & Backing Pumping Systems |  |  |  | 2136.8
2.2.3 |  | Diagnostic Roughting & Backing Systems |  |  |  | 1710.4
2.3 | Fuel Recovery and Processing Systems - C. Gentile |  |  | X |  | 3407.2
2.3.1 |  | Fuel Recovery & Processing System |  |  |  | 3407.2
2.3.2 |  | Radiation Monitoring Systems |  |  |  | 0 | Using Existing Equipment
2.4 | RF Heating/Current Drive Systems - Swain |  |  |  |  | 56904.8
2.4.1 |  | ICRF Systems |  |  |  | 56904.8
| 2.4.1.1 |  | Antennas |  | X | 7024
| 2.4.1.2 |  | Tuning & Matching Systems |  | X | 2153.6
| 2.4.1.3 |  | Transmission Lines |  | X | 2858.4
| 2.4.1.4 |  | RF Sources |  | X | 29741.6
| 2.4.1.5 |  | DC Power Supplies |  | X | 11224.8
| 2.4.1.6 |  | Local I&C and Sensors |  | X | 3902.4
2.4.2 |  | ECRF Systems (Later Upgrade) |  |  |  |  | NOT IN BASELINE => LATER UPGRADE
2.4.3 |  | Lower Hybrid Systems (Later Upgrade) |  |  |  |  | NOT IN BASELINE => LATER UPGRADE
2.5 | Neutral Beam Injection System - Swain | [5 empty] | NOT IN BASELINE => LATER UPGRADE
3 - Diagnostic Systems | [5 empty] | 17879.2 | PHASE I ONLY
3.1 | Startup Diagnostics (Phase I) - Young / Ellis |  |  |  |  | 17879.2
3.2 | ICRF/Divertor Check (Phase II) Diagnostics - Young/Ellis | [5 empty] | NOT IN BASELINE => LATER UPGRADE
3.3 | Full Physics DD (Phase III) Diagnostics - Young/Ellis | [5 empty] | NOT IN BASELINE => LATER UPGRADE
3.4 | Full Phsics DT (Phase IV) Diagnostics - Young/Ellis | [5 empty] | NOT IN BASELINE => LATER UPGRADE
4 - Power Systems | [5 empty] | 127920 | Assumes All Power Supplied by Grid => +~$34.3M if MG
4.1 | Site Power Supplies - Woolley / Neumeyer |  |  |  | X | 10400
4.1.1 |  | Substations &Utilities Interfaces
4.1.2 |  | AC Distribution Systems
4.1.3 |  | Emergency Power Supply Systems
4.2 | Experimental Magnet Power Supply Systems - Woolley / Neumeyer |  |  |  | X | 117520
4.2.1 |  | TF Coil Power Supplies
4.2.2 |  | PF Coils Power Supplies
4.2.3 |  | FEC Coil Power Supplies
4.2.4 |  | RWM Coil Power Supplies (Upgrade)
4.2.5 |  | IC Coil Power Supplies
4.2.6 |  | Common Magnet Electrical Power Equipment
5 - Central Instrumentation & Controls | [5 empty] | 15280.8
5.1 | Instrumentation and Control Systems -Oliaro |  |  |  | X | 6100.8
5.2 | Data Acquisition Systems - Oliaro |  |  |  | X | 5496
5.3 | Network Infrastructure and Distribution - Oliaro |  |  |  | X | 3684
6 - Site and Facilities | [5 empty] | 119901.6
6.1 | Facility Modifications - Dilling |  |  |  |  | 14376
6.1.1 |  | Site & Facility Improvements |  |  | X | 12335.2
6.1.2 |  | Interfaces with Offsite Service Providers |  |  | X | 2040.8
6.2 | Building and Structures - Dilling |  |  |  |  | 78015.2
6.2.1 |  | Safety Related Buildings and Structures |  |  |  | 49310.4
| 6.2.1.1 |  | Tokamak & Hot Cell Building |  | X | 41205.6
| 6.2.1.2 |  | Radioactive Systems Support Building |  | X | 2885.6
| 6.2.1.3 |  | Tritium & Vacuum Pumping Building |  | X | 0 | Deleted
| 6.2.1.4 |  | Radwaste Systems Building |  | X | 3614.4
| 6.2.1.5 |  | Emergency Power Supply Building |  | X | 1604.8
6.2.2 |  | Non-Safety Related Buildings & Structures |  |  |  | 28704.8
| 6.2.2.1 |  | Assembly & Mockup Building |  | X | 8914.4
| 6.2.2.2 |  | Magnet Power Conversion Building |  | X | 3753.6
| 6.2.2.3 |  | Cooling System/Heat Rejection Building |  | X | 400.8
| 6.2.2.4 |  | Cryogenics Systems Building |  | X | 379.2
| 6.2.2.5 |  | ICRF Power Supply Building |  | X | 4950.4
| 6.2.2.6 |  | Laboratory Office Building |  | X | 8800
| 6.2.2.7 |  | Operations and Control Building |  | X | 941.6
| 6.2.2.8 |  | Plant Utilities Building |  | X | 564.8
6.3 | Water Cooling Systems - Dilling |  |  |  |  | 5542.4
6.3.1 |  | PFC Cooling Water Systems (Outside Cryostat) |  |  |  | 985.6
6.3.2 |  | VV Heating & Cooling Water Systems (Outside Cryostat) |  |  |  | 312
6.3.3 |  | Secondary Component Cooling & Chilled Water Systems |  |  |  | 2952.8
6.3.4 |  | Plant Heat Rejection System |  |  |  | 1292
6.4 | Cryogenic Cooling Systems - Dilling |  |  |  |  | 1203.2
6.4.1 |  | Liquid Nitrogen Cooling Piping and Hardware |  |  | X | 704.8
6.4.2 |  | Liquid Helium Cooling Piping and Hardware |  |  | X | 498.4
6.5 | Waste Handling and Treatment Systems |  |  |  |  | 7469.6
6.5.1 |  | Liquid Radioactive Waste Treatment System |  |  | X | 1392.8
6.5.2 |  | Water De-Tritiation System |  |  | X | 4849.6
6.5.3 |  | High Level Solid Waste Processing System |  |  | X | 638.4
6.5.4 |  | Low Level Solid Waste Treatment System |  |  | X | 101.6
6.5.5 |  | Toxic Material Treatment System |  |  | X | 487.2
6.6 | Utility Systems |  |  |  |  | 13295.2
6.6.1 |  | Inert Gas Distribution System |  |  | X | 599.2
6.6.2 |  | Breathing Air System |  |  | X | 673.6
6.6.3 |  | Compressed Air System |  |  | X | 3365.6
6.6.4 |  | Potable Water Treatment System |  |  | X | 2604
6.6.5 |  | Demineralized Water Treatment System |  |  | X | 708
6.6.6 |  | Sanitary Drainage System |  |  | X | 1382.4
6.6.7 |  | Industrial Drainage System |  |  | X | 1382.4
6.6.8 |  | Fire Protection System |  |  | X | 2580
7 - Machine Assembly and Remote Maintenance | [5 empty] | 66979.2
7.1 | Torus Systems Assembly and Installation. - Heitzenroeder |  |  |  | X | 4946.4
7.2 | Ancillary Systems Assembly and Installation - Heitzenroeder |  |  |  | X | 1441.6
7.3 | Special Machine Assembly Tools & Equip..- Heitzenroeder |  |  |  | X | 1769.6
7.4 | In-Vessel Measurement Systems - Nelson |  |  |  |  | 551.2
7.4.1 |  | Magnetic Field Measurement System |  | X |  | 139.2
7.4.2 |  | Mechanical Position Measurement/Metrology Systems |  | X |  | 412 | Based on one laser tracker and two Faro arms
7.4.3 |  | Measurement Systems R&D |  | X |  | 0 | None Anticipated
7.5 | Remote Handling Systems - Burgess |  |  |  |  | 43060
7.5.1 |  | In-Vessel Transporters |  |  | X | 10855.2
| 7.5.1.1 |  | Articulated Booms |  |  | 4109.6
| 7.5.1.2 |  | End-Effectors |  |  | 6745.6
7.5.2 |  | In-Vessel Inspection Systems |  |  | X | 2202.4
| 7.5.2.1 |  | In-Vessel Metrology System |  | X | 1787.2
| 7.5.2.2 |  | In-Vessel Viewing System |  | X | 415.2
7.5.3 |  | Port Assembly Handling Systems |  | X |  | 13470.4
| 7.5.3.1 |  | Midplane Port Handling Vehicle |  |  | 6502.4
| 7.5.3.2 |  | Auxiliary Port Handling Vehicle |  |  | 5684
| 7.5.3.3 |  | Dexterous Manipulators |  |  | 1284
7.5.4 |  | Remote Handing Tools |  | X |  | 5176.8
| 7.5.4.1 |  | Pipe Cutting, Welding & Inspection Tools |  |  | 5055.2
| 7.5.4.2 |  | Lip-Seal Cuuting, Welding & Inspection Tools |  |  | 0 | Combined with 7.5.4.1
| 7.5.4.3 |  | Power Wrenches for Port Assembly Attachments |  |  | 121.6
7.5.5 |  | Containment and Transport Systems |  | X |  | 7810.4
| 7.5.5.1 |  | Transfer Casks |  |  | 4554.4
| 7.5.5.2 |  | Cask Docking Interfaces |  |  | 271.2
| 7.5.5.3 |  | Cask Transport Air Cushion Vehicles |  |  | 2428
| 7.5.5.4 |  | Midplane Port Shielded Enclosure |  |  | 556.8
7.5.6 |  | Remote Handling Control Room & Test Stand |  | X |  | 3544.8
| 7.5.6.1 |  | Remote Handling Control Room Equipment |  |  | 616
| 7.5.6.2 |  | Test Stand Group Labor |  |  | 2928.8
7.6 | Hot Cell Facility Remote Handling Systems - Burgess |  |  |  |  | 15210.4
7.6.1 |  | Hot Cell Bridge Crane Systems |  |  | X | 1465.6
7.6.2 |  | Hot Cell Bridge Mounted Manipulator Systems |  |  | X | 3614.4
7.6.3 |  | Hot Cell Shielded Window Workstations |  |  | X | 3519.2
7.6.4 |  | Hot Cell Viewing Systems |  |  | X | 930.4
7.6.5 |  | Hot Cell Component Repair Stations |  |  |  | 5152.8
| 7.6.5.1 |  | Port Assembly Repair Station |  | X | 2340.8
| 7.6.5.2 |  | Divertor Repair Station |  | X | 2469.6
| 7.6.5.1 |  | Cryopump Repair Station |  | X | 342.4
7.6.6 |  | Hot Cell Component Handling Fixtures |  |  |  | 528
| 7.6.6.1 |  | Divertor Module Handling Fixtures |  | X | 191.2
| 7.6.6.2 |  | Port Assembly Handling Fixtures |  | X | 223.2
| 7.6.6.1 |  | Limiter Module Handling Fixtures |  | X | 56.8
| 7.6.6.1 |  | First Wall Module Handling Fixtures |  | X | 56.8
TOTAL DIRECT COSTS | [5 empty] | 739890.4
CONTINGENCY @ 25.5% (US ACCOUNTING ONLY) | [5 empty] | 188672.052 | NOT IN ITER ESTIMATE
LAB ENGINEERING @ 20% (US ACCOUTNTING ONLY) | [5 empty] | 147978.08 | NOT IN ITER ESTIMATE
INDIRECT CAPITAL COSTS
Research and Development During Construction
1.R - Fusion Power Core
1.1.R |  | PFC R&D |  |  | X | 7960.8 | Formerly 1.1.8
1.2.R |  | Vacuum Vessel R&D |  |  |  |  | None Required
1.3.R |  | TF Magnet R&D |  |  | X | 2870.4 | Formerly 1.3.6
1.4.R |  | PF Magnet R&D |  |  | X | 984.8 | Formerly 1.4.7
1.5.R |  | Cryostat R&D |  |  |  |  | None Required
1.6.R |  | Machine Support Structure R&D |  |  | X | 662.4 | None Required
2.R - Auxiliary Systems
2.1.R |  | Fueling R&D |  |  |  |  | None Required
2.2.R |  | Vacuum Pumping R&D |  |  |  |  | None Required
2.3.R |  | Fuel Processing R&D |  |  |  |  | None Required
2.4.1.R |  | ICRF R&D |  |  | X | 3628 | Formerly 2.4.1.7
2.4.2.R |  | ECRF R&D |  |  |  |  | None Required
2.4.3.R |  | LHH R&D |  |  |  |  | None Required
2.5.R |  | NB R&D |  |  |  |  | None Required
2.6.R |  | Device Instrumentation & Diagnostics R&D |  |  |  |  | None Required
2.7.R |  | Central Instrumentation & Control R&D |  |  |  |  | None Required
2.8.R |  | Power Supplies R&D |  |  |  |  | None Required
3.R - Remote Handling & Machine Assembly
3.3.R |  | Special Assembly Tooling R&D |  |  |  |  | None Required
3.4.R |  | Power Core Metrology R&D |  |  |  |  | None Required
3.5.R |  | Power Core Remote Handling R&D |  |  |  |  | None Required
3.6.R |  | Hot Cell Remote Handling R&D |  |  |  |  | None Required
Total Research and Development During Construction | [5 empty] | 16106.4
8 - Project Support & Oversight
8.1 | Project Management & Control - Simmons |  |  |  | X | 12180
8.2 | Systems Engineering - Heitzenroeder |  |  |  |  | 25440
8.2.1 |  | Design Integration |  |  | X | 21800
8.2.2 |  | Configuration Management & Control |  |  | X | 3640
8.3 | Environmental and Safety Management - Petti/Simmons |  |  |  | X | 3470
8.4 | Construction Management - Dilling / Heitzenroeder |  |  | X |  | 65580
8.5 | Scientific Support - Meade |  |  |  | X | 10180
Total Project Support and Oversight | [5 empty] | 116850
TOTAL INDIRECT COSTS | [5 empty] | 132956.4
TOTAL DIRECT AND INDIRECT CAPTAL COSTS | [5 empty] | 872846.8 | DOES NOT INCLUDE CONTINGENCY OR LAB ENGINEERING
COMISSIONING (PREPARATION FOR OPERATIONS)
9 - Preparations for Operations | [5 empty] | 19780
9.1 | Pre-Operational Planning - Simmons |  |  |  | X | 1730
9.2 | Pre-Opeational and Integrated Systems Testing - Heitzenroeder |  |  |  | X | 1310
9.3 | Operational Spares - Simmons |  |  |  | X | 16740