## Prototype
Proof of Concept Prototype
Tasks |  |  | Week Ending:
Phase/Segment/Task |  |  | 2003-04-18 | 2003-04-25 | 2003-05-02 | 2003-05-09 | 2003-05-16 | 2003-05-23 | 2003-05-30 | 2003-06-06 | 2003-06-13 | 2003-06-20 | 2003-06-27 | 2003-07-04 | 2003-07-11 | 2003-07-18
Project Management
Project Management
Status reports and status meetings
Business Scenario Development
Finalize business scenarios | bar: 2003-04-18 to 2003-05-16
Identify team leads for each business scenario team | bar: 2003-04-18 to 2003-05-09
Define workplan for business scenario development | bar: 2003-04-18
Create initial high-level site map | bar: 2003-04-18
Create site map template | bar: 2003-04-18 to 2003-04-25
Create paper-based storyboard template | bar: 2003-04-18 to 2003-04-25
Create demo script templates | bar: 2003-04-25
Kickoff meeting | bar: 2003-04-25
Conduct working session I (Scope) | bar: 2003-05-02
Create scope document for each scenario | bar: 2003-05-02 to 2003-07-04
Create site map for each scenario | bar: 2003-05-02 to 2003-07-04
Create overall site map | bar: 2003-05-02 to 2003-05-16
Conduct working session II (Review Site Map/Scope Documents) | bar: 2003-05-09
Develop content for each screen in site map | bar: 2003-05-09
Conduct working session III (Site Map, Storyboards) | bar: 2003-05-16
Finalize content for each screen in site map | bar: 2003-05-16 to 2003-07-04
Create paper-based storyboards (sample for each scenario) | bar: 2003-05-16 to 2003-07-04
Conduct working session IV (Story Boards) | bar: 2003-05-23
Conduct working session V (Look and Feel) | bar: 2003-05-30
Conduct working session VI (Finalize look and feel and Scenarios) | bar: 2003-06-06
Conduct working session VII | bar: 2003-06-13
Conduct working session VIII | bar: 2003-06-20
Conduct working session IX | bar: 2003-06-27
Conduct working session X | bar: 2003-07-04
Conduct working session XI | bar: 2003-07-11
Conduct working session XII | bar: 2003-07-18
Technical Architecture
Identify hosting facility | bar: 2003-04-18 to 2003-05-09
Create budget document detailing necessary HW/SW | bar: 2003-04-25 to 2003-05-02
Identify existing infrastructure available for use | bar: 2003-04-25
Create coding guidelines | bar: 2003-04-25 to 2003-05-02
Create comprehensive operations plan and technical architecture document | bar: 2003-04-25 to 2003-05-30
User Interface Standards and Templates
Review graphical treatments with project stakeholders (Kim Taylor and POC Team) | bar: 2003-05-30
Obtain final signoff on graphical treatment | bar: 2003-06-06
Create photoshop-based templates | bar: 2003-05-30 to 2003-06-06
Create custom graphical images | bar: 2003-06-06 to 2003-06-20
Create style guide based on templates | bar: 2003-06-06 to 2003-06-20
Send style guide to external business groups | bar: 2003-06-20
Development
Install and configure server development environment | bar: 2003-04-25 to 2003-05-02
Install and configure development workstations | bar: 2003-04-25 to 2003-05-02
Create navigation skeleton based on defined site map | bar: 2003-05-23 to 2003-05-30
Integrate demo with external projects | bar: 2003-06-13 to 2003-06-20
Code ASP pages | bar: 2003-05-23 to 2003-06-20
Create unit test script | bar: 2003-05-30 to 2003-06-06
Perform unit test on development environment | bar: 2003-06-13 to 2003-06-20
Correct identified issues | bar: 2003-06-13 to 2003-07-04
Create document to migrate code and data to production environment | bar: 2003-06-13 to 2003-06-20
Incorporate modifications from review meetings | bar: 2003-07-04 to 2003-07-18
Testing
Create system test plan | bar: 2003-06-06
Conduct system test Pass 1 on production environment | bar: 2003-06-13 to 2003-06-20
Correct identified issues | bar: 2003-06-13 to 2003-06-20
Conduct system test Pass 2 on production environment | bar: 2003-06-20 to 2003-07-04
Correct identified issues | bar: 2003-06-20 to 2003-07-04
Marketing and Communications
Review Prototype with users | bar: 2003-06-27 to 2003-07-18
Create demo scripts (step by step guide to demoing scenarios) | bar: 2003-05-30 to 2003-07-18
In Progress
Completed
In Jeopardy
Behind Schedule
Scheduled

## eAuthentication
eAuthentication
TASKS |  |  |  |  | Week Ending:
Phase/Segment/Task |  |  |  | Responsibility | 2003-04-11 | 2003-04-18 | 2003-04-25 | 2003-05-02 | 2003-05-09 | 2003-05-16 | 2003-05-23 | 2003-05-30 | 2003-06-06 | 2003-06-13 | 2003-06-20 | 2003-06-27 | 2003-07-04 | 2003-07-11 | 2003-07-18 | 2003-07-25
WebCAAF Ownership & Decision Making Model
| Define WebCAAF Team |  |  | Unangst, Niedermayer | bar: 2003-06-13 to 2003-07-04
| Define Board of Directors |  |  | Unangst, Niedermayer | bar: 2003-07-04 to 2003-07-25
| Define Delegation of Authorities |  |  | Unangst, Niedermayer | bar: 2003-07-04 to 2003-07-25
| Define Support Levels |  |  | Unangst, Niedermayer | bar: 2003-07-04 to 2003-07-25
WebCAAF Funding Model
| Define Funding Strategies |  |  | Unangst, Niedermayer | bar: 2003-06-27 to 2003-07-25
| Define Budget |  |  | Unangst, Niedermayer | bar: 2003-06-13 to 2003-06-27
Project Management for eAuthentication Effort
| Project Management of eAuthentication effort |  |  | eGov Team
| eAuthentication Next Steps Memo |  |  | eGov Team | bar: 2003-04-25
| eAuthentication Approach Meeting |  |  | eGov Team | bar: 2003-04-25
| Determine Documentation Set and Audience |  |  | eGov Team, Unangst | bar: 2003-04-25
| Address OMB Watch List Issues |  |  | eGov Team, Unangst | bar: 2003-05-09
| Identify Critical Success Factors |  |  | eGov Team | bar: 2003-07-25
Evaluation of existing Authentication Gateways
Assessment of WebCAAF
|  | Conduct initial assessment |  | eGov Team | bar: 2003-04-11
|  | Conduct design activities |  | eGov Team | bar: 2003-04-18 to 2003-05-02
|  | Develop WebCAAF expansion high-level design document |  | eGov Team | bar: 2003-05-09 to 2003-05-16
WebCAAF Integration with GSA
|  | Conduct initial assessment |  | eGov Team | bar: 2003-04-11
|  | WebCAAF/GSA integration design activities |  | eGov Team | bar: 2003-04-18 to 2003-05-02
|  | Develop WebCAAF/GSA integration design document |  | eGov Team | bar: 2003-05-09 to 2003-05-16
|  | Gap Analysis of WebCAAF, GSA and NFC |  | eGov Team | bar: 2003-05-09 to 2003-05-23
WebCAAF Expansion to USDA
WebCAAF as a General Support System
|  | Document WebCAAF Certification & Accreditation Status |  | Unangst, Lindstrom | bar: 2003-07-04 to 2003-07-25
|  | Develop WebFarm ASP Guidebook |  | EAI Team (Miller, Acosta, COS) | bar: 2003-05-16 to 2003-07-25
|  | Document Security Concepts |  | Lindstrom, eGov Team | bar: 2003-07-04 to 2003-07-25
|  | Define Help Desk and Support |  | Lindstrom, eGov Team | bar: 2003-07-04 to 2003-07-25
|  | Refine Roles and Responsibilities |  | Lindstrom, eGov Team | bar: 2003-07-04 to 2003-07-25
|  | Refine O&M P&P's |  | Lindstrom, eGov Team | bar: 2003-07-04 to 2003-07-25
|  | Refine Configuration Management/Change Control P&P's |  | Lindstrom, eGov Team | bar: 2003-07-04 to 2003-07-25
|  | Refine WebCAAF Auditing and Reporting |  | Lindstrom, eGov Team | bar: 2003-07-04 to 2003-07-25
|  | WebCAAF Auxillary System Document |  | VanNatta | bar: 2003-07-04 to 2003-07-25
WebCAAF Technical Expansion
|  | Detailed Design Activities |  | eGov Team | bar: 2003-05-16 to 2003-06-27
|  | Develop WebCAAF expansion detailed design document |  | eGov Team | bar: 2003-07-04
|  | Develop WebCAAF Agency Guidebook |  | eGov Team | bar: 2003-07-04 to 2003-07-25
-WebCAAF History, Scope, Objectives, etc. | bar: 2003-07-04 to 2003-07-25
-Document Registration Guidance | bar: 2003-07-04 to 2003-07-25
-LDAP Guidance | bar: 2003-07-04 to 2003-07-25
-Authentication Guidance | bar: 2003-07-04 to 2003-07-25
-Authorization Guidance | bar: 2003-07-04 to 2003-07-25
-Role Based Access Control | bar: 2003-07-04 to 2003-07-25
-Logon services integration | bar: 2003-07-04 to 2003-07-25
-Integration Requirements for Applications in Web Farms | bar: 2003-07-04 to 2003-07-25
-Integration Requirements for Applications outside Web Farms | bar: 2003-07-04 to 2003-07-25
-System Life Cycle for Agencies Preparing to use WebCAAF | bar: 2003-07-04 to 2003-07-25
-System Life Cycle for Application/WebCAAF integration | bar: 2003-07-04 to 2003-07-25
Directory Services Design
|  | Initial investigation existing capabilities in USDA |  | eGov Team | bar: 2003-05-16
|  | Directory Services Options Analysis |  | eGov Team | bar: 2003-05-23 to 2003-05-30
|  | Architecture Design Activities |  | eGov Team | bar: 2003-06-06 to 2003-06-20
|  | Ensure Design Meets GSA ECP standards |  | eGov Team | bar: 2003-06-27
|  | User Registration Design Activities |  | eGov Team | bar: 2003-07-04 to 2003-07-11
|  | Develop Directory Servces Detailed Design Document |  | eGov Team | bar: 2003-07-18 to 2003-07-25
Identity Management Design
|  | Identity Management High-Level Design Activities |  | eGov Team | bar: 2003-05-16 to 2003-05-30
|  | Identity Management High-Level Design Document |  | eGov Team | bar: 2003-06-06 to 2003-06-13
|  | Identity Management Detailed Design Activities |  | eGov Team | bar: 2003-06-20 to 2003-07-04
|  | Identity Management Detailed Design Document |  | eGov Team | bar: 2003-07-11 to 2003-07-25
eAuthentication Physical Architecture
|  | Select and Design Development Environment |  | eGov Team | bar: 2003-07-11
|  | Select and Design Test Environment |  | eGov Team | bar: 2003-07-11
|  | Select and Design Production Environment |  | eGov Team | bar: 2003-07-18 to 2003-07-25
High Level PKI Infrastructure Assessment and Design
Investigate exsisting PKI in USDA
|  | NFC initial investigation |  | eGov Team | bar: 2003-04-11
|  | Other PKI implementations in USDA |  | eGov Team | bar: 2003-04-11
| Investigate outsourced PKI (e.g. VeriSign, Entrust) |  |  | eGov Team | bar: 2003-04-18 to 2003-05-09
| Investigate/design OCSP servers |  |  | eGov Team | bar: 2003-05-09
| Develop Electronic Signature Guidance |  |  | eGov Team | bar: 2003-05-16 to 2003-05-23
| PKI Integration High-level Design Document |  |  | eGov Team | bar: 2003-05-16
| PKI Primer Document |  |  | Lindstrom
Requirements gathering from Agencies
Define Security Levels
|  | Create Levels of Assurance Matrix template (dependent on NIST draft Pub 199) |  | eGov Team | bar: 2003-05-02
Create Requirements Gathering Materials
|  | Create Impact Profile Assessment Procedure |  | eGov Team | bar: 2003-05-02
|  | Create Interaction Impact Profile Scorecard |  | eGov Team | bar: 2003-05-02
|  | Create Interaction CI&A Risk Assessment Procedure |  | eGov Team | bar: 2003-05-09 to 2003-05-30
|  | Create Assurance Level Mapping Procedure |  | eGov Team | bar: 2003-04-25 to 2003-05-02
|  | Create Interaction Requirements Questionnaire |  | eGov Team | bar: 2003-05-02
Define agency eAuthentication requirements
|  | Agency One on One Meetings to define requirements |  | eGov Team | bar: 2003-05-02 to 2003-06-20
|  |  | Define interactions/transactions included in scope | eGov Team | bar: 2003-04-25 to 2003-05-09
|  |  | Perform training activities with agency representatives | eGov Team | bar: 2003-04-25 to 2003-06-20
|  |  | Present, train and assist with Impact Profile Assessment Procedure | eGov Team | bar: 2003-04-25 to 2003-06-20
|  |  | Present, train and assist with Interaction Impact Profile Scorecard | eGov Team | bar: 2003-04-25 to 2003-06-20
|  |  | Present, train and assist with Interaction CI&A Risk Assessment Procedure | eGov Team | bar: 2003-04-25 to 2003-06-20
|  |  | Present, train and assist with Assurance Level Mapping Procedure | eGov Team | bar: 2003-04-25 to 2003-06-20
|  |  | Present, train and assist with Interaction Requirements Questionnaire | eGov Team | bar: 2003-05-09 to 2003-06-20
|  |  | Review/Assist risk profile activities with agencies | eGov Team | bar: 2003-06-20 to 2003-06-27
Review agency requirements | bar: 2003-06-20 to 2003-07-04
|  |  | Create compiled interaction/transaction authentication assurance level results | eGov Team | bar: 2003-06-20 to 2003-07-04
|  |  | Create compiled interaction/transaction technical requirements | eGov Team | bar: 2003-06-20 to 2003-07-04
Document Agency eAuthentication Requirements | bar: 2003-07-11 to 2003-07-18
|  |  | Document functional requirements | eGov Team | bar: 2003-07-11
|  |  | Document technical requirements | eGov Team | bar: 2003-07-11
|  |  | Review requirements with agencies | eGov Team | bar: 2003-07-11 to 2003-07-18
Design Agency Application Architecture
| Create intraction/transaction access control classes |  |  | eGov Team | bar: 2003-06-20
| Design Application Approach Guidelines/Technical Input Q for each control class |  |  | eGov Team | bar: 2003-06-20 to 2003-07-04
| Prepare eAuthentication Solution Overview presentation |  |  | eGov Team | bar: 2003-06-06 to 2003-07-11
| Present Application Approach Guidelines to the Agencies |  |  | eGov Team | bar: 2003-07-11 to 2003-07-18
| Support Agencies with architecture guidelines |  |  | eGov Team | bar: 2003-07-18 to 2003-07-25
| Support revision of C&A documentation |  |  | eGov Team | bar: 2003-07-11 to 2003-07-25
| Identify Training |  |  | eGov Team | bar: 2003-07-25
In Progress
Completed
In Jeopardy
Behind Schedule
Scheduled

## eLearning
eLearning
Tasks
Phase/Segment/Task |  |  |  |  | Responsibility | 2003-04-25 | 2003-05-02 | 2003-05-09 | 2003-05-16 | 2003-05-23 | 2003-05-30 | 2003-06-06 | 2003-06-13 | 2003-06-20 | 2003-06-27 | 2003-07-04 | 2003-07-11 | 2003-07-18 | 2003-07-25 | 2003-08-01 | 2003-08-08 | 2003-08-15 | 2003-08-22 | 2003-08-29 | 2003-09-05 | 2003-09-12 | 2003-09-19 | 2003-09-26 | 2003-10-03 | 2003-10-10 | On-Going
Project Management
|  | Project Management |  |  | ELRN
|  | Status reports and status meetings |  |  | ELRN
|  | Quality Assurance |  |  | ELRN, GOLRN
On-Line Training
|  | Participate in Content provider demos |  |  | ELN, GOLRN, USDA
|  | Define SLA or similar agreement with Content Providers |  |  | ELRN, GOLRN, Content Provider
|  | Agency decisions and purchase of licenses |  |  | USDA
|  | Load Data into GoLearn.gov and Test User Registration |  |  | ELRN, GOLRN
|  | Communicate Access & Registration Process to Users |  |  | ELRN, GOLRN
|  | GoLive with GoLearn.gov access for USDA employees |  |  | ELRN, GOLRN, USDA
Analysis
Implementation Approach
|  | Create Implementation Approach presentation (who, what, how) |  |  | ELRN
|  |  | Identify Core eLearning Team and other decision-makers |  | ELRN
System Requirements
|  | Define Service level (service & support) requirements |  |  | ELRN
|  |  | Validate with core ELN team and others(VA IT, CyberSecurity) |  | ELRN, GOLRN TBD
|  | Revalidate and communicate all reqt's to core eLearning team |  |  | ELRN
Product and Service Analysis * (contingent upon confirming GoLearn process)
|  | Define LMS Selection Process (included in approach) |  |  | ELRN, GOLRN
|  | eLearning Overview - LMS Demo (GoLearn, GeoLearning, Plateau) |  |  | ELRN, GOLRN, USDA, LMS
|  | Submit ALL requirements to GoLearn |  |  | ELRN, GOLRN
|  |  | Attach mission statement (Performance measures for LMS provider) |  | ELRN
|  | Create Evaluation Plan for Assessing LMS products |  |  | ELRN
|  | LMS Provider Orals and Solution Demos |  |  | ELRN, GOLRN, LMS
|  |  | Plan, schedule, and conduct follow-up sessions |  | ELRN, GOLRN, LMS
|  |  | Review Draft LMS Proposal |  | ELRN, GOLRN
|  |  | Revise and Finalize Proposal |  | ELRN, GOLRN, LMS
|  | Assess LMS options and make selection |  |  | ELRN, GOLRN, USDA
|  |  | Meet with Fed Agencies using LMS's (ATF, IRS, etc) |  | ELRN
|  |  | Make LMS recommendation |  | ELRN
Obtain Funding for the design and development of LMS by GoLearn
Product and Service Selection
|  | Draft Statement of Work |  |  | ELRN, GOLRN, LMS
|  | Award Contract with LMS provider and GoLearn.gov |  |  | ELRN, GOLRN, USDA
Prepare for Implementation
|  | Kick-Off Meeting to discuss implementation plan and next steps |  |  | ELRN, GOLRN, USDA, LMS
Design |  |  |  | * Design through build tasks and timeline will be dependent upon LMS provider's implementation process
Design Execution Architecture
|  | Design, Review, and Confirm Execution Arch with LMS provider |  |  | GOLRN, LMS
Standards
|  | Document UI and branding standards |  |  | ELRN, GOLRN, USDA
LMS Design
|  | LMS Discovery Session Planning |  |  | ELRN, GOLRN LMS
|  | Conduct LMS Discovery Session with Selected LMS |  |  | ELRN, GOLRN, LMS, USDA
|  | Define & Confirm Scope |  |  | ELRN, GOLRN, USDA
|  | Create LMS Detailed Design |  |  | GOLRN, USDA
(Sample items: How to register, filter info, curriculum design etc.)
|  | Create User Inteface Design |  |  | GOLRN, USDA, LMS
Pilot
|  | Conduct Test Pilot of Solution |  |  | ELRN, GOLRN, USDA
Test Planning
|  | Define System Test Plan and scripts (System, Unit, and Assembly) |  |  | GOLRN
|  | User Acceptance/Usability Test Plan and Scripts |  |  | GOLRN
Review: Functional Design
|  | Review Session |  |  | ELRN, GOLRN
|  | Review Updates |  |  | GOLRN
Define Business Processes for Agency Integration
|  | Planning |  |  | ELRN, GOLRN, USDA
|  | Process Design Meetings |  |  | ELRN, GOLRN, USDA
|  | Plan (How to Define and Customize Curriculums) |  |  | ELRN, GOLRN, USDA
|  | Register (How to Enroll and Administer Online) |  |  | ELRN, GOLRN, USDA
|  | Deliver (Define Content Loading Procedures) |  |  | ELRN, GOLRN, USDA
|  | Certify (How to Track Completion, Competency, and Compliance) |  |  | ELRN, GOLRN, USDA
|  | Measure (Managing Results, Integration with HR & Finance) |  |  | ELRN, GOLRN, USDA
Interface Design & Data Conversion
|  | Design Legacy LMS conversion |  |  | ELRN, GOLRN, USDA
|  | Design Interfaces for HR and Finance Systems |  |  | ELRN, GOLRN, USDA
|  | Develop Data conversion Approach (process, tools, and scripts) |  |  | GOLRN
Review: Process & Conversion Design
|  | Review Session |  |  | ELRN, GOLRN, USDA
|  | Review Updates |  |  | ELRN, GOLRN
Technical Architecture
Design
|  | Identify infrastructure needed for solution and conduct gap analysis |  |  | ELRN, GOLRN,
|  | Create physical architecture diagram and narrative |  |  | GOLRN, LMS
|  | Design Tech Arch for HR and Finance Integration |  |  | GOLRN, ELRN, LMS
Setup Technical Environments
|  | Confirm Technical Environment Configuration |  |  | GOLRN, LMS
|  | Establish a Development, Testing/UAT, and Production Environments |  |  | GOLRN
|  | Install, Configure, and Test LMS application |  |  | GOLRN
Build
LMS
|  | Configure Base LMS Modules |  |  | GOLRN, LMS
|  | Build Customized Modules and Components * (TBD from Rqt's) |  |  | GOLRN, LMS
|  | Unit Test |  |  | GOLRN, LMS
|  | Load Test Data |  |  | GOLRN,
Review: LMS Build & Test
|  | Review Session |  |  | ELRN, GOLRN
Interface & Conversion
|  | Build connection to HR System (PeopleSoft) |  |  | ELRN, GOLRN
|  | Build connection to Finance System |  |  | ELRN, GOLRN
|  | Unit Test |  |  | ELRN, GOLRN
|  | Assembly Test |  |  | ELRN, GOLRN
Review: Interface Build & Test
|  | Review Session |  |  | ELRN, GOLRN
Testing
Execute Test Plans and Fixes
|  | Conduct System Test Pass 1 on Production Environment |  |  | ELRN, GOLRN
|  | Debug |  |  | GOLRN
|  | Conduct System Test Pass 2 on Production Environment |  |  | ELRN, GOLRN
|  | Debug |  |  | GOLRN
|  | Conduct Usability Testing |  |  | ELRN, GOLRN, USDA
|  | Modifications |  |  | GOLRN
Implementation
Data Migration
|  | Convert and load production User data (HR, Finance) |  |  | ELRN, GOLRN, USDA
|  | Migrate Legacy LMS data |  |  | ELRN, GOLRN
|  | Load existing and new content |  |  | GOLRN
|  | Turn off Legacy LMS systems |  |  | ELRN, GOLRN, USDA
Review: Migration Complete
|  | Review Session |  |  | ELRN, GOLRN, USDA
Training
|  | Document standard operational policies and procedures |  |  | ELRN
|  | Planning and Logistics |  |  | ELRN
|  | Develop training materials (TC's and End User) |  |  | ELRN
|  | Prepare Training Coorinators |  |  | ELRN, GOLRN, USDA
|  | Train end users on use of eLearning solution |  |  | ELRN, GOLRN, USDA
Maintenance and Support
|  | Planning |  |  | ELRN, GOLRN
|  | Establish Maintenance and Support Plan for LMS |  |  | ELRN, GOLRN
Deployment
|  | Rollout, maintain, and support production LMS (ongoing) |  |  | ELRN, GOLRN
Review: Phase 1 Implementation Complete -Go Live!
|  | Review Session |  |  | ELRN, GOLRN
Marketing and Communications
Marketing
|  | Educate users on new solution value, benefits, and procedures |  |  | GOLRN
|  | Coordinate Prototype Team activities |  |  | PROTO
Communications
|  | Communicate project initiatives, changes, events, and progress |  |  | ELRN, GOLRN, USDA
|  | eLearning Postcard and Website Updates |  |  | ELRN, GOLRN, USDA
Change Management Planning and Implementation
|  | Provide Agency Assistance and guidance |  |  | ELRN, GOLRN, USDA
In Progress
Completed
In Jeopardy
Behind Schedule
Scheduled

## usda.gov
usda.gov
Tasks | [7 empty] | Week Ending:
Phase/Segment/Task |  |  | No. of Units | Estimating Factor | Hours per unit | Total Hours | Responsibility | 2003-04-25 | 2003-05-02 | 2003-05-09 | 2003-05-16 | 2003-05-23 | 2003-05-30 | 2003-06-06 | 2003-06-13 | 2003-06-20 | 2003-06-27 | 2003-07-04 | 2003-07-11 | 2003-07-18 | 2003-07-25 | 2003-08-01 | 2003-08-08 | 2003-08-15 | 2003-08-22
Project Management for usda.gov and Web Presence
| Manage project |  | 18 | Weeks | 15 | 270 | LA
| Create weekly status reports and attend status meetings |  | 18 | Weeks | 1 | 18 | LA
| Create and manage workplan |  | 18 | Weeks | 4 | 72 | LA
Create Document Templates
| Create Requirements document template |  | 1 | Document | 4 | 4 | BW | bar: 2003-04-25
| Create Use Case Scenarios Template |  | 1 | Document | 4 | 4 | BW | bar: 2003-04-25
| Create Physical Architecture Template |  | 1 | Document | 4 | 4 | BW | bar: 2003-04-25 to 2003-05-02
| Create Application Architecture Template |  | 1 | Document | 4 | 4 | BW | bar: 2003-04-25 to 2003-05-02
| Create Detailed Design Template |  | 1 | Document | 4 | 4 | BW | bar: 2003-04-25 to 2003-05-02
| Obtain stakeholder signoff on templates |  | 5 | Documents | 2 | 10 | LA | bar: 2003-04-25 to 2003-05-02
Agency Initiative Overview
Prepare approach presentation | bar: 2003-05-09
Plan meeting | bar: 2003-05-16 to 2003-05-23
Facilitate Meeting | bar: 2003-05-30
Document and prepare for decision meetings | bar: 2003-05-23
Define Application Requirements
| Identify key stakeholders |  | 1 | Document | 8 | 8 | BW | bar: 2003-04-25
| Meet with stakeholders for brainstorming sessions |  | 2 | Meetings | 8 | 16 | LA, BW | bar: 2003-04-25 to 2003-05-02
Define functional requirements
|  | Compile baseline functional requirements | 1 | Document | 40 | 40 | CW | bar: 2003-04-25 to 2003-05-02
|  | Collect functional requirements | 1 | Document | 80 | 80 | CW , LA | bar: 2003-05-09 to 2003-05-16
|  | Review and prioritize functional requirements | 2 | Meetings | 24 | 48 | CW , LA | bar: 2003-05-16 to 2003-05-23
|  | Make changes to functional requirements and finalize | 1 | Document | 40 | 40 | CW | bar: 2003-05-23
Define technical requirements
|  | Compile baseline technical requirements | 1 | Document | 40 | 40 | BW | bar: 2003-04-25 to 2003-05-02
|  | Collect technical requirements | 1 | Document | 40 | 40 | BW | bar: 2003-05-09 to 2003-05-16
|  | Review and prioritize technical requirements | 2 | Meetings | 24 | 48 | BW | bar: 2003-05-16 to 2003-05-23
|  | Make changes to technical requirements and finalize | 1 | Document | 40 | 40 | BW | bar: 2003-05-23
Define usda.gov Information Architecture/ Site Map
| Define information architecture (site map) |  | 1 | Document | 40 | 40 | LA | bar: 2003-05-16 to 2003-05-23
| Review site map with stakeholders |  | 2 | Meetings | 8 | 16 | LA | bar: 2003-05-23 to 2003-05-30
| Incorporate review comments and update site map |  | 1 | Document | 24 | 24 | LA | bar: 2003-05-23 to 2003-06-06
Develop Use Case Scenarios
| Develop detailed use cases |  | 12 | Scenarios | 8 | 96 | BW, An 2 | bar: 2003-05-30 to 2003-06-06
| Review use cases with stakeholders |  | 4 | Meetings | 8 | 32 | BW | bar: 2003-06-06 to 2003-06-20
| Incorporate review comments and update use cases |  | 1 | Document | 40 | 40 | An 2 | bar: 2003-06-13
Define Process for Contributing Content
| Develop process flows |  | 1 | Presentation | 80 | 80 | Con 1, CW | bar: 2003-05-30 to 2003-06-06
| Review with stakeholders |  | 2 | Meetings | 8 | 16 | Con 1 | bar: 2003-06-06
| Incorporate review comments and update process flows |  | 1 | Document | 40 | 40 | CW | bar: 2003-06-13
Design usda.gov User Interface
Develop wireframes
|  | Create wireframes | 12 | Screens | 16 | 192 | LA, Con1, CW | bar: 2003-06-13 to 2003-06-27
|  | Review wireframes with stakeholders | 4 | Meetings | 8 | 32 | LA, Con1, CW | bar: 2003-06-20 to 2003-06-27
|  | Incorporate review comments and update wireframes | 12 | Screens | 2 | 24 | bar: 2003-06-27 to 2003-07-04
Develop HTML templates for usda.gov
|  | Create HTML code | 12 | Screens | 16 | 192 | Con 1, CW, An 2 | bar: 2003-06-20 to 2003-07-04
|  | Test HTML code for browser compatibility | 12 | Screens | 5 | 60 | bar: 2003-06-27 to 2003-07-11
|  | Test HTML code for accessibility | 12 | Screens | 2 | 24 | bar: 2003-06-27 to 2003-07-11
|  | Update HTML code |  |  |  |  | 3.45 | bar: 2003-06-27 to 2003-07-11
Develop style guide for usda.gov
|  | Write style guide for site | 1 | Document | 40 | 40 | CW | bar: 2003-07-11
|  | Incorporate review comments and update style guide | 1 | Document | 24 | 24 | CW | bar: 2003-07-18
Conduct Usability Testing
Conduct usability testing
|  | Create usability approach presentation | 1 | Presentation | 40 | 40 | Con 1, CW | bar: 2003-07-25
|  | Create usability scripts | 1 | Script | 40 | 40 | CW | bar: 2003-08-01
|  | Conduct tests | 8 | Tests | 4 | 32 | Con 1, CW, An 2 | bar: 2003-08-08 to 2003-08-15
|  | Deliver results and recommendations | 1 | Presentation | 40 | 40 | Con 1, CW | bar: 2003-08-22
Design Physical and Application Architecture
| Create physical architecture |  | 1 | Document | 40 | 40 | BW | bar: 2003-07-11
| Create application architecture |  | 1 | Document | 80 | 80 | BW, An 2 | bar: 2003-07-18
| SME Review |  | 2 | Weeks | 8 | 16 | SME | bar: 2003-07-25
| Review physical and application architecture with stakeholders |  | 4 | Meetings | 8 | 32 | BW, An 2 | bar: 2003-07-25
| Revise physical and application architecture based on reviews |  | 1 | Document | 40 | 40 | BW | bar: 2003-07-25 to 2003-08-01
| Coordinate portals architecture with other Enablers |  | 5 | Meetings | 4 | 20 | BW | bar: 2003-07-11 to 2003-08-01
Detailed Design
| Create detailed design |  | 1 | Document | 160 | 160 | BW, C1, An 2 | bar: 2003-08-01 to 2003-08-15
| Review detailed design with stakeholders |  | 4 | Meetings | 24 | 96 | BW, C1 | bar: 2003-08-15 to 2003-08-22
| Finalize detailed design |  | 1 | Document | 40 | 40 | BW, C1, An 2 | bar: 2003-08-22
[5 empty] | FTE'S REQUIRED TO FINISH IN 16 WEEKS: | #VALUE!
In Progress
Completed
In Jeopardy
Behind Schedule
Scheduled
eDeployment Product Selection
eDeployment Product Selection
eDeployment Product Selection
eDeployment Product Selection

## eDeployment
eDeployment Pre-Implementation Tasks
TASKS |  |  | Week Ending:
Phase/Segment/Task |  |  | 2003-04-25 | 2003-05-02 | 2003-05-09 | 2003-05-16 | 2003-05-23 | 2003-05-30 | 2003-06-06 | 2003-06-13 | 2003-06-20 | 2003-06-27 | 2003-07-04 | 2003-07-11 | 2003-07-18 | 2003-07-25 | 2003-08-01 | 2003-08-08 | 2003-08-15 | 2003-08-22
Project Planning and Project Management
Manage project
Prepare status reports
Workplanning
Create pre-Implementation workplan | bar: 2003-04-25
Manage workplan
Prepare pre-implementation approach | bar: 2003-04-25
Workplan Implementation Phase | bar: 2003-08-01
Agency Initiative Overview
Prepare approach presentation template | bar: 2003-05-02
Web Content Management
Prepare approach presentation | bar: 2003-05-09
Plan meeting | bar: 2003-05-09
Facilitate Meeting | bar: 2003-06-06
Document and prepare for decision meetings | bar: 2003-06-06
Portal
Prepare approach presentation | bar: 2003-05-02
Plan meeting | bar: 2003-05-02
Facilitate Meeting | bar: 2003-06-06
Document and prepare for decision meetings | bar: 2003-06-06
Document Management
Prepare approach presentation | bar: 2003-05-09
Plan meeting | bar: 2003-05-09
Facilitate Meeting | bar: 2003-06-06
Document and prepare for decision meetings | bar: 2003-06-06
Assess Current Environment
Assess agency technology assets
Create agency technology survey | bar: 2003-04-25
Revise survey based on existing documentation | bar: 2003-05-02 to 2003-05-09
Distribute survey | bar: 2003-06-06
Compile survey results | bar: 2003-06-13
Assess hosting capabilities
Create evaluation matrix | bar: 2003-06-06
Assess USDA hosting capabilities (NITC, Service Centers, Agencies, etc.) | bar: 2003-06-20 to 2003-07-04
Prepare Hosting Capabilities Recommendation | bar: 2003-07-11
Compile recommendations on reusable assets | bar: 2003-06-13
Prepare for Vendor Assessment
Identify vendor selection stakeholders | bar: 2003-05-23
Create detailed vendor assessment approach | bar: 2003-05-16 to 2003-05-23
Define approach and template for evaluation process | bar: 2003-04-25 to 2003-05-02
Create list of components for evaluation | bar: 2003-05-30
Define Technology guiding principles | bar: 2003-06-06 to 2003-06-13
Content Management
Review functional and technical requirements | bar: 2003-05-30
Prioritize functional and technical requirements | bar: 2003-06-06 to 2003-06-13
Create evaluation documents | bar: 2003-06-13
Finalize evaluation document and distribute | bar: 2003-06-13 to 2003-06-20
Create evaluation matrix | bar: 2003-06-27
Document Management
Review functional and technical requirements | bar: 2003-05-30
Prioritize functional and technical requirements | bar: 2003-06-06 to 2003-06-13
Create evaluation documents | bar: 2003-06-13
Finalize evaluation document and distribute | bar: 2003-06-13 to 2003-06-20
Create evaluation matrix | bar: 2003-06-27
Portal
Review functional and technical requirements | bar: 2003-05-30
Prioritize functional and technical requirements | bar: 2003-06-06 to 2003-06-13
Create evaluation documents | bar: 2003-06-13
Finalize evaluation document and distribute | bar: 2003-06-13 to 2003-06-20
Create evaluation matrix | bar: 2003-06-27
Compile list of vendors to be considered | bar: 2003-06-13 to 2003-06-20
Identify approach for non-evaluation components | bar: 2003-06-20
Vendor Assessment and Procurement
Content Management
Address vendor questions | bar: 2003-06-27
Facilitate Vendor Oral Presentations/demos | bar: 2003-07-04 to 2003-07-11
Complete evaluation matrix | bar: 2003-07-11 to 2003-07-18
Create recommendations presentation | bar: 2003-07-25
Review RFP results with stakeholders | bar: 2003-08-01
Portal
Address vendor questions | bar: 2003-06-27
Facilitate Vendor Oral Presentations/demos | bar: 2003-07-04 to 2003-07-11
Complete evaluation matrix | bar: 2003-07-11 to 2003-07-18
Create recommendations presentation | bar: 2003-07-25
Review RFP results with stakeholders | bar: 2003-08-01
Document Management
Address vendor questions | bar: 2003-06-27
Facilitate Vendor Oral Presentations/demos | bar: 2003-07-04 to 2003-07-11
Complete evaluation matrix | bar: 2003-07-11 to 2003-07-18
Create recommendations presentation | bar: 2003-05-23; 2003-07-25
Review RFP results with stakeholders | bar: 2003-08-01
Non-RFP components
Perform research on non-RFP components | bar: 2003-05-30 to 2003-06-20
Make recommendations for non-RFP components | bar: 2003-06-27 to 2003-07-11
Review non-RFP recommendations with stakeholders | bar: 2003-07-18
Negotiate software fees and licenses with vendors | bar: 2003-07-25 to 2003-08-01
Initiate procurement process | bar: 2003-07-25 to 2003-08-08
Early Adopter Planning Assistance
Prepare early adopter roadmap | bar: 2003-05-30 to 2003-06-06
Create early adopter agreement | bar: 2003-06-13
Develop early adopter templates
Create workplan template | bar: 2003-06-13
Provide Early Adopter Support | bar: 2003-05-30 to 2003-08-22
Design Application Architecture
eDeployment Application Architecture
Overall | bar: 2003-08-08 to 2003-08-15
Content Management | bar: 2003-08-08 to 2003-08-15
Document Management | bar: 2003-08-08 to 2003-08-15
Portals/Search | bar: 2003-08-08 to 2003-08-15
Review application architecture with stakeholders | bar: 2003-08-22
SME Review | bar: 2003-08-22
Revise application architecture based on reviews | bar: 2003-08-22
Design Physical Architecture
eDeployment Physical Architecture
Select and Design Development Environment | bar: 2003-07-25
Select and Design Test Environment | bar: 2003-08-01
Select and Design Production Environment | bar: 2003-08-08
SME Review | bar: 2003-08-08
Revise physical architecture based on reviews | bar: 2003-08-15
Review physical architecture with stakeholders | bar: 2003-08-15
In Progress
Completed
In Jeopardy
Behind Schedule
Scheduled