## Sheet1
|  | SANDRA | MARC | JACK |  |  | JOSE |  |  |  | BOB | BOB | GRANT |  |  | JACK | GRANT |  |  | Sherri | Grant | JACK | SANDRA | SANDRA
|  | 1 | 2 | 3 | 4 | ASSEMBLY |  | 5 | DATASHEETS |  | 6 | 7 | 8 | 9 | Electrical tests |  |  |  |  | 10 | 11 | 13 | 12 | 14
Date | Planned Modules Shipped | OK/ANALYSIS | VI | Preship test | SB | HYBRID | MODULE | SB | HYBRID | MODULE | Metrology | Special Analysis | IV | H. Init | H. LTW | H. LTC | M Init | M LTT | M PM | Scan VI | Upload VI | Label boxex | Upload signoff | DB Shipped
2004-05-10 | 60 | 60
2004-05-17 | 100 | 100
2004-05-24 | 100 | 140
2004-05-31 | 140 | 190 | 231 | 231 | 460 | 501 | 445 | 0 | 0 | 0 | 184 | 190 | 263 | 150 | 150 | 150 | 150 | 150 | 150 | 141 | 141 | 140 | 140 | 140
2004-06-07 | 140 | 240 | 290 | 241 | 460 |  |  | 60 | 60 | 60 | 184 | 240 | 263 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 190 | 140 | 140 | 140
2004-06-14 | 180 | 280 | 350 | 300 | 480 |  |  | 120 | 120 | 120 | 184 | 280 | 280 | 230 | 230 | 230 | 230 | 230 | 230 | 240 | 240 | 180 | 180 | 180
2004-06-21 | 180 | 280 | 410 | 360 | 500 |  |  | 180 | 180 | 180 | 184 | 280 | 280 | 230 | 230 | 230 | 230 | 230 | 230 | 280 | 280 | 180 | 180 | 180
2004-06-28 | 220 | 320 | 470 | 420 | 520 |  |  | 240 | 240 | 240 | 320 | 320 | 320 | 270 | 270 | 270 | 270 | 270 | 270 | 320 | 320 | 220 | 220 | 220
2004-07-05 | 260 | 360 | 540 | 480 | 540 |  |  | 300 | 300 | 300 | 360 | 360 | 360 | 310 | 310 | 310 | 310 | 310 | 310 | 360 | 360 | 260 | 260 | 260
2004-07-12 | 300 | 400 |  | 540 |  |  |  | 360 | 360 | 360 | 400 | 400 | 400 | 350 | 350 | 350 | 350 | 350 | 350 | 400 | 400 | 300 | 300 | 300
2004-07-19 | 340 | 440 | [5 empty] | 420 | 420 | 420 | 440 | 440 | 440 | 390 | 390 | 390 | 390 | 390 | 390 | 440 | 440 | 340 | 340 | 340
2004-07-26 | 380 | 480 | [5 empty] | 480 | 480 | 480 | 480 | 480 | 480 | 430 | 430 | 430 | 430 | 430 | 430 | 480 | 480 | 380 | 380 | 380
2004-08-02 | 420 | 540 |  |  |  | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 490 | 490 | 490 | 490 | 490 | 490 | 540 | 540 | 420 | 420 | 420
2004-08-09 | 460 | [12 empty] | 540 | 540 | 540 | 540 | 540 | 540 |  |  | 460 | 460 | 460
2004-08-16 | 500 | [20 empty] | 500 | 500 | 500
2004-08-23 | 540 | [20 empty] | 540 | 540 | 540
2004-08-30
2004-09-06
2004-09-13
2004-09-20
2004-09-27
1 | OK/ANALYSIS | Analysis of test data to produce list of modules "OK to Oxford" to be worked on
2 | VI | Visual Inspection of modules, carrying boxes, applying bar code
3 | Preship test | Confirmation (short electrical) test of modules after visual inspection
4 | ASSEMBLY | Upload of SB assembly following the module construction and assignment of P# to serial number. Hybrid and Module Assembly follow the Test Data analysis
5 | DATASHEETS | Upload of assembly datasheets started on 5/31 can follow Test Data Analysis
6 | Metrology | Metrology files uploads
7 | Special Analysis | Special Analysis to provide input for quality summary (eg. Oscillation, Special Settings, Retest results) following the OK/Analysis list
8 | IV | IV data uploads after conversion of excel files from Jose to produce row data and plots in the format required by DB
9 | Electrical tests | Test Data uploads (Hybrid Initital, Hybrid LTT Warm, Hybrid LTT Cold, Module Initial, Module LTT, Module post metrology) following the OK/Analysis list. This operation is automatic but list of tests must be produced first
10 | Scan VI | Scan of Visual Inspection reports to be done using scanner in Sandra's office.
11 | Upload VI | VI files transferred to appropriate machine and uploaded to DB after conversion.
12 | Label boxex | Labels with module info (serial number, type, special setting) are printed and applied to carrying boxes
13 | Upload signoff | Quality summary, Signoff report uploaded to DB
14 | DB Shipped | Modules virtually (DB) shipped to Oxford after actual shipment