## Sheet1
Cost Estimate variance 3/14/00
Comparison of D0 baseline cost estimate (PMP ver1.3, June 17, 1998) with Current cost estimate
NOTE: The baseline cost estimate is in FY95$ and the curren estimate is in Then Yr$ [Sorry, it's the best we can do at the moment]
WBS | System | Baseline M&S (FY95 k$) | Contingency | Total | Current M&S (Then Yr k$) | Contingency | Total | VARIANCE
1.1.1 | Silicon Tracker | 4952 | 786 | 5738 | 7871 | 230 | 8101 | 2363
1.1.2 | Fiber Tracker | 7377 | 1601 | 8978 | 7734 | 100 | 7834 | -1144
1.1.3 | CPS | 355 | 62 | 417 | 238 | 0 | 238 | -179
1.1.4 | FPS | 440 | 80 | 520 | 524 | 5 | 529 | 9
1.1.5 | Tracking Electr. | 2289 | 324 | 2613 | 3694 | 100 | 3794 | 1181
1.2.1 | Cal Electr. | 4055 | 379 | 4434 | 4348 | 15 | 4363 | -71
1.2.2 | ICD | 301 | 40 | 341 | 304 | 10 | 314 | -27
1.3.1 | Cosmic Ray scint | 1056 | 0 | 1056 | 1223 | 0 | 1223 | 167
1.3.2 | Central Muon system | 981 | 99 | 1080 | 952 | 0 | 952 | -128
1.3.3 | Forward Muon Trigger (Pixels) | 1709 | 262 | 1971 | 2133 | 0 | 2133 | 162
1.3.4 | Forward Muon Tracking (MDT) | 1158 | 206 | 1364 | 1374 | 33 | 1407 | 43
1.3.5 | Muon Electronics | 3624 | 443 | 4067 | 3907 | 0 | 3907 | -160
1.4.1 | Trigger Framework | 1337 | 257 | 1594 | 1859 | 0 | 1859 | 265
1.4.2 | Lum Monitor | 134 | 25 | 159 | 136 | 0 | 136 | -23
1.4.3 | Level 1 Trig | 1289 | 197 | 1486 | 1500 | 0 | 1500 | 14
1.4.4 | Level 2 Trig | 1818 | 356 | 2174 | 2047 | 35 | 2082 | -92
1.4.5 | Level 3 Trig | 739 | 129 | 868 | 1064 | 0 | 1064 | 196
1.5.1 | Online | 605 | 117 | 722 | 722 | 0 | 722 | 0
3.1.1 | Solenoid | 5041 | 272 | 5313 | 4918 | 0 | 4918 | -395
|  | 39260 | 5635 | 44895 | 46548 | 528 | 47076 | 2181