## Template
MATERIAL SUBMITTAL LIST AND REVIEW ESTIMATE
| LIST OF MATERIAL SUBMITTALS Note:(Complete this portion and attach to Spec. 01330) | [7 empty] | SUBMITTAL REVIEW ESTIMATE
| Park/PMIS/Project Title | [7 empty] | (Complete this portion for AE Const. Serv. task order negotiation)
| SUBMITTAL |  |  | REQUIREMENTS (indicate with an "X") |  |  |  |  | CMR FIELD REVIEW ("X") | A/E REVIEW TIME (indicate number of hours)
| Spec. Sec. | Par. No. | Description | CERT./LAB TEST | REPORT/CALC. OR PLAN | SAMPLE | SHOP DRAWING | Mfg. DATA & INSTRUCTIONS |  | ARCH (hrs) | CE (hrs) | SE (hrs) | ME (hrs) | EE (hrs) | PM - Coor. (hrs) | LA (hrs)
| Note:(See color coded instructions on page 2 - Instructions) | [7 empty] | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Instructions
"MATERIAL SUBMITTAL LIST AND REVIEW ESTIMATE" INSTRUCTIONS
PHASE OF WORK | RESPONSIBLE PARTY | DESCRIPTION OF TASKS
DESIGN SERVICES (CONSTRUCTION DOCUMENTS PHASE) | Design A/E | 1. Fill out Park/PMIS/Project title cell with project reference information.
2. Use this form to record construction submittal requirements for the project. Fill out the Specification Section, Paragraph number, Description columns on the left side of the form. Insert additional rows, as required, for sections containing multiple submittals.
3. In the columns designated "REQUIREMENTS (indicate with an 'X")", indicate the submittal requirement(s) by placing an "X" in the appropriate box(s).
4. Copy the "List Of Material Submittals" side of the form (Yellow portion), and attach a black and white version to the end of specification section 01330 in the project manual. Delete instructional notes on the top and bottom of the page.
CONSTRUCTION SERVICES (CONSTRUCTION PHASE) | Construction COR | 1. Utilize the "List Of Material Submittals" form submitted with the Final Construction Documents. If amendments have been issued make adjustments to the submittal requirements if necessary.
2. Indicate which submittals will be reviewed by the Construction Management Representative (CMR) in the field by placing an "X" in the far right column.If more than one submittal item is indicated on the same row and the review duties will be split between the A/E and CMR, than add another row and copy/paste the CMR items to that new row and indicate CMR field review. The objective is to clearly indicate who is responsible for the submittal review, CMR or A/E.
3. Attach this form to the "A/E Construction Services" Scope of Services.
4. Utilize this form to generate the estimated time required for the AE to accomplish the submittal reviews by inserting your estimated number of hours per discipline under corresponding column headings.
5. Add discipline headings columns, as required.
6. Use the total number of hours per discipline at the bottom of the form and apply the hourly rates listed in the IDIQ base contract to formulate the government estimate for submittal reviews.
7. Use the information contained within this form to negotiate the submittal review portion of the AE Construction Services task order.
8. Provide this form to the CMR so they have an understanding of which submittals they are responsible for and which are to be forwarded to the AE.
| AE | 1. Indicate level of effort required for each submittal review by inserting the number of hours for each discipline under the "A/E Review Time (Indicate number of hours)" column.
2. Submittals shown with an "X" in the far right column under "CMR Field Review" will not be the A/E's responsibility and these rows are to be left blank.
3. Use the total number of hours indicated for each discipline and apply the appropriate rates from the IDIQ base contract to formulate your estimate.
4. Use this estimate to negotiate the submittal review portion of the AE Construction Services portion of the task order.

## List of Submittals Sample
LIST OF MATERIAL SUBMITTALS
Death Valley National Park, PMIS 06660, Rehabilitate Maintenance Facilities
SUBMITTAL |  |  | REQUIREMENTS (indicate with an "X")
Spec. Sec. | Par. No. | Description | CERT./LAB TEST | REPORT/CALC. OR PLAN | SAMPLE | SHOP DRAWING | Mfg. DATA & INSTRUCTIONS
2110 | 1.3 | Excavation Safety Plan |  | X
2120 | 1.4 | Signed copies of manifest | X
2320 | 1.2 | Procedures for trench dewatering |  | X
2501 | 1.3 | Water and sewer test accuracy cert. | X
2502 | 1.2 | Water line marking tape sample |  |  | X
2517 | 1.2 | Fire Hydrants
|  | Manufactures information: x-section |  |  |  |  | X
|  | Certification with AWWA C502-94 | X
2725 | 1.2 | Aggregate base course | X
2778 | 1.2 | Walks, curbs and gutters, mix design |  | X
3300 | 1.3 | Cast in-Place Concrete
|  | Steel placement shop drawing |  |  |  | X
|  | Batching and hauling plan |  | X
|  | Rebar certification | X
4100 | 1.2 | Mortar
|  | Cured mortar sample |  |  | X
|  | Material certification & test reports | X
4201 | 1.3 | Masonry Work
|  | Shop drawings |  |  |  | X
|  | Masonry unit sample |  |  | X
|  | Mfg. information on admixtures |  |  |  |  | X
5120 | 1.4 | Structural steel |  |  |  | X | X
5311 | 1.3 | Steel roof deck shop drawings |  |  |  | X
5400 | 1.3 | Cold Formed Metal Framing
|  | Shop drawings and erection diagrams |  |  |  | X
|  | Mill certificates | X
|  | Welder certificates | X
6402 | 1.3 | Interior architectural woodwork |  | X |  | X | X
7100 | 1.4 | Cold Fluid Applied Waterproofing
|  | Product data |  |  |  |  | X
|  | Shop drawings |  |  |  | X
|  | Installer certification | X
|  | Product test reports | X
7260 | 1.2 | Vapor retarder mfg. installation instructions |  |  |  |  | X
7610 | 1.3 | Sheet metal roofing |  |  | X | X | X
8110 | 1.3 | Steel Doors and Frames
|  | Shop drawings |  |  | X
|  | Catalog cuts and install instructions |  |  |  |  | X
|  | Door schedule |  | X
8520 | 1.3 | Aluminum windows |  |  | X | X | X
8710 | 1.2 | Finish hardware schedule |  | X
9310 | 1.6 | Ceramic Tile
|  | Sample |  |  | X
|  | Mfg. literature |  |  |  |  | X
|  | Certification | X
9901 | 1.4 | Painting
|  | Mfg. color chart |  |  |  |  | X
|  | Paint sample applied to like material |  |  | X
|  | Mfg. information |  |  |  |  | X
10800 | 1.7 | Toilet and bath acc. mfg. info |  |  |  |  | X
11452 | 1.2 | Kitchen appliances, product data |  |  |  |  | X
12500 | 1.3 | Horizontal louver blinds |  |  |  |  | X
15060 | 1.4 | Piping and accessories | X |  |  | X | X
15170 | 1.3 | Electric motor efficiencies | X
15800 | 1.3 | Ductwork |  |  |  | X | X
16470 | 1.4 | Panel boards | X |  |  | X | X
16500 | 1.4 | Type D & Type N fixtures | X |  |  |  | X

## Review Estimate Sample
MATERIAL SUBMITTAL LIST AND REVIEW ESTIMATE
| LIST OF MATERIAL SUBMITTALS | [7 empty] | SUBMITTAL REVIEW ESTIMATE
| Death Valley National Park, PMIS 06660, Rehabilitate Maintenance Facilities | [7 empty] | (Complete this portion for AE Const. Serv. task order negotiation)
| SUBMITTAL |  |  | REQUIREMENTS (indicate with an "X") |  |  |  |  | CMR FIELD REVIEW ("X") | A/E REVIEW TIME (indicate number of hours)
| Spec. Sec. | Par. No. | Description | CERT./LAB TEST | REPORT/CALC. OR PLAN | SAMPLE | SHOP DRAWING | Mfg. DATA & INSTRUCTIONS |  | ARCH (hrs) | CE (hrs) | SE (hrs) | ME (hrs) | EE (hrs) | PM - Coor. (hrs) | LA (hrs)
| 2110 | 1.3 | Excavation safety plan |  | X |  |  |  | X
| 2120 | 1.4 | Signed copies of manifest | X |  |  |  |  | X
| 2320 | 1.2 | Procedures for trench dewatering |  | X | [5 empty] | 2
| 2501 | 1.3 | Water and sewer test accuracy cert. | X |  |  |  |  | X
| 2502 | 1.2 | Water line marking tape sample |  |  | X |  |  | X
| 2517 | 1.2 | Fire Hydrants
|  |  | Manufactures information: x-section |  |  |  |  | X |  |  | 1
|  |  | Certification with AWWA C502-94 | X |  |  |  |  | X
| 2725 | 1.2 | Aggregate base course | X | [6 empty] | 3
| 2778 | 1.2 | Walks, curbs and gutters, mix design |  | X | [5 empty] | 3 | 1
| 3300 | 1.3 | Cast in-Place Concrete
|  |  | Steel placement shop drawing |  |  |  | X |  |  |  | 1 | 2
|  |  | Batching and hauling plan |  | X | [6 empty] | 1
|  |  | Rebar certification | X | [7 empty] | 1
| 4100 | 1.2 | Mortar
|  |  | cured mortar sample |  |  | X |  |  |  | 1 | 1
|  |  | Material certification & test reports | X |  |  |  |  | X
| 4201 | 1.3 | Masonry Work
|  |  | Shop drawings |  |  |  | X |  |  |  |  | 4
|  |  | Masonry unit sample |  |  | X |  |  | X | 1
|  |  | Mfg. information on admixtures |  |  |  |  | X |  |  |  | 1
| 5120 | 1.4 | Structural steel |  |  |  | X | X |  |  |  | 4
| 5311 | 1.3 | Steel roof deck shop drawings |  |  |  | X |  |  |  |  | 4
| 5400 | 1.3 | Cold Formed Metal Framing
|  |  | Shop drawings and erection diagrams |  |  |  | X |  |  |  |  | 4
|  |  | Mill certificates | X |  |  |  |  | X
|  |  | Welder certificates | X |  |  |  |  | X
| 6402 | 1.3 | Interior architectural woodwork |  | X |  | X | X |  | 6
| 7100 | 1.4 | Cold Fluid Applied Waterproofing
|  |  | Product data |  |  |  |  | X
|  |  | Shop drawings |  |  |  | X |  |  | 2
|  |  | Installer certification | X |  |  |  |  | X
|  |  | Product test reports | X |  |  |  |  | X
| 7260 | 1.2 | Vapor retarder mfg. installation instructions |  |  |  |  | X | X
| 7610 | 1.3 | Sheet metal roofing |  |  | X | X | X |  | 3 |  | 2
| 8110 | 1.3 | Steel Doors and Frames
|  |  | Shop drawings |  |  | X |  |  |  | 3
|  |  | Catalog cuts and install instructions |  |  |  |  | X |  | 2
|  |  | Door schedule |  | X |  |  |  |  | 3
| 8520 | 1.3 | Aluminum windows |  |  | X | X | X |  | 6
| 8710 | 1.2 | Finish hardware schedule |  | X |  |  |  |  | 3
| 9310 | 1.6 | Ceramic Tile
|  |  | Sample |  |  | X |  |  |  | 2
|  |  | Mfg. literature |  |  |  |  | X | X
|  |  | Certification | X |  |  |  |  | X
| 9901 | 1.4 | Painting
|  |  | Mfg. color chart |  |  |  |  | X | X
|  |  | Paint sample applied to like material |  |  | X |  |  |  | 2
|  |  | Mfg. information |  |  |  |  | X |  | 1
| 10800 | 1.7 | Toilet and bath acc.mfg.info |  |  |  |  | X |  | 3
| 11452 | 1.2 | Kitchen appliances, product data |  |  |  |  | X |  | 3
| 12500 | 1.3 | Horizontal louver blinds |  |  |  |  | X | X
| 15060 | 1.4 | Piping and accessories | X |  |  | X | X |  |  |  |  | 6
| 15800 | 1.3 | Ductwork |  |  |  | X | X |  |  |  |  | 6
| 16470 | 1.4 | Panel boards | X |  |  | X | X | [5 empty] | 6
[9 empty] | Total | 41 | 11 | 24 | 12 | 6 | 0 | 0