## 1_2_2
|  | Preradiator (WBS 1.2.2) |  |  | Engineer |  | Mech Spare (%) |  | Elect.Spares (%) |  | Cost/FTE Physicist, Engineer, Designer, Technician
|  | Cost Estimate/Funding Profile |  |  | Designer |  | 5 |  | 10 |  | 80 | 60 |  | 50 |  | 30
|  | FY 05$ in thousands |  |  | Tech | [5 empty] | Russian | 24 |  | 20 |  | 18
|  |  | Base |  | Contingency | Total | EDIA | Mfg. | EDIA | Mfg. | Total | Physicist |  | Eng |  | Admin |  | Designer |  | Tech |  | Total | [6 empty] | Physicist |  |  | unit
WBS |  |  | Cost | Contingency | % | Cost | Labor | Labor | Matls | Matls | FTE's | FTE's | Hrs. | FTE's | Hrs. | FTE's | Hrs. | FTE's | Hrs. | FTE's | Hrs. | Base Cost | FY 2005 | FY 2006 | FY 2007 | FY 2008 | FY 2009 | FY 2010 | Labor |  | Units | price
1.2.2 | Preradiator |  | 20927.9798 | 6753.0903 | 32.27% | 27681.0701 | 3066.7592 | 4389.7212 | 0 | 13471.4994 | 230.9724 | 33.6387 | 55315.6032 | 43.8917 | 76193.457 | 0 | 0 | 8.75 | 15400 | 144.682 | 254305.8759 | 20927.9798 | 709.9275 | 4455.5691 | 6279.5195 | 5595.5433 | 3887.4203 | 0 | 2586.3456
1.2.2.1 | Chamber System |  | 3316.819 | 1425.6244 | 42.98% | 4742.4434 | 365 | 1164 | 0 | 1787.819 | 52.425 | 7.375 | 12980 | 5.25 | 9240 |  | 0 | 1 | 1760 | 38.8 | 68288 | 3316.819 | 131.3518 | 626.6729 | 930.4707 | 930.4707 | 697.853 | 0 | 590
1.2.2.1.1 | Chambers |  | 2894.619 | 1273.6324 | 44% | 4168.2514 | 280 | 1119 | 0 | 1495.619 | 48.425 | 6.375 | 11220 | 4.25 | 7480 |  | 0 | 0.5 | 880 | 37.3 | 65648 | 2894.619 | 105.1018 | 521.4896 | 824.7373 | 824.7373 | 618.553 | 0 | 510
1.2.2.1.1.1 | Design |  | 85 | 37.4 | 44% | 122.4 | 85 |  |  |  | 3 | 1.5 | 2640 | 1 | 1760 |  |  | 0.5 | 880 |  |  | 85 | FY 2005: 21.25; FY 2006: 63.75 | 120
1.2.2.1.1.2 | Prototype |  | 335.407 | 147.5791 | 44% | 482.9861 | 60 | 120 |  | 155.407 | 6.5 | 1.5 | 2640 | 1 | 1760 |  |  |  |  | 4 | 7040 | 335.407 | FY 2005: 83.8518; FY 2006: 251.5553 | 120
1.2.2.1.1.3 | Fabrication/Procurement |  | 2474.212 | 1088.6533 | 44% | 3562.8653 | 135 | 999 |  | 1340.212 | 38.925 | 3.375 | 5940 | 2.25 | 3960 |  |  |  |  | 33.3 | 58608 | 2474.212 |  | 206.1843 | 824.7373 | 824.7373 | 618.553 | 0 | 270
1.2.2.1.2 | Gas System |  | 422.2 | 151.992 | 36% | 574.192 | 85 | 45 | 0 | 292.2 | 4 | 1 | 1760 | 1 | 1760 |  | 0 | 0.5 | 880 | 1.5 | 2640 | 422.2 | 26.25 | 105.1833 | 105.7333 | 105.7333 | 79.3 | 0 | 80
1.2.2.1.2.1 | Design |  | 42.5 | 15.3 | 36% | 57.8 | 42.5 |  |  |  | 1.25 | 0.5 | 880 | 0.5 | 880 |  |  | 0.25 | 440 |  |  | 42.5 | FY 2005: 10.625; FY 2006: 31.875 | 40
1.2.2.1.2.2 | Prototype |  | 62.5 | 22.5 | 36% | 85 | 27.5 | 15 |  | 20 | 1.5 | 0.5 | 880 | 0.25 | 440 |  |  | 0.25 | 440 | 0.5 | 880 | 62.5 | FY 2005: 15.625; FY 2006: 46.875 | 40
1.2.2.1.2.3 | Fabrication/Procurement |  | 317.2 | 114.192 | 36% | 431.392 | 15 | 30 |  | 272.2 | 1.25 |  | 0 | 0.25 | 440 |  |  |  |  | 1 | 1760 | 317.2 |  | 26.4333 | 105.7333 | 105.7333 | 79.3 | 0
1.2.2.1.2.3.1 | In module(tube,MFM x278) |  |  |  | 36% |  |  |  |  | 82.2
1.2.2.1.2.3.2 | Rec.system(MFC,pump x4) |  |  |  | 36% |  |  |  |  | 120
1.2.2.1.2.3.3 | Plumbing |  |  |  | 36% |  |  |  |  | 40
1.2.2.1.2.3.4 | Gas shack |  |  |  | 36% |  |  |  |  | 20
1.2.2.1.2.3.5 | DAQ |  |  |  | 36% |  |  |  |  | 10
1.2.2.2 | Scintillator System |  | 2806.2354 | 670.0386 | 23.88% | 3476.274 | 310.4592 | 707.7192 | 0 | 1788.057 | 32.9296 | 3.9243 | 6906.8032 | 3.9243 | 6906.8032 |  | 0 | 1.5 | 2640 | 23.581 | 41150.5181 | 2806.2354 | 91.314 | 488.3009 | 815.9638 | 809.0518 | 601.6048 | 0 | 313.9456
1.2.2.2.1 | Scintillator Plates |  | 1556.1754 | 466.8526 | 30% | 2023.028 | 310.4592 | 598.4592 | 0 | 647.257 | 27.7973 | 2.4243 | 4266.8032 | 3.9243 | 6906.8032 | 0 | 0 | 1.5 | 2640 | 19.9486 | 35109.6064 | 1556.1754 | 83.189 | 351.5186 | 407.8065 | 407.8065 | 305.8548 | 0 | 193.9456
1.2.2.2.1.1 | Design |  | 60 | 18 | 30% | 78 | 60 | 0 |  | 0 | 2 | 1 | 1760 | 1 | 1760 | [6 empty] | 60 | FY 2005: 15; FY 2006: 45 | 80
1.2.2.2.1.2 | Prototype |  | 272.756 | 81.8268 | 30% | 354.5828 | 135 | 60 |  | 77.756 | 5.5 | 1 | 1760 | 1 | 1760 |  |  | 1.5 | 2640 | 2 | 3520 | 272.756 | FY 2005: 68.189; FY 2006: 204.567 | 80
1.2.2.2.1.3 | Fabrication/Procurement |  | 1223.4194 | 367.0258 | 30% | 1590.4452 | 115.4592 | 538.4592 |  | 569.501 | 20.2973 | 0.42432 | 746.8032 | 1.9243 | 3386.8032 |  |  |  |  | 17.9486 | 31589.6064 | 1223.4194 |  | 101.9516 | 407.8065 | 407.8065 | 305.8548 | 0 | 33.9456
1.2.2.2.2 | WLS fiber |  | 651.5 | 143.33 | 22% | 794.83 | 0 | 97.5 | 0 | 554 | 4.75 | 1.5 | 2640 | 0 | 0 |  | 0 | 0 | 0 | 3.25 | 5720 | 651.5 | 8.125 | 75.9583 | 206.3333 | 206.3333 | 154.75 | 0 | 120
1.2.2.2.2.2 | Prototype |  | 32.5 | 7.15 | 22% | 39.65 | 0 | 7.5 |  | 25 | 0.75 | 0.5 | 880 | [6 empty] | 0.25 | 440 | 32.5 | FY 2005: 8.125; FY 2006: 24.375 | 40
1.2.2.2.2.3 | Fabrication/Procurement |  | 619 | 136.18 | 22% | 755.18 | 0 | 90 |  | 529 | 4 | 1 | 1760 | [6 empty] | 3 | 5280 | 619 |  | 51.5833 | 206.3333 | 206.3333 | 154.75 | 0 | 80
1.2.2.2.3 | Scintillator readout |  | 598.56 | 59.856 | 10% | 658.416 | 0 | 11.76 | 0 | 586.8 | 0.38234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.38234 | 320.9117 | 598.56 | 0 | 60.824 | 201.824 | 194.912 | 141 | 0 | 0 |  | 1152
1.2.2.2.3.1 | Photo Tube |  | 366 | 36.6 | 10% | 402.6 | 0 | 0 | 0 | 366 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 366 | 0 | 30.5 | 122 | 122 | 91.5 | 0 | 0
1.2.2.2.3.1.3 | Fabrication/Procurement |  | 366 | 36.6 | 10% | 402.6 |  | 0 |  | 366 | 0 |  | 0 | [8 empty] | 366 |  | 30.5 | 122 | 122 | 91.5 | 0 | 0 |  |  | 240
1.2.2.2.3.2 | MU Metal Shield/Bases |  | 150 | 15 | 10% | 165 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 12.5 | 50 | 50 | 37.5 | 0 | 0
1.2.2.2.3.2.3 | Fabrication/Procurement |  | 150 | 15 | 10% | 165 |  | 0 |  | 150 | 0 |  | 0 | [8 empty] | 150 |  | 12.5 | 50 | 50 | 37.5 | 0 | 0 |  |  | 100
1.2.2.2.3.3 | Cables |  | 48 | 4.8 | 10% | 52.8 | 0 | 6 | 0 | 42 | 0.2 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0.2 | 0 | 48 | 0 | 4 | 16 | 16 | 12 | 0 | 0
1.2.2.2.3.3.3 | Fabrication/Procurement |  | 48 | 4.8 | 10% | 52.8 |  | 6 |  | 42 | 0.2 |  | 0 | [6 empty] | 0.2 |  | 48 |  | 4 | 16 | 16 | 12 | 0 | 0
1.2.2.2.3.4 | Preampifier |  | 34.56 | 3.456 | 10% | 38.016 | 0 | 5.76 | 0 | 28.8 | 0.18234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.18234 | 320.9117 | 34.56 | 0 | 13.824 | 13.824 | 6.912 | 0 |  |  |  |  | 25
1.2.2.2.3.3.3 | Fabrication/Procurement |  | 34.56 | 3.456 | 10% | 38.016 |  | 5.76 |  | 28.8 | 0.18234 |  | 0 | [6 empty] | 0.18234 | 320.9117 | 34.56 | 0 | 13.824 | 13.824 | 6.912 |  | 0
1.2.2.3 | Electronics |  | 7951.847 | 1661.0974 | 20.89% | 9612.9444 | 1366 | 536 | 0 | 6049.847 | 44.2972 | 3 | 5280 | 18.6 | 31680 |  | 0 | 5 | 8800 | 17.6972 | 31146.9858 | 7951.847 | 339.1368 | 1640.0603 | 2269.25 | 2145.05 | 1558.35 | 0 | 240
1.2.2.3.1 | Anode Electronics |  | 2424.388 | 484.8776 | 20% | 2909.2656 | 610 | 240 | 0 | 1574.388 | 20 | 1 | 1760 | 6 | 10560 |  | 0 | 5 | 8800 | 8 | 14080 | 2424.388 | 168.997 | 652.691 | 582.8 | 582.8 | 437.1 | 0 | 80
1.2.2.3.1.1 | Design |  | 220 | 44 | 20% | 264 | 220 | 0 |  |  | 4.5 | 0.5 | 880 | 2 | 3520 |  |  | 2 | 3520 |  | 0 | 220 | FY 2005: 55; FY 2006: 165 | 40
1.2.2.3.1.2 | Prototype |  | 455.988 | 91.1976 | 20% | 547.1856 | 300 | 60 |  | 95.988 | 8 | 0.5 | 880 | 2.5 | 4400 |  |  | 3 | 5280 | 2 | 3520 | 455.988 | FY 2005: 113.997; FY 2006: 341.991 | 40
1.2.2.3.1.3 | Fabrication/Procurement |  | 1748.4 | 349.68 | 20% | 2098.08 | 90 | 180 |  | 1478.4 | 7.5 | 0 | 0 | 1.5 | 2640 |  |  |  |  | 6 | 10560 | 1748.4 |  | 145.7 | 582.8 | 582.8 | 437.1 | 0 | 0
1.2.2.3.2 | Cathode Electronics |  | 2305.549 | 461.1098 | 20% | 2766.6588 | 360 | 180 | 0 | 1765.549 | 13 | 1 | 1760 | 6 | 10560 | 0 | 0 | 0 | 0 | 6 | 10560 | 2305.549 | 87.8872 | 426.4951 | 651.3333 | 651.3333 | 488.5 | 0 | 80
1.2.2.3.2.1 | Design |  | 120 | 24 | 20% | 144 | 120 | 0 |  |  | 2.5 | 0.5 | 880 | 2 | 3520 |  |  |  | 0 |  | 0 | 120 | FY 2005: 30; FY 2006: 90 | 40
1.2.2.3.2.2 | Prototype |  | 231.549 | 46.3098 | 20% | 277.8588 | 150 |  |  | 81.549 | 3 | 0.5 | 880 | 2.5 | 4400 | [6 empty] | 231.549 | FY 2005: 57.8873; FY 2006: 173.6618 | 40
1.2.2.3.2.3 | Fabrication/Procurement |  | 1954 | 390.8 | 20% | 2344.8 | 90 | 180 |  | 1684 | 7.5 | 0 | 0 | 1.5 | 2640 |  |  |  |  | 6 | 10560 | 1954 |  | 162.8333 | 651.3333 | 651.3333 | 488.5 | 0 | 0
1.2.2.3.3 | HV, LV Pss and controllers |  | 2565.31 | 513.062 | 20% | 3078.372 | 240 | 67.5 | 0 | 2257.81 | 6.25 | 0 | 0 | 4 | 7040 | 0 | 0 | 0 | 0 | 2.25 | 3960 | 2565.31 | 49.7525 | 346.4492 | 788.7667 | 788.7667 | 591.575 | 0 | 0
1.2.2.3.3.1 | Design |  | 90 | 18 | 20% | 108 | 90 | 0 |  |  | 1.5 |  | 0 | 1.5 | 2640 |  |  |  | 0 |  | 0 | 90 | FY 2005: 22.5; FY 2006: 67.5 | 0
1.2.2.3.3.2 | Prototype |  | 109.01 | 21.802 | 20% | 130.812 | 60 | 0 |  | 49.01 | 1 |  | 0 | 1 | 1760 | [6 empty] | 109.01 | FY 2005: 27.2525; FY 2006: 81.7575 | 0
1.2.2.3.3.3 | Fabrication/Procurement |  | 2366.3 | 473.26 | 20% | 2839.56 | 90 | 67.5 |  | 2208.8 | 3.75 | 0 | 0 | 1.5 | 2640 |  |  |  |  | 2.25 | 3960 | 2366.3 |  | 197.1917 | 788.7667 | 788.7667 | 591.575 | 0 | 0
1.2.2.3.4 | DAQ interface |  | 294.7 | 129.668 | 44% | 424.368 | 156 | 13.5 | 0 | 125.2 | 4.05 | 1 | 1760 | 2.6 | 3520 | 0 | 0 | 0 | 0 | 0.45 | 792 | 294.7 | 32.5 | 111.225 | 54.9 | 54.9 | 41.175 | 0 | 80
1.2.2.3.4.1 | Design |  | 60 | 26.4 | 44% | 86.4 | 60 | 0 |  |  | 1.5 | 0.5 | 880 | 1 | 1760 |  |  |  | 0 |  | 0 | 60 | FY 2005: 15; FY 2006: 45 | 40
1.2.2.3.4.2 | Prototype |  | 70 | 30.8 | 44% | 100.8 | 60 | 0 |  | 10 | 1.5 | 0.5 | 880 | 1 | 1760 | [6 empty] | 70 | FY 2005: 17.5; FY 2006: 52.5 | 40
1.2.2.3.4.3 | Fabrication/Procurement |  | 164.7 | 72.468 | 44% | 237.168 | 36 | 13.5 |  | 115.2 | 1.05 | 0 | 0 | 0.6 | [5 empty] | 0.45 | 792 | 164.7 |  | 13.725 | 54.9 | 54.9 | 41.175 | 0 | 0
1.2.2.3.5 | Scintillator Electronics |  | 361.9 | 72.38 | 20% | 434.28 | 0 | 35 | 0 | 326.9 | 0.99715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.99715 | 1754.9858 | 361.9 | 0 | 103.2 | 191.45 | 67.25 | 0 |  |  |  | 1152 | 290 | chan/board
1.2.2.3.5.1 | WFD Boards |  | 231.5 | 46.3 | 20% | 277.8 | 0 | 32 | 0 | 199.5 | 0.91168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.91168 | 1604.5584 | 231.5 | 0 | 57.875 | 115.75 | 57.875 | 0 |  |  |  | 105 | 1900 | 12
1.2.2.3.5.1.3 | Fabrication/Procurement |  | 199.5 | 39.9 | 20% | 239.4 |  |  |  | 199.5 | 0 | [10 empty] | 199.5 | 0 | 49.875 | 99.75 | 49.875 |  | 0
1.2.2.3.5.1.5 | Test |  | 32 | 6.4 | 20% | 38.4 |  | 32 |  |  | 0.91168 |  | 0 | [6 empty] | 0.91168 | 1604.5584 | 32 | 0 | 8 | 16 | 8 |  | 0 |  |  |  |  | brds/col
1.2.2.3.5.2 | Crate Data-Collection Boards |  | 55.5 | 11.1 | 20% | 66.6 | 0 | 3 | 0 | 52.5 | 0.08547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08547 | 150.4274 | 55.5 | 0 | 7.875 | 38.25 | 9.375 | 0 |  |  |  | 14 | 3750 | 8
1.2.2.3.5.2.3 | Fabrication/Procurement |  | 52.5 | 10.5 | 20% | 63 |  |  |  | 52.5 | 0 |  | 0 | [8 empty] | 52.5 | 0 | 7.875 | 36.75 | 7.875 |  | 0
1.2.2.3.5.2.5 | Test |  | 3 | 0.6 | 20% | 3.6 |  | 3 |  |  | 0.08547 |  | 0 | [6 empty] | 0.08547 | 150.4274 | 3 | 0 | 0 | 1.5 | 1.5 |  | 0 |  |  |  |  | col/crate
1.2.2.3.5.3 | VXI Mainframes & Controller |  | 74.9 | 14.98 | 20% | 89.88 | 0 | 0 | 0 | 74.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.9 | 0 | 37.45 | 37.45 | 0 | 0 |  |  |  | 7 | 10700 | 2 |  |  | 7
1.2.2.3.5.3.3 | Fabrication/Procurement |  | 74.9 | 14.98 | 20% | 89.88 |  |  |  | 74.9 | 0 |  | 0 | [8 empty] | 74.9 | 0 | 37.45 | 37.45 | 0
1.2.2.4 | Mechanical |  | 3623.75 | 2319.2 | 64% | 5942.95 | 542.5 | 1121.25 | 0 | 1960 | 55.875 | 9.25 | 16280 | 8 | 14080 |  | 0 | 1.25 | 2200 | 37.375 | 65780 | 3623.75 | 88.125 | 536.9792 | 1090.4167 | 1090.4167 | 817.8125 | 0 | 740
1.2.2.4.1 | Support plates |  | 1738.75 | 1112.8 | 64% | 2851.55 | 265 | 813.75 | 0 | 660 | 37.125 | 5.5 | 9680 | 4 | 7040 |  | 0 | 0.5 | 880 | 27.125 | 47740 | 1738.75 | 41.25 | 254.8958 | 524.5833 | 524.5833 | 393.4375 | 0 | 440
1.2.2.4.1.1 | Design |  | 55 | 35.2 | 64% | 90.2 | 55 | 0 |  |  | 1.5 | 0.5 | 880 | 0.5 | 880 |  |  | 0.5 | 880 |  | 0 | 55 | FY 2005: 13.75; FY 2006: 41.25 | 40
1.2.2.4.1.2 | Prototype |  | 110 | 70.4 | 64% | 180.4 | 30 | 60 |  | 20 | 3 | 0.5 | 880 | 0.5 | 880 |  |  |  |  | 2 | 3520 | 110 | FY 2005: 27.5; FY 2006: 82.5 | 40
1.2.2.4.1.3 | Fabrication/Procurement*** |  | 1573.75 | 1007.2 | 64% | 2580.95 | 180 | 753.75 |  | 640 | 32.625 | 4.5 | 7920 | 3 | 5280 |  |  |  |  | 25.125 | 44220 | 1573.75 |  | 131.1458 | 524.5833 | 524.5833 | 393.4375 | 0 | 360
1.2.2.4.2 | Support rails |  | 1265 | 809.6 | 64% | 2074.6 | 145 | 120 | 0 | 1000 | 8.5 | 2 | 3520 | 2 | 3520 |  | 0 | 0.5 | 880 | 4 | 7040 | 1265 | 28.75 | 182.0833 | 383.3333 | 383.3333 | 287.5 | 0 | 160
1.2.2.4.2.1 | Design |  | 55 | 35.2 | 64% | 90.2 | 55 |  |  |  | 1.5 | 0.5 | 880 | 0.5 | 880 |  |  | 0.5 | 880 |  | 0 | 55 | FY 2005: 13.75; FY 2006: 41.25 | 40
1.2.2.4.2.2 | Prototype |  | 60 | 38.4 | 64% | 98.4 | 30 | 30 |  |  | 2 | 0.5 | 880 | 0.5 | 880 |  |  |  |  | 1 | 1760 | 60 | FY 2005: 15; FY 2006: 45 | 40
1.2.2.4.2.3 | Fabrication/Procurement*** |  | 1150 | 736 | 64% | 1886 | 60 | 90 |  | 1000 | 5 | 1 | 1760 | 1 | 1760 |  |  |  |  | 3 | 5280 | 1150 |  | 95.8333 | 383.3333 | 383.3333 | 287.5 | 0 | 80
1.2.2.4.3 | Transport/storage |  | 620 | 396.8 | 64% | 1016.8 | 132.5 | 187.5 | 0 | 300 | 10.25 | 1.75 | 3080 | 2 | 3520 |  | 0 | 0.25 | 440 | 6.25 | 11000 | 620 | 18.125 | 100 | 182.5 | 182.5 | 136.875 | 0 | 140
1.2.2.4.3.1 | Design |  | 42.5 | 27.2 | 64% | 69.7 | 42.5 |  |  |  | 1.25 | 0.5 | 880 | 0.5 | 880 |  |  | 0.25 | 440 |  | 0 | 42.5 | FY 2005: 10.625; FY 2006: 31.875 | 40
1.2.2.4.3.2 | Prototype |  | 30 | 19.2 | 64% | 49.2 | 0 | 30 |  |  | 1.5 | 0.5 | 880 |  | 0 |  |  |  |  | 1 | 1760 | 30 | FY 2005: 7.5; FY 2006: 22.5 | 40
1.2.2.4.3.3 | Fabrication/Procurement*** |  | 547.5 | 350.4 | 64% | 897.9 | 90 | 157.5 |  | 300 | 7.5 | 0.75 | 1320 | 1.5 | 2640 |  |  |  |  | 5.25 | 9240 | 547.5 |  | 45.625 | 182.5 | 182.5 | 136.875 | 0 | 60
1.2.2.5 | External PV |  | 2322.1284 | 325.098 | 14% | 2647.2264 | 10 | 726.352 | 0 | 1585.7764 | 25.2057 | 2.2094 | 0 | 0.23742 | 417.8538 | 0 | 0 | 0 | 0 | 22.7488 | 40055.572 | 2322.1284 | 0 | 1052.9559 | 911.0184 | 358.1542 | 0 | 0 | 72
1.2.2.5.1 | PMT - Instrumented Modules |  | 1288.3784 | 180.373 | 14% | 1468.7514 | 0 | 579.352 | 0 | 709.0264 | 18.3397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.3397 | 32277.9209 | 1288.3784 | 0 | 511.1434 | 511.1434 | 266.0917 | 0 | 0 | 0
1.2.2.5.1.1 | Modules |  | 731.0584 | 102.3482 | 14% | 833.4066 | 0 | 449.712 | 0 | 281.3464 | 14.2359 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.2359 | 25055.1795 | 731.0584 | 0 | 290.0014 | 290.0014 | 151.0557 | 0 | 0 | 0 | Mod. Units | 1080
1.2.2.5.1.1.1 | Scintillator Tiles |  | 156.0924 | 21.8529 | 14% | 177.9453 |  | 116.64 |  | 39.4524 | 3.6923 | [8 empty] | 3.6923 | 6498.4615 | 156.0924 | 0 | 62.437 | 62.437 | 31.2185 |  | 0 |  | + spares | 1080
1.2.2.5.1.1.2 | Lead Tiles |  | 202.986 | 28.418 | 14% | 231.404 |  | 132.192 |  | 70.794 | 4.1846 | [8 empty] | 4.1846 | 7364.9231 | 202.986 | 0 | 81.1944 | 81.1944 | 40.5972 |  | 0
1.2.2.5.1.1.3 | WLS Fiber |  | 132.84 | 18.5976 | 14% | 151.4376 |  | 16.2 |  | 116.64 | 0.51282 | [8 empty] | 0.51282 | 902.5641 | 132.84 | 0 | 53.136 | 53.136 | 26.568 |  | 0
1.2.2.5.1.1.4 | Assembly |  | 176.04 | 24.6456 | 14% | 200.6856 |  | 136.08 |  | 39.96 | 4.3077 | [8 empty] | 4.3077 | 7581.5385 | 176.04 | 0 | 70.416 | 70.416 | 35.208 |  | 0
1.2.2.5.1.1.5 | Test |  | 38.88 | 5.4432 | 14% | 44.3232 |  | 38.88 |  |  | 1.2308 | [8 empty] | 1.2308 | 2166.1538 | 38.88 | 0 | 15.552 | 15.552 | 7.776 |  | 0
1.2.2.5.1.1.6 | Packing |  | 24.22 | 3.3908 | 14% | 27.6108 |  | 9.72 |  | 14.5 | 0.30769 | [8 empty] | 0.30769 | 541.5385 | 24.22 | 0 | 7.266 | 7.266 | 9.688 |  | 0
1.2.2.5.1.2 | Module Instrumentation |  | 544.32 | 76.2048 | 14% | 620.5248 | 0 | 116.64 | 0 | 427.68 | 3.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6923 | 6498.4615 | 544.32 | 0 | 217.242 | 217.242 | 109.836 | 0 | 0 | 0
[30 empty] | + spares | 1080
1.2.2.5.1.2.1 | Phototube |  | 219.24 | 30.6936 | 14% | 249.9336 |  | 5.4 |  | 213.84 | 0.17094 | [8 empty] | 0.17094 | 300.8547 | 219.24 | 0 | 87.696 | 87.696 | 43.848 |  | 0
1.2.2.5.1.2.2 | Preamplifier |  | 32.4 | 4.536 | 14% | 36.936 |  | 5.4 |  | 27 | 0.17094 | [8 empty] | 0.17094 | 300.8547 | 32.4 | 0 | 12.96 | 12.96 | 6.48 |  | 0
1.2.2.5.1.2.3 | LV-HV Converter |  | 139.32 | 19.5048 | 14% | 158.8248 |  | 5.4 |  | 133.92 | 0.17094 | [8 empty] | 0.17094 | 300.8547 | 139.32 | 0 | 55.728 | 55.728 | 27.864 |  | 0
1.2.2.5.1.2.4 | Mechanics |  | 64.8 | 9.072 | 14% | 73.872 |  | 32.4 |  | 32.4 | 1.0256 | [8 empty] | 1.0256 | 1805.1282 | 64.8 | 0 | 25.92 | 25.92 | 12.96 |  | 0
1.2.2.5.1.2.5 | Assembly |  | 78.84 | 11.0376 | 14% | 89.8776 |  | 58.32 |  | 20.52 | 1.8462 | [8 empty] | 1.8462 | 3249.2308 | 78.84 | 0 | 31.536 | 31.536 | 15.768 |  | 0
1.2.2.5.1.2.6 | Test |  | 4.86 | 0.6804 | 14% | 5.5404 |  | 4.86 |  |  | 0.15385 | [8 empty] | 0.15385 | 270.7692 | 4.86 | 0 | 1.944 | 1.944 | 0.972 |  | 0
1.2.2.5.1.2.7 | Packing |  | 4.86 | 0.6804 | 14% | 5.5404 |  | 4.86 |  |  | 0.15385 | [8 empty] | 0.15385 | 270.7692 | 4.86 | 0 | 1.458 | 1.458 | 1.944 |  | 0
1.2.2.5.1.3 | Cosmic Ray Test of Module/PMT |  | 13 | 1.82 | 14% | 14.82 |  | 13 |  |  | 0.41152 | [8 empty] | 0.41152 | 724.2798 | 13 | 0 | 3.9 | 3.9 | 5.2 |  | 0
1.2.2.5.2 | Instrumentation |  | 760.75 | 106.505 | 14% | 867.255 | 10 | 74 | 0 | 676.75 | 2.3457 | 0 | 0 | 0.23742 | 417.8538 | 0 | 0 | 0 | 0 | 2.0983 | 3710.5413 | 760.75 | 0 | 325.3125 | 343.375 | 92.0625 | 0 | 0 | 0
[31 empty] | 1080 | 626.6204
1.2.2.5.2.1 | HV Control System |  | 100 | 14 | 14% | 114 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 75 | 25 | 0 | 0 | 0 | 0 |  | 74 | 1040 | 16 | 64 | 768 | 1
1.2.2.5.2.1.1 | 34 VME Carriers |  | 13 | 1.82 | 14% | 14.82 |  |  |  | 13 | 0 | [8 empty] | 0 | 0 | 13 | 0 | 9.75 | 3.25 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.2.1.2 | 136 IP Modules |  | 67 | 9.38 | 14% | 76.38 |  |  |  | 67 | 0 | [8 empty] | 0 | 0 | 67 | 0 | 50.25 | 16.75 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.2.1.3 | 3 VME/VXI Mainframes |  | 20 | 2.8 | 14% | 22.8 |  |  |  | 20 | 0 | [8 empty] | 0 | 0 | 20 | 0 | 15 | 5 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.2.2 | Cosmic Ray Pre Calibration |  | 143 | 20.02 | 14% | 163.02 | 0 | 0 | 0 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 143 | 0 | 107.25 | 35.75 | 0 | 0 | 0 | 0 |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.2.2.1 | PMT & HV |  | 78 | 10.92 | 14% | 88.92 |  |  |  | 78 | 0 | [8 empty] | 0 | 0 | 78 | 0 | 58.5 | 19.5 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.2.2.2 | 10 VME Modules -LTD |  | 28 | 3.92 | 14% | 31.92 |  |  |  | 28 | 0 | [8 empty] | 0 | 0 | 28 | 0 | 21 | 7 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.2.2.3 | 6 VME Modules - Trigger |  | 27 | 3.78 | 14% | 30.78 |  |  |  | 27 | 0 | [8 empty] | 0 | 0 | 27 | 0 | 20.25 | 6.75 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.2.2.4 | 1 VME Mainframe |  | 10 | 1.4 | 14% | 11.4 |  |  |  | 10 | 0 | [8 empty] | 0 | 0 | 10 | 0 | 7.5 | 2.5 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.2.3 | Monitoring & Calibration System |  | 92 | 12.88 | 14% | 104.88 | 10 | 55 | 0 | 27 | 1.8044 | 0 | 0 | 0.23742 | 417.8538 | 0 | 0 | 0 | 0 | 1.557 | 2757.8348 | 92 | 0 | 14 | 60 | 18 | 0 | [5 empty] | chan/unit | units/crate |  | crates
1.2.2.5.2.3.1 | Design |  | 10 | 1.4 | 14% | 11.4 | 10 |  |  |  | 0.23742 |  |  | 0.23742 | 417.8538 | [6 empty] | 10 | 0 | 10 | 0 | 0 |  | 0 |  |  | 18 | 1085 | 64 | 8 |  | 2
1.2.2.5.2.3.2 | Prototype |  | 10 | 1.4 | 14% | 11.4 |  | 5 |  | 5 | 0.14245 | [8 empty] | 0.14245 | 250.7123 | 10 | 0 | 4 | 6 | 0 |  | 0
1.2.2.5.2.3.3 | Fabrication/Procurement |  | 72 | 10.08 | 14% | 82.08 |  | 50 |  | 22 | 1.4245 | [8 empty] | 1.4245 | 2507.1225 | 72 | 0 | 0 | 54 | 18 |  | 0
1.2.2.5.2.4 | Readout Electronics |  | 402.75 | 56.385 | 14% | 459.135 | 0 | 19 | 0 | 383.75 | 0.54131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.54131 | 952.7066 | 402.75 | 0 | 117.5625 | 211.125 | 74.0625 | 0 | 0 | 0
1.2.2.5.2.4.1 | WFD Boards |  | 261 | 36.54 | 14% | 297.54 | 0 | 16 | 0 | 245 | 0.45584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45584 | 802.2792 | 261 | 0 | 65.25 | 130.5 | 65.25 | 0 |  |  |  | 1080 | 290 | chan/board
1.2.2.5.2.4.1.3 | Fabrication/Procurement |  | 245 | 34.3 | 14% | 279.3 |  |  |  | 245 | 0 | [10 empty] | 245 | 0 | 61.25 | 122.5 | 61.25 |  | 0 |  |  | 99 | 1900 | 12
1.2.2.5.2.4.1.5 | Test |  | 16 | 2.24 | 14% | 18.24 |  | 16 |  |  | 0.45584 | [8 empty] | 0.45584 | 802.2792 | 16 | 0 | 4 | 8 | 4 |  | 0
1.2.2.5.2.4.2 | Crate Data-Collection Boards |  | 51.75 | 7.245 | 14% | 58.995 | 0 | 3 | 0 | 48.75 | 0.08547 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08547 | 150.4274 | 51.75 | 0 | 7.3125 | 35.625 | 8.8125 | 0 | [5 empty] | brds/col
1.2.2.5.2.4.2.3 | Fabrication/Procurement |  | 48.75 | 6.825 | 14% | 55.575 |  |  |  | 48.75 | 0 | [10 empty] | 48.75 | 0 | 7.3125 | 34.125 | 7.3125 |  | 0 |  |  | 13 | 3750 | 8
1.2.2.5.2.4.2.5 | Test |  | 3 | 0.42 | 14% | 3.42 |  | 3 |  |  | 0.08547 | [8 empty] | 0.08547 | 150.4274 | 3 | 0 | 0 | 1.5 | 1.5 |  | 0
1.2.2.5.2.4.3 | VXI Mainframes & Controller |  | 90 | 12.6 | 14% | 102.6 |  |  |  | 90 | 0 | [10 empty] | 90 | 0 | 45 | 45 | 0 |  |  |  |  | 7 | 10700 | 2 |  |  | 7
0
1.2.2.5.2.5 | Electronic Racks & LV Power Supplies |  | 23 | 3.22 | 14% | 26.22 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 11.5 | 11.5 | 0 | 0 | 0 | 0
[31 empty] | 16 | 410
1.2.2.5.2.5.1 | LV Power Supplies |  | 5 | 0.7 | 14% | 5.7 |  |  |  | 5 | 0 | [10 empty] | 5 | 0 | 2.5 | 2.5 | 0 |  | 0 |  |  | 5 | 5250
1.2.2.5.2.5.2 | Electronic Racks |  | 18 | 2.52 | 14% | 20.52 |  |  |  | 18 | 0 | [10 empty] | 18 | 0 | 9 | 9 | 0 |  | 0
1.2.2.5.3 | Shipping |  | 80 | 11.2 | 14% | 91.2 |  |  |  | 80 | 0 | [10 empty] | 80 | 0 | 40 | 40 | 0 |  | 0 |  |  | 1 | 5250
1.2.2.5.4 | Assembly & Test |  | 84 | 11.76 | 14% | 95.76 | 0 | 36 | 0 | 48 | 2.849 | 1.7094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1396 | 2005.698 | 84 | 0 | 78.25 | 5.75 | 0 | 0 | 0 | 72 |  | 1 | 5250
1.2.2.5.4.1 | Mechanical & Optical Test |  | 61 | 8.54 | 14% | 69.54 |  | 18 |  | 43 | 0.5698 | [8 empty] | 0.5698 | 1002.849 | 61 | 0 | 61 | 0 | 0 |  | 0 |  |  | 0 | 1040 | 16 | 64 | 768 | 0
1.2.2.5.4.2 | Cosmic Ray Test |  | 23 | 3.22 | 14% | 26.22 |  | 18 |  | 5 | 0.5698 | [8 empty] | 0.5698 | 1002.849 | 23 | 0 | 17.25 | 5.75 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.4.3 | Technical Support |  | 0 | 0 | 14% | 0 |  |  |  | 0 | 1.7094 | 1.7094 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 72 |  | 1 | 1040 | 16 | 64 | 768 | 0
1.2.2.5.6 | Cabling |  | 109 | 15.26 | 14% | 124.26 | 0 | 37 | 0 | 72 | 1.6713 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1713 | 2061.4118 | 109 | 0 | 98.25 | 10.75 | 0 | 0 | 0 | 0 |  | 0 | 5250
1.2.2.5.6.1 | LV-PS Cables |  | 32 | 4.48 | 14% | 36.48 |  | 3 |  | 29 | 0.094967 | [8 empty] | 0.094967 | 167.1415 | 32 | 0 | 32 | 0 | 0 |  | 0 |  |  | 0 | 1040 | 16 | 64 | 768 | 0
1.2.2.5.6.2 | HV Control Cables |  | 8 | 1.12 | 14% | 9.12 |  | 4 |  | 4 | 0.12662 | [8 empty] | 0.12662 | 222.8553 | 8 | 0 | 6 | 2 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.6.3 | Signal Cables |  | 34 | 4.76 | 14% | 38.76 |  |  |  | 34 | 0 | [8 empty] | 0 | 0 | 34 | 0 | 34 | 0 | 0 |  | 0 |  |  | 1 | 1040 | 16 | 64 | 768 | 0
1.2.2.5.6.4 | Assembly & Installation |  | 25 | 3.5 | 14% | 28.5 |  | 20 |  | 5 | 0.63311 | [8 empty] | 0.63311 | 1114.2767 | 25 | 0 | 18.75 | 6.25 | 0 |  | 0 |  |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.5.6.5 | Technical Support & Test |  | 10 | 1.4 | 14% | 11.4 |  | 10 |  | 0 | 0.81656 | 0.5 | [7 empty] | 0.31656 | 557.1383 | 10 | 0 | 7.5 | 2.5 | 0 |  | 0 | 0 |  | 26 | 4790 | 20 | 4 |  | 1
1.2.2.6 | Work at BNL |  | 607.2 | 340.032 | 56% | 947.232 | 172.8 | 134.4 | 0 | 300 | 10.24 | 2.88 | 5068.8 | 2.88 | 5068.8 | 0 | 0 | 0 | 0 | 4.48 | 7884.8 | 607.2 | 0 | 50.6 | 202.4 | 202.4 | 151.8 | 0 | 230.4
1.2.2.6.1 | Pre-installation work at BNL |  | 492 | 275.52 | 56% | 767.52 | 96 | 96 | 0 | 300 | 6.4 | 1.6 | 2816 | 1.6 | 2816 |  | 0 | 0 | 0 | 3.2 | 5632 | 492 | 0 | 41 | 164 | 164 | 123 | 0 | 128
1.2.2.6.1.1 | Design |  | 0 | 0 | 56% | 0 | 0 |  |  |  | 0 | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 | 0 | FY 2005: 0; FY 2006: 0 | 0
1.2.2.6.1.2 | Prototype |  | 0 | 0 | 56% | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | [5 empty] | 0 | 0 | FY 2005: 0; FY 2006: 0 | 0
1.2.2.6.1.3 | Fabrication/Procurement*** |  | 492 | 275.52 | 56% | 767.52 | 96 | 96 |  | 300 | 6.4 | 1.6 | 2816 | 1.6 | 2816 |  |  |  |  | 3.2 | 5632 | 492 |  | 41 | 164 | 164 | 123 | 0 | 128
1.2.2.6.2 | Installation monitoring |  | 115.2 | 64.512 | 56% | 179.712 | 76.8 | 38.4 | 0 | 0 | 3.84 | 1.28 | 2252.8 | 1.28 | 2252.8 | 0 | 0 | 0 | 0 | 1.28 | 2252.8 | 115.2 | 0 | 9.6 | 38.4 | 38.4 | 28.8 | 0 | 102.4
1.2.2.6.2.3 | Fabrication/Procurement*** |  | 115.2 | 64.512 | 56% | 179.712 | 76.8 | 38.4 |  |  | 3.84 | 1.28 | 2252.8 | 1.28 | 2252.8 |  |  |  |  | 1.28 | 2252.8 | 115.2 |  | 9.6 | 38.4 | 38.4 | 28.8 | 0 | 102.4
1.2.2.10 | Management |  | 300 | 12 | 4% | 312 | 300 |  |  |  | 10 | 5 | 8800 | 5 | 8800 |  |  | 0 | 0 |  |  | 300 | 60 | 60 | 60 | 60 | 60 | 0 | 400
Change 1: chamber construction material, Pin --> soldering, Foil-->router
Change 2: Scintillator production, x1.4 --> x1.2
Change 3: Management, 5 designer FTE --> 0
CAN/US excahnge rate |  |  | 0.8
Change 5: Tech labor, 40-->30
Change 6: WLS fiber, 6m--> 3m, added 250km clear fiber assuming $1/m
Change 7: Installation, corrected FTEs to the estimated work
Change 8: Pre-installation, corrected to the estimated numbers.
Change 9: Deleted 1.2.2.5.5 (installation) since this is for calorimeter but EPV doesn't require this step.

## Materials
Estimates for Prototype
| Estimate | Purchased | Status
| (Assumed $1 US= $1.4 CAD, Tax & Shipping not included) |  |  |  |  | can/us | 0.8
Wire Chamber: | Ptototype |  |  |  | 1module | 34 mod. | US(1.25an)
(in Canadian $)
WC sum | 184407 |  |  |  | 62639.5 | 2129743 | 1340212
Cathode Foil | 28000 |  | Ordered | Use router | 14000 | 476000 | 0
Foil for initial Fiberglass prototype | 250 | 250 | In hand |  |  | 0
Initial Fiberglass protype | 2435 | 2435 | Ordered |  |  | 0
Tooling for Fiberglass sheets | 15800 |  |  |  |  | 0
Fiberglass sheets for protype (8 chambers) | 35000 |  |  |  | 35000 | 1190000 | 952000
Splicing unit | 35392 |  |  |  |  | 0
Mounting table for splicing unit | 7000 |  |  |  |  | 0
Labour for splicing at Profile | 3000 |  |  |  |  | 0
Plastic tub & zinc solution | 4000 |  |  |  |  | 0
Wire for chambers | 7000 |  |  |  | 5250 | 178500 | 142800
Crimp Pins (for readout & non-readout ends) | 24000 |  |  | pin-->solder | 900 | 30600 | 24480
HV Mill Max Sockets& Blocks (for 625 instead of 225 needed) | 19600 |  |  |  | 5292 | 179928 | 128520
Ground Connectors (for non-readout end) | 2930 |  |  |  | 2197.5 | 74715 | 59772
Glue |  |  |  |  | 150 | 5100 | 4080
Combs |  |  |  | pin-->comb | 1050 | 35700 | 28560
Gas System
Gas System Pressure Controller | ?
Scintillator: | 87851 |  |  |  | 23279.25 | 791494.5 | 569500.9714
Scintillator glue Jig | 30000
Styron | 6300 | 6300 | In hand | x1.4-->1.2 | 4725 | 160650 | 110160
Dopents | 7056 | 7056 | In hand | x1.4-->1.2 | 5292 | 179928 | 123379.2
Multistage sizer | 4000 |  |  |  |  | 0 | 0
mods to multistage sizer | 2000 |  |  |  |  | 0 | 0
Celco tests (2 anticipated) | 2400 |  |  |  |  | 0 | 0
New Spider plate (if needed) | 3000 |  |  |  |  | 0 | 0
Commercial Drying of Styron | [5 empty] | 0 | 0
Liquid Nitrogen for runs | 1000 |  |  |  | 750 | 25500 | 17485.7143
Celco production for prototype | 15000 |  |  | x1.4-->1.2 | 5625 | 191250 | 131142.8571
Scintillator machining | ? |  |  |  |  | 0
Paniting and wrapping of Scintillator sheets | 4500 |  |  |  | 2531.25 | 86062.5 | 68850
Hole drilling & jig machining of Scintillator and G10 | 5000 |  |  |  |  | 0
Edge Plates | ? |  |  |  |  | 0
Spacers (0.040" & 0.25" G10) | 3808 |  | Ordered |  | 2856 | 97104 | 77683.2
Glue & Supplies | 2000 |  |  |  | 1500 | 51000 | 40800
Aluminim L Unit in 2 pieces | ? |  |  |  |  | 0
4'x8' G10 for laminate testing | 1787 |  | Ordered |  |  | 0
Wave Shifter fibers | ?
Phototubes | ?
Phototube Readouts | ?
Total: | 272258 | 16041
Note on F11: khan: us$20,000
Note on G12: khan: US$ 172.50
Note on F16: khan: us$25,280
Note on F22: khan: us$14,000
Note on F23: khan: us$ 2092.50
Note on A28: khan: Openshaw
Note on G33: khan: us$4500
Note on G34: khan: us$5040
Note on F43: khan: $500 per sheet
Note on A45: khan: Robert
Note on G46: khan: 5 x $96 for 0.040"+ 5 x $448 for 0.25" = US$ 2720
Note on A48: khan: Robert
Note on G49: khan: 8x$98 for 0.010 + 2x$157 for 0.010 with Cu + 2x89 for 0.050 = us$1276
Note on A52: khan: Toshio
Note on A53: khan: Toshio
Note on A54: khan: Toshio

## Labour
Labor cost for production
|  |  | Per week |  | During the construction period |  |  | Unit: (FTE x year)
|  | # of elements | Prod. Rate | Total weeks | FTE (phys.) | FTE (eng.) | FTE ( tech.) | Total phys. | Total eng. | Total tech.
1.2.2 | Preradiator |  |  |  | 3 | 2.5 | 25.3 | 9.0493 | 8.6743 | 81.6236
1.2.2.1 | Chamber |  |  |  | 1.5 | 1 | 14.8 | 3.375 | 2.25 | 33.3
| Overseeing | 272 | 1.8133 | 150 | 0.5 | 1 |  | 1.125 | 2.25 | 0
| Material inspection | 272 | 1.8133 | 150 |  |  | 0.4 | 0 | 0 | 0.9
| G10 board machining | 272 | 1.8133 | 150 |  |  | 1 | 0 | 0 | 2.25
| Laminating foils | 272 | 1.8133 | 150 |  |  | 1 | 0 | 0 | 2.25
| Frame assembly | 272 | 1.8133 | 150 |  |  | 2 | 0 | 0 | 4.5
| Stringing | 272 | 1.8133 | 150 |  |  | 4 | 0 | 0 | 9
| Tension test/wire replacement | 272 | 1.8133 | 150 |  |  | 2 | 0 | 0 | 4.5
| Strip connection | 272 | 1.8133 | 150 |  |  | 2 | 0 | 0 | 4.5
| Cover installation | 272 | 1.8133 | 150 |  |  | 0.4 | 0 | 0 | 0.9
| Tests | 272 | 1.8133 | 150 | 1 |  | 1 | 2.25 | 0 | 2.25
| Misc. | 272 | 1.8133 | 150 |  |  | 1 | 0 | 0 | 2.25
1.2.2.2 | Scintillator | [6 empty] | 0.42432 | 1.9243 | 17.9486
| Production | 9547.2 | 450 | 21.216 |  | 1 | 1 | 0 | 0.42432 | 0.42432
| Inspection (hole, surface) | 9547.2 | 450 | 21.216 |  |  | 1 | 0 | 0 | 0.42432
| Tests (light yield, attenuation) | 9547.2 | 450 | 21.216 | 1 |  |  | 0.42432 | 0 | 0
| Machining (tongue/groove) | 306 | 2.04 | 150 |  |  | 2 | 0 | 0 | 4.5
| Machining (holes) | 306 | 2.04 | 150 |  |  | 1 | 0 | 0 | 3
| Inspection (ends, sides) | 306 | 2.04 | 150 |  |  | 0.2 | 0 | 0 | 0.6
| Plane fabrication (glue) | 306 | 2.04 | 150 |  | 0.5 | 1.5 | 0 | 1.5 | 4.5
| Painting | 306 | 2.04 | 150 |  |  | 1.5 | 0 | 0 | 4.5
| Test (after WLS) | 306 | 2.04 | 150 | 0.5 |  |  | 1.5 | 0 | 0
1.2.2.3 | Chamber electronics |  |  |  | 0 | 1.7 | 5.2 | 0 | 5.1 | 14.7
1.2.2.3.1 | Anode |  |  |  |  | 0.5 | 2 | 0 | 1.5 | 6
| Adaptor cards | 4896 | 32.64 | 150 |  |  | 0.5 | 0 | 0 | 1.5
| Readout cards | 816 | 5.44 | 150 |  | 0.5 | 1 | 0 | 1.5 | 3
| Cables | 4896 | 32.64 | 150 |  |  | 0.5 | 0 | 0 | 1.5
1.2.2.3.2 | Cathode |  |  |  |  | 0.5 | 2 | 0 | 1.5 | 6
| Adaptor cards | 4896 | 32.64 | 150 |  |  | 0.5 | 0 | 0 | 1.5
| Rreadout cards | 816 | 5.44 | 150 |  | 0.5 | 1 | 0 | 1.5 | 3
| Cables | 4896 | 32.64 | 150 |  |  | 0.5 | 0 | 0 | 1.5
1.2.2.3.3 | HV,LV power supplies, crates | 34 | 0.22667 | 150 |  | 0.5 | 1 | 0 | 1.5 | 2.25
1.2.2.3.4 | DAC interface | 34 | 0.22667 | 150 |  | 0.2 | 0.2 | 0 | 0.6 | 0.45
1.2.2.4.1 | Module assembly |  |  |  | 1.5 | 1 | 10.5 | 4.5 | 3 | 25.125
| Overseeing | 34 | 0.22667 | 150 | 0.5 | 1 |  | 1.5 | 3 | 0
| Bolting layers | 34 | 0.22667 | 150 |  |  | 0.25 | 0 | 0 | 0.5625
| L-plate installation | 34 | 0.22667 | 150 |  |  | 0.5 | 0 | 0 | 1.125
| Cable installation | 34 | 0.22667 | 150 |  |  | 0.25 | 0 | 0 | 0.5625
| Electronics installation | 34 | 0.22667 | 150 |  |  | 0.5 | 0 | 0 | 1.125
| PMT installation | 34 | 0.22667 | 150 |  |  | 0.25 | 0 | 0 | 0.5625
| PV installation | 34 | 0.22667 | 150 |  |  | 0.5 | 0 | 0 | 1.125
| Gas system | 34 | 0.22667 | 150 |  |  | 0.25 | 0 | 0 | 0.75
| Cooling system | 34 | 0.22667 | 150 |  |  | 0.25 | 0 | 0 | 0.75
| System for local trigger | 34 | 0.22667 | 150 |  |  | 0.5 | 0 | 0 | 1.5
| Support installation | 34 | 0.22667 | 150 |  |  | 0.25 | 0 | 0 | 0.5625
| WLS fiber tests/cut/polish | 34 | 0.22667 | 150 |  |  | 2 | 0 | 0 | 4.5
| WLS fiber installation | 34 | 0.22667 | 150 |  |  | 4 | 0 | 0 | 9
| Module test | 34 | 0.22667 | 150 | 1 |  | 1 | 3 | 0 | 3
1.2.2.4.2 | Support rails
1.2.2.4.3 | Storage/transport | 34 | 0.22667 | 150 | 0.25 | 0.5 | 1 | 0.75 | 1.5 | 5.25

## Notes
WBS |  | Estimate basis | (many prices are in Canadian $ here)
1.2.2 | Preradiator
1.2.2.1 | Chamber System
1.2.2.1.1 | Chambers
1.2.2.1.1.1 | Design
1.2.2.1.1.2 | Prototype
1.2.2.1.1.3 | Fabrication/Procurement | Quotation | Cost of most material came from quotations (see Materials). Labor estimates are based on E949 chamber construction.
1.2.2.1.2 | Gas System
1.2.2.1.2.1 | Design
1.2.2.1.2.2 | Prototype
1.2.2.1.2.3 | Fabrication/Procurement
1.2.2.1.2.3.1 | In module(tube,MFM x278) | Catalog price | gas in module tube-in-1/4-cu(0.37*12),sleeve-nut-1/4(0.21+0.82)*6, tube-out-1/2-cu(0.76$/ft*12ft),sleeve-nut/1/2(1.07)(<--triumf store) MFmeter-Honeywell-AWM3100V(80.00),needle-valve(200)=300 *278=83,400
1.2.2.1.2.3.2 | Rec.system(MFC,pump x4) | Engineer's est. | gas system(pump, MFC...)(25k)+regenerator(5k)=30k *4=120,000
1.2.2.1.2.3.3 | Plumbing | Engineer's est. | gas plumbing(mesa area)(15k+25k) =40,000 mat.(12 lines S.S. 5/8 tubing with several valves in each line) + labour
1.2.2.1.2.3.4 | Gas shack | Engineer's est. | gas shack 20,000 by R.Openshaw based on the work on Mesa area construction 5 years ago.
1.2.2.1.2.3.5 | DAQ | Engineer's est. | DAQ 10,000
1.2.2.2 | Scintillator System
1.2.2.2.1 | Scintillator Plates
1.2.2.2.1.1 | Design
1.2.2.2.1.2 | Prototype | Quotation
1.2.2.2.1.3 | Fabrication/Procurement | Quotation | The material costs are based on the purchase made for prototypes. The labor is based on how much we needed in the prototype production.
1.2.2.2.2 | WLS fiber
1.2.2.2.2.2 | Prototype | Quotation
1.2.2.2.2.3 | Fabrication/Procurement | Quotation | fiber fabrication 4(quad) x 8(module) x 9(layers) x 192(N/layer) x 6(m) = 331(km) This is bare minimum. 331(km) x 34/32(spare mod.) x 1.3 = 450(km) 450000(m) x 2.28($/m, for 2km quote in early 2004, Y11) = 1000k Jan. 8, 2005: 6 m ==> 3m, 2.28==>2.00 make 1000k==>450k 3m clear fiber 250000(m) x $1 = 250k Total 1000k ==> 700k, no labour of fusing added. Jan 31,2005: if no clear fiber, 1000k*5/6*0.75/1.3*1.1=529k. In US.
1.2.2.2.3 | Scintillator readout
1.2.2.2.3.1 | Photo Tube
1.2.2.2.3.1.3 | Fabrication/Procurement | Quotation | Based on the quotation for 83087 ($240/pmt in us for 4000, $290 for 40) by Burle. Hamamatsu's quotation for R1450 for compatible tubes are $275 for 4000.
1.2.2.2.3.2 | MU Metal Shield/Bases
1.2.2.2.3.2.3 | Fabrication/Procurement | Engineer's est. | Hamamatsu's quote for pmt (4000) increased to $464 with bases.==>$190.
1.2.2.2.3.3 | Cables
1.2.2.2.3.3.3 | Fabrication/Procurement |  | Cables cables and connectors between pmt and edge panel 1600 x (3 connectors+1m cable+panel, 3x8+3+1) labour(FTE) 1600 x (15/60) x 1/2000 = 0.2
1.2.2.2.3.4 | Preampifier
1.2.2.2.3.3.3 | Fabrication/Procurement |  | We don't know this is really necessary. The numbers came from D. Schamberger.
1.2.2.3 | Electronics
1.2.2.3.1 | Anode Electronics
1.2.2.3.1.1 | Design
1.2.2.3.1.2 | Prototype
1.2.2.3.1.3 | Fabrication/Procurement | Quotation | There is a more detail spread sheet for this system by P. Amaudruz. All material costs are based on quotations though for a slightly smaller scale purchase, so the values were multiplied by 0.9 for large quantity purchase. The cost of labour is for the tests of the cards based on one readout card/day for 0.5 eng. and 1 tech., 12 adaptor cards/day for 1 tech. , and 12 cable bundles/day 1 for tech..
1.2.2.3.2 | Cathode Electronics
1.2.2.3.2.1 | Design
1.2.2.3.2.2 | Prototype
1.2.2.3.2.3 | Fabrication/Procurement | Quotation | There is a more detail spread sheet for this system by P. Amaudruz. All material costs are based on quotations though for a slightly smaller scale purchase, so the values were multiplied by 0.9 for large quantity purchase. The cost of labour is for the tests of the cards based on one readout card/day for 0.5 eng. and 1 tech., 12 adaptor cards/day for 1 tech. , and 12 cable bundles/day 1 for tech..
1.2.2.3.3 | HV, LV Pss and controllers
1.2.2.3.3.1 | Design
1.2.2.3.3.2 | Prototype
1.2.2.3.3.3 | Fabrication/Procurement | Engineer's est. | There is a more detail spread sheet for this system by P. Amaudruz. All material costs are based on quotations though for a slightly smaller scale purchase, so the values were multiplied by 0.9 for large quantity purchase.
1.2.2.3.4 | DAQ interface
1.2.2.3.4.1 | Design
1.2.2.3.4.2 | Prototype
1.2.2.3.4.3 | Fabrication/Procurement | Engineer's est. | Conceptual estimate so far.
1.2.2.3.5 | Scintillator Electronics
1.2.2.3.5.1 | WFD Boards
1.2.2.3.5.1.3 | Fabrication/Procurement
1.2.2.3.5.1.5 | Test
1.2.2.3.5.2 | Crate Data-Collection Boards
1.2.2.3.5.2.3 | Fabrication/Procurement
1.2.2.3.5.2.5 | Test
1.2.2.3.5.3 | VXI Mainframes & Controller
1.2.2.3.5.3.3 | Fabrication/Procurement
1.2.2.4 | Mechanical
1.2.2.4.1 | Support plates |  | See Labour.
1.2.2.4.1.1 | Design
1.2.2.4.1.2 | Prototype
1.2.2.4.1.3 | Fabrication/Procurement*** | Engineer's est.
1.2.2.4.2 | Support rails
1.2.2.4.2.1 | Design
1.2.2.4.2.2 | Prototype
1.2.2.4.2.3 | Fabrication/Procurement*** | Engineer's est.
1.2.2.4.3 | Transport/storage |  | transport 17 shipments x 16000 + (2 boxes, 2000) x 2 =29200
1.2.2.4.3.1 | Design
1.2.2.4.3.2 | Prototype
1.2.2.4.3.3 | Fabrication/Procurement*** | Physicist' est. | Base on the past shipments
1.2.2.5 | External PV
1.2.2.5.1 | PMT - Instrumented Modules
1.2.2.5.1.1 | Modules
1.2.2.5.1.1.1 | Scintillator Tiles
1.2.2.5.1.1.2 | Lead Tiles
1.2.2.5.1.1.3 | WLS Fiber
1.2.2.5.1.1.4 | Assembly
1.2.2.5.1.1.5 | Test
1.2.2.5.1.1.6 | Packing
1.2.2.5.1.2 | Module Instrumentation
1.2.2.5.1.2.1 | Phototube
1.2.2.5.1.2.2 | Preamplifier
1.2.2.5.1.2.3 | LV-HV Converter
1.2.2.5.1.2.4 | Mechanics
1.2.2.5.1.2.5 | Assembly
1.2.2.5.1.2.6 | Test
1.2.2.5.1.2.7 | Packing
1.2.2.5.1.3 | Cosmic Ray Test of Module/PMT
1.2.2.5.2 | Instrumentation
1.2.2.5.2.1 | HV Control System
1.2.2.5.2.1.1 | 34 VME Carriers
1.2.2.5.2.1.2 | 136 IP Modules
1.2.2.5.2.1.3 | 3 VME/VXI Mainframes
1.2.2.5.2.2 | Cosmic Ray Pre Calibration
1.2.2.5.2.2.1 | PMT & HV
1.2.2.5.2.2.2 | 10 VME Modules -LTD
1.2.2.5.2.2.3 | 6 VME Modules - Trigger
1.2.2.5.2.2.4 | 1 VME Mainframe
1.2.2.5.2.3 | Monitoring & Calibration System
1.2.2.5.2.3.1 | Design
1.2.2.5.2.3.2 | Prototype
1.2.2.5.2.3.3 | Fabrication/Procurement
1.2.2.5.2.4 | Readout Electronics
1.2.2.5.2.4.1 | WFD Boards
1.2.2.5.2.4.1.3 | Fabrication/Procurement
1.2.2.5.2.4.1.5 | Test
1.2.2.5.2.4.2 | Crate Data-Collection Boards
1.2.2.5.2.4.2.3 | Fabrication/Procurement
1.2.2.5.2.4.2.5 | Test
1.2.2.5.2.4.3 | VXI Mainframes & Controller
1.2.2.5.2.5 | Electronic Racks & LV Power Supplies
1.2.2.5.2.5.1 | LV Power Supplies
1.2.2.5.2.5.2 | Electronic Racks
1.2.2.5.3 | Shipping
1.2.2.5.4 | Assembly & Test
1.2.2.5.4.1 | Mechanical & Optical Test
1.2.2.5.4.2 | Cosmic Ray Test
1.2.2.5.4.3 | Technical Support
1.2.2.5.6 | Cabling
1.2.2.5.6.1 | LV-PS Cables
1.2.2.5.6.2 | HV Control Cables
1.2.2.5.6.3 | Signal Cables
1.2.2.5.6.4 | Assembly & Installation
1.2.2.5.6.5 | Technical Support & Test
1.2.2.6 | Work at BNL
1.2.2.6.1 | Pre-installation work at BNL | Physicist's est. | Pre-Inst. assume 3 years of installation 32 x 5(weeks)/50(weeks) (0.5 phys. + 0.5 eng. + 1tech) = 1.6 phys + 1.6 eng + 3.2 tech No travel expense here assuming "operation" may cover it.
1.2.2.6.1.1 | Design
1.2.2.6.1.2 | Prototype
1.2.2.6.1.3 | Fabrication/Procurement***
1.2.2.6.2 | Installation monitoring | Physicist's est. | Installation assume 3 years of installation 32 x 2(weeks)/50(weeks) (1 phys. + 0.5 eng. + 1tech) = 1.28 (phys+eng+tech) No travel expense here assuming "operation" may cover it. These numbers are based on the E949 drift chamber installation.
1.2.2.6.2.3 | Fabrication/Procurement***
1.2.2.10 | Management | Physicist's est.

## Contingency
|  | Contingency |  |  |  |  | multi-factor |  |  |  | status
WBS |  |  | T | C | S | D | T | C | S | D
1.2.2 | Preradiator
1.2.2.1 | Chamber System | 44 | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.1.1 | Chambers | 44 | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.1.1.1 | Design | 44 | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.1.1.2 | Prototype | 44 | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.1.1.3 | Fabrication/Procurement | 44 | 4 | 6 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2 | Gas System | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2.1 | Design | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2.2 | Prototype | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2.3 | Fabrication/Procurement | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2.3.1 | In module(tube,MFM x278) | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2.3.2 | Rec.system(MFC,pump x4) | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2.3.3 | Plumbing | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2.3.4 | Gas shack | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.1.2.3.5 | DAQ | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
|  | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.2 | Scintillator System | 36 | 4 | 4 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.2.1 | Scintillator Plates | 30
1.2.2.2.1.1 | Design | 30 | 8 | 6 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.2.1.2 | Prototype | 30 | 8 | 6 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.2.1.3 | Fabrication/Procurement | 30 | 8 | 6 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.2.2 | WLS fiber | 22 | 4 | 6 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.2.2.2 | Prototype | 22 | 4 | 6 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.2.2.3 | Fabrication/Procurement | 22 | 4 | 6 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.2.3 | Scintillator readout | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.2.3.1 | Photo Tube | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.2.3.1.3 | Fabrication/Procurement | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.2.3.2 | MU Metal Shield/Bases | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.2.3.2.3 | Fabrication/Procurement | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.2.3.3 | Cables | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.2.3.3.3 | Fabrication/Procurement | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.2.3.4 | Preampifier | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.2.3.3.3 | Fabrication/Procurement | 10 | 2 | 4 | 2 | 0 | 2 | 1 | 1 | 1
1.2.2.3 | Electronics | 20
1.2.2.3.1 | Anode Electronics | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.1.1 | Design | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.1.2 | Prototype | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.1.3 | Fabrication/Procurement | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.2 | Cathode Electronics | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.2.1 | Design | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.2.2 | Prototype | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.2.3 | Fabrication/Procurement | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.3 | HV, LV Pss and controllers | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.3.1 | Design | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.3.2 | Prototype | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.3.3 | Fabrication/Procurement | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.4 | DAQ interface | 44 | 6 | 6 | 4 | 4 | 4 | 2 | 1 | 1
1.2.2.3.4.1 | Design | 44 | 6 | 6 | 4 | 4 | 4 | 2 | 1 | 1
1.2.2.3.4.2 | Prototype | 44 | 6 | 6 | 4 | 4 | 4 | 2 | 1 | 1
1.2.2.3.4.3 | Fabrication/Procurement | 44 | 6 | 6 | 4 | 4 | 4 | 2 | 1 | 1
1.2.2.3.5 | Scintillator Electronics | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.5.1 | WFD Boards | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.5.1.3 | Fabrication/Procurement | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.5.1.5 | Test | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.5.2 | Crate Data-Collection Boards | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.5.2.3 | Fabrication/Procurement | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.5.2.5 | Test | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.5.3 | VXI Mainframes & Controller | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.3.5.3.3 | Fabrication/Procurement | 20 | 4 | 4 | 4 | 4 | 2 | 1 | 1 | 1
1.2.2.4 | Mechanical | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.1 | Support plates | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.1.1 | Design | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.1.2 | Prototype | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.1.3 | Fabrication/Procurement*** | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.2 | Support rails | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.2.1 | Design | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.2.2 | Prototype | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.2.3 | Fabrication/Procurement*** | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.3 | Transport/storage | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.3.1 | Design | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.3.2 | Prototype | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.4.3.3 | Fabrication/Procurement*** | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
|  | 64 | 8 | 8 | 8 | 8 | 4 | 2 | 1 | 1
1.2.2.5 | External PV
1.2.2.5.1 | PMT - Instrumented Modules | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.1 | Modules | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.1.1 | Scintillator Tiles | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.1.2 | Lead Tiles | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.1.3 | WLS Fiber | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.1.4 | Assembly | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.1.5 | Test | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.1.6 | Packing | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.2 | Module Instrumentation | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.2.1 | Phototube | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.2.2 | Preamplifier | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.2.3 | LV-HV Converter | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.2.4 | Mechanics | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.2.5 | Assembly | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.2.6 | Test | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.2.7 | Packing | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.1.3 | Cosmic Ray Test of Module/PMT | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2 | Instrumentation | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.1 | HV Control System | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.1.1 | 34 VME Carriers | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.1.2 | 136 IP Modules | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.1.3 | 3 VME/VXI Mainframes | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.2 | Cosmic Ray Pre Calibration | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.2.1 | PMT & HV | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.2.2 | 10 VME Modules -LTD | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.2.3 | 6 VME Modules - Trigger | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.2.4 | 1 VME Mainframe | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.3 | Monitoring & Calibration System | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.3.1 | Design | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.3.2 | Prototype | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.3.3 | Fabrication/Procurement | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.4 | Readout Electronics | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.4.1 | WFD Boards | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.4.1.3 | Fabrication/Procurement | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.4.1.5 | Test | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.4.2 | Crate Data-Collection Boards | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.4.2.3 | Fabrication/Procurement | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.4.2.5 | Test | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.4.3 | VXI Mainframes & Controller | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.5 | Electronic Racks & LV Power Supplies | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.5.1 | LV Power Supplies | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.2.5.2 | Electronic Racks | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.3 | Shipping | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
|  | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.4 | Assembly & Test | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.4.1 | Mechanical & Optical Test | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.4.2 | Cosmic Ray Test | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.4.3 | Technical Support | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.6 | Cabling | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.6.1 | LV-PS Cables | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.6.2 | HV Control Cables | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.6.3 | Signal Cables | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.6.4 | Assembly & Installation | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.5.6.5 | Technical Support & Test | 14 | 2 | 4 | 2 | 4 | 2 | 1 | 1 | 1
1.2.2.6 | Work at BNL | 56 | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.6.1 | Pre-installation work at BNL | 56 | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
|  | 56 | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.6.1.1 | Design | 56 | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.6.1.2 | Prototype | 56 | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.6.1.3 | Fabrication/Procurement*** | 56 | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
1
1.2.2.6.2 | Installation monitoring | 56 | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.6.2.3 | Fabrication/Procurement*** | 56 | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
|  |  | 8 | 6 | 4 | 8 | 4 | 2 | 1 | 1
1.2.2.10 | Management | 0
|  | 4 | 1 | 1 | 2 | 0 | 1 | 1 | 1 | 1