## CMR Template
NATIONAL ENERGY TECHNOLOGY LABORATORY
COST MANAGEMENT REPORT
1 Title: | Research and Development | [10 empty] | 2 Reporting Period: |  | 7/30/2008 to 8/30/2008 |  |  |  | 3 Identification Number: |  | DE-NT0005432 Mod # A001
4 Participant Name and Address: | MY COMPANY, LLC | [10 empty] | 5 Cost Plan Date: |  | 10/01/2008 to 9/30/2009 |  |  |  | 6 Contract Start Date: |  | 2008-10-01
| 4567 Apple Lane, Anywhere, USA | [16 empty] | 7 Contract Completion Date: |  | 2011-09-30
Element Identification | [6 empty] | Obligations |  |  | Plan |  | Accrued Costs | [5 empty] | Projections
[12 empty] | Reporting Period |  | FY to date |  | Cumulative to Date
8 CLIN/Task Number / Title | 9 Rev | 10 Approp Year | 11 Reporting Entity | 12 Program Number | 13 WFO Or Project No | 14 Local Use | 15 Prior FY Funding | 16 Current FY Obligations | 17 Total Obligations | 18 Approved FY Cost Plan | 19 Total Plan Value | 20 Actual | 21 Plan | 22 Actual | 23 FY Bal of Plan | 24 Actual | 25 Plan | 26 Open Commitments | 27 Next Month Plan | 28 FY Total Cost | 29 Funds Expiration
CLIN 01 Mission Specific Support
0005432.01 | A | 2008 | 220201 | 1610328 |  | 02863001 | 0 | 2000 | 2000 | 150000 | 156000 | 2000 | 2500 | 53060 | 140007 | 53060 | 91158 | 40000 | 2000 | 231166 | 2008-05-17
0005432.01 | A | 2008 | 220201 | 1610232 |  | 02863001 | 1000 | 4000 | 5000 | 56000 | 56000 | 2000 | 2600 | 16756 | 44992 | 16756 | 5000 | 0.5 | 3 | 3 | 2008-05-17
0005432.01 | A | 2008 | 220201 | 1610247 |  | 02863001 |  | 4000 | 4000 | 56000 | 56000 | 2000 | 2600 | 16000 | 45000 | 22 | 29 | 1 | 3 | 3 | 2008-05-17
CLIN 01 TOTAL | [6 empty] | 1000 | 10000 | 11000 | 262000 | 268000 | 6000 | 7700 | 85816 | 229999 | 69838 | 96187 | 40001.5 | 2006 | 231172
CLIN 02 Research Information Technology Support
0005432.02 | A | 2008 | 220318 | 1610328 |  |  | 120000 |  | 120000 | 0 | 204649 | 0 | 0 | 0 | 0 | 15677 | 115799 | 60000 | 0 | 0 | 2008-05-17
0005432.02 | A | 2008 | 220221 | 1610232 |  |  | 15000 |  | 15000 | 0 | 164085 | 0 | 0 | 0 | 0 | 12568 | 92846 | 1000 | 0 | 0 | 2008-05-17
0005432.02 | B | 2009 | 220318 | 1610232 |  |  |  | 15000 | 15000 | 200000 | 164085 | 13000 | 25000 | 13000 | 75000 | 13000 | 117846 | 2500 | 25000 | 85000 | 2009-04-25
CLIN 02 TOTAL | [6 empty] | 135000 | 15000 | 135000 | 200000 | 368734 | 13000 | 25000 | 13000 | 75000 | 41245 | 326491 | 63500 | 25000 | 85000
CLIN 03 Engineering Research
0005432.03 | A | 2008 | 220221 | 1720285 |  |  | 122000 | 0 | 122000 | 0 | 360648.66 | 17677.13 | 33502.86 | 68736.89 | 228856.64 | 68736.89 | 206957.48 | 139286.65 | 7000 | 435814.32 | 2008-05-17
0005432.03 | A | 2008 | 220221 | 1610257 |  |  | 21000 | 0 | 21000 | 0 | 220085.34 | 14567.63 | 27458.15 | 29323.35 | 116231.37 | 29323.35 | 121844.52 | 83888.23 | 11000 | 238075.68 | 2008-05-17
0005432.03 | B | 2009 | 220221 | 1720285 |  |  |  | 10000 | 10000 | 350000 | 720649 | 20000 | 25000 | 20000 | 325000
CLIN 03 TOTAL | [6 empty] | 143000 | 10000 | 153000 | 350000 | 1301383 | 32244.76 | 60961.01 | 98060.24 | 345088.01 | 98060.24 | 328802 | 223174.88 | 18000 | 673890
30 Subtotal FE
31 Subtotal NonFE
32 Total
33 Figures Expressed In: Whole Dollars | [6 empty] | 34 Signature of Participant's Project Manager and Date | [5 empty] | 35 Signature of Participant's Authorized Financial Representative and Date
36 NOTES:

## Invoice Detail
NATIONAL ENERGY TECHNOLOGY LABORATORY
Invoice/Staffing Data
1 Participant Name and Address |  |  | 3 To: U.S. DOE - NETL
P. O. Box 10940
Pittsburgh PA, 15236
4 Invoice No.
5 Invoice Date:
2 Contract No.: |  |  | 6 Billing Period:
[5 empty] | Current Period | [8 empty] | Cumulative
12 Hours
[5 empty] | Worked of | 13 Total Cost | 14 Total
| 8 Labor Category (E N/E) or Description |  |  | 11 Current | Available | Current | FTE | 15 Labor by Site | [6 empty] | 17 Prev | 18 Current
7 Name |  | 9 Status | 10 Employer | Rate | 160 | Period | Labor hours | Mgn | Pgh | Tul | Alb | AK | Offsite | 16 Hours | Costs | Cost
19 CLIN 01 Mission Specific Support
Jones, Tom | Program Mgt Support Specialist (E) | FT | ABC, Inc. | 32.16 | 160 | 5145.6 | 1 | 1 | [5 empty] | 460 | 9648 | 14793.6
Lemon, Jason | Secretary 1 (NE) | FT | ABC, Inc. | 25.65 | 160 | 4104 | 1 |  | 1 |  |  |  |  | 460 | 7695 | 11799
Page, Sharon | Word Processing Operator 1 (NE) | FT | ABC, Inc. | 27.13 | 152 | 4123.76 | 0.95 |  | 0.95 |  |  |  |  | 452 | 8139 | 12262.76
Vernon, Greg | Word Processing Operator 1 (NE) | FT | ABC, Inc. | 27.13 | 152 | 4123.76 | 0.95 |  | 0.95 |  |  |  |  | 452 | 8139 | 12262.76
Palm, Karen | Clerk 1 (NE) | PT | XYZ Co. | 28.02 | 80 | 2241.6 | 0.5 |  | 0.5 |  |  |  |  | 380 | 8406 | 10647.6
| 20 TOTAL: |  |  |  | 704 | 19738.72 | 4.4 | 1 | 3.4 |  |  |  | 0 | 2204 | 42027 | 61765.72
21 (Planned/Actual Labor hours - Current XXX / XXX)
22 (Planned/Actual Labor hours - Cumulative XXXX /XXXX )
23 Other Direct Costs (ODCs) | 24 Description
25 Materials | [5 empty] | 100 | [8 empty] | 100 | 200
26 Travel | [5 empty] | 200 | [8 empty] | 500 | 700
27 Training | [5 empty] | 300 | [8 empty] | 300 | 600
28 Total ODCs | [5 empty] | 600 | [8 empty] | 900 | 1500
29 Fee | [5 empty] | 100 | [8 empty] | 50 | 150
30 Total Cost &Fee | [5 empty] | 20438.72 | [8 empty] | 42977 | 63415.72
31 Labor Summary by Program Number
|  | Reporting Entity | Actual RP Cost
CLIN | Program Number |  |  | Mgn | Pgh | Offsite
0005432.01 | 1610328 | 220201 | 7554.23 | 0.38271 | 1.3012
0005432.01 | 1610232 | 220201 | 3589.12 | 0.18183 | 0.61823
0005432.01 | 1610323 | 220201 | 8595.37 | 0.43546 | 1.4806
Subtotal |  |  | 19738.72 | 1 | 3.4

## Staff Summary
NATIONAL ENERGY TECHNOLOGY LABORATORY
Staffing Report Summary
1 Participant Name and Address |  |  |  | 3 To: U.S. DOE - NETL
P. O. Box 10940
Pittsburgh PA, 15236
2 Contract No.: DE-NT0005432 |  |  |  | 4 Reporting Period:
5 Contract: ABC | FTE Staffing Summary
Program Area | 6 Program Direction | Coal Programs | Oil - Gas | Environmental Restoration | Clean Coal | CHRIS (YN) (b) | Mining | PMC (c) | Reimbursable and WFO | 7 Other Inst | 8 Non Inst | 9 Total
Program Numbers (a) | 1610318-331 | 1610214-252 1610884-910 1610317 1610345 | 1610447-451 1610253-271 1610911-955 1610484-871 1610876-878 | 1610346-352 | 1610306-316 1610357-405 | 1713278-279 1714193 1721310 2221494-1554 | 1610303 | 1004170-224 1004241-400 1004402-572 1004577-593 1004609-663 1004665-900 1005098 2923835-3845 3123553-668 2220651-1068 2221134-1339 2221494-1554 1110486-678 1721119-26 | 1720285-936 | 1610276-303 1610317 1610686-688 1610703 | 1610305 1610334 1110449-466 1110499-678 1721119-24 | FTEs
10 MGN | 0.81817 |  |  | 0.18183 | 1.25 | [6 empty] | 2.25
PGH | 2.7818 |  |  | 0.61823 | [7 empty] | 3.4
TUL | 0.5 |  | 0.5 |  |  |  | 0.3 |  |  |  |  | 1.3
ALB | 0 | [10 empty] | 0
AK | [11 empty] | 0
Offsite | [11 empty] | 0
11 TOTAL | 4.0999 | 0 | 0.5 | 0.80006 | 1.25 | 0 | 0.3 | 0 | 0 | 0 | 0 | 6.95
12 Headcount Staffing Summary
MGN | 152
PGH | 148
TUL | 2
ALB | 2
AK | 1
Offsite | 60
TOTAL | 365
(a) Program numbers as assigned according to FY budget requirements.
(b) YN supports CHRIS (ITES contract only)
(c) Show FTEs for these Program Number Values ONLY if they are associated with Reporting Entities 6XX (ORD) and 4XX (OSAP); otherwise show under Non Inst
(d) Show FTEs for these Program Number Values ONLY if they are associated with Reporting Entities 6XX (ORD) and 4XX (OSAP) under Reimb & WFO