## May 17, 2005

## RSVP Review Report

Executive Summary

Introduction. The Rare Symmetry Violating Process (RSVP) Review Panel met at Brookhaven National Laboratory (BNL) April 20-22, 2005, to evaluate the status of the RSVP project. More specifically, the charge to the Panel was to review the cost, schedule, scope, technical and management project baseline as well as the plans for operations and the associated costs and schedule. The evaluation of physics importance was not a part of the charge, which is being evaluated by a separate Panel; however we were invited to comment on the significance of the physics should we so desire.

The RSVP project is quite complex and extensive. It includes two experiments, KOPIO (rare K decay) and MECO (muon capture with electron emission), in addition to required modifications to the BNL Alternating Gradient Synchrotron (AGS), beamlines for the experiments, and the associated Project Management structure. To cover the diverse nature of the Project, the Panel was subdivided by expertise into six subgroups, each covering one aspect of the project. The six areas were: KOPIO experiment; MECO experiment; MECO solenoid magnet; AGS, Booster and associated beamlines; operations and commissioning; and management.  The MECO magnet was split out as a separate topic because of its highly technical nature and significant cost. After plenary introductory talks, most of the Panel’s work was done in individual breakout groups involving presentations by and discussions with the cognizant physicists, engineers, and/or project staff and internal discussions in executive sessions. The Panel held periodic executive sessions with all members present. In the following, we present our findings on issues requested in the charge.

State of readiness. The Panel was impressed with the amount of work that has been done on this Project. The results of that work are clearly visible in the much better understanding today of the technical, cost, and schedule issues of different Project elements than was true a year ago, as well as we can judge it from the reports of previous reviews. The state of readiness of different components, however, is still rather uneven. In some areas, such as the AGS modifications and the MECO solenoid, significant engineering design has already been done. A number of the detector subsystems, on the other hand, are still in rather early phases of development. However, there do not appear to be any irresolvable technical challenges in these areas and they are not on a critical path. Their “benign neglect” to date has been frequently due to conscious decisions by the Project management as to how best to allocate scarce engineering resources. For both experiments, the simulations in several areas still need to be refined and made more realistic (e.g. full reconstruction algorithms need to be incorporated) in order to validate to the extent possible the current design.

Technical design. The Panel felt that the technical design of the experiments and associated accelerator infrastructure is well matched to the stated physics goals. However, there are some areas of concern. The recent change to the baseline design of the MECO tracker and the immaturity of the design of the trigger and data acquisition systems for KOPIO are examples. We found no show-stoppers that would prevent the achievement of these goals with the proposed apparatus. The experiments, however, are very difficult and frequently push the available technology to its performance limit. Several of the accelerator performance requirements, while not necessitating new technology to achieve them, will explore as yet untested domains. (A particular example is the MECO criterion of 10E-9 inter-bunch extinction of the extracted beam in the presence of high peak currents circulating in the AGS.) Thus, technical risks are present that could have implications on both cost and schedule and on the ultimate ability of the experiments to achieve their sensitivity goals..

Ideally, one would like to test the feasibility and performance of high risk items as soon as possible so as to minimize cost and schedule risk. Some that might need iteration are accelerator modifications and their impact on high intensity operation; KOPIO neutral beam and its neutron halo; and performance of detector subsystems in their actual environments. Unfortunately, many of these are long lead items and generally require operation in full intensity environment. The commissioning schedule must be thought out very carefully so as to optimize opportunities for “early warnings.”

Schedule. The tight schedule being proposed may be one of the most significant contributors to the cost risk. The technical challenges in both accelerator and detector areas may well cause slippage of the start of data taking by a year or more. Thus, a float of roughly this duration should be built in into the construction and operation schedule. The cost impact of such a prolongation is not yet accounted for.

Construction cost. The cost is a major concern for this Project and the Panel tried to understand the estimates as well as it could in the limited time available. The reliability of cost estimates clearly depends on the state of readiness of a given subsystem. As stated above, the latter is rather uneven throughout the Project at this time and hence the costs quoted vary in their precision. We found that the “Lockheed formula,” used by the proponents to calculate the contingency for each subsystem so as to take proper account of the state of its readiness, significantly underestimates the contingency required. The top level Project management has tried to correct for this by imposing an overall project contingency of 45%.  This is as yet undifferentiated among the various project segments.

In evaluating the validity of the cost estimates, we examined all the components of major subsystems to see if any essential elements were left out. We feel comfortable that no large cost elements are missing. We have also looked in some detail at the methodology used to obtain the cost estimates for various selected items and found no obvious flaw that would invalidate those estimates. The current cost estimates appear most reliable for the AGS upgrades, MECO magnets, and the Project Management: the 45% top-down cost contingency imposed seems to be an overestimate in these areas. On the other hand, because of their less mature status, the 45% contingency might be an underestimate for the two detector subsystems. The Panel thus feels that the Project’s estimate of total MREFC cost of $282M in then-year dollars (including pre-operations and commissioning) could be adequate, the assumed contingency being sufficient to cover potential cost underestimates. This cost estimate is based on an inflation rate of 2.8%, whereas the feeling of the Panel was that this rate is likely to be higher over the period of this project. For example, the current labor rate escalation used by the DOE Laboratories is in the 3.5-4% range. The difference becomes significant when one extrapolates 10 years or so into the future. The quoted detector construction cost assumes very significant physicist contribution in labor; new groups will need to be recruited or currently involved groups greatly enlarged to meet those projected contributions. No contingency is provided to cover possible shortfalls in “off-project” physicist labor that would have to be compensated by “on-project” hires.

RSVP (especially KOPIO) has significant participation from groups outside the United States; they are playing important role in the experiments and are counted on for significant in-kind contributions. It is quite likely that a decision to go ahead expeditiously would result in significant additional participation, relieving somewhat the pressure on contributions from the US groups. We urge creation of appropriate financial and management structures to encourage significant and timely participation of non-US groups.

Operations costs. The success of RSVP goes beyond the completion of the construction of the experiments and of the accelerator upgrades and beamlines. The goal, after all, is production of scientific results. Thus, attention and high priority must be given to the creation of appropriate conditions for operation of the experiments. At the conclusion of MREFC, there will be additional costs related to RSVP operation falling mainly in two categories: incremental costs for operation of the AGS/Booster complex and costs for incremental support of the participating university and National Laboratory groups. The Panel tried to estimate these costs under different scenario assumptions.

Based mainly on input from the experimental collaborations (which appears reasonable to us) we estimate that the additional required support level per experiment for participating groups is $2.5M per year. This will need to start during the construction phase and continue through the operations phase. Most likely this sum would be divided between NSF and DOE in a ratio reflecting the traditional support source of the participating groups. Thus the funding required is about $25M (in FY05$) for both experiments during construction phase and $5M (FY05$) per year during  the  operations phase of the Project. Because of the importance of this issue, NSF should work with DOE to see how one can achieve the required staffing levels of the involved groups.

The estimate of NSF-borne AGS operational costs is somewhat more complicated, depending on the fraction of the time that RHIC is running and the details of its mode of operation. We were asked to evaluate what these costs might be to achieve the goals of the experiments for three different scenarios assuming different levels of DOE support of RHIC (and hence AGS). We did so based on the input of the AGS staff, who used the data from the prior operating experience of AGS. The support level scenarios were cost optimized for most economic delivery of the number of protons on target requested by RSVP experiments and the most relevant numbers are given in Table I below. For “1/3 healthy RHIC” scenario, RHIC and RSVP running would be in alternate years. The costs are given in then-year $.  3.5% annual inflation rate was used since the costs are dominated by expenditures on power and labor.

Table I. Estimated AGS Operating Costs to be Borne by NSF

| Mode | Years of operation | Weeks/year | Cost to NSF |
| --- | --- | --- | --- |
| Healthy RHIC | 2011-2019 | 25 | $156M |
| 1/3 Healthy RHIC | 2011-2018 | 42 or 0 * | $195M |
| No DOE funds for AGS | 2011-2015 | 42 | $361M |

* In this mode RHIC and RSVP run in alternate years

It is clear to us that there is a major NSF cost exposure connected with the operating costs, especially if one allows for the likelihood that these experiments will require a substantially longer period of data taking than the number of years currently planned.

The potential NSF cost burden is directly related to the DOE plans regarding its support of AGS operations. NSF should initiate discussions with DOE on this issue as soon as possible.

Cost Summary. We summarize in Table II the major costs of the RSVP program for both the construction and operations phases. All costs are expressed in then-year dollars.

Table II. Summary of the major costs of the RSVP program

| Activity | Cost (then year $) |
| --- | --- |
| Construction (MREFC) | $267 M |
| Pre-operations and commissioning | $15 M |
| Physicist Support (construction and operations) | $61 – 92M |
| Operations | $156 – 361 M |
| Decontamination and Decommissioning (D & D) | $20 M |

There are a number of potential cost risks for the items in the Table II that are difficult to quantify.  One might highlight the lack of float in the construction and preoperations schedule and the possibility that the initial data taking will be slower than expected. The Panel also felt that 25% contingency assumed for D&D was too low in light of inherent uncertainties involved here.

Management. There has been a recent management reorganization with the creation of a centralized office charged with overseeing all different components of the Project. The Panel endorses this management change and sees it as an essential step in getting the Project on the way. This transition is still in process; undoubtedly there will be some painful adjustments but we are confident that with good will all around, good communications, and development of a management plan that achieves a wise balance between centralized and delegated responsibilities, this reorganization will lead to creation of conditions that will greatly enhance the likelihood of a successful construction project and achievement of the Project’s scientific goals. As an example, there are a number of areas where some rearrangement of responsibilities between different subprojects might be productive. We recommend active involvement by the central Project office in studying and adjudicating these issues.

An important element in the execution of this project is the novel relationship between the Project, the host Laboratory, and the two funding agencies. Even though BNL and DOE are not the official “sponsors” of RSVP, they will play a crucial role in it. BNL has to have a strong commitment to the success of RSVP and we were gratified to hear such a commitment from BNL directorate. DOE, besides supporting the activities of BNL, will   need to support a large (probably major) fraction of university groups participating in RSVP. Those groups will be crucial to RSVP success and their operating budgets will have to receive high enough priority among competing requests so as to be able to discharge their anticipated obligations. Even though most of these groups will probably be groups with traditional support from HEP division,  a number of DOE NP supported groups may also want to be involved. We urge the NSF to review current communication mechanisms between NSF, DOE, BNL and RSVP management to see whether they are adequate for the success of the RSVP Project.

Conclusion. To conclude, the Panel believes that the RSVP physics program addresses frontier physics questions that are not likely to be addressed elsewhere on this time scale. Furthermore, the construction and initial operation would occur in a time frame when few other particle physics activities will be going on in US. Thus it would make a major contribution to the health of the field in US. The proposed experimental arrangements appear well suited towards addressing the physics goals and we see no major show-stoppers. There are a number of technical challenges but they do not seem to be fundamental; no new inventions are required to achieve the proposed goals. The experiments are very difficult, however, and achievement of the proposed sensitivity is not certain. The management team in place is experienced and a management structure is being developed that should significantly improve the probability of success. Because of the long range nature of the program, there has to be a commitment on the part of US funding agencies to support it for at least a decade. There are cost risks to NSF arising principally from technical uncertainties that might affect the length of operation required to reach science goals and from the uncertainty in the extent of DOE support for AGS operations in the future.

###### Introduction

The Rare Symmetry Violating Process (RSVP) Review Panel met at Brookhaven National Laboratory (BNL) April 20-22, 2005, to evaluate the status of the RSVP project. More specifically, the charge to the Panel was to review the cost, schedule, scope, technical and management project baseline as well as the plans for operations and the associated costs and schedule. The evaluation of physics importance was not a part of the charge, which is being evaluated by a separate Panel; however we were invited to comment on the significance of the physics should we so desire. The charge to the Panel is attached to this Report as Appendix A.

## The RSVP project is quite complex and extensive. It includes two experiments, KOPIO (rare K decay) and MECO (muon capture with electron emission), in addition to required modifications to the BNL Alternating Gradient Synchrotron (AGS) and the booster synchrotron, beamlines for the experiments, and the associated Project Management structure. To cover the diverse nature of the Project, the Panel was subdivided by expertise into six subgroups, each covering one aspect of the project. The six areas were: KOPIO experiment; MECO experiment; MECO solenoid magnet; AGS, Booster and associated beamlines; operations and commissioning; and management. The membership of the Panel and its division into subgroups is given in Appendix B.

The morning part of the first day was spent in plenary session listening to the overview talks about different parts of the RSVP Project. The Panel also heard brief comments about RSVP by Dr. Michael Turner, the Associate Director of NSF for Mathematics and Physical Sciences. In the afternoon four separate breakout sessions were held corresponding to KOPIO experiment, MECO experiment, MECO magnet, and AGS/booster upgrades. The management and operations/commissioning groups split themselves up between the fours sessions so as to get the flavor of issues of concern to their subgroups but specific to the four subprojects.

The following two days were spent in breakout sessions or in executive sessions. The latter were sometimes internal to subgroups and sometimes included the whole Panel. The NSF program officers sat on all presentations and discussions. The breakout sessions had some prepared presentations but were for the most part discussions focusing on specific questions that the Panel had for the proponents. The meeting ended with a closeout session, open to the senior members of the collaboration and RSVP Project. This session was also attended by theNSF officials including Dr. Turner, and representatives of the DOE NP office. The session was followed by a brief executive session to draft the outline of the Executive Summary.  The detailed agenda is attached to this report as Appendix C.

This report is organized as follows. We start with a brief discussion of the physics of the RSVP Project and our general view of its significance. Subsequently we discuss the findings, comments, and recommendations of each Panel subgroup regarding the issues in their “jurisdiction”. Finally, at the end we summarize our finding and conclusions, identifying what we view as potentially most important issues to resolve, the most likely cost exposures, and the most important actions NSF needs to take to make the Project a success.

Physics of RSVP

The RSVP Project consists of two experiments, KOPIO and MECO. The former proposes to search for and measure the branching ratio for the decay mode with a sensitivity about two orders of magnitude better than the projected limit from the ongoing experiment in Japan. The MECO experiment is a search for the capture of - on a nucleus (Al target) with the emission of an electron, a process forbidden in the Standard Model (SM). The projected sensitivity of the experiment (5 events at BR=10-16 ) is about 3 orders of magnitude below the existing limit of 6 x 10-13 (on Ti target).

The evaluation of physics significance of these experiments was not part of the charge to the Panel. The Panel was invited, however to comment if it so desired about the importance of the physics and how it fits in with the world efforts in particle physics. The Panel held no discussion on this topic so what follows is a rather informal view of Panel’s members on this subject.

The RSVP Project addresses what are undoubtedly key issues in particle physics today, ie the physics beyond the Standard Model. The experiments are complementary to the experiments at the energy frontier at the Large Hadron Collider (LHC) at CERN in Geneva, Switzerland, in which many US groups are playing a prominent role. These experiments could probe mass scales of new physics (through virtual diagram effects) which are inaccessible to high energy colliders like Tevatron and LHC.. Observation of the process  - -> e-  or measurement of the branching ratio for K0(0  bar that is in disagreement with the Standard Model would be a conclusive indication of new physics beyond the Standard Model. Numerous recent theoretical extensions of the Standard Model predict significant effects in these two channels that the RSVP Project should be able to observe and measure.

The ongoing experiments addressing the RSVP goals - in Japan for the KOPIO channel and in Switzerland for the search for the muon number violation - will undoubtedly improve our knowledge of these processes but will still be significantly short of the RSVP goals. The E931a, at KEK, has a sensitivity goal of about 10-10 for the branching ratio of the decay K0(0  bar, compared to SM prediction of 3 x 10-11. The MEG experiment at PSI for the decay  (e   has a goal of ultimate sensitivity of 10-14. At that level, the ability of MEG to search for new physics would approach that of MECO.

There are tentative plans, at the Letter of Intent level, to propose experiments of comparable sensitivity to KOPIO and MECO at the new Japanese accelerator JPARC, currently under construction and scheduled to start commissioning in 2007. Whether these efforts will come to fruition is uncertain at this time and it is unlikely that they could compete with RSVP if the latter were to proceed expeditiously. Thus RSVP is well positioned to be able to make potentially significant impact on the particle physics if it proceeds on current schedule and is able to reach the proposed sensitivity.

# KOPIO Detector System (WBS 1.2)

###### Summary

KOPIO is one of two experiments comprising the RSVP project. The goal of this experiment is to observe the ultra-rare decay KL  0 _bar and to measure its branching ratio to about 10% accuracy. Within the Standard Model, this decay is dominated by direct-CP violating processes and is expected to have a branching ratio of  3 ± 0.6 x 10-11 with very small theoretical uncertainties. Determination of the branching ratio (KL  0 _bar) cleanly measures the height of the unitary CKM triangle, and thus probes directly the source of CP violation in the Standard Model.  Any deviations from expectations, such as discrepancies with measurements from the b-quark sector, would signal the presence of new physics.

The experimental aspects of measuring B (KL  0 _bar) are challenging since only the final state 0   can be directly observed. KOPIO proposes to reconstruct and identify the KL  0 _bar final state through a precise reconstruction of the decay kinematics (energy, position and angles) of the photons, use of the time-of-flight to determine the K0L momentum, and construction of a hermetic photon veto for the entire apparatus. The largest single source of background is expected to be the CP-violating decay KL  00.  Other decay modes and accidental photons are also potential sources of background and have to be suppressed by many orders of magnitude through timing, energy, and kinematic constraints. The proposed technique requires that beam be extracted from the AGS every 40ns in 200ps bunches. Two new RF cavities, driven at 25MHz and 100MHz, will be used to achieve such a micro-bunched structure and together with hermetic photon and charged particle veto systems will provide critical tools for background rejection.

The panel was impressed with the amount of effort to date expended on the planning of the experiment. At the conceptual level KOPIO appears to be well thought-out and ingenious. It is also understood that limited funds available so far have led to a yet-incomplete detailed design of the experiment, but the panel has not identified any “show-stoppers”. Significantly more effort, however, is necessary to bring all the components of the apparatus to the same detailed level of design and understanding of performance limitations. More realistic and high statistics simulation studies are needed.

Due to the limited time available for the review the panel was unable to thoroughly review the physics capabilities of KOPIO, but no reason was found to doubt the claims presented in the Conceptual Design Report available to the panel. The panel also points out that findings and recommendations of the recent Ritchie’s Panel, which reviewed the state of simulations and the physics reach of KOPIO, have been largely accepted by the KOPIO collaboration. Finally, past history teaches that experiments of this type will require significant upgrades and/or modifications to reach the design sensitivity.

The WBS structure of KOPIO and the baseline costs of KOPIO systems are shown in the Table below. Based on prior experiments, the panel judged that the assignment of contingency costs based on the bottoms-up “Lockheed formula” is not correct for this type of project. The top-down contingency proposed by the RSVP management is 45%. While this is more reasonable, the contingency should be based explicitly on the maturity of design, the schedule risk, and prior experience with the technology. Hence, the panel recommends that KOPIO redo the contingency analysis for each task, taking into account these factors.

| WBS | System Name | Material Cost | Labor Cost | Base Cost |
| --- | --- | --- | --- | --- |
| 1.2 | KOPIO | $31,638K | $21,581K | $53,219K |
| 1.2.1 | Vacuum | $2,019K | $1,188K | $3,206K |
| 1.2.2 | Preradiator | $12,140K | $5,071K | $17,210K |
| 1.2.3 | Calorimeter | $3,160K | $2,133K | $5,293K |
| 1.2.4 | Charged Particle Veto | $1,389K | $1,242K | $2,631K |
| 1.2.5 | Photon Veto | $4,319K | $2,875K | $7,194K |
| 1.2.6 | Catcher | $3,006K | $145K | $3,151K |
| 1.2.7 | Trigger | $889K | $1,734K | $2,622K |
| 1.2.8 | DAQ | $1,882K | $713K | $2,595K |
| 1.2.9 | Off-line Computing | $591K | $185K | $776K |
| 1.2.10 | Detector Systems | $1,864K | $4,195K | $6,059K |
| 1.2.11 | Project Services | $378K | $2,102K | $2,480K |

The KOPIO sub-panel reviewed mainly the detector system and only peripherally discussed related beam issues. It should be, however, emphasized, that the parameters of the beam and precision of the beam line construction are crucial for the performance of the entire detector. For example, a 1mm shift in collimator causes a 37% increase in the beam halo.

Detailed findings, comments and recommendations of the KOPIO sub-panel are presented below. First, we  summarize our direct response to the charge to the KOPIO sub-panel:

- Technical approach and feasibility

  - The panel assesses that conducting early beam tests, as the beamline elements become available, is the only way to assure that the background rates and the detector performance will be adequate.

  - Refine simulations to improve credibility of background calculations.

- Completeness of the plan (WBS)

  - The panel found the KOPIO work breakdown structure to be reasonably complete.

  - The panel does not concur with the project management’s plans to include the cost of spares in the contingency funds. Spares should be included in the baseline cost.

- Readiness to proceed to construction

  - The panel concurs with KOPIO’s assessment that significant engineering is required to the complete detailed design and bottoms-up costing of the experiment.

  - A significant expansion of the Collaboration will be necessary to complete the design and prepare production plans.

- Likely duration of the experiment

  - Past experience for this type of experiment teaches that upgrades and improvements will be necessary to reach the design sensitivity.

- Technical metrics of progress

  - The panel deemed it necessary to develop a comprehensive set of technical milestones to be used to measure the progress.

  - The panel assesses that the growth of the collaboration, which is required for the project execution, should be monitored.

- Costs and schedule

  - The panel recommends that KOPIO refines its contingency analysis to improve credibility of cost estimation.

The sub-panel also judges that KOPIO is an extremely challenging experiment and the achievement of the proposed sensitivity (requiring 12000 hours of data taking at 100 Tp/spill) may  take longer than anticipated in terms of calendar years due to numerous technical challenges in the Project... Furthermore, as discussed in Operations section, for several of the possible AGS operating scenarios the required projected running time is longer than 5 years.

###### Vacuum system

##### Findings

The vacuum system consists of five major parts: the upstream decay vessel, the magnet vacuum box, the downstream vacuum tank, the vacuum pumping station, and the vacuum transition parts (windows and a vacuum membrane). This is “the biggest technical challenge” of the experiment. Most of this 12 m3 vacuum system should operate with 10-7 torr vacuum, and the vacuum vessels need to house the Charged Particle Veto system which will hermetically cover all the walls. This veto system and the Magnet Photon Veto systems will reside in a 10-3 torr vacuum separated from the high vacuum by a thin membrane.

The vacuum vessels have to be thin (less than 7% of a radiation length) and are the central components of the experiment, which would be built around them. The collaboration has spent significant engineering effort on the decay vessel. After investigating and prototyping several options, the design chosen is a spun aluminum tank for which a vendor quote exists. The design of the pumping system is advanced and well understood. The state of engineering of other components, including mounting of the inner vetoes, is less advanced. The collaboration recognizes and has budgeted for the still-significant engineering necessary for a detailed design of all the system components.

##### Comments

The collaboration spent a significant fraction of scarce engineering resources on the design of the vacuum system. Given the central location and criticality of the system this was a good judgment.  The vacuum system, however, needs further more detailed integration with the veto systems to be installed on the walls of all vacuum vessels. More specifically, the mounting scheme of the Charged Particle Veto and the Magnet Photon Veto, the signal and voltage feed-through connectors, and the membrane need to be designed in detail.

The costing of the system appears to be well advanced. The schedule depends on the available engineering resources for completing the detailed design which still has some challenging pieces only in an early conceptual stage (e.g., feedthroughs). The costing of the magnet and downstream vacuum boxes agrees well with the past experience of constructing similar devices at BNL. The main cost drivers are the decay vessel and the pumping station. Their cost with an overall contingency level of 45% seems adequate.

##### Recommendations

- Complete the engineering design of the vacuum system integrating inside-vacuum veto systems.

###### Preradiator

# Findings

The Preradiator is a 3 x 3 m2 set of 8 modules comprised of cathode strip drift chambers and scintillator planks (8 mm thick) with lead radiators.  Each module consists of 8 planes of drift chambers and 9 planes of scintillators.  The total depth of the Preradiator is 1.375 m (2.8 radiation lengths).  It has been designed to measure the gamma ray location with a position accuracy of 5 mm and an angular accuracy of 25 mrad.  The probability of converting 2 photons within the Preradiator is about 80%.  The cathode strip chambers consist of 74k channels of anode readout (wire TDCs) and 74k channels of cathode readout (strip ADCs).  There are roughly 8k channels of scintillator readout.

Surrounding the scintillator-drift chamber central portion is an array of 1152 External Photon Vetoes (EPV).  These EPV modules are made of a lead-scintillator shashlyk design with a depth of 15.9 radiation lengths.  They are identical to the modules in the calorimeter, and the phototubes are readout in the same standard method as the other photon vetoes in KOPIO.

The TRIUMF group is responsible for the design, construction, installation and operation of the Preradiator scintillator - drift chamber modules.  This includes the design and construction of the front-end electronics.  It does not include the EPV modules.

# Comments

The conceptual design developed by the Preradiator group is a good match to the requirements of finding and measuring accurately the photons from the o decay.  The group has done a very good job and should be congratulated on the thoroughness of their work.

The cathode strip drift chambers are well-suited to measuring the position and angle of the o conversions.  This is a well-developed technology that has been used in other contemporary experiments.  TRIUMF has found a local source for the large 5ft x 5ft fiberglass-epoxy panels, which are difficult to find.

The scintillator design uses extruded planks with holes for the wavelength-shifting (WLS) fibers, a technology used by MINOS.  Each scintillator plank is read out at both ends, and a trigger is generated using mean-timer techniques. The design is both clever and compact.

The WBS structure shows good detail and is fairly complete.  It includes three years of funding for a Project Engineer to provide the engineering discipline necessary to guide this system through production and commissioning.  The labor costs defined for the chamber-scintillator production are comparable to the material costs, which seems reasonable.  However, the labor costs for the electronics are significantly less than the material costs, which may indicate a shortage of estimated labor.  In general, a large fraction of the labor comes from physicists (post-docs, students, etc.), which poses a risk if the base program funding does not cover this projected number of physicists.

The estimated base cost for the drift chamber front-end readout is at a reasonable cost.  However, the WBS structure allocates all electronics labor to the anode readout, and none to the cathode.  The labor costs should be parceled out correctly for each item.  The present cost estimate includes no cost for spares.  Clearly these are important, and it should be a general policy to incorporate at least 10% spares for all electronics boards and components. This is particularly true for any components such as Field Programmable Gate Arrays (FPGAs) that are likely to go out of production before the experiment is finished.

Electronics testing is assumed to be done by the vendors as part of the production contracts.  While this is necessary, it is likely that additional testing will be required during the final assembly and commissioning of the Preradiator, which has not been included in the WBS costs.

Although the External Photon Vetoes are included in the WBS funding structure, there is no group that currently has the responsibility for them.  The Russian groups will produce the lead-scintillator shashlyk modules, but the work of integrating and commissioning these modules has not been allocated.

The cathode strip chambers are excellent antennas and thus are very susceptible to noise.  Solids grounds are essential. Grounding, of course, is very much an art and this may require considerable work and testing at Brookhaven during the installation and commissioning which has not been costed in the WBS.

The contingency of 31% seems low in view of the risks (physicist labor, additional testing, External Photon Veto integration and installation, lack of spares, etc.).

# Recommendations

1) Evaluate the need for spares and increase the cost estimates appropriately.

2) Define the responsibility for integration and installation of the External Photon Vetoes.

3) Redo the labor costing for the electronics, allocate the costs to the correct WBS tasks.

4) Do a bottoms-up contingency estimate using a better suited algorithm than the Lockheed formula.

###### Photon Vetoes, Calorimeter, Beam Catcher

Findings

Photon vetoes: The photon veto system of KOPIO consists of five subsystems: Upstream, Barrel, Magnet, and Downstream Vetoes, as well as the External Photon Veto associated with the Preradiator.  This system must achieve photon veto inefficiencies of order 10-4 for KOPIO to succeed.  Therefore the demands on this system, both in construction and monitoring, are extraordinary.  The Upstream Veto hermetically covers the upstream end of the vacuum decay region, while the Barrel Veto surrounds the vacuum decay region. The Magnet Veto lines the inside of the D4 magnet, although the phototubes are outside region of magnetic field. The Downstream Veto lines the inside of the downstream vacuum tank.

All parts of the veto systems are a lead/scintillator technology read out with wavelength- shifting fibers into phototubes. The Barrel Veto and Preradiator External Photon Veto consist of so-called “shashlyk” construction, while all other components of the photon veto are “log” construction.  Shashlyk modules consist of a lead-scintillator sandwich, with the wavelength-shifting fibers perpendicular to the scintillator tiles and passing though holes in the scintillator and lead. The “log” construction is also a lead-scintillator sandwich, but with the wavelength-shifting fibers mounted in grooves along the length of the scintillator slabs.

The total number of readout channels in all five systems is about 2700.  KOPIO’s Russian collaborators have the major responsibly for construction and testing of all of the photon vetoes. This group has extensive experience with this technology and a good track record of delivery for PHENIX, LHC-b and HERA-b.  Their cost estimates are detailed and based on past experience.

The signal will be read out through wavelength-shifting fibers into phototubes. Tubes from the BNL experiment E949 detector will be recycled where possible. The Upstream Veto and Barrel Veto will use E949 phototubes, with 20-30% spare phototubes in each case. New phototubes will be needed from the Magnet Veto and Downstream Veto. The Magnet Veto will require long optical fibers to bring the light outside of the magnet region to the phototubes. The Downstream Veto will also require optical fibers since the phototubes will be outside of the downstream vacuum tank.

The high voltage supplies and front-end electronics will be uniform throughout the photon veto system and will be constructed by the Russian collaborators. Prototypes have been constructed, and an example was shown at the review.

Calorimeter: The calorimeter will be a shashlyk design, also built by the Russian collaborators. The total number of channels in the calorimeter is 1600, read out through avalanche photodiodes (APDs) rather than phototubes. A specific APD and vendor have been identified. The front end electronics for the APDs is similar to the photon veto electronics, but details such as overall gain are modified to fit the requirements of the APDs. Beam tests indicate that the calorimeter will achieve the required energy resolution of ΔE/E = 3%/√E(GeV).   Prototypes of the shashlyk Barrel Veto and Calorimeter modules were shown at the review.

Beam Catcher: The most downstream veto is a novel design to be constructed by the Japanese collaborators. This detector sits in a very intense neutron flux. It must be insensitive to neutrons and efficient at the 99% level for photons of energy 300 MeV and above.  The solution is an aerogel Cherenkov counter with lead converter sheets, read out by 5 inch phototubes. The total number of channels in this sub-detector is 420. The Japanese group has built prototypes and tested them in the KEK beam.  Good agreement between simulations and data has been achieved. Even though the Beam Catcher is sensitive to only 0.3% of the neutrons, it still contributes 4-5% dead-time to the experiment.

Light Emitting Diode (LED) Monitoring system: All channels of the photon veto and the calorimeter will be continuously monitored with an LED flasher system. This system will be constructed by the Russian collaborators, who have adopted a design used in LHC-b and have already chosen a specific blue LED as the light source.  It will continuously monitor the gain of all channels and will detect a component failure within a few beam spills.

##### Comments

Photon vetoes:  The level of photon rejection required by this detector is extraordinary, but seems achievable.  A great deal of effort has already gone into the design of this system, consistent with its importance and difficulty.

Spares:   Except for the calorimeter, no spares of the front end electronics are costed in the baseline.  Subsystems that are using photomultipliers from BNL experiment 949 have adequate spare phototubes.  For the cases when new phototubes must be purchased, no spares are included. In a system such as the photon veto which cannot tolerate even one dead channel, spares must be included as part of the baseline.

Mechanical mounts and integration:  Items that stood out as not-yet-engineered are the mechanical mounts and details of integration of the photon vetoes into the rest of the detector. In most cases there was not even a conceptual design for the mechanical mounts, and the responsibility is not clearly defined.  Design and construction of the mounts requires some care, since gaps and inert material must be avoided.

##### Recommendations

1) Conduct beam tests of the Photon Veto system as soon as possible to verify that the extraordinary demands placed on this system are met.

2) Assign responsibility for the mechanical mounting of the Photon Vetoes and develop a detailed design.

3) Include spares in the baseline costing.

###### Charged Particle Veto

Findings

The Charged Particle Veto (CPV) is a 2 mm thick segmented scintillator envelope inside the vacuum vessel to detect charged particles with >99.99% efficiency and ~100% solid angle.  Neighboring scintillator plates, with areas up to 40x50 cm2, overlap by as much as 2 cm to avoid cracks in the acceptance.  The only hole in the acceptance is at the vacuum vessel’s upstream end.  Each scintillator is viewed by 2—3 direct-mount phototubes for redundancy, to compensate for the servicing inaccessibility.  Each phototube is coupled to a Cockroft-Walton style base.  An external LED-based flasher system is used to monitor the gain stability (to ~20%) and to detect phototube/base failures.

The Zurich group is responsible for the design, fabrication, validation, shipping, installation, and maintenance of the Barrel CPV, located inside the main vacuum vessel.  The design is well-advanced, and has been proven with beam tests at PSI.  BNL is responsible for the Downstream CPV, located inside the downstream rectangular pipe of the vacuum vessel.  This design is conceptual. The CPV will adopt the design of the front-end electronics to be used in the other scintillator-based subsystems.

Comments

A 2—3 mil thick barrier is proposed between the 10-7 torr vacuum in the center of the main vessel and the ~10-3 torr vacuum in its periphery (where the out-gassing Barrel CPV components reside).  Perhaps this barrier will also separate the main vessel’s vacuum from the downstream pipe’s ~10-3 torr vacuum.  This barrier is conceptual, and there is some apparent tension in its design due to the conflicting goals of a good central vacuum (to avoid neutron-induced π0 backgrounds) and a thin inert-material layer in front of the Barrel CPV (already wrapped in opaque VM2000).  No mechanism for maintaining the structural integrity of this barrier—to avoid its collapse into the central volume—has been suggested, but this mechanism will no doubt contribute to the dead layer budget.

No vacuum barrier is needed for the Downstream CPV, since the downstream pipe’s vacuum is ~10-3 torr.  However, the opaque barrier must be ~1 mg/cm2 thick BaF2 so that the effective dead layer is within bounds for the grazing-entry charged particles.

The electronics procurement and installation cost is included in WBS 1.2.4, but it is not clear if Zurich/BNL or an as-yet-unspecified data acquisition group will be responsible for the work.

The base cost of this subsystem is reasonable.  The cost drivers (on-detector readout components and scintillator) were probed to WBS level 7 and were well documented with recent price quotations for materials and estimates for fabrication/assembly costs.  All aspects of the work, including material procurement, design, labor, testing, tooling, integration, shipping and installation, are included in the WBS.  The manpower needs, as addressed in the WBS, are adequate.

Integration with the vacuum vessel (feedthroughs for the signals, low voltage, and LED-flasher fibers; mechanical support of the CPV; heat transfer; high/low-vacuum barrier design) should be addressed as soon as possible, to avoid delays in the procurement of the vacuum vessel and/or later redesign of it to accommodate the needs of the CPV. This has been recommended earlier in the Vacuum section.

A determination of the steady-state lifetime of the actual phototube models to be used in the CPV (after initial burn-in to cull any that suffer infant mortality) is critical and should be performed in a dark vacuum environment as early as possible.  This lifetime is one of the ingredients in determining the “mean time between failures” (MTBF) of a CPV element.  The same configuration can be used to test for other potential failure modes (of the mechanical couplings or bases, for example).

##### Recommendations

- Transfer the responsibility for procurement, installation, commissioning, operation, and maintenance of the readout electronics to the Data Acquisition Group, when it is firmed.

- Determine as soon as possible a “mean time between failures” of CPV subsystems operated in KOPIO-like conditions.

###### Electronics, Trigger and DAQ

##### Findings

KOPIO front-end electronics consists of: 1) Photo-detector (avalanche photodiode – APD or photomultiplier tube – PMT) front-ends, followed by high-speed waveform digitizers; 2) Anode wire time digitizers in the Preradiator, and 3) Cathode wire ADCs in the Preradiator.

To simplify the front-end electronics, KOPIO will use the same basic electronics for all photo-detectors in the experiment. The readout consists of PMT bases and APD preamp/shapers which have been prototyped. Their outputs feed into 250 MHz ADCs, which can be staggered to obtain 500 MHz sampling.  For prototype tests, an 8-channel CAMAC digitizer, produced by Yale, has been used. The Preradiator chamber electronics makes use of ASICs developed for LHC and is described under WBS 1.2.2.

Following the front-end, data are concentrated by collector boards and fed to the Level 1 trigger as well as the data acquisition (DAQ) system.  The dead-timeless Level 1 trigger consists of various FPGA-based logic boards as well as the experiment timing distribution.  A further Level 3 software trigger will consist of a 400-node processor farm.  A separate Level 2 trigger is being left open as an option in case the Level 3 trigger is not sufficiently powerful.

The electronics, DAQ and trigger are conventional designs, with prototypes existing for most of the front-end. Photo-detectors are “owned” by sub-systems, and in the present WBS photo-detector front-end electronics and integration are also “owned” by the sub-system. Photo-detector calibration systems will be designed by the calorimeter group and used by all of the experiment. Slow control is part of DAQ.  A common user interface will be provided as part of the online system, and each sub-system “owns” its slow control data.

The Level 1 trigger will consist of full-custom boards.  The Level 1 trigger will be dead-timeless, and is scaleable via backplane communication.  Whereas much of the front-end has been prototyped, the Level 1 trigger is still in the conceptual design phase, and it is assumed that new groups from Italy will pick up this task.  In addition to the main physics trigger, triggers are foreseen for calibration, cosmic rays, pre-scaled 00 events (or pre-scaled micro-bunches) but other triggers are still in the conceptual phase.

The Preradiator chamber electronics (see section 1.2.2) has been engineered by TRIUMF, which will also oversee production.

##### Comments

The use of a common readout platform for all photo-detectors represents an efficient and economical choice.

The electronics effort is understaffed. Only a small amount of engineering, other than for the Preradiator, has been done. Electronics engineering manpower must be identified to: port the 8-channel digitizers into a 36-channel 9U VME card, including back-end FPGAs for data concentration and communication to the DAQ and trigger; design the data collectors; design the Level 1 trigger boards; and implement electronics tests, integration and QA/QC.

An experiment integration manager is part of the project. However, the interface between the integration manager and the electronics activity – particularly in matters of grounding – is not well defined.  Electronics and data acquisition is presently informally coordinated by Stony Brook.

The schedule is tight in two areas:

- The Level 1 trigger has roughly 6 months of float (which is quite short for this stage of the project)

- A 10x10 calorimeter prototype, with final electronics, is planned to be ready in roughly 18 months.  This sets a deadline for, at a minimum, the waveform digitizers.

The “Lockheed formula” for contingency dramatically underestimates the appropriate contingency on the electronics. Given sufficient manpower, a contingency on the order of 50% is not unreasonable. However, if schedule crunches require employing significant amounts of professional engineering, costs may be considerably higher. Further, manpower estimates are not unreasonable, but are more appropriate for an “iteration” rather than production of the final electronics.

##### Recommendations

1) Consider forming an electronics group for all electronics exclusive of the chamber electronics. Appoint a WBS Level 3 electronics manager who coordinates all of the photo-detector readout, trigger and DAQ.

2) Add manpower to the electronics, and use that as a metric of progress.

###### Offline software

Findings

The Offline subsystem is responsible for all data that flows out of the L3 trigger.  The hardware consists of off-the-shelf components:  a tape silo (with 4 tape drives and 600 1-tera bytes (TB) tapes) to accommodate all of the raw data acquired in a 25-week run; a 100-TB disk farm to store the skimmed data from this run; an 84 dual-CPU processor farm to analyze a subset of the data in real time at ~1000 events/second; 15 workstations for users; network switches; and racks.  The software consists of the codes and specifications for simulation, event reconstruction, calibration-constants generation and validation, quality assurance monitoring, analysis, skimming, and data management.

Non-real-time event reconstruction, calibration constants generation, reprocessing, analysis, and skimming will be accomplished using the offline farm, the L3 farm, and off-site computing power at the collaborators’ institutions (utilizing Internet-2 and other high-speed networking interconnects that are being implemented now for LHC and similar needs).

The hardware requirements and costs have been determined by a conservative “Moore’s Law” like extrapolation of the performance and storage capability of equipment available today to FY2009, when the equipment will be purchased.  The number of CPUs needed in the offline farm is determined by the processing time per event (based on GLAST and E949 experience) and the 1 kHz processing target.  The base hardware cost is reasonable, and is well-documented with recent price quotations for comparable equipment. This includes a 0.5 FTE system manager, to be shared with the L3 trigger group. The WBS for the hardware is complete.

The base software cost is dominated by the salary of one software professional, who will be responsible for the design of the data format, the data management system, the analysis framework, the detector description language, and all documentation.  He/she will be assisted by a no-cost 0.2 FTE/year physicist.

The manpower requirements for code development in FY2005—2010 are estimated at 9—12 FTE/year of no-cost physicists, rising in the out years.  The present staffing level is 9 FTE.

Comments

The software cost is underestimated, unless another FTE, i.e., no-cost physicist(s), can be named to work with the salaried programmer.  The WBS for the software has a complete list of items, but the timelines for the work to be performed are still undefined: they will be solidified at a workshop to be held in Fall 2005.

The timelines for the software work need to be determined sooner so that code development is not delayed:  the proposed software workshop should be held in Summer 2005.  The task managers for each code development effort should be identified as soon as possible thereafter.

The anticipated workload for the software professional appears to be spread out uniformly over FY2005—2007.  However, the bulk of the design work should be completed in FY2005, so 2 additional FTE’s (no-cost physicists) may need to be allocated in FY2005 to assist this professional.  Only the software professional and a 0.2—0.5 FTE no-cost physicist is required in the out years for maintenance and refinement of the code/data design and continuing documentation work.

The anticipated workload for the code-development no-cost physicists appears to be spread out uniformly over FY2005-2010.  However, the bulk of the code development (for simulation, event reconstruction, calibration constants generation, and analysis) should be completed in FY2005 so that realistic detector simulations that might affect KOPIO final design can be carried out in FY2006.  Therefore, at least 18 no-cost physicist FTE’s (preferably each >0.5 FTE) will likely be necessary in FY2005-2006, before tailing off to the steady state of 12 FTE’s in FY2009 stated in the Offline group’s plan. Hence, the Offline effort appears substantially understaffed.

Recommendations

1) Establish the timelines and task managers for the software development by the end of summer 2005.

2) Expand the software development manpower by allocating 10 more FTE physicists in the early stages of the project.

The MECO Detector System (WBS 1.3)

Overview

The charge to the MECO subcommittee regarding the MECO WBS element was to evaluate the “science requirements, technical requirements (flow-down from science requirements), system design, design and development tasks, critical design issues, performance simulations, DAQ and data systems, magnet specifications, background issues, completeness of design, readiness to proceed, and proper identification and management of risks.”   To gather the information and make our evaluation, we met with the experimental team (headed by Bill Molzon, the spokesperson) for most of the days of April 20-22, 2005.  We would like to acknowledge the complete cooperation of all the proponents of MECO and the thoroughness and high quality of their response to our inquiries; they made our work efficient.

The scientific goal of the MECO experiment is to search for the rare process, muon-electron conversion, in the field of an aluminum nucleus with a single event branching ratio sensitivity of 2 x 10-17.  The search is to be carried out using the Alternating Gradient Synchrotron (AGS) at Brookhaven National Laboratory.  To achieve this sensitivity the experimenters plan to collect data for 2 x 107 live-seconds over a calendar period of 5 years This assumes 24 week/yr AGS operation, equal sharing of beamtime between MECO and KOPIO during those 5 years, and AGS intensity of 20 Tp/s.  The backgrounds from all sources are expected to 0.25 events in a 2 window around the characteristic energy of 105 MeV.

The four crucial characteristics for success of the experiment are the muon flux, the interpulse extinction of 10-9, the electron-momentum resolution, and the cosmic-ray veto efficiency.  The muon flux and interpulse extinction depends on developments within the AGS complex and the operation of the extremely clever magnet system.  Other parts of the RSVP review panel are examining these systems.

A very simplified view of the MECO detector is that electrons from the conversion are contained in a magnetic field where their momentum is measured by a straw tube tracker and candidate events trigger the data acquisition if sufficient energy is observed in a lead-tungstate calorimeter.  The center of the detector is non-interacting to control the rates from other modes. Backgrounds from cosmic rays are eliminated by active veto detectors. For the detector to be successful in limiting backgrounds to the 0.25-event level, the resolution from the straw tracker, , needs to be 0.29 MeV.  This non-Gaussian response function is also characterized by an equivalent FWHM resolution of 0.90 MeV.  The overall tracking efficiency of is expected to be 80%.  The inefficiency of the cosmic-ray veto system must be less than or equal to 0.01%.  The trigger calorimeter resolution, (cal), must be better than 8% for the trigger acceptance to be slowly varying above 80 MeV with a value of 80%.

The overall impression of the MECO detector system is positive.  The subcommittee finds the detector to be well designed to meet the scientific and technical requirements.  An experiment that proposes a 104 increase in sensitivity beyond previous measurements cannot be without risk, but the proponents have identified and planned for the challenges.  The momentum resolution has passed extensive Monte-Carlo studies and provides only a moderate risk from degraded resolution in the actual data.  The cosmic-ray shield should work.  The calorimeter requirements should easily be exceeded, and the collaboration goal of better than 6% seems achievable.

In our judgment, the experiment appears ready to proceed on technical grounds.

In general, the detectors are not particularly high-risk technologies.  All of them have to work well for the experiment to succeed, particularly the tracking detectors, which make the primary physics measurement, and must have well-understood momentum resolution. The calorimeter forms the trigger. If the resolution is not as now conceived, the consequence is a higher trigger rate but not necessarily a loss in physics performance.  The cosmic ray veto is also relatively straightforward technology and should be able to eliminate backgrounds that originate outside the experiment with the required rejection.  We have a general worry about the cost for hidden labor.  Student and physicist labor is accounted for but included at zero dollar cost. And there is a lot of it involved in the detector construction. This must be supported by university grants sufficiently to perform the project. The costs for different subsystems, as provided to us, are listed in the Table below. These do not include any contingency.

|  | System Name | Material Costs | Labor Costs | Base Cost |
| --- | --- | --- | --- | --- |
| 1.3 | MECO | $13,052K | $8,722K | $21,774 K |
| 1.3.1 | Extinction | $1,062K | $624K | $1,686K |
| 1.3.2 | Production Target and Shield | $2,490K | $219K | $2,709K |
| 1.3.3 | Muon Beamline | $1,209K | $1,265K | $2,473K |
| 1.3.4 | Straw Tracker | $2,280K | $998K | $3,277K |
| 1.3.5 | Electron Calorimeter | $3,466K | $1,177K | $4,643K |
| 1.3.6 | Cosmic Ray Shield | $1,003K | $306K | $1,309K |
| 1.3.7 | Trigger and DAQ | $884K | $584K | $1,468K |
| 1.3.8 | Simulations and Offline Analysis | $148K | $113K | $261K |
| 1.3.9 | Integration and Installation | $125K | $1,266K | $1,391K |
| 1.3.10 | Project Office | $386K | $2,169K | $2,555K |

Straw Tube Tracker

The straw tracking system measures the trajectory of electrons generated from the decay of muons in the stopping target. It thus provides a crucial means of rejecting electrons from the decay of muonic atoms and accepting electrons from the signal reaction N ( eN.  Since a significant part of the resolution comes from multiple scattering in the target, there is some safety factor in the detector performance. Regardless, great care is required to see that this detector nearly achieves its design resolution, especially in the face of foreseeable pattern resolution difficulties.

The straw tracking system faces a major decision in August 2006 to choose between the L (straws nearly parallel with the magnet axis) and the T (straws perpendicular with the magnet axis) tracking detector design. Some simulation work and prototype development are now going forward at a low level on university budgets. The prototypes have had some nice preliminary results.  The MECO team is waiting for the beginning of fiscal year 2006 when, if approved, funding will begin for the design and construction of demonstration prototypes of both the L and T type tracker.

The subcommittee was comfortable with this schedule given that the tracker design decision does not negatively impact the overall schedule by waiting a year.

The design of the central tracking system is driven mainly by the requirements of the physics; namely accurate track measurement, large background rejection and good pattern recognition. The current design gives a calculated width of the signal electron energy peak of 0.9 MeV FWMH. The resulting size and complexity of the detector is comparable to the barrel straw tracking system at ATLAS at CERN.

In general, the technical design does not push the limits of technology.  The use of straws with 15 micron walls in a vacuum, however, is close to the edge.   If the thinner walls induce a problem, the straws with 25 micron walls remain back-up.

The use of gas containing CF4 requires special precautions regarding chamber current and gas water content. With the relatively low chamber current in MECO, compared to ATLAS for example, there should be a comfortable operating range in MECO as long as all the wires are gold plated. If stainless steel or nichrome wires are used to exploit the charge division option, the aging of the wires will have to be studied.

Nevertheless, it might be advantageous to instrument the unconnected wire ends in the T- Tracker so that charge division measurements can be made.

Charge division should be studied with simulations in the next few months to discover whether a significant increase in performance of the tracker is probable.

The simulations should uncover whether the pattern recognition is substantially improved under adverse rate or background conditions.  The cost of additional channels is relatively small because the high fixed costs of ASIC production have already been paid.

The schedule appears to be well thought out and matched to the resources available.  In particular there do not appear to be any bottlenecks where too many tasks are scheduled at the same time.

The total cost of the straw tracker as presently estimated is $3,277K without contingency. This number appears to be properly evaluated. The contingency, taken as 45% additional, is $1,475K. The main cost drivers are in the electronics: the design and fabrication of the preamplifiers take up $656K, and the same for the digitizers take up $906K exclusive of contingency. It is difficult to estimate the contingency on this type of product, but 45% is at least close (see below). Among the mechanical items, the straws themselves are the biggest cost driver at $247K. The company that makes them, Lamina, is a unique supplier whose product has been qualified by many experiments. In the past they have been reasonable about their charges and the 45% contingency should be adequate.

As always with tasks distributed among several groups of collaborators, it is important to have a coordinator in the areas of mechanical items, electronic items and cost and schedule.

In general the straw tube tracking system shows good preliminary design and careful attention to detail.

Calorimeter

The review of this part of the project is positive. The total cost is $4.64M plus 24.3% contingency. The cost estimate is well done and well documented.  The cost drivers are PbWO4, for which there are two foreign vendors and for which the costs appear appropriate at this time. The second cost driver is the avalanche photo-diodes (APDs) built by RMD. In this case there is either insufficient data about the yield to know precisely how many to order, or an increased cost per unit than is presently used as a result of sending tighter specifications to the company. Coupled with only 5% spares ordered, there seems to be risk in the cost larger than the 31% contingency assigned to this part.

We suggest both an early order of 10% of the APDs, so that an evaluation can be made to better determine the yield of the final product, and that the spares-count is increased to at least 10%.

The calorimeter support is to be carbon fiber. However, there is no engineering, so the 20% contingency seems low by at least a factor of two on this $220,000 item. The calorimeter electronics is priced at a 20% contingency level, and is based on vendor estimates for stuffed boards.

The overall schedule is believable and has sufficient slack that the calorimeter should be completed well in advance of the project, provided the delivery of the crystals is not 1.5 times as long as expected. The subcommittee was impressed by the emphasis on technicians and engineers for quality control and testing in the subproject.

Cosmic-Ray Veto

The cosmic ray veto is essential for the success of the experiment and is straightforward technology.    The cosmic ray veto scintillators surround the detector and have to reduce external backgrounds by a factor of 10,000. The use of overlapping scintillator modules with three layers is an appropriate solution to the problem.

However, the project planning is not up to the standards of the other detector elements and should be brought to the same level as other tasks.

The total cost is listed $1.3M plus 14.8% contingency. The principal costs of the extruded scintillating bars and wavelength shifting fiber, module assembly, multi-anode phototubes, and preamplifier electronics looks accurate, but there are worries about some details and about missing items in the cost estimate.  For instance, a missing piece of the cost estimate is several months of travel to support a technician or engineer in the vicinity of Itasca Plastics in Illinois. The material for the bars includes a factor of 25% for extrusion waste and for spares, but there is only 10% spare fiber and that may not be enough. The wavelength-shifting fiber is to be purchased cut and polished. It is then to be aluminized on one end, but the cost of the aluminizing process is not within the cost estimate.  Drawing on advice or experience from Fermilab or from an experienced collaborator would be useful for handling the fibers. Fixtures needed during assembly are not included in the cost. As assemblies come together, spare modules are nonexistent.

The detector construction schedule stretches until October 2010, making this among the last detectors to be finished and is determined by the university constraints, such as space available for the assembly work and other resources. It is worrisome that the schedule for assembly does not include identification and cost of space available at the university, as that is an issue in this case.  It is noted that there is no post-assembly detector testing and characterization indicated in the WBS.  It is expected that the plan will undergo significant evolution as further development of the detail occurs. A 50% contingency level would be more appropriate at this time.

Electronics

The Committee has an overall positive view of the MECO electronics and data acquisition system.  The electronics systems considered were the straw tracker electronics, the calorimeter electronics, the cosmic ray shield electronics  and the trigger and DAQ .  The estimated costs, and costs with contingency are listed in the Table below.

The overall contingency on the electronics is 26%, which traditionally is rather low for electronics and DAQ.  Previous experiments had contingencies as high as 50% to 70%.  The scope of the electronics, the number of channels, the data rates, and the processing requirements are all well within the bounds of what has been already achieved in other experiments.  Much of the cost estimate is based on existing designs of running systems, and appears to the committee to be a conservative estimate.  Given this consideration, the committee’s view is that the cost estimate and contingency is at the right level.

| System | Cost | Cost with Contingency |
| --- | --- | --- |
| Straw Tracker | $1,652K | $2,134K |
| Electron Calorimeter | $1,145K | $1,374K |
| Cosmic Ray Shield | $254K | $283K |
| Trigger and DAQ | $1,468K | $1,897K |
| Total | $4,519K | $5,688K |

The committee believes that the collaboration overall has the technical skills to accomplish the goals of the project, however, there remains a need for a project electronics engineer.  The coordination between the straw tracker electronics project, the calorimeter electronics project and the DAQ and trigger needs to be improved.

An overall optimization of the electronics systems, paying particular attention to the interfaces between the systems and commonality of solutions should take place.

The committee believes that while an optimization may result in a slightly different system design, the overall costs will remain the same.

There are several minor omissions the committee found during discussions: 1) The signals from the target monitor, extinction monitor and magnetic field monitor are not accounted for in the event record; 2) The cooling for the crates in the racks is also not included in the cost estimate, even though the title of section 1.3.7.3 is “Enclosures, Power, Cooling, and Interconnects”; 3) The description of the electronics for the cosmic ray shield appears to be a place holder for an actual design.

Extinction magnet

The extinction factor of 10-9 is crucial to the success of the experiment.  The RF modulated magnet is important to guarantee achievement of the goal.  The subcommittee did not feel technically qualified to judge the extinction magnet and refers it to the AGS subcommittee.

Other tasks

A number of the tasks associated with the target, vacuum systems, and software were examined.  All cost and labor estimates matched well with the experience of the subcommittee.

Management

The subproject will undergo a change of its project leader.  Some question arose regarding the ease with which UC Irvine will be able to disperse money throughout the MECO collaboration.  Considering this type of managerial issue, where should the new subproject leader reside, Irvine or BNL?  This decision will soon face the project office.

The collaboration presented its estimate of how much it must grow to have adequate manpower for carrying out the experiment.  The academic staff (in FTEs) needs to grow by more than 100%, currently estimated to be 3 faculty, 14 postdocs and 13 graduate students.

We estimate the cost of this growth to be $2.5M/yr to the funding agencies and they should plan for the growth.

While the schedule is achievable, there is inadequate float called out in the project document.  An example of where it could be helpful to plan for float would be to know who to give the highest priority for early funding in a constrained budget profile.

Float should be explicitly added to the detector part of the project planning.

The WBS contains some tasks that look like they belong to the accelerator project.  Examples include the extinction magnet and the proton target, where the AGS staff will apply their expertise to their proper operation.  As they are part of the primary proton beam line, the accelerator staff will ultimately be responsible for their performance.  However, the experimenters have invested heavily in their success because of their importance to the experiment.  The AGS subcommittee of this review finds that the experimenters can carry out these WBS elements so long as they involve the AGS staff at a detailed level in their development.

As noted by other subcommittees, the Lockheed contingency methodology seems to fail in the MECO detector application.  The resulting contingency is just too small for a project with the identified uncertainties.

MECO Magnet System

# Introduction

The magnet system is a key element of the MECO experiment, and at a fractional base cost of 28%, is the single most expensive and technically demanding element of RSVP. A high energy proton beam from the AGS is directed into the bore of the Production Solenoid (PS), producing pions.  A fraction of the resulting muons are captured in the PS and in the Transport Solenoid (TS). Finally, the muons are brought to rest in the Detector Solenoid (DS).

# Findings

Brad Smith, manager for the MECO magnet system, described the design as being between conceptual design and preliminary design.  Based on the information presented, the Sub-Panel concurs.  The Sub-Panel wishes to thank Brad Smith, Joe Tuzullo, George Ganetis, and the other presenters for their excellent presentations and discussions which were so essential to this review

MECO Magnet System Design Details

The Sub-Panel received presentations on the magnet designs, cryogenic system and power supplies along with in-depth discussions on them.  Based on this, the Sub-Panel found the designs to be well conceived, with no significant outstanding issues.  However, a number of design recommendations are  made (see the Recommendations section) which are primarily offered for consideration to reduce costs and possibly reduce risks.   Notes from these presentations are presented below as background information for the sections which follow:

  - Final design activities are just getting underway in some areas.

  - Magnet system has benefited from multiple successful reviews:

    - Interim design review in September, 01.

    - FDR in February, 02.

    - Magnet Acquisition Panel review in September 02.

    - RSVP review  in October 04.

  - The primary design driver is the field specification.

    - Field quality is achieved through coil geometry, current selection and placement, tolerance analysis (corroborated by vendor quotes on dimensioned and toleranced mandrel drawings), and fabrication control.  An installation alignment procedure has been developed to compensate for cool-down deformations; magnet mounts permit an additional 1-2 cm of adjustment.

      - Some studies of the effect of steel properties remain to be performed, but are not expected to present difficulties or introduce changes to the magnet design philosophy.

      - Field mapping using Hall probes on cross structures is conceptually planned to confirm installation.

  - Brad Smith notes that the field meets all specifications, including:

    - Temperature. margin >1.5K

    - J/Jc(B,T)<0.4

    - Structural design meets the FIRE (Fusion Ignition Research Experiment) structural design criteria.

      - Meets structural criteria throughout transient.

      - Includes any combination of magnets energized or not, cryogenic bores at vacuum or atmosphere, and combined thermal, EM, and gravity loads.

  - Superconductor for DS, PS, and TS magnets consist of  NbTi soldered into a Cu channel. The TS coils near the APS window do not use the copper channel.

    - Cabled SSC superconductor; now in warehouse near MIT will be used.

    - Conductor is similar to G0 superconductor which is now in operation.

    - Conductors from each end of each spool will be tested at BNL for Jc(B,T).

    - Quench analysis using MIT 3-D

      - Adiabatic calculation.

      - Dump initiated when coil resistive voltage >100 mV for >1s.

    - Vmax<2kV;  Tmax<150

  - Insulation:

    - Turn to turn: ½ lap 0.001”  Kapton + ½ lap of 0.004  fiberglass.

      - R&D planned to evaluate if interleaving glass with Kapton is advantageous.

    - Ground insulation:  40mil of Kapton/ glass.  Mix is not specified

      - Ground voltage is 1 kV using balanced, floating power supplies with single point ground.

      - Ground planes are planned over ground wrap of PS coils.

    - TS and DS are encased in Cu sheets which perform same function as the ground wrap in detecting degradation in ground insulation.

    - Cold leads will have center plane grounded .

    - Lifetime neutron fluence is 3.3 X 1020 neutrons.  Total estimated dose is 36 Mrads.

      - It was stated during presentation that mechanical or dielectric strength will not be degraded at these levels.  Data in the literature supports this conclusion.

      - Radiation induced gas evolution in the insulation needs to be adequately addressed in operational plans.  The magnet group contracted an insulation study with CMI; in their report, they recommended that the coils be pumped to remove gas and warmed to room temperature at 1/3-life intervals.

    - Electrical tests:  hipot, megger, and turn to turn voltage tests planned before and after VPI.  Levels were not stated.

      - The plan is to perform electrical tests before and after ”cold cycle” 80K –RT and repeat the tests.

  - Magnet fabrication

    - Build to specification approach is planned.

    - Fixed price contract(s) after successful Final Design Reviews (FDRs).

    - The current plan is to supply tooling and conductor in order to meet schedule.

    - Schedule:

      - Complete final design by 3/16/07.

      - Complete tooling by 4/28/08.

      - Issue RFPs 10/23/06; 1/3/07; 3/16/07.

      - Award contracts, 8/30/07; 11/6/07; 1/23/08.

      - Solenoid fabrication complete 6/9/10.

    - The magnets will be purchased through MIT’s procurement office under MIT rules and requirements which will flow down from NSF.

    - Requests for Information are planned to be issued later this year to get feedback on strategy / plans from industry.

Cost Estimates and Estimating Methodology

In general, the Sub-Panel found that the estimating approaches for all three elements of the magnet system (magnets, cryogenic system, and power supplies) were sound.

- Magnet cost estimates and schedules:

  - Established with MIT-developed process based spreadsheet estimates supplemented by vendor quotes and a 2001 General Atomics study.

  - Costs include required G&A for procurements; estimates in current $, industrial labor rates, a G&A rate of 16.2% with a 13.7% fee added (based on data from the ITER survey).

  - Contingency, based on the Lockheed formula, resulted in 14% for simple items like shipping to 39% for fabrication of complex items such as vacuum enclosures or items which are at an early stage of development such as the magnetic field mapping. The Sub-Panel considers these levels to be appropriate.

  - The Sub-Panel's major concern is the use of a fee of 10 to 13%, which may be low for fixed price contracts in which this  factor would cover both the vendor’s profit and contingency for unexpected costs.

  - The currently proposed schedule shown below was judged to be realistic but challenging. Funding and project decisions must be made on a timely basis for this schedule to be achieved:

    - Complete final design by 3/16/07.

    - Complete tooling by 4/28/08.

    - Issue Requests for Proposals (RFPs): 10/23/06; 1/3/07; 3/16/07.

    - Award contracts, 8/30/07; 11/6/07; 1/23/08.

    - Solenoid fabrication complete 6/9/10.

It may be necessary to re-assess this schedule if it is decided to have the magnet fabricator(s) provide the tooling.

- There were several aspects of the current plans for design, development, and fabrication plans for the magnet that cause concerns. The current plan to design, fabricate, and supply tooling to the coil manufacturer(s) has serious downside risks.   Not only may this approach be incompatible with the customary fabrication procedures of the manufacturer selected, but it introduces major concerns over who is responsible for the tooling performance, for manufacturing problems introduced by tooling, schedule delays, responsibility for safety, etc.

  - Magnet system costs increased from $35M to $58M recently for the following reasons:

    - Magnet iron  added $2.8M  (1500 tonnes of plates bolted together)

    - Cryogenics system was included in this WBS  $4.5+2.6= $7.1M

    - Coil Tooling costs were added - ( PS tooling=$1.9M;  TS tooling = $1.65M+1.62 M; DS tooling =$1.53M  Coil tooling design =$0.9M )    Coil Tooling Total = $7.5 M

The remaining costs are  primarily due to the addition of 2 PS coils, a thickness increase in the transport vacuum. liner, the addition of a base frame under TS, and the addition of  superconductor testing at BNL.

2.  Cryogenic System Cost Estimate:

  - The estimate is based on the MIT design. the BNL estimate was very close to a recently obtained industrial estimate which is reflected in the project estimate for the cryogenic system.

  - The BNL department C-AD expects that design changes can be made which will save ~$500K;  even more if conduction cooling of the PS magnet is adopted.

  - The cryogenic system is state of the art, but does not break any new ground.  Highly experienced RHIC engineers and technicians will be responsible for the system.

  - 1000 W is a standard refrigerator size.

  - There are only 2 qualified suppliers, and both are European.

  - C-AD will install, assemble, test, commission, operate, and perform periodic inspections. All of this is well within their capability.

3.  Electrical System Cost Estimate:

Total cost is $1903K plus 26 % contingency (Installation cost is covered by other systems). Spares are not costed, but there are RHIC spares for all except for the high current power supplies; these should be costed and added.

  - Very experienced RHIC engineers and technicians will be in charge of the MECO electrical system.

  - 6 power supplies will be used; they are 12 pulse SCR converters, similar to RHIC insertion region design for which specifications exist.

  - Having a common design between RHIC and MECO is  a maintenance and  operational advantage.  BNL has spares for RHIC which can be shared.  Existing controls software and hardware can be used. The control system and quench protection system is similar RHIC’s with slow and  fast power extraction systems. Mature diagnostics software will make commissioning faster.

  - Recent quotes on RHIC components were used in developing the MECO cost estimate. The energy extraction resistor cost estimate received is high: it is planed to explore ways to reduce the cost.

  - RHIC quench detector design of which 24 are currently in use and which are fail safe will be used.   The RHIC quench protection system with modifications will be adopted.

  - The lack of environmental controls in the RHIC service building caused trips on RHIC, especially in spring.  This is not expected to be an issue  for MECO because of operational experience and a better quality and different location for the apparatus.

  - Voltage taps across each of the 96 coils and at each joint between the coils for redundancy are planned.

Project Approach

- The Sub-Panel concurred with the current plan for a copper R&D coil, the additional superconductor tests which were recently added, and the planned additional insulation R&D.    However, it is also strongly recommended that consideration be given to fabricating a “first article” coil to confirm manufacturing and QA plans and magnet design and performance.

- The Sub-Panel applauds the features of the plan to promote buy-in and ownership by BNL.  Using the cryogenic capability to supply the refrigerator system, using the power supply group to supply that feature and the quench protection is a very good start of this effort. It is recommended that the vacuum system, magnetic field measurement and cryostat assembly around the cold mass be regarded as other candidates for buy-in.

- The Sub-Panel commends the plan to adopt as much of the RHIC power supply and control system designs and control software as possible.  This will be advantageous for operation, spares and maintenance.

- No technical risk assessment has been performed to date; this must be performed as soon as possible.

- The Sub-Panel concurs with the general manpower and management plans.  MIT, BNL-C-AD, and BNL-SMG all have extremely well qualified and experienced managers and key personnel assigned to the magnet project.  MIT will require a peak of 15 people; currently ~7.5 are available.   This shortfall is planned to  be covered by new hires.

# Recommendations

- The current plan to supply tooling for coil manufacturers should be re-considered or at least confirmed through discussions with potential coil manufacturers since it may not be compatible with the manufacturer selected, and introduces concerns over who is responsible tooling performance, manufacturing problems introduced by tooling, schedule delays due to tooling, responsibility for safety, etc.  It is suggested that:

  - An option where emphasis is placed on finishing FDR’s as quickly as possible and the tooling is part of the coil subcontracts be considered.

  - “Bag molding” as an alternative to hard VPI molding be considered.  It could possibly save cost and schedule.

- Confirm that the large sizes and weights of the units as presently planned can be shipped to BNL from suppliers and handled at BNL.

- Review if the 13.7% fee (currently used in cost estimates) to determine if it is sufficient to cover vendor’s contingencies and profit which manufacturers will include into fixed price proposals.

- A high level of quality assurance (QA) will be necessary for the success of the project since a magnet repair with welded cryostat design will be very difficult.

  - It is recommended that the Specifications and Statements of Work (SOWs) be very  carefully written and internally peer reviewed to ensure that adequate QA is included, all essential functional and technical requirements are defined and, where methods are critical, that they are extensively described (for example:  LN cold cycling tests).

  - If full time on site QA is planned, it should be defined in the SOW so it is negotiated up front.

  - A cryostat design which anticipates the need for access for maintenance or repairs should be considered.

- Introduce an offset in the cryogenic and utility feeds of the magnets to improve maintainability.

- Consider further the concept of short cold bus runs between the cryostat and the vapor cooled copper leads, all of which would be inside the shield wall. Conduction cooled buses appear to be a lower cost option than the RHIC cold-cross connect concept. Costs for planned RHIC type cold cross connects are high (now costed at 1083K$ - for equipment, WBS 1.5.2.17.3, and  890K$ - for installation, WBS 1.5.3.15)

- The Sub-Panel was pleased to learn that consideration is being given to a PS and TS magnet cryostat design approach to improve the possibility of making repairs and easing shipping concerns. Under discussion is the proposal for BNL to be responsible for the assembly of the cryostats around delivered cold masses.  If this approach is adopted, it should be critically examined and peer reviewed.

- Current plan to cold cycle test the coils should be reviewed.

  - It is essential to assure that magnets are not damaged during this test by excessively severe thermal transients or condensed moisture.

  - As an alternative, shipping one or more of the first coils of each type to BNL for superconducting operational tests should be considered.   The Sub-Panel strongly concurs with the current plan to have the manufacturers supply completed cold masses; the cold test program  would need to be accommodated by either returning an individual coil to the manufacturer after tests or installing the tested coil at BNL.

- It is recommended that consideration be given to making the manufacturer’s first article coil a prototype.  Since a total of 96 coils are required, this addition would be a relatively minor cost increase.  A TS coil is suggested because of the high number of coils and their smaller radius.  This first article would  confirm manufacturing and QA plans and magnet design and performance.

- A reduction of the number of coils in the PS and DS should be considered.  This may simplify the design and could reduce costs, but will require a new and detailed magnetic field analysis.

- Where possible, an increase in the electrical insulation thickness to make it more tolerant of manufacturing irregularities should be considered, and:

  - Develop insulation design / test criteria and peer review them thoroughly.

  - Confirm the dielectric strength with tests of actual materials planned for use.

- It is recommended that electromagnetic load analysis, field analysis, and structural analyses of closely interfaced items such as the production target, radiation shield, anti proton absorber windows be performed by the magnet group.

- A separate vacuum system for the target area, independent of the cryostat should be seriously considered.  This will simplify magnet design and alignment.  It is recognized that this is not an easy task, and will require some thought.

- No safety issues were identified; however, it is recognized that this project will require a number of safety reviews. Therefore it is strongly recommended that ES&H reviews be explicitly included in schedules and manpower plans.

- Although many power supply spares can be shared with RHIC, spares should be added for the unique components.  The BNL engineer roughly estimates the cost of spares to be $50 -60K.

- Costs given for field measuring (31 days +$70K for equipment) appear low and should be reviewed.

- It is recommended that the magnetic field specifications be finalized as quickly as possible.   This is necessary for the magnet work to proceed efficiently.

- Although the Sub-Panel was made aware of an earlier recommendation by the Magnet Oversight Group to consider conduction cooling for the PS magnet, the Sub-Panel has serious reservations as to the advisability of pursuing this design change in view of the uncertainties inherent in the calculations of the magnitude of the nuclear heating and its effect on the temperature margin of the superconductor.  The Sub-Panel recommends that pool boiling  helium remain the preferred cooling method for the PS magnet.

- Materials in heavily irradiated areas should be carefully chosen to minimize activation.  This will be beneficial both to maintenance and to the ultimate disposal and decontamination and decommissioning cost.

AGS/Booster Upgrades (WBS 1.4)

Summary

This part of the project consists of upgrades to the AGS, AGS Booster and beam lines to meet the physics demands of MECO and KOPIO in a way consistent with uninterrupted RHIC operation.  This involves the replacement of some radiation damaged components, replacement of certain devices and the addition of others to meet the special experimental requirements of RSVP.  Beam lines must also be rebuilt to meet the special requirements.

We concluded that this part of the project is well planned and the costs conservatively estimated.  We find the schedule for final engineering, procurement, installation and commissioning to be quite aggressive, leading to concomitant schedule risk.  The need for continuous high intensity running while maintaining beam quality needed for success presents challenges of a unique nature.  Beam halo and extinction quality will be intensity dependent and achieving the needed values could limit the intensity, thereby extending the operating time required to meet the physics goals.  As it will not be practical to assess these matters experimentally until very late in the project, it will be important to use all of the simulation tools now available to gain confidence that the designs will meet the requirements or to show in a timely fashion that modifications are required.

# Technical  Approach and Feasibility of meeting MECO and KOPIO Requirements

A table of the technical specifications that the accelerator complex is required to provide to the experiments was made available to the committee, and is included in the conceptual design report. The challenging components of the requirements are the overall charge, the peak current, timing considerations, and a specification on the absence of particles between micropulses, a parameter that the project refers to as “extinction”. Many of these requirements have already been met by the AGS in previous operation. The committee is most concerned about the extinction requirement. For the MECO experiment the requirement is 10-9. This has not been provided in operation, although a low intensity experiment yielded 10-7. Simulations and, where possible, experiments need to be done to continue to provide confidence that this parameter can be met. There are multiple systems in the baseline to deal with extinction. First is an AC magnet, kicker system in the AGS itself. Second is a gap cleaning system in the switchyard using a high frequency resonant dipole. This could not be tested until late in the construction process. The committee feels that there should not be any showstoppers in this technique, but that thorough simulations need to continue to:

- better define engineering specifications (e.g., tolerances)

- indicate where the kicked out particles end up (what gets activated)

- provide confidence that the extinction criteria can be met

Management Issue : The resonant dipole is one of several systems which presently resides in a WBS other than 1.4, although it will ultimately be the responsibility of BNL to maintain and operate. There is debate within the project as well as within the review committee whether this responsibility should be transferred to BNL. The committee encourages the project to ensure that the responsibilities for these systems are clearly defined and that the other party is fully involved in a complete and formal review process.

# Technical Approach and Feasibility of the Required AGS Upgrades

The project has noted that there are four drivers for AGS upgrades:

Ensure that RSVP Operations do not interfere with RHIC

Ensure that RSVP operations comply with BNL environmental protection guidelines

Ensure clean operation at high intensity

Provide unique RSVP operational requirements

The first three of these are fairly straight forward upgrades involving replacement of standard components. The committee believes they are feasible, and not challenging. The final driver, providing for the unique RSVP requirements will be more challenging, but are feasible and well thought out. Many of the techniques have been demonstrated. We continue to express concern that they must provide the science requirements at the very high intensities needed, and with a number of new components installed in the AGS that could excite instabilities. This needs the attention of extensive simulations, and experiments where possible.

Application of extensive simulations and experiments, where possible, are needed

# Overall Readiness of RSVP WBS 1.4 to Proceed to Construction

The committee was told by the project that they believe they are ready to proceed with construction of all components. The committee concurs with this conclusion on all the components in the first three categories noted in above charge element. We are less certain on the new items needed for RSVP scientific requirements. However, we don’t believe there are fundamental issues that would require significant engineering, so that the project could proceed with long lead or critical path items.

# Likely Duration of Construction, Commissioning and Operation

The committee believes that the construction schedule can be met but that commissioning and the full achievement of required beam parameters will take longer than anticipated. As noted above, there is schedule risk for the duration of operations arising from the need for continuous high intensity operation.

## Technical Metrics for Progress

Performance of the AGS has been monitored against technical metrics for many years. Key metrics are total charge, peak current, repetition rate, beam energy, and the temporal properties of the extracted beam. These metrics are presented in tables, for best past performance and for RSVP needs. As noted earlier the new challenging metric is “extinction”, namely the measure of particles outside of the extracted micro bunches. It will not be possible to measure this accurately until well into construction. However it is planned to measure extinction in the beamline, and by the experiments.

Suggested end of project metrics for AGS/Booster are:  MECO – 10 TP/ pulse; slow extracted from AGS; extinction measured externally 10E-8 with internal extinction system operating; rep time of  <10s; dp/p < 1.5 of design goal.

# Assessment of Cost and Schedule by Examining WBS Plan Down to the Lowest Level

We drilled down in several different areas. The “area categories” are: complex new items (extinction hardware), labor intensive tasks (cable replacement), straightforward procurements (F6 septum), and large ticket items (booster and AGS caps, the largest single item). In each case we found the cost estimates to be well based, detailed and contain adequate ED&I. Labor hours were counted based on tasks that BNL engineers have performed. In cases where there is uncertainty, healthy line item contingency was assigned (although the overall WBS 1.4 contingency from the bottoms-up derivation is 24.4%).

Example ( WBS 1.4.2): The beam line design is not yet finalized and aperture requirements need review.  Mechanical modifications : The costing was based on similar work preformed for the Spallation Neutron Source; Installation: A  bottom up estimation for the installation of one magnet and its power supply was done.  The  comparison was made to a historical installation of a particular beam line by looking at the time for installation of the whole beam line divided by the number of elements.  The agreement was satisfactory and was a good consistency check on the number of hours needed;  Vacuum: A detailed look at the cost of the vacuum part of the switchyard inside the AGS enclosure was carried out.  A bottom up figure of $13.5K  was derived and $15K was entered in the Project spread sheet;  Instrumentation: The cost of the external profile monitors (EPM) was examined.  These devices have been built in the recent past and there is a provision to reuse some parts.  The cost estimate appears sound.

Management Issue:  The current view seems to be that the experiment will be in control of the beam line including the final extinction device.  There is a potential for conflict between the accelerator operations group and the experiment operations.  This needs attention.

# Completeness of the WBS Structure

At this stage of the project we feel that the work scoped in WBS 1.4 is not omitting any major items. The overall project contingency of 45%, will cover minor omissions. It is worth noting that the AGS team that will perform this work just completed the SNS ring, utilizing less than 5% contingency from the original baseline. We note that spares needed for RSVP operation are not included in the baseline although spares needed for reliable RHIC operation in concert with RSVP operation are included. This does present some operational risk to RSVP since a failure of one of these components will not only cause RSVP downtime, but also consume RSVP operating funds.

# Conclusion

While there is engineering work and extensive simulation work yet to be done, the WBS 1.4 part of the project is under control.  As mentioned above, the nature of the project makes it difficult to estimate now the needed operating period duration adding a schedule risk with concomitant cost risk.

## Operations and Preoperations Costs

##### Summary costs and risks

The operating costs are evaluated in FY-05 dollars for the three requested scenarios (“healthy RHIC”, “1/3 healthy RHIC”, no DOE support for RHIC/AGS operations), assuming an energy cost of $65/MWhr.  This energy rate has been negotiated through 2008 and is likely to go up during actual RSVP operations.  The costs in parentheses are actual-year dollars calculated for an overall inflation rate of 3.5% per year.  The risk of higher than inflation power cost increases has not been assessed. These cost estimates are based on stated integrated intensities required for the achievement of the proposed scientific goals: 4 x 1020 protons for MECO and 6 x 1020 protons for KOPIO.

### Cost of meeting RSVP needs in “Healthy RHIC” scenario	$110 M ($156 M)

#### Completion of the planned program in 9 years of operations, FY11-FY19

### Operating cost for “1/3rd Healthy RHIC”	$139 M ($195 M)

#### Completion of the planned program in 8 years of operations, FY11-FY18

#### Assumes alternating years of RHIC-only and RSVP-only operations, with 42 weeks for RSVP during the on-year

#### Meets MECO integrated luminosity need, KOPIO integrated luminosity need within 10%

#### Added cost (compared to “Healthy RHIC”)	$29 M ($38 M)

### Operating cost if RHIC/AGS operations is not supported by DOE	$274 M ($361 M)

#### Completion of the planned program in 5 years of operations, FY11-FY15

#### Assumes 4 years of AGS operations at 43 weeks/year and 1 year at 25 weeks per year

#### Added cost (compared to “Healthy RHIC”)	$164 M ($205 M)

### Increased support of university groups to run experiments 	$5 M/yr

#### Same level of support is needed during construction: total of $25 M

#### During RSVP operations, the total burden to the core HEP/NP programs at DOE and/or NSF will be between $25-45 M ($33-64 M) depending on scenario

### D&D (Decontamination and Decommissioning) costs have been estimated at $20 M.  They have not been incorporated into the operations budget, but are part of the total R&RA budget.  There is a significant risk that the actual cost can increase significantly due to changing regulations and/or unanticipated findings during actual D&D.  Neither this risk, nor inflation have been quantified.

### Additional cost risks occur related to slippages in schedule, uncertainties of the ultimate beam intensity, background issues, and degree of success in the beam elimination strategy.  These risks have not  been quantified.

## Detailed findings – Operations Cost

RSVP operations costs reflect the incremental costs to the RHIC program that cover expected incremental needs for the accelerator-beam transport system including the H- ion source, RFQ linac, 200 MeV linac, Booster synchrotron, the AGS, extraction, switchyard transport, proton transport to the 2 target stations for KOPIO and MECO, the neutral kaon beam for KOPIO and the muon beam line for MECO.

The accelerator and beam-line system needed to operate RSVP includes 4 accelerators with over 300 magnets and a comparable number of power supplies, approximately 1400 meters of vacuum system and components, pertinent RF systems, instrumentation, access control systems, radiation security systems.  The operating costs reported include the incremental costs for electrical power, crafts and shops support, computer network infrastructure, waste management expenses, HVAC, and, in addition, the cryogenic operations of the MECO solenoid transport and detector magnet, as well as all the utilities and infrastructure support for the accelerator, beam line magnets and power supplies and vacuum systems, as well as physics, engineering and technical support for both KOPIO and MECO.

### Not included in these cost are the costs of running the detectors by the experimental groups nor the costs of analyzing the experiments.  These costs are not fully determined and are supposed to be covered by the HEP/NP base programs.  A crude guess of this additional obligation for the base program is of the order of $2.5 M/year/experiment, $5M/year total in FY2005 dollars. This requires an approximate commitment of $25-45 M by the base budgets over 5-9 years..  Assuming 3.5% inflation per year, the actual-year totals are estimated at $33-64 M, depending on operating scenario.

### The cost of preoperations, is estimated at approximately $12 M ($4 M/year, over three years). The first two years are identified in the R&RQA budget and the third year is identified in the MREFC budget.  BNL estimates the total actual-year cost for pre-operations and commissioning at $15.4 M.  This cost has been analyzed for the “healthy” RHIC funding scenario, but is not likely to increase much for the 1/3rd “healthy” RHIC scenario since the needed RSVP commissioning runs are short (8 weeks) and can be spread over the entire RHIC operations period.  If DOE funding of RHIC/AGS is terminated, the full AGS operating cost must be carried by RSVP.

### Normal, experience-based mitigation of unscheduled downtime from component failures (appropriate spare parts) is included via the M&S component of the operating budget.

BNL has analyzed the cost of several running scenarios by using an experience-based model for the manpower needs.  They include models with concurrent RHIC operations, combinations with and without concurrent operations and two models for 25 and 42-week runs without RHIC operational during the running year.  In the “Healthy RHIC” scenario, 15 weeks of operation is concurrent and 10 weeks is for RSVP alone.  BNL has provided a model for “1/3 Healthy RHIC”.  This model would address situations in which RHIC is only funded to operate a combined run every 2 years.  During the off year, RSVP would receive an increased proton flux per hour, as there would be no need to use the AGS for RHIC injection.  This increase in intensity occurs also for the portion of the “Healthy RHIC” operation that is for RSVP alone.  The magnitude of this week-averaged intensity gain can be up to 50%, depending on the ion species delivered to RHIC.  The cost model is based on a full cost recovery of all aspects of operations.  The assumptions about the RHIC scenario are somewhat arbitrary and are meant to display a reasonable range of possibilities.  Actual costs will depend on the funding for RHIC, and over the several years of operations, can be a combination of the several scenarios.  We expect that the actual costs will fall somewhere within the range of scenarios presented here.

The manpower need is estimated on an incremental basis to the RHIC staff, because the base RHIC staff is insufficient to support RSVP operations without the additional personnel.  RSVP operations will use the combined matrixed RHIC and RSVP staff to run the program.  The estimated incremental staff of 18 FTE for concurrent operations with RHIC is reasonable, based on past experience.  A detailed work-load analysis for this staff does not exists and cannot yet be developed in good faith years ahead of actual operations.

The budget scenario for “1/3rd Healthy RHIC” operations requires additional effort to compensate for the anticipated loss in RHIC personnel: BNL estimates that NSF funding for 33 FTE will be needed for 25 weeks operations and 45 FTE for 42 weeks operations during a non-RHIC running year.  The 25 and 42 week/year models assume that RHIC and RSVP would operate in alternating years.  The AGS stand-alone model (termination of the RHIC program) requires support for 135 FTE.

The tables below summarize possible RSVP operations plans for three RHIC support scenarios (“Healthy RHIC”, “1/3 Healthy RHIC”, “No DOE Funds for RHIC/AGS Operations”).  All costs are in FY05 dollars and assume the currently negotiated energy cost of $65/MWhr – a rate that BNL has negotiated through 2008.  Included in parentheses are actual-year dollars based on an annual inflation rate of 3.5%.  While the energy cost is likely to go up during actual RSVP operations, the risk of power cost increases higher than inflation has not been assessed further.

| Healthy RHIC Funding Scenario |
| --- |
|  | Cost | MECO | KOPIO |
| year | FY05-M$ | AY-M$ | weeks | protons (1020) | weeks | protons (1020) |
| 2011 | 12.4 | (15.2) | 0 |  | 25 | 0.7 |
| 2012 | 11.6 | (14.8) | 25 | 0.9 | 0 |  |
| 2013 | 12.9 | (17.0) | 0 |  | 25 | 1.1 |
| 2014 | 11.6 | (15.8) | 25 | 1.5 | 0 |  |
| 2015 | 12.5 | (17.6) | 0 |  | 25 | 1.1 |
| 2016 | 11.3 | (16.5) | 25 | 1.6 | 0 |  |
| 2017 | 12.5 | (18.9) |  |  | 25 | 1.1 |
| 2018 | 12.5 | (19.5) |  |  | 25 | 1.1 |
| 2019 | 12.5 | (20.2) |  |  | 25 | 1.1 |
| Totals | 109.8 | (155.6) |  | 4.0 |  | 6.2 |

The preferred mode of operations in the “Healthy RHIC” funding scenario is 25 weeks per year RSVP operations to allow time for RHIC startup and maintenance.  The table assumes 10 weeks of AGS stand-alone operations for RSVP and 15 weeks of concurrent RSVP and RHIC operations (with 10 weeks heavy ions and 5 weeks protons in RHIC through 2014 and 5 weeks of heavy ions and 10 weeks of protons in RHIC starting in 2015).  The total operations cost in FY05 (actual year) dollars would be $110 M ($156 M).  An additional $45 M ($64 M) for university support would have to be provided from the base HEP programs at NSF and/or DOE.

The other two scenarios do not involve concurrent RHIC and AGS operations.  In the “1/3 Healthy RHIC” funding scenario, RHIC operations would alternate with AGS stand-alone operations with 42 weeks of RSVP running time during the on-years.  In this scenario, the program could be completed in 8 years.  The total operations cost in FY05 (actual year) dollars would be $139 M ($195 M).  An additional $40 M ($56 M) for university support would have to be provided from the base HEP programs at NSF and/or DOE.

| 1/3 Healthy RHIC Funding Scenario |
| --- |
|  | Cost | MECO | KOPIO |
| year | FY05-M$ | AY-M$ | weeks | protons (1020) | weeks | protons (1020) |
| 2011 | 4.0 | (4.9) | 0 |  | 0 |  |
| 2012 | 30.4 | (38.7) | 21 | 1.1 | 21 | 0.6 |
| 2013 | 4.5 | (5.9) | 0 |  | 0 |  |
| 2014 | 30.4 | (41.4) | 21 | 1.6 | 21 | 1.1 |
| 2015 | 4.5 | (6.3) | 0 |  | 0 |  |
| 2016 | 30.4 | (44.4) | 17 | 1.3 | 25 | 1.4 |
| 2017 | 4.0 | (6.0) | 0 |  | 0 |  |
| 2018 | 30.4 | (47.5) | 0 |  | 42 | 2.4 |
| Totals | 138.6 | (195.3) |  | 4.0 |  | 5.5 |

If there should be no DOE funds for RHIC/AGS operations, the preferred mode for RSVP operations would be 4 years of AGS stand-alone operations with 42 weeks/year followed by 1 year with 25 weeks.  The total operations cost in FY05 (actual year) dollars would be $274 M ($361 M).  An additional $25 M ($33 M) for university support would have to be provided from the base HEP programs at NSF and/or DOE.

| No DOE funds for RHIC/AGS (42 weeks/year ops) |
| --- |
|  | Cost | MECO | KOPIO |
| Year | FY05-M$ | AY-M$ | weeks | protons (1020) | weeks | protons (1020) |
| 2011 | 56.7 | (69.7) | 0 | 0 | 42 | 1.2 |
| 2012 | 56.7 | (72.1) | 42 | 2.2 | 0 |  |
| 2013 | 56.7 | (74.7) | 0 |  | 42 | 2.4 |
| 2014 | 56.7 | (77.3) | 23 | 1.8 | 19 | 1.0 |
| 2015 | 47.5 | (67.0) | 0 |  | 25 | 1.4 |
| Totals | 274.3 | (360.8) |  | 4.0 |  | 6.0 |

An alternate operating plan with only 25 weeks/year RSVP operations would reduce the annual expenditure rate from $56.7 M to $47.5 M, but the total operations cost would increase to $333 M ($454 M) since it would require two additional years of operations. The additional support needed for university groups would increase to $35M ($48 M) in this scenario.

##### Approach used by BNL for cost breakdown

The RSVP manpower estimate has been broken down into 8 categories.

#### The “machine” category consist of physicists, engineers and technicians that are in the main control room and provide for the trouble-shooting and repair of machine components.

#### The “controls” group supports all the machine and beam line hardware and software.

#### The “beams” group maintains all the switchyard and external beam line components, such as power supplies, vacuum, instrumentation and provides the support watch during operations.

#### The “utilities” group maintains and operates, the power, water, HVAC etc. utilities for the accelerators, beam lines and experiments.

#### The “access control” group provides the necessary support and testing of all the safety systems for the accelerators and experimental area.

#### The “experiment” group provides the direct technician support that the AGS provides to KOPIO and MECO and responds to the experimenter requests. This includes the liaison physicist and engineer who have the responsibility for the care and feeding of their assigned experiment.

#### “Beam tuning” is one of the major responsibilities for the physicist at the initial stages of operations.  The experimental groups invariably lack the adequate technical support staff to prepare, modify and repair much of their equipment.

#### The “cryogenic” group has the responsibility to operate and maintain the cryogenic equipment for MECO.

The budget estimates are broken down into the following categories:

#### Salary – includes wages, overtime, shift differential and fringe;

#### Distributed technical services – includes the purchased services of BNL trades, crafts and shops;

#### Purchases – includes the purchases of materials, supplies, expendables, spares;

#### MECO fixed cost – includes the year round base costs to keep the solenoids cold;

#### Power – includes the incremental power costs to operate all the accelerators and beams for RSVP and assumes a newly negotiated rate of $65/MWhr;

#### Waste management – includes the costs to remove and ship various wastes, both hazardous and radioactive;

#### Overhead – includes the BNL overhead, allocations, material handling burden and the C-AD organizational burden piece that supports the RSVP part of the costs for BNL ES&H oversight, experimenter training, radiation technician (health physics) support, computer network infrastructure support and department administrative and financial support.

## Detailed Findings – Operations Planning and Risks

##### ES&H planning

BNL has done a good job in identifying hazards and ES&H documentation requirements that must be met for commissioning and operations.  The group is aware that they will need SAD’s (Safety Analysis Documents), ASE (Accelerator safety Envelope), ARR (Accelerator Readiness Review), a commissioning plan and conduct of operations document.  As appropriate at this stage, the documentation needs have been identified and are understood.  There will sufficient time to develop and document the detailed ES&H plans if RSVP proceeds.  At this early stage no issues of concern are identified.

##### Spare Parts

While some significant upgrades are planned to improve the reliability of AGS high intensity operations, no spare parts specific to RSVP needs are planned – in the (reasonable) hope that major components (e.g. magnets, electrostatic septum)) would  not fail during the planned lifetime of RSVP.  The operating plan includes an experience-based budget for expected replacement and for building needed spare parts when the needs are clear.  If, for example, the septum should fail, the AGS could run in a less than optimal mode while a spare is being put together.  The operations group is also planning to purchase selected long lead-time items that would help mitigate the amount of downtime for single point failures.  While this strategy helps contain cost, it also entails an enhanced risk of sometimes running at lower intensity – or not at all.

##### Operations Plan

BNL has developed the various operating plans depending on the different RHIC funding scenarios, but it must be also recognized that these plans will evolve over time as the project gets closer to pre-operation and operation.  The AGS group has an outstanding track record (50 years of experience) in operating the accelerator, and they have run at high intensity (7(1013 protons/spill) in the past.  Much of their operations planning is based on past experience.  There is some unknown risk of instabilities developing in the particular running modes required for RSVP at intensities above about 6(1013 protons/spill that could cause unwanted beam losses or unanticipated problems with the cleanliness of the beam extinction.  The magnitude of this potential risk will remain unknown until the required beams can be developed and the extinction can be diagnosed.  This should clearly be done as early in the project as possible.

The issue of beam intensity is most critical for MECO.  KOPIO has the ability to mitigate the impact of lower than expected beam intensity by adjusting the AGS duty factor to optimize the experiment’s sensitivity.  For instance, a 30% reduction of beam intensity would only result in a 12% reduction in sensitivity.

Production Target Region of MECO

We asked more detailed questions about the equipment in the vicinity of the muon production target region of MECO and arrived at the following findings:

### The external magnetic field of the MECO solenoid extends out to very large distances – the 5 Gauss contour is nearly at the outer walls of the experimental hall.  Additional analyses of the effects of this field are needed – in particular the iron-dominated proton beam transport near the solenoid may be affected.  Regions from which electric motors and power transformers must be excluded must be defined as well as the region in which magnetic tools must be excluded. Analyses of the forces on the transport magnets are also needed.

### In the event of a quench, this external field will drop rapidly. Some components may heat up – in particular the copper heat shield surrounding the production target might have a problem – and substantial mechanical forces may appear at the heat shield and beam transport magnets. An analysis of the mechanical and thermal stresses on equipment in the external field region and inside the P solenoid needs to be done.

### Conversely, the effect of the soft iron beam transport magnets near the production target on the field inside the solenoid needs analysis that has yet to be provided.

### The proposed production target, vacuum windows, and heat shield designs seem adequate.  However, the mechanical design of the support mechanisms for the production target and the heat shield need to be more robust – and the superconducting magnet designers suggest that the 30-ton heat shield should not be supported from the magnet cryostat.

### The radiation shielding provided by the heat shield appeared to be adequate, but there is only a safety factor of x2-3 in both the thermal load on the superconducting coils and the radiation lifetime of the organic materials in the magnet coils.  The detailed design process for the superconducting solenoids of MECO should be carefully monitored to assure that these safety factors are not compromised.  We heard from committee member Steve St. Lorant about a 5-Tesla superconducting solenoid that survived 1011 Rads at SLAC. The lessons learned from the post mortem of this design should be incorporated into the MECO magnet.

### The radiation shielding provided by the heat shield, together with the coil design, results in the temperature margin of 1.5 K (which is the design criteria value) for the superconductor at the peak nuclear heat load.  The peak radiation induced heating contributes to a temperature rise of ~0.1K. Therefore it would be reasonable to expect that the magnets could operate at nuclear heating multiples of 2-3 times this, albeit with a reduced temperature margin of 1.3-1.4 K, which is still a reasonable margin. The maximum calculated radiation dose to the insulator is 3.6x107 rads;  the literature indicates epoxy-glass can withstand ~109 rads with  reasonable radiation damage. We heard from committee member Steve St. Lorant about a 5-Tesla superconducting solenoid that survived 1011 Rads at SLAC. The lessons learned from the post mortem of this design should be incorporated into the MECO magnet. MECO's operating scenario must take into account the possibility of radiation-induced gas evolution insulation damage.  Based on a contracted study of this, the magnets should be pumped to remove the hydrogen gas which is evolved on warmup from the epoxy by radiation exposure and they should be warmed up to room temperature at insulation. Continued attention to detail during the final design and construction is necessary to assure that these valuable design margins are not compromised.

### Considerable experience with large-volume external magnetic fields was gained in the G-2 experiment at BNL.  Bringing some of this experience to the MECO team would be a wise move.  Further, the superconducting magnet group is well-equipped to handle the issues of heating and forces in the event of a quench.  This group should be able to quickly evaluate quench-induced effects in the MECO production target heat shield, a calculation that has not yet been done.  They may also be in a position to evaluate effects of external soft iron magnets on the internal field of the MECO solenoid and forces on these soft iron magnets.

.

# Management

# Findings and Comments

RSVP is joint responsibility of NSF with US and international university and national laboratory partners. The DOE, through Brookhaven laboratory has the responsibility to upgrade and operate the AGS to meet the RSVP requirements and for onsite integration and installation of the experiments and AGS upgrades.

RSVP is embedded in an unusual management environment that has the following elements:

An NSF project using the accelerator facility at Brookhaven, a DOE National Laboratory.

Shared agency responsibility for the accelerator facility: the NSF would support incremental AGS operating costs assuming that DOE funding for base operations continues for the needed operating life of the MECO and KOPIO experiments.

Brookhaven as host laboratory for RSVP is very supportive of the science and project but is not a sponsor that could provide supporting resources. DOE is also not a direct sponsor of the project.

The host laboratory as a DOE laboratory does not have full responsibility for the success of the NSF project.

The RSVP project itself is very complex with project offices at Columbia and BNL and four almost stand-alone subprojects, including two complex multi-university experiments—KOPIO and MECO and two technical subprojects—the MECO magnet, and a series of AGS upgrades as well is the task of integrating these elements. There is a transition now taking place from distributed management of the sub-projects to a centralized management of RSVP as a single project.

From the DOE perspective the DOE Brookhaven Site Office has oversight responsibility for the AGS scope including integration of the project and so has assigned a Federal Project Director for this part of RSVP.

After much negotiation a unique and complicated management structure has been developed to address this situation and to account for the needed oversight given the responsibilities of the two funding agencies and Brookhaven. The management structure can be viewed as a work in progress and, as such, should be given adequate time to see if it works. If not, changes should be made.

For RSVP to be successful, coherent and cooperative management and communications is needed within and between the project team, the host lab, the scientific collaborations, the agencies (NSF and DOE), and the foreign partners. Since the ultimate scientific success of RSVP is the overriding consideration, this requirement extends well beyond the needs of just executing a successful MRE project.

A key challenge for all of these entities is the integration of the existing semi-autonomous sub-projects into a single well-managed project focused on delivering what is needed to achieve the scientific goals of RSVP.

During the past year with the appointment of an RSVP Project Director and deputy, RSVP has embarked on the difficult transition from two semi-independent experiments towards and integrated project with a centralized management structure.

The new project leadership brings considerable experience and a successful track record with big complex projects. One of their challenges is to put together a truly integrated project management team that works well together.

This difficult transition to an integrated project is by no means complete. There continues to be ample indication of conflicting cultures (management and scientific) and a reluctance to modify long-standing ways of doing things. This results in differing expectations among the participating cultures and severe communications challenges.

A major challenge for RSVP management, Brookhaven and the agencies will be to act constructively and effective on this issue so that a smoothly functioning management environment that embraces and is supported by the RSVP management, the collaborations, the agencies and Brookhaven management can be developed rather rapidly.

A key element for success is open and frequent communication between the central management team, the collaboration spokespersons and the laboratory management. The management subcommittee suggests that such meetings begin as soon as possible and occur at least on a monthly basis if not more frequently.

A fully engaged host laboratory is also required for this project to succeed. We are pleased to note that the Brookhaven Director has assured the committee of his full support and the Associate Director for High Energy and Nuclear Physics is very committed to the success of RSVP. Within existing constraints they are seeking positive steps to take in support of RSVP. In addition, the AGS management is fully engaged in meeting RSVPs needs.

The success of the RSVP science program will require significant and sustained support from the NSF’s research program to assure that the collaborations are of sufficient size to succeed, and that the operations of the AGS are sustained for a long enough period of time to achieve the goals of the experiments.

The funding climate is now difficult in both NSF and those parts of DOE that are relevant to RSVP. This increases the difficulty of assuring adequate support for the RSVP collaborations and could limit the support for RSVP at Brookhaven.

There are important elements of RSVP that will be contributed by foreign partners and collaborators. It is important that structures such as the International Finance Committee be put in place and made active as soon as possible to enable foreign participation to move forward and to allow foreign collaborators to obtain the support they need to fully contribute to RSVP.

The overarching RSVP management structure involves a cooperative agreement between NSF and the Columbia RSVP Office that distributes NSF funds under subcontract to Stony Brook for distribution to KOPIO institutions, to UC Irvine for MECO institutions and to MIT for the MECO Magnet. Funds for Brookhaven project activities will go from NSF to DOE through an Interagency Transfer and then to Brookhaven. There will be MOUs between the Columbia RSVP Office with Stony Brook for KOPIO, with UC Irvine for MECO, with MIT for the MECO Magnet, and with Brookhaven for AGS project activities. The MOUs are not yet in place.

There will also be MOUs between the project management for each of the experiments and the collaborating institutions that execute work packages. These MOUs are not yet in place. An RSVP MOU template exists which generally does address the right items.

The philosophy of the project leadership is to centralize project management support (e.g. schedulers, safety and QA oversight) in the Brookhaven Project office rather than with the subproject management (KOPIO, MECO, etc.). This is the right philosophy because it will enable a more integrated project team and provide for more centralized control of the work and resource flow. It is important that there be buy-in to this approach by the sub-project managers.

The RSVP Project office advocates an overall project contingency of 45% based on the community’s experience-base with large complex detector projects. The committee agrees that at least 45% is appropriate for the project at this stage. Significant uncertainties exist because some subsystems lack mature designs, spares have not been included in a consistent manner, unusual cost escalations and currency exchange issues have not always been taken into account, and labor shortfalls, especially for uncosted physicist labor have not been taken into account. There is no schedule float in the current plan so  any delay will likely result in increased costs that must come from the project contingency.  This contingency must be “centrally managed” by the RSVP project office utilizing a formal change control process that includes a change control board. The contingency will be used flexibly by RSVP project management to deal with problems as they arise and is not owned by any of the sub-projects. We suggest that a spokesperson from each experiment sit on the change control board so that the impacts on the physics-driven requirements are always considered in change control actions.

Defining the MECO magnet as a separate subproject was only done a few months ago. The committee views this as a positive step because it will assure more focused central management attention and support the procurement strategy recommended by the management oversight group. The planned integration of BNL personnel into the MECO magnet effort is a big plus to assure smooth integration of the magnet. This should be fully implemented as soon as possible and be reflected in the project’s organization chart.

There are some scope elements in the detectors’ WBS or the AGS WBS that might better be moved to the other. Examples include heat shield in MECO and the extinction system in the MECO beam-line. The committee suggests that the RSVP project office carefully evaluate these types of items and determine where they belong in the project to minimize the overall risk to RSVP.

At this stage the RSVP draft project management plan is an overarching document which refers to separate project management plans for KOPIO, MECO, AGS upgrade and the MECO magnet. These separate project management plans are appendices to the overall RSVP project management plan and not integrated into the document.

This use of separate project management plans for MECO, KOPIO, AGS and the MECO Magnet dilute the coherence and authority of the RSVP project office, risks inefficiencies and duplication of effort as well as multiple overlapping management processes. A single integrated project management plan should be developed with buy-in from all levels of the management structure. Special attention should be paid to the difficult problem of tracking costs and progress at a variety of institutions with different accounting practices and systems.

The management subcommittee has several comments concerning the baseline cost estimate:

The base cost estimate for the RSVP project management is $9.1M for the Columbia office and $8.6M for the BNL office. The assigned contingency for each is 11%, which we regard as too low. The staffing and other costs that would be supported by this budget seem adequate and appropriate for a project of this scale and complexity. A 20% contingency would be more appropriate.

The baseline cost estimate was prepared without the usual level of engineering effort so there is some risk associated with the traditional optimism of physicists in regard to cost, schedule and technical uncertainties as well as overall systems engineering issues.

The overall RSVP cost estimate uses an inflation rate of about 2.8% throughout the whole project duration. Although this is roughly the DOE guideline for materials and supplies, it is significantly below the current effective yearly increase in the cost of doing business for many research institutions and doesn’t represent to true current inflation rate that is relevant to RSVP. DOE laboratories currently estimate real inflation for labor costs is in the 4-5% range. In addition there is a significant likelihood that inflation will grow during the period of RSVP construction.

It is clear that a significant expansion of research grants will be needed for NSF funded RSVP collaborators to provide needed manpower the cost of which in the construction estimate and not now covered by grants. This is especially important because there is no contingency in the construction phase explicitly provided to deal with shortfalls in physicist effort.

The overall RSVP schedule is aggressive with no little or no float and so represents a substantial challenge to the management and a significant cost risk to the project.

There are also a number of significant cost exposures for the NSF that extend beyond the cost of the construction project. These exposures include:

The cost for AGS operations. The estimated cost has no contingency. The yearly AGS operating costs that may be higher than expected due to increases in power costs, increased inflation-driven personnel costs, unexpected maintenance costs, etc.

History indicates that it is likely that AGS operation will have to extend significantly longer than the minimum 5-9  years we estimate are needed to successfully reach the stated scientific goals of RSVP. Also it is likely that some significant additional operating time will be needed to deal with accelerator commissioning issues such as beam halo and extinction.

The assumption that NSF will only have to provide incremental AGS operating costs may not be sustained. Should the DOE NP program terminate its support of operations of AGS, NSF would have to bear full ~$50M (FY05$)/year cost of AGS operations if RSVP is to reach its scientific goals.

The estimated D & D cost of $20M has an estimated 25% contingency that is much too low. There are many uncertainties related to D&D, especially looking many years into the future.

The AGS is a fifty-year old accelerator facility that has not been used for robust fixed target operations for many years. RSVP requires high intensity, robust operations over long periods with a resulting high radiation environment for accelerator components. There is a risk that the facility components may not perform reliably in this environment over the many years of running needed. Higher failure rates and longer repair and maintenance times are possible. The resource planning for RSVP should take this possibility into account.

The extremely high intensity beams required by RSVP and the resulting radiation environment as well as challenging experimental components will present potential elevated safety risks that must also be addressed by the project and later by the management of the operations phase of RSVP.

The draft management plan indicates that safety and QA are being delegated from the RSVP project office to the sub-project managers. The RSVP project office at Brookhaven will include a safety officer and a QA officer to assure that safety and QA are properly addressed by the project. Safety at collaborating institutions will be a local responsibility and the standard safety requirements for equipment to be operated at the AGS are operative for all RSVP equipment and will be adhered to by collaborating institutions.

# Recommendations

1. NSF should immediately set up frequent stakeholders meetings to assure that all elements of RSVP are well coordinated and that the project, the collaborations, the funding agencies and the host laboratory are all fully aware of the status of all relevant activities and issues.

2. A rapid transition to an integrated project under the direction of the RSVP Project Director should be accomplished. This should include but not be limited to the following:

Developing and implementing a single management plan covering all aspects of RSVP.

Assuring that sub-project managers are fully accountable to the project office.

Significantly increasing communications between the central management, the sub-project management, the collaboration spokespersons and the Brookhaven management

Completing the MOUs between the central project office and the institutional centers for the major sub-projects.

3. RSVP and NSF should address the overall costing issues:

Utilize more realistic inflation rates (e.g. 4%- 5% for labor costs).

Reanalyze the project schedule allowing realistic schedule float so that the cost risk of using the current schedule can be qualified.

Analyze the relevant risks and include appropriate contingency in estimates of operations costs.

Include in the base construction cost adequate spares to cover yield problems and infant mortality at startup; Include in the operations cost adequate spares and replacements to maintain the physics capability of the accelerators, beamlines, target stations, and experiments.

4. RSVP should complete the MOUs involving institutions handling work packages. These MOUs should be detailed and specify the scope of work packages, the method of accomplishing the work, deliverables, resources provided by RSVP, specific manpower including names of key people, facilities to be provided by the institution, and schedules with milestones.

5. Structures such as the international finance committee should be put in place and made active as soon as possible to enable foreign participation to move forwards and to allow foreign collaborators to obtain the support they need.

6. The inter-agency agreement between DOE and NSF should be put in place to facilitate the timely flow of funds for activities at Brookhaven so that the schedule for these activities can be met.

7. Clear performance goals for the AGS defining the successful completion of that portion of the project should be part of the project plan. There should also be a documented agreement between NSF, BNL and RSVP indicating a time-dependent set of operational goals (e.g. protons on target, extinction level, etc.) for the AGS beam delivered to the experiments. We suggest specific performance goals in this area in the chapter on AGS upgrades.

Summary

RSVP is a very difficult project but its physics is exciting and important. Achievement of RSVP goals will be very challenging. This is not surprising – were it not so it would have been done already or be in the process of being done by others. The successful execution requires pushing the technology to its limit, both in the detector and in the accelerator areas. The complex management issues are unprecedented in high energy physics.

These are formidable challenges but they would likely be manageable in normal fiscal times. Unfortunately, the times we are in are not ordinary. The budgetary conditions that we live under have strongly influenced the rate at which the RSVP project has been able to proceed and hence also the state of its readiness today. They will also undoubtedly affect the ultimate decision as to whether and how one should proceed with the Project in the future.

In our review we have found that even though significant amount of work has been done to date, there are a number of areas where the current status is still relatively immature. For example, due to the lack of adequate engineering support in the past, several of the RSVP systems are still incompletely defined. Deficiencies in addressing some of the simulation issues are strongly correlated with insufficient university group strengths. In the body of the report we make specific recommendations to the NSF, Project Management and the Collaborations regarding actions that are required. We end this report by underlining several general areas where significant action is needed and/or where there is potentially significant cost exposure to the Foundation.

1. The success of this Project will require extraordinary coordination between the NSF and DOE (both its NP and HEP Divisions). We urge NSF to formulate specific agreements with DOE regarding the responsibilities and fiscal obligations of each party for the wide spectrum of possible future developments. We specifically point to the issue of future of RHIC  and hence responsibility for AGS operations cost and the possible need to extend the schedule of RSVP beyond 2016 that is currently envisaged. These and other uncertainties in the post-construction phase represent risks in several hundred million dollar range. It is important for the funding agencies to take the steps needed to reduce or account for these risks in their planning for RSVP.

2. The current strength of RSVP groups is insufficient to carry out this program successfully and expeditiously. Additional groups (both from US and abroad) will need to join and the strength of the existing groups will have to be augmented. Presumably, the program will become more attractive to the non-US groups once a firm commitment, with associated funding, is made to proceed with the program. To achieve the required stronger US participation, there has to be a high priority given to this Project by the funding agencies. This will necessitate a commitment by both NSF and DOE to provide sufficient funds to the research groups desiring to participate in RSVP. Short of that, the schedule will slip and/or significant “on-project” costs will be incurred to fill in for the anticipated “off-project” physicist contributions.

3. There are a number of technical challenges in the Project and they have the potential of generating schedule slippage and cost overruns. The most important of these should be identified and given sufficient resources so as to minimize these risks. Furthermore, the overall construction and commissioning schedule, currently very tight in a number of areas, should be allocated adequate float (schedule contingency) and associated cost risk to allow for the level of unexpected developments due to technical difficulties and other unknowns that usually are associated with a project of this complexity..

4. In the scenario where RSVP runs concurrently with RHIC operations, the goals of the experiments, as expressed in the CDR and presentations to the Panel and translated into number of protons on target, cannot be met in five years. Thus one should plan from the beginning on longer operation period if those goals need to be achieved.

APPENDIX  A

CHARGE TO THE 
RSVP BASELINE REVIEW COMMITTEE
April 12, 2005

The NSF requests that you review the cost, schedule, scope, technical, and management project baseline for the Rare Symmetry Violating Process (RSVP) project.  We ask that you also review the plans for operations and the associated costs and schedule.

The review will be held at Brookhaven National Laboratory (BNL) on April 20-22, 2005.  We ask that you provide a preliminary executive summary of your report by Friday, May 6, and a full report describing your findings, assessment, and recommendations on or about Friday, May 20, 2005. This schedule is aggressive, but the timing is dictated by internal NSF reviews leading up to the planned presentation to the National Science Board in August 2005.

The RSVP project consists of two experiments – MECO and KOPIO – that will be mounted and run at BNL, in an incremental mode relative to the DOE/BNL RHIC program.  If the project is approved, NSF would provide funds for the associated construction project, and later, the incremental costs of maintenance and operations (M&O) of the AGS and the M&O for the experimental apparatus during the conduct of the experiments.  The goal of the MECO experiment, which stands for ‘Muon to Electron Conversion’, is to measure the branching ratio for this lepton flavor-changing process with a sensitivity of ~1 in 1017.  The goal of the KOPIO experiment is to measure the branching ratio for the process , a process of fundamental interest in understanding the observed matter-antimatter asymmetry in the universe, with an uncertainty of ~10% for a 3.10-11 branching ratio.  Both experiments, at their design sensitivity, should shed light on possible new physics beyond the Standard Model.

Your review should include:

- an assessment of the technical approaches and feasibility of the MECO and KOPIO experiments that constitute the RSVP project, including what the likely performance regarding the level of sensitivity will be;

- an assessment of the technical approach and feasibility of the required AGS upgrades and external beam lines;

- an assessment of the overall readiness of RSVP, including each subsystem, to proceed to construction, recognizing, importantly, that the construction project will include significant engineering design and development activity;

- an assessment of the likely duration of the experiment construction, commissioning, and the needed period of operations;

- identification of the technical metrics against which progress can be measure (e.g., beam performance, detector efficiency, signal-to-noise that can be achieved);

- an assessment of costs of RSVP operations under different scenarios for AGS running: a ‘healthy’ RHIC/AGS operating budget, RHIC not running, and RHIC/AGS running 1/3rd the ‘healthy’ level.

- an assessment of costs and schedule by scrutinizing the RSVP WBS plan down to the lowest level for key cost drivers, and for technically-challenging elements, and using agreed-upon sampling of other WBS elements; and

- an assessment of the completeness of the WBS structure, possible items omitted, and the associated cost and schedule impacts, and, where appropriate, opportunities for cost reductions consistent with meeting the project science goals.

In carrying out this work, we ask that you examine each of the major RSVP subsystems, project management, and commissioning/operations.  The key elements of these major tasks are given below, for reference:

- MECO detector: science requirements, technical requirements (flow-down from science requirements), system design, design and development tasks, critical design issues, performance simulations, DAQ and data systems, magnet specs, background issues, completeness of design, readiness to proceed, proper identification and management of risks;

- MECO magnet: technical feasibility of the high-field, large volume, tapered-field superconducting solenoid, plans for design and development, schedule for design and development, prototyping and testing plans, integration issues, control system issues, critical issues, procurement plans, project oversight, safety issues, manpower plans, risk assessment and management;

- KOPIO detector: science requirements, technical requirements (flow-down from science requirements), system design, design and development tasks, critical design issues, performance simulations, DAQ and data systems, vacuum system, safety matters, background issues, completeness of design, readiness to proceed, and proper identification and management of risks;

- AGS modifications and external beam lines: pulse structure, beam extinction requirements, beam halo requirements, beamline design, beamline instrumentation needs, diagnostic instrumentation needs, beam development plans/running, systems integration regarding controls, cryogenics, and safety, reliability issues, radiation effects issues, cooling, shielding, and proper identification and management of risk;

- Project management: organization (including the BNL/project interface), internal oversight, reporting and NSF oversight plans, advisory mechanisms, PMCS cost and schedule tracking, resource loading of schedule, FTE analysis, staffing buildup issues, contingency management approach, change control process, project integration activities, critical path analyses for major subsystems, status of MOUs with foreign partners, appropriateness of the cost and scope of the planned management activity;

- Commissioning/operations: commissioning plans and beam development (both part of the construction project), engineering runs at reduced sensitivity or for other purpose, analysis of incremental FTE needs, completeness of plans for commissioning and for operations, appropriateness of staffing, availability of  (and priority in obtaining) appropriate BNL staff for operations, EH&S issues (radiation mitigation, status of clearances by relevant external organizations, plans for D&D), and any analysis computing infrastructure needed beyond that normally provided in base grants.

In conducting your review of RSVP, your scrutiny should extend down to and include examination of work-package costs, bases-for-cost-estimates, the labor involved and time involved, and the risk analysis/appropriateness of contingency in both cost and schedule.  Finally, while an independent HEPAP subcommittee review of the science of RSVP is also being carried out, the Panel may also wish to comment on the scientific importance of RSVP in the context of the worldwide program in elementary particle physics.

APPENDIX  B

PANEL MEMBERSHIP

KOPIO Subpanel

Marjorie Corcoran, Rice University

Peter Denes, Lawrence Berkeley National Laboratory

Karol Lang (Subpanel chair), University of Texas, Austin

Richard Loveless, University of Wisconsin

Leo Piilonen, Virginia Polytechnic Institute

Stan Wojcicki (Panel chair), Stanford University

MECO Subpanel

Myron Camp bell, University of Michigan

Martin Cooper (Subpanel chair), Los Alamos National Laboratory

Tom Diehl, Fermi National Accelerator Laboratory

David Rust, University of Indiana (ret)

MECO Magnet Subpanel

George Biallas, Jefferson Laboratory

Phil Heitzenroeder (Subpanel chair), PPPL

Steve St.Laront, SLAC (ret)

AGS Subpanel

Rod Gerig, Argonne National Laboratory

Craig Moore, Fermi National Accelerator Laboratory

Maury Tigner (Subpanel chair), Cornell University

Commissioning/Operations Subpanel

Konrad Gelbke (Subpanel chair), MSU/NSCL

Robert Mau, Fermi National Accelerator Laboratory

Arch Thiessen, Los Alamos National Laboratory (ret)

Management Subpanel

Joel Butler, Fermi National Accelerator Laboratory

Jay Marx (Subpanel chair), Lawrence Berkeley NationalLaboratory

Stan Wojcicki (Panel chair), Stanford University

APPENDIX  C

RSVP AGENDA

Wednesday 20 April 2005

08:00 – 09:00	Executive Session - Berkner Hall, Room B

09:10 – 11:50	PLENARY SESSION – Berkner B

09:10 – 09:30	Introduction (Willis)

09:30 – 10:10	Overview of RSVP Project (Kotcher)

10:10 – 10:30	KOPIO Overview (Littenberg)

10:30 – 10:50	MECO Overview (Molzon)

10:50 – 11:10	Break

11:10 – 11:30	MECO Magnet (Smith)

11:30 – 11:50	AGS Overview (Pile)

11:50 – 12:10	BNL Management View (Chaudhari)

12: 30 – 13:30	Executive Session Working Lunch – Berkner A

13:45 – 17:30	BREAKOUT SESSION A

(These sessions should start with 30-minute presentations by Project Managers)

KOPIO

MECO Detectors

MECO Magnet

AGS – Construction

17:30 – 18:30	Executive Session – Berkner B

18:30 – Adjourn

18:35 – Drinks at Berkner Hall

19:00 – Dinner at Berkner Hall

Thursday 21 April 2005

08:00 – 09:00	Executive Session – Berkner B

09:00 – 12:00	BREAKOUT SESSIONS B

KOPIO

MECO Detectors

MECO Magnet

AGS – Construction

Operations

Management

12:00 – 13:00	Executive Session Working Lunch – Berkner A

13:00 – 16:00 	BREAKOUT SESSIONS C

Detectors

AGS Construction & Operations & MECO Magnet

Management

Projects provided with questions from Committee, if any

16:00 – 17:30	Executive Session – Berkner B

Friday 22 April 2005

Berkner Hall, Room B

08:30 – 09:30	Response from Projects to questions from Committee, if any

09:30 – 14:00	Executive Session including Working Lunch

14:30-16:00	Closeout

16:00-18:00	Executive Session (Report Development)