## Sheet1
Revision Date | 2005-10-19
End of 3 month Period | 2006-01-19
Holiday + Vacation Days This Period | 8
Workdays Available This Period | 58
Level of Effort Support Tasks | Requestor | Charge # | % Time Month 1 | % Time Month 2 | % Time Month 3 | %Time This Period | Workdays This Period
NSTX | All | 1150****X350 | 10% | 10% | 25% | 15% | 8.7
Misc. support-TVPS PLC/PC update | [5 empty] | 0% | 0
Startup checks-TVPS, GIS, MIG/Peng | [5 empty] | 0% | 0
gauging, GDC, TIV/Shutters | [5 empty] | 0% | 0
[6 empty] | 0% | 0
[6 empty] | 0% | 0
Summary Level of Effort---> | Workdays This Period | %Time This Period
| 8.7 | 0.15
Specific Tasks | Requestor | Charge # | WP# | Workdays Spent | Est. Workdays Month 1 | Est. Workdays Month 2 | Est. Workdays Month 3 | Estimated Workdays This Period | Estimated Workdays After This Period | %Time This Period | % Complete
Movable Glow Probe | Kugal | 1150-****-X350 | 1187 |  | 5 | 4 | 4 | 13 | 5 | 22.41% | 0%
TC/Flow interlocks, Automate motion | [7 empty] | 0 |  | 0%
with GDC process | [7 empty] | 0 |  | 0%
Lithium Evaporator (LITER) | Kugal | 1151-****-K130 | 1263 |  | 5 | 10 | 5 | 20 | 10 | 34.48% | 0%
Controls, Cabling, TIV interlocks | [7 empty] | 0 |  | 0%
Dignostic Shutters/TIV's | Roquemore | 1150-****-X350 |  |  | 3 | 7 | 5 | 15 | 5 | 25.86% | 0%
Complete (4) assigned installations | [7 empty] | 0 |  | 0%
Controls/cabling, (4?) new | [7 empty] | 0 |  | 0%
NCSX- coil test intsrumention | Gettlefinger | 9450-1***-1414 |  |  | 2 | 2 | 0 | 4 | 20 | 6.897% | 0%
Data analysis support | [7 empty] | 0 |  | 0%
Future Coil Test instrumentaion | [7 empty] | 0 |  | 0%
[8 empty] | 0 |  | 0%
[8 empty] | 0 |  | 0%
[8 empty] | 0 |  | 0%
[8 empty] | 0 |  | 0%
[8 empty] | 0 |  | 0%
Summary Specific Tasks---> | Workdays This Period | %Time This Period
| 52 | 0.89655
Summary This Period---> | Workdays This Period | %Time This Period
| 60.7 | 104.7%
Workday Balance---> | -2.7
Check vs. Available Workdays---> | X