## December 2007 IPS
MS Project Row ID | Outline Level | Summary Task? | Site Code | Name | SPIRE/Program Goal/Milestone | GOAL Alert (45 d) | % Comp | Float | Duration | Baseline Start | Baseline Finish | Start | Finish
1 | 1 | Yes |  | ASR-11 Integrated Program Schedule | NA | No | 59% | 0 d | 3169 d | 1999-07-20 08:00 | 2010-09-30 17:00 | 1999-07-20 08:00 | 2011-08-29 17:00
2 | 2 | No | 000 | Last System Delivered to Operational Site | NA | No | 0% | 385 d | 0 d | 2008-08-27 17:00 | 2008-08-27 17:00 | 2008-09-10 17:00 | 2008-09-10 17:00
3 | 2 | No | 000 | Last Site Acceptance Test (SAT) Complete | NA | No | 0% | 16 d | 0 d | 2008-12-31 17:00 | 2008-12-31 17:00 | 2009-09-14 17:00 | 2009-09-14 17:00
4 | 2 | No | 000 | Last Operational Readiness Date (ORD) | 2009-09-30 17:00 | Yes | 0% | -173 d | 0 d | 2009-09-30 17:00 | 2009-09-30 17:00 | 2010-03-22 17:00 | 2010-03-22 17:00
5 | 2 | No | 000 | Last Site Dismantle/Deactivation Complete | NA | No | 0% | 182 d | 0 d | 2010-08-09 17:00 | 2010-08-09 17:00 | 2011-02-28 17:00 | 2011-02-28 17:00
6 | 2 | No | 000 | Last Site Complete (Latest Finish) | NA | No | 0% | 0 d | 0 d | 2010-09-30 17:00 | 2010-09-30 17:00 | 2011-08-29 17:00 | 2011-08-29 17:00
7 | 2 | Yes | 001/Mor | FAA Moratoriums | NA | No | 32% | 0 d | 557 d | 2007-11-16 19:00 | 2010-01-04 03:00 | 2007-11-16 19:00 | 2010-01-04 03:00
8 | 3 | No | 001/Mor | Thanksgiving 2007 Moratorium | NA | No | 100% | 0 hrs | 224 hrs | 2007-11-16 19:00 | 2007-11-26 03:00 | 2007-11-16 19:00 | 2007-11-26 03:00
9 | 3 | No | 001/Mor | Holiday/New Years 2007/08 Moratorium | NA | No | 86% | 0 hrs | 452 hrs | 2007-12-14 19:00 | 2008-01-02 15:00 | 2007-12-14 19:00 | 2008-01-02 15:00
10 | 3 | No | 001/Mor | Thanksgiving 2008 Moratorium | NA | No | 0% | 0 hrs | 224 hrs | 2008-11-21 19:00 | 2008-12-01 03:00 | 2008-11-21 19:00 | 2008-12-01 03:00
11 | 3 | No | 001/Mor | Holiday/New Years 2008/09 Moratorium | NA | No | 0% | 0 hrs | 392 hrs | 2008-12-19 19:00 | 2009-01-05 03:00 | 2008-12-19 19:00 | 2009-01-05 03:00
12 | 3 | No | 001/Mor | Thanksgiving 2009 Moratorium | NA | No | 0% | 0 hrs | 224 hrs | 2009-11-20 19:00 | 2009-11-30 03:00 | 2009-11-20 19:00 | 2009-11-30 03:00
13 | 3 | No | 001/Mor | Holiday/New Years 2009/10 Moratorium | NA | No | 0% | 0 hrs | 392 hrs | 2009-12-18 19:00 | 2010-01-04 03:00 | 2009-12-18 19:00 | 2010-01-04 03:00
001
14 | 2 | Yes | SMX | Santa Maria, CA (SMX) | NA | No | 100% | 0 d | 0 d | 2006-10-02 08:00 | 2006-10-02 08:00 | 2006-10-02 08:00 | 2006-10-02 08:00
15 | 3 | No | SMX | SMX Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2006-10-02 08:00 | 2006-10-02 08:00 | 2006-10-02 08:00 | 2006-10-02 08:00
16 | 3 | No | SMX | SMX Complete (Latest Finish) | NA | No | 100% | 0 d | 0 d | 2006-10-02 08:00 | 2006-10-02 08:00 | 2006-10-02 08:00 | 2006-10-02 08:00
17 | 2 | Yes | RST | Rochester, MN (RST) | NA | No | 100% | 0 d | 340 d | 2005-10-05 08:00 | 2007-01-31 17:00 | 2005-10-05 08:00 | 2007-01-17 17:00
18 | 3 | No | RST | RST Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2005-10-05 08:00 | 2005-10-05 08:00 | 2005-10-05 08:00 | 2005-10-05 08:00
19 | 3 | No | RST | RST Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 210 d | 2005-10-05 08:00 | 2006-07-25 17:00 | 2005-10-05 08:00 | 2006-07-25 17:00
20 | 3 | No | RST | RST Dismantle/Deactivate | NA | No | 100% | 0 d | 130 d | 2006-07-26 08:00 | 2006-10-17 17:00 | 2006-07-26 08:00 | 2007-01-17 17:00
21 | 3 | No | RST | RST Complete (Latest Finish) | NA | No | 100% | 0 d | 0 d | 2007-01-31 17:00 | 2007-01-31 17:00 | 2007-01-17 17:00 | 2007-01-17 17:00
22 | 2 | Yes | CAE | Columbia, SC (CAE) | NA | No | 100% | 0 d | 264 d | 2006-07-20 08:00 | 2007-07-27 17:00 | 2006-07-20 08:00 | 2007-07-13 17:00
23 | 3 | No | CAE | CAE Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2006-07-20 08:00 | 2006-07-20 08:00 | 2006-07-20 08:00 | 2006-07-20 08:00
24 | 3 | No | CAE | CAE Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 201 d | 2006-07-20 08:00 | 2007-04-11 17:00 | 2006-07-20 08:00 | 2007-04-17 17:00
25 | 3 | No | CAE | CAE Start Dismantle/Deactivate | NA | No | 100% | 0 d | 0 d | 2007-04-11 17:00 | 2007-04-11 17:00 | 2007-04-18 17:00 | 2007-04-18 17:00
26 | 3 | No | CAE | CAE Dismantle/Deactivate | NA | No | 100% | 0 d | 63 d | 2007-04-12 08:00 | 2007-06-06 17:00 | 2007-04-18 08:00 | 2007-07-13 17:00
27 | 3 | No | CAE | CAE Complete (Latest Finish) | NA | No | 100% | 0 d | 0 d | 2007-07-27 17:00 | 2007-07-27 17:00 | 2007-07-13 17:00 | 2007-07-13 17:00
28 | 2 | Yes | VRB | Vero Beach, FL (VRB) | NA | No | 100% | 0 d | 217 d | 2006-09-27 08:00 | 2007-09-28 17:00 | 2006-09-27 08:00 | 2007-07-17 17:00
29 | 3 | No | VRB | VRB CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2006-09-27 08:00 | 2006-09-27 08:00 | 2006-09-27 08:00 | 2006-09-27 08:00
30 | 3 | No | VRB | FAA Optimization | NA | No | 100% | 0 d | 14 d | 2006-09-27 08:00 | 2007-01-16 17:00 | 2006-11-27 08:00 | 2006-12-15 17:00
31 | 3 | No | VRB | Field Familiarization | NA | No | 100% | 0 d | 44 d | 2007-01-17 08:00 | 2007-03-20 17:00 | 2006-12-16 08:00 | 2007-02-14 17:00
32 | 3 | No | VRB | VRB Flight Check | NA | No | 100% | 0 d | 2 d | 2007-03-21 08:00 | 2007-03-27 17:00 | 2007-02-15 08:00 | 2007-02-16 17:00
33 | 3 | No | VRB | VRB Re-Optimization for 120 nmi extended range | NA | No | 100% | 0 d | 22 d | 2007-02-19 08:00 | 2007-02-25 17:00 | 2007-02-19 08:00 | 2007-03-16 17:00
34 | 3 | No | VRB | VRB Flight Check (Post Re-optimization) | NA | No | 100% | 0 d | 2 d | 2007-03-01 08:00 | 2007-03-16 17:00 | 2007-03-19 08:00 | 2007-03-20 17:00
35 | 3 | No | VRB | VRB Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-03-27 17:00 | 2007-03-27 17:00 | 2007-03-22 17:00 | 2007-03-22 17:00
36 | 3 | No | VRB | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 84 d | 2007-03-28 08:00 | 2007-05-22 17:00 | 2007-03-23 08:00 | 2007-07-17 17:00
37 | 3 | No | VRB | VRB Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-05-22 17:00 | 2007-05-22 17:00 | 2007-07-17 17:00 | 2007-07-17 17:00
38 | 3 | No | VRB | VRB Complete (Latest Finish) | NA | No | 100% | 0 d | 0 d | 2007-09-28 17:00 | 2007-09-28 17:00 | 2007-07-17 17:00 | 2007-07-17 17:00
39 | 2 | Yes | SDL | North Valley, AZ (SDL) | NA | No | 100% | 0 d | 422 d | 2006-04-04 08:00 | 2009-06-30 17:00 | 2006-04-04 08:00 | 2007-11-05 17:00
40 | 3 | No | SDL | Construction Contract Awarded | NA | No | 100% | 0 d | 0 d | 2006-04-04 08:00 | 2006-04-04 08:00 | 2006-04-04 08:00 | 2006-04-04 08:00
41 | 3 | No | SDL | SDL Site Construction | NA | No | 100% | 0 d | 209 d | 2006-05-17 08:00 | 2007-01-23 17:00 | 2006-05-17 08:00 | 2007-02-26 17:00
42 | 3 | No | SDL | SDL Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2007-01-23 17:00 | 2007-01-23 17:00 | 2007-02-26 17:00 | 2007-02-26 17:00
43 | 3 | No | SDL | Equipment Install and Optimization | NA | No | 100% | 0 d | 72 d | 2007-01-24 08:00 | 2007-04-17 17:00 | 2007-02-27 08:00 | 2007-06-04 17:00
44 | 3 | No | SDL | SDL Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 7 d | 2007-04-18 08:00 | 2007-05-01 17:00 | 2007-06-05 08:00 | 2007-06-13 17:00
45 | 3 | No | SDL | Resolution of Open Items | NA | No | 100% | 0 d | 13 d | 2007-05-02 08:00 | 2007-07-24 17:00 | 2007-06-14 08:00 | 2007-07-02 17:00
46 | 3 | No | SDL | SDL CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-07-24 17:00 | 2007-07-24 17:00 | 2007-07-02 17:00 | 2007-07-02 17:00
47 | 3 | No | SDL | SDL IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 100% | 0 d | 45 d | 2007-07-03 08:00 | 2007-08-24 17:00 | 2007-07-03 08:00 | 2007-08-24 17:00
48 | 3 | No | SDL | SDL IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 100% | 0 d | 28 d | 2007-08-25 08:00 | 2007-09-21 17:00 | 2007-08-25 08:00 | 2007-09-21 17:00
49 | 3 | No | SDL | SDL IOC Readiness Phase 3 (before Flight Check) | NA | No | 100% | 0 d | 14 d | 2007-09-22 08:00 | 2007-10-05 17:00 | 2007-09-22 08:00 | 2007-10-05 17:00
50 | 3 | No | SDL | SDL Flight Check | NA | No | 100% | 0 d | 1 d | 2008-02-06 08:00 | 2008-02-12 17:00 | 2007-10-06 08:00 | 2007-10-06 17:00
51 | 3 | No | SDL | SDL Initial Operating Capability (IOC) | 2007-12-31 17:00 | No | 100% | 0 d | 0 d | 2008-02-12 17:00 | 2008-02-12 17:00 | 2007-10-06 17:00 | 2007-10-06 17:00
52 | 3 | No | SDL | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 30 d | 2008-02-13 08:00 | 2008-04-22 17:00 | 2007-10-07 08:00 | 2007-11-05 17:00
53 | 3 | No | SDL | SDL Operational Readiness Date (ORD)/Commissioning | 2008-01-31 17:00 | No | 100% | 0 d | 0 d | 2008-04-22 17:00 | 2008-04-22 17:00 | 2007-11-05 17:00 | 2007-11-05 17:00
54 | 3 | No | SDL | SDL Complete (Latest Finish) | NA | No | 100% | 0 d | 0 d | 2009-06-30 17:00 | 2009-06-30 17:00 | 2007-11-05 17:00 | 2007-11-05 17:00
55 | 2 | Yes | FNT | Flint, MI (FNT) | NA | No | 100% | 0 d | 521 d | 2005-12-01 08:00 | 2007-11-30 17:00 | 2005-12-01 08:00 | 2007-11-20 17:00
56 | 3 | No | FNT | FNT Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2005-12-01 08:00 | 2005-12-01 08:00 | 2005-12-01 08:00 | 2005-12-01 08:00
57 | 3 | No | FNT | FNT Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 390 d | 2005-12-01 08:00 | 2007-07-11 17:00 | 2005-12-01 08:00 | 2007-05-21 17:00
58 | 3 | No | FNT | FNT Start Dismantle/Deactivate | NA | No | 100% | 0 d | 0 d | 2007-07-12 08:00 | 2007-09-05 17:00 | 2007-05-22 17:00 | 2007-05-22 17:00
59 | 3 | No | FNT | FNT Dismantle/Deactivate | NA | No | 100% | 0 d | 163 d | 2007-07-12 08:00 | 2007-09-05 17:00 | 2007-05-22 08:00 | 2007-11-20 17:00
60 | 3 | No | FNT | FNT Complete (Latest Finish) | NA | No | 100% | 0 d | 0 d | 2007-11-30 17:00 | 2007-11-30 17:00 | 2007-11-20 17:00 | 2007-11-20 17:00
61 | 2 | Yes | COS | Colorado Springs, CO (COS) | NA | No | 100% | 0 d | 505 d | 2006-02-01 08:00 | 2008-09-30 17:00 | 2006-02-01 08:00 | 2007-12-28 17:00
62 | 3 | No | COS | COS Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2006-02-01 08:00 | 2006-02-01 08:00 | 2006-02-01 08:00 | 2006-02-01 08:00
63 | 3 | No | COS | Equipment Install and Optimization | NA | No | 100% | 0 d | 85 d | 2006-02-01 08:00 | 2006-05-30 17:00 | 2006-02-01 08:00 | 2006-05-30 17:00
64 | 3 | No | COS | COS Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 8 d | 2006-05-31 08:00 | 2006-06-09 17:00 | 2006-05-31 08:00 | 2006-06-09 17:00
65 | 3 | No | COS | Resolution of Open Items | NA | No | 100% | 0 d | 75 d | 2006-06-12 08:00 | 2006-09-22 17:00 | 2006-06-12 08:00 | 2006-09-22 17:00
66 | 3 | No | COS | COS CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2006-09-22 17:00 | 2006-09-22 17:00 | 2006-09-22 17:00 | 2006-09-22 17:00
67 | 3 | No | COS | FAA Optimization | NA | No | 100% | 0 d | 14 d | 2006-09-25 08:00 | 2007-02-09 17:00 | 2006-09-11 08:00 | 2006-09-28 17:00
68 | 3 | No | COS | Field Familiarization | NA | No | 100% | 0 d | 26 d | 2007-02-12 08:00 | 2007-05-04 17:00 | 2006-09-29 08:00 | 2006-11-03 17:00
69 | 3 | No | COS | COS Flight Check | NA | No | 100% | 0 d | 5 d | 2007-05-07 08:00 | 2007-05-11 17:00 | 2006-11-08 08:00 | 2006-11-13 17:00
70 | 3 | No | COS | COS Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-05-11 17:00 | 2007-05-11 17:00 | 2006-11-13 17:00 | 2006-11-13 17:00
71 | 3 | No | COS | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 122 d | 2007-05-14 08:00 | 2007-07-06 17:00 | 2006-11-14 08:00 | 2007-04-24 17:00
72 | 3 | No | COS | COS Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-07-06 17:00 | 2007-07-06 17:00 | 2007-04-24 08:00 | 2007-04-24 08:00
73 | 3 | No | COS | COS Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 188 d | 2007-07-09 08:00 | 2008-04-11 17:00 | 2006-10-02 08:00 | 2007-06-11 17:00
74 | 3 | No | COS | COS Start Dismantle/Deactivate | NA | No | 100% | 0 d | 0 d | 2008-04-11 17:00 | 2008-04-11 17:00 | 2007-06-12 17:00 | 2007-06-12 17:00
75 | 3 | No | COS | COS Dismantle/Deactivate | NA | No | 100% | 0 d | 186 d | 2008-04-14 08:00 | 2008-06-06 17:00 | 2007-06-12 08:00 | 2007-12-28 17:00
76 | 3 | No | COS | COS Complete (Latest Finish) | NA | No | 100% | 0 d | 0 d | 2008-09-30 17:00 | 2008-09-30 17:00 | 2007-12-28 17:00 | 2007-12-28 17:00
77 | 2 | Yes | ACT | Waco, TX (ACT) | NA | No | 100% | 0 d | 518 d | 2006-04-10 08:00 | 2007-05-31 17:00 | 2006-01-16 08:00 | 2007-12-31 17:00
78 | 3 | No | ACT | ACT Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2006-04-10 08:00 | 2006-04-10 08:00 | 2006-04-10 08:00 | 2006-04-10 08:00
79 | 3 | No | ACT | ACT Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 228 d | 2006-04-10 08:00 | 2006-11-03 17:00 | 2006-01-16 08:00 | 2006-11-27 17:00
80 | 3 | No | ACT | ACT Dismantle/Deactivate | NA | No | 100% | 0 d | 290 d | 2006-11-06 08:00 | 2006-12-29 17:00 | 2006-11-28 08:00 | 2007-12-31 17:00
81 | 3 | No | ACT | ACT Complete (Latest Finish) | NA | No | 100% | 0 d | 0 d | 2007-05-31 17:00 | 2007-05-31 17:00 | 2007-12-31 17:00 | 2007-12-31 17:00
82 | 2 | Yes | LAN | Lansing, MI (LAN) | NA | No | 99% | 956 d | 606 d | 2006-02-14 08:00 | 2007-05-31 17:00 | 2005-09-15 08:00 | 2008-01-01 17:00
83 | 3 | No | LAN | LAN Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2006-02-14 08:00 | 2006-02-14 08:00 | 2006-02-14 08:00 | 2006-02-14 08:00
84 | 3 | No | LAN | LAN Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 272 d | 2006-02-14 08:00 | 2006-09-29 17:00 | 2005-09-15 08:00 | 2006-09-29 17:00
85 | 3 | No | LAN | LAN Dismantle/Deactivate | NA | No | 99% | 956 d | 333 d | 2006-10-02 08:00 | 2006-11-24 17:00 | 2006-10-02 08:00 | 2008-01-01 17:00
86 | 3 | No | LAN | LAN Complete (Latest Finish) | NA | No | 0% | 956 d | 0 d | 2007-05-31 17:00 | 2007-05-31 17:00 | 2008-01-01 17:00 | 2008-01-01 17:00
87 | 2 | Yes | PUB | Pueblo, CO (PUB) | NA | No | 82% | 824 d | 677 d | 2005-12-09 08:00 | 2008-09-26 08:00 | 2005-12-09 08:00 | 2008-07-01 17:00
88 | 3 | No | PUB | PUB Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2005-12-09 08:00 | 2005-12-09 08:00 | 2005-12-09 08:00 | 2005-12-09 08:00
89 | 3 | No | PUB | Equipment Install and Optimization | NA | No | 100% | 0 d | 178 d | 2005-12-09 08:00 | 2006-08-15 17:00 | 2005-12-09 08:00 | 2006-08-15 17:00
90 | 3 | No | PUB | PUB Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 8 d | 2006-08-16 08:00 | 2006-08-25 17:00 | 2006-08-16 08:00 | 2006-08-25 17:00
91 | 3 | No | PUB | Resolution of Open Items | NA | No | 100% | 0 d | 24 d | 2006-08-28 08:00 | 2006-09-28 17:00 | 2006-08-28 08:00 | 2006-09-28 17:00
92 | 3 | No | PUB | PUB CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2006-09-27 08:00 | 2006-09-27 08:00 | 2006-09-22 08:00 | 2006-09-22 08:00
93 | 3 | No | PUB | FAA Optimization | NA | No | 100% | 0 d | 14 d | 2006-09-27 08:00 | 2007-02-13 17:00 | 2006-10-17 08:00 | 2006-11-03 17:00
94 | 3 | No | PUB | Field Familiarization | NA | No | 100% | 0 d | 61 d | 2007-02-14 08:00 | 2007-05-08 17:00 | 2006-11-06 08:00 | 2007-01-23 17:00
95 | 3 | No | PUB | PUB Flight Check | NA | No | 100% | 0 d | 2 d | 2007-05-09 08:00 | 2007-05-15 17:00 | 2007-01-24 08:00 | 2007-01-25 17:00
96 | 3 | No | PUB | PUB Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-05-15 17:00 | 2007-05-15 17:00 | 2007-02-25 17:00 | 2007-02-25 17:00
97 | 3 | No | PUB | PUB Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 71 d | 2007-05-16 08:00 | 2007-07-10 17:00 | 2007-02-26 08:00 | 2007-05-31 17:00
98 | 3 | No | PUB | PUB Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-07-10 17:00 | 2007-07-10 17:00 | 2007-05-31 17:00 | 2007-05-31 17:00
99 | 3 | No | PUB | PUB Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 266 d | 2007-07-11 08:00 | 2008-04-15 17:00 | 2006-06-15 08:00 | 2007-06-12 17:00
100 | 3 | No | PUB | PUB Start Dismantle/Deactivate | NA | No | 100% | 0 d | 0 d | 2008-04-15 17:00 | 2008-04-15 17:00 | 2007-06-13 17:00 | 2007-06-13 17:00
101 | 3 | No | PUB | PUB Dismantle/Deactivate | NA | No | 97% | 1154 d | 192 d | 2008-04-16 08:00 | 2008-06-10 17:00 | 2007-06-13 08:00 | 2008-01-04 17:00
102 | 3 | No | PUB | PUB Complete Real Estate Transfer | NA | No | 0% | 1154 d | 179 d | 2008-04-16 08:00 | 2008-06-10 17:00 | 2008-01-05 08:00 | 2008-07-01 17:00
103 | 3 | No | PUB | PUB Complete (Latest Finish) | NA | No | 0% | 1154 d | 0 d | 2008-09-26 08:00 | 2008-09-26 08:00 | 2008-07-01 17:00 | 2008-07-01 17:00
104 | 2 | Yes | FSM | Ft. Smith, AR (FSM) | NA | No | 95% | 934 d | 541 d | 2006-07-06 08:00 | 2007-05-31 17:00 | 2006-01-15 08:00 | 2008-01-31 17:00
105 | 3 | No | FSM | FSM Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2006-07-06 08:00 | 2006-07-06 08:00 | 2006-07-06 08:00 | 2006-07-06 08:00
106 | 3 | No | FSM | FSM Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 296 d | 2006-07-06 08:00 | 2006-12-20 17:00 | 2006-01-15 08:00 | 2007-02-26 17:00
107 | 3 | No | FSM | FSM Dismantle/Deactivate | NA | No | 91% | 1306 d | 297 d | 2006-12-21 08:00 | 2007-02-14 17:00 | 2007-02-27 08:00 | 2008-01-31 17:00
108 | 3 | No | FSM | FSM Complete (Latest Finish) | NA | No | 0% | 1306 d | 0 d | 2007-05-31 17:00 | 2007-05-31 17:00 | 2008-01-31 17:00 | 2008-01-31 17:00
109 | 2 | Yes | SCK | Stockton, CA (SCK) | NA | No | 98% | 933 d | 1064 d | 2006-01-27 08:00 | 2007-07-31 17:00 | 2004-01-15 08:00 | 2008-02-01 17:00
110 | 3 | No | SCK | SCK Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2006-01-27 08:00 | 2006-01-27 08:00 | 2006-01-27 08:00 | 2006-01-27 08:00
111 | 3 | No | SCK | SCK Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 728 d | 2006-01-27 08:00 | 2007-03-29 17:00 | 2004-01-15 08:00 | 2006-10-30 17:00
112 | 3 | No | SCK | SCK Dismantle/Deactivate | NA | No | 93% | 1305 d | 388 d | 2007-03-30 08:00 | 2007-05-24 17:00 | 2006-10-31 08:00 | 2008-02-01 17:00
113 | 3 | No | SCK | SCK Complete (Latest Finish) | NA | No | 0% | 1305 d | 0 d | 2007-07-31 17:00 | 2007-07-31 17:00 | 2008-02-01 17:00 | 2008-02-01 17:00
114 | 2 | Yes | SBA | Santa Barbara, CA (SBA) | NA | No | 68% | 761 d | 606 d | 2006-06-13 08:00 | 2007-07-31 17:00 | 2006-06-15 08:00 | 2008-09-28 17:00
115 | 3 | No | SBA | SBA Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2006-06-13 08:00 | 2006-06-13 08:00 | 2006-07-11 08:00 | 2006-07-11 08:00
116 | 3 | No | SBA | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 80 d | 2006-06-13 08:00 | 2006-10-16 17:00 | 2006-07-12 08:00 | 2006-10-31 17:00
117 | 3 | No | SBA | SBA Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2006-10-16 17:00 | 2006-10-16 17:00 | 2006-11-01 08:00 | 2006-11-01 08:00
118 | 3 | No | SBA | SBA Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 168 d | 2006-10-17 08:00 | 2007-01-08 17:00 | 2006-06-15 08:00 | 2007-01-30 17:00
119 | 3 | No | SBA | SBA Dismantle/Deactivate | NA | No | 78% | 1065 d | 372 d | 2007-01-09 08:00 | 2007-03-05 17:00 | 2007-01-31 08:00 | 2008-03-31 17:00
120 | 3 | No | SBA | SBA Complete Real Estate Transfer | NA | No | 0% | 1065 d | 176 d | 2007-01-09 08:00 | 2007-03-05 17:00 | 2008-04-01 08:00 | 2008-09-28 17:00
121 | 3 | No | SBA | SBA Complete (Latest Finish) | NA | No | 0% | 1065 d | 0 d | 2007-07-31 17:00 | 2007-07-31 17:00 | 2008-09-28 17:00 | 2008-09-28 17:00
122 | 2 | Yes | PNS | Pensacola, FL South ( PNS) | NA | No | 67% | 696 d | 737 d | 2006-05-16 08:00 | 2007-11-30 17:00 | 2006-03-15 08:00 | 2008-12-27 17:00
123 | 3 | No | PNS | PNS Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 10 d | 2006-05-16 08:00 | 2006-05-29 17:00 | 2006-05-16 08:00 | 2006-05-29 17:00
124 | 3 | No | PNS | Resolution of Open Items | NA | No | 100% | 0 d | 54 d | 2006-05-30 08:00 | 2006-08-11 17:00 | 2006-05-30 08:00 | 2006-08-11 17:00
125 | 3 | No | PNS | PNS CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2006-08-11 17:00 | 2006-08-11 17:00 | 2006-08-11 17:00 | 2006-08-11 17:00
126 | 3 | No | PNS | FAA Optimization | NA | No | 100% | 0 d | 23 d | 2006-08-14 08:00 | 2006-12-01 17:00 | 2006-09-05 08:00 | 2006-10-05 17:00
127 | 3 | No | PNS | Field Familiarization | NA | No | 100% | 0 d | 115 d | 2006-12-04 08:00 | 2007-01-26 17:00 | 2006-10-06 08:00 | 2007-03-07 17:00
128 | 3 | No | PNS | PNS Flight Check | NA | No | 100% | 0 d | 1 d | 2007-01-29 08:00 | 2007-02-02 17:00 | 2007-03-08 08:00 | 2007-03-08 17:00
129 | 3 | No | PNS | PNS Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-02-02 17:00 | 2007-02-02 17:00 | 2007-04-01 08:00 | 2007-04-01 08:00
130 | 3 | No | PNS | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 24 d | 2007-02-05 08:00 | 2007-04-06 17:00 | 2007-04-02 08:00 | 2007-05-03 17:00
131 | 3 | No | PNS | PNS Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-04-06 17:00 | 2007-04-06 17:00 | 2007-05-03 17:00 | 2007-05-03 17:00
132 | 3 | No | PNS | PNS Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 376 d | 2007-04-09 08:00 | 2007-08-03 17:00 | 2006-03-15 08:00 | 2007-08-13 17:00
133 | 3 | No | PNS | PNS Start Dismantle/Deactivate | NA | No | 100% | 0 d | 0 d | 2007-08-03 17:00 | 2007-08-03 17:00 | 2007-08-14 17:00 | 2007-08-14 17:00
134 | 3 | No | PNS | PNS Dismantle/Deactivate | NA | No | 43% | 975 d | 322 d | 2007-08-06 08:00 | 2007-09-28 17:00 | 2007-08-14 08:00 | 2008-06-30 17:00
135 | 3 | No | PNS | PNS Complete Real Estate Transfer | NA | No | 0% | 975 d | 180 d | 2007-08-06 08:00 | 2007-09-28 17:00 | 2008-07-01 08:00 | 2008-12-27 17:00
136 | 3 | No | PNS | PNS Complete (Latest Finish) | NA | No | 0% | 975 d | 0 d | 2007-11-30 17:00 | 2007-11-30 17:00 | 2008-12-27 17:00 | 2008-12-27 17:00
137 | 2 | Yes | ABI | Abilene, TX (ABI) | NA | No | 75% | 733 d | 813 d | 2005-10-07 08:00 | 2008-06-27 17:00 | 2005-10-07 08:00 | 2008-11-05 17:00
138 | 3 | No | ABI | ABI Equipment Delivered to Site | NA | No | 100% | 0 d | 35 d | 2005-10-07 08:00 | 2005-11-24 17:00 | 2005-10-07 08:00 | 2005-11-24 17:00
139 | 3 | No | ABI | Equipment Install and Optimization | NA | No | 100% | 0 d | 172 d | 2005-11-25 08:00 | 2006-07-24 17:00 | 2005-11-25 08:00 | 2006-07-24 17:00
140 | 3 | No | ABI | ABI Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 9 d | 2006-07-25 08:00 | 2006-08-04 17:00 | 2006-07-25 08:00 | 2006-08-04 17:00
141 | 3 | No | ABI | Resolution of Open Items | NA | No | 100% | 0 d | 39 d | 2006-08-07 08:00 | 2006-09-28 17:00 | 2006-08-07 08:00 | 2006-09-28 17:00
142 | 3 | No | ABI | ABI CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2006-09-25 08:00 | 2006-09-25 08:00 | 2006-09-25 08:00 | 2006-09-25 08:00
143 | 3 | No | ABI | FAA Optimization | NA | No | 100% | 0 d | 25 d | 2006-10-27 08:00 | 2007-01-12 17:00 | 2006-09-25 08:00 | 2006-10-27 17:00
144 | 3 | No | ABI | Field Familiarization | NA | No | 100% | 0 d | 75 d | 2007-01-15 08:00 | 2007-04-06 17:00 | 2006-10-30 08:00 | 2007-02-05 17:00
145 | 3 | No | ABI | ABI Flight Check | NA | No | 100% | 0 d | 2 d | 2007-04-09 08:00 | 2007-04-13 17:00 | 2007-02-06 08:00 | 2007-02-07 17:00
146 | 3 | No | ABI | ABI Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-04-13 17:00 | 2007-04-13 17:00 | 2007-03-15 17:00 | 2007-03-15 17:00
147 | 3 | No | ABI | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 157 d | 2007-04-16 08:00 | 2007-06-08 17:00 | 2007-03-16 08:00 | 2007-09-27 17:00
148 | 3 | No | ABI | ABI Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-06-08 17:00 | 2007-06-08 17:00 | 2007-09-27 17:00 | 2007-09-27 17:00
149 | 3 | No | ABI | ABI Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 363 d | 2007-06-11 08:00 | 2008-03-14 17:00 | 2006-07-10 08:00 | 2007-11-13 17:00
150 | 3 | No | ABI | ABI Start Dismantle/Deactivate | 2008-02-29 17:00 | No | 100% | 0 d | 0 d | 2008-03-14 17:00 | 2008-03-14 17:00 | 2007-11-14 17:00 | 2007-11-14 17:00
151 | 3 | No | ABI | ABI Dismantle/Deactivate | NA | No | 26% | 1027 d | 177 d | 2008-03-17 08:00 | 2008-05-09 17:00 | 2007-11-14 08:00 | 2008-05-08 17:00
152 | 3 | No | ABI | ABI Complete RE Transfer | NA | No | 0% | 1027 d | 181 d | 2008-03-17 08:00 | 2008-05-09 17:00 | 2008-05-09 08:00 | 2008-11-05 17:00
153 | 3 | No | ABI | ABI Complete (Latest Finish) | NA | No | 0% | 1027 d | 0 d | 2008-06-27 17:00 | 2008-06-27 17:00 | 2008-11-05 17:00 | 2008-11-05 17:00
154 | 2 | Yes | FAR | Fargo, ND (FAR) | NA | No | 64% | 614 d | 904 d | 2005-11-16 08:00 | 2007-11-30 17:00 | 2005-11-16 08:00 | 2009-04-21 17:00
155 | 3 | No | FAR | FAR Equipment Delivered to Site | NA | No | 100% | 0 d | 12 d | 2005-11-16 08:00 | 2005-12-01 17:00 | 2005-11-16 08:00 | 2005-12-01 17:00
156 | 3 | No | FAR | Equipment Install and Optimization | NA | No | 100% | 0 d | 207 d | 2005-12-02 08:00 | 2006-09-18 17:00 | 2005-12-02 08:00 | 2006-09-18 17:00
157 | 3 | No | FAR | FAR Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 9 d | 2006-09-19 08:00 | 2006-09-29 17:00 | 2006-09-19 08:00 | 2006-09-29 17:00
158 | 3 | No | FAR | Resolution of Open Items | NA | No | 100% | 0 d | 30 d | 2006-10-02 08:00 | 2006-11-10 17:00 | 2006-10-02 08:00 | 2006-11-10 17:00
159 | 3 | No | FAR | FAR CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2006-11-10 17:00 | 2006-11-10 17:00 | 2006-10-23 08:00 | 2006-10-23 08:00
160 | 3 | No | FAR | FAA Optimization | NA | No | 100% | 0 d | 12 d | 2006-11-13 08:00 | 2007-03-02 17:00 | 2007-01-08 08:00 | 2007-01-23 17:00
161 | 3 | No | FAR | Field Familiarization | NA | No | 100% | 0 d | 67 d | 2007-03-05 08:00 | 2007-05-25 17:00 | 2007-01-24 08:00 | 2007-04-23 17:00
162 | 3 | No | FAR | FAR Flight Check | NA | No | 100% | 0 d | 2 d | 2007-05-28 08:00 | 2007-06-01 17:00 | 2007-04-24 08:00 | 2007-04-25 17:00
163 | 3 | No | FAR | FAR Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-06-01 17:00 | 2007-06-01 17:00 | 2007-05-10 17:00 | 2007-05-10 17:00
164 | 3 | No | FAR | FAR Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 51 d | 2007-06-04 08:00 | 2007-07-27 17:00 | 2007-05-11 08:00 | 2007-07-20 17:00
165 | 3 | No | FAR | FAR Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-07-27 17:00 | 2007-07-27 17:00 | 2007-07-20 17:00 | 2007-07-20 17:00
166 | 3 | No | FAR | FAR Site Dismantle/Deactivation Planning | NA | No | 100% | 0 d | 357 d | 2007-07-30 08:00 | 2007-09-21 17:00 | 2006-06-15 08:00 | 2007-09-25 17:00
167 | 3 | No | FAR | FAR Start Dismantle/Deactivation | NA | No | 100% | 0 d | 0 d | 2007-09-24 08:00 | 2007-09-24 08:00 | 2007-09-26 17:00 | 2007-09-26 17:00
168 | 3 | No | FAR | FAR Dismantle/Deactivate | NA | No | 25% | 860 d | 390 d | 2007-09-24 08:00 | 2007-11-16 17:00 | 2007-09-26 08:00 | 2008-10-19 17:00
169 | 3 | No | FAR | FAR Complete RE Transfer | NA | No | 0% | 860 d | 184 d | 2007-09-24 08:00 | 2007-11-16 17:00 | 2008-10-20 08:00 | 2009-04-21 17:00
170 | 3 | No | FAR | FAR Complete (Latest Finish) | NA | No | 0% | 860 d | 0 d | 2007-11-30 17:00 | 2007-11-30 17:00 | 2009-04-21 17:00 | 2009-04-21 17:00
171 | 2 | Yes | FAI | Fairbanks, AK (FAI) | NA | No | 70% | 624 d | 1057 d | 2005-01-14 08:00 | 2007-11-30 17:00 | 2005-04-01 08:00 | 2009-04-07 17:00
172 | 3 | No | FAI | FAI CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2005-01-14 08:00 | 2005-01-14 08:00 | 2005-04-21 08:00 | 2005-04-21 08:00
173 | 3 | No | FAI | FAA Optimization | NA | No | 100% | 0 d | 13 d | 2005-01-14 08:00 | 2006-09-27 17:00 | 2005-07-12 08:00 | 2005-07-28 17:00
174 | 3 | No | FAI | Field Familiarization | NA | No | 100% | 0 d | 0 d | 2006-09-28 08:00 | 2006-11-08 17:00 | 2006-09-04 08:00 | 2006-09-04 08:00
175 | 3 | No | FAI | FAI Flight Check | NA | No | 100% | 0 d | 2 d | 2006-11-09 08:00 | 2006-11-15 17:00 | 2006-09-05 08:00 | 2006-09-06 17:00
176 | 3 | No | FAI | FAI Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2006-10-24 08:00 | 2006-10-24 17:00 | 2006-10-24 08:00 | 2006-10-24 08:00
177 | 3 | No | FAI | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 183 d | 2006-11-16 08:00 | 2007-01-10 17:00 | 2006-10-25 08:00 | 2007-06-28 17:00
178 | 3 | No | FAI | FAI Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-01-10 17:00 | 2007-01-10 17:00 | 2007-06-28 17:00 | 2007-06-28 17:00
179 | 3 | No | FAI | FAI Site Dismantle/Deactivation Planning | NA | No | 86% | 0 d | 930 d | 2007-01-11 08:00 | 2007-08-08 17:00 | 2005-04-01 08:00 | 2008-06-10 17:00
180 | 3 | No | FAI | FAI Start Dismantle/Deactivate | 2008-08-31 17:00 | No | 0% | 81 d | 0 d | 2007-08-08 17:00 | 2007-08-08 17:00 | 2008-06-11 17:00 | 2008-06-11 17:00
181 | 3 | No | FAI | FAI Dismantle/Deactivate | NA | No | 0% | 874 d | 119 d | 2007-08-09 08:00 | 2007-10-03 17:00 | 2008-06-11 08:00 | 2008-10-07 17:00
182 | 3 | No | FAI | FAI Complete RE Transfer | NA | No | 0% | 874 d | 182 d | 2007-08-09 08:00 | 2007-10-03 17:00 | 2008-10-08 08:00 | 2009-04-07 17:00
183 | 3 | No | FAI | FAI Complete (Latest Finish) | NA | No | 0% | 874 d | 0 d | 2007-11-30 17:00 | 2007-11-30 17:00 | 2009-04-07 17:00 | 2009-04-07 17:00
184 | 2 | Yes | MCN | Macon, GA (MCN) | NA | No | 68% | 687 d | 690 d | 2006-08-22 08:00 | 2008-05-30 17:00 | 2006-06-01 08:00 | 2009-01-08 17:00
185 | 3 | No | MCN | MCN Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 9 d | 2006-08-22 08:00 | 2006-09-01 17:00 | 2006-08-22 08:00 | 2006-09-01 17:00
186 | 3 | No | MCN | Resolution of Open Items | NA | No | 100% | 0 d | 36 d | 2006-09-04 08:00 | 2006-10-31 17:00 | 2006-09-04 08:00 | 2006-10-23 17:00
187 | 3 | No | MCN | MCN CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2006-10-31 17:00 | 2006-10-31 17:00 | 2006-10-23 17:00 | 2006-10-23 17:00
188 | 3 | No | MCN | FAA Optimization | NA | No | 100% | 0 d | 12 d | 2006-11-01 08:00 | 2007-02-19 17:00 | 2007-01-08 08:00 | 2007-01-23 17:00
189 | 3 | No | MCN | Field Familiarization | NA | No | 100% | 0 d | 98 d | 2007-02-20 08:00 | 2007-04-23 17:00 | 2007-01-24 08:00 | 2007-06-05 17:00
190 | 3 | No | MCN | MCN Flight Check | NA | No | 100% | 0 d | 2 d | 2007-04-24 08:00 | 2007-04-30 17:00 | 2007-06-06 08:00 | 2007-06-07 17:00
191 | 3 | No | MCN | MCN Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-04-30 17:00 | 2007-04-30 17:00 | 2007-06-12 17:00 | 2007-06-12 17:00
192 | 3 | No | MCN | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 155 d | 2007-05-01 08:00 | 2007-06-25 17:00 | 2007-06-13 08:00 | 2007-11-28 17:00
193 | 3 | No | MCN | MCN Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-06-25 17:00 | 2007-06-25 17:00 | 2007-11-28 17:00 | 2007-11-28 17:00
194 | 3 | No | MCN | MCN Site Dismantle/Deactivation Planning | NA | No | 97% | 15 d | 479 d | 2007-06-26 08:00 | 2008-03-31 17:00 | 2006-06-01 08:00 | 2008-01-15 17:00
195 | 3 | No | MCN | MCN Start Dismantle/Deactivate | 2008-01-31 17:00 | Yes | 0% | 15 d | 0 d | 2008-03-31 17:00 | 2008-03-31 17:00 | 2008-01-16 17:00 | 2008-01-16 17:00
196 | 3 | No | MCN | MCN Dismantle/Deactivate | NA | No | 0% | 963 d | 177 d | 2008-04-01 08:00 | 2008-05-26 17:00 | 2008-01-16 08:00 | 2008-07-10 17:00
197 | 3 | No | MCN | MCN Complete RE Transfer | NA | No | 0% | 963 d | 182 d | 2008-04-01 08:00 | 2008-05-26 17:00 | 2008-07-11 08:00 | 2009-01-08 17:00
198 | 3 | No | MCN | MCN Complete (Latest Finish) | NA | No | 0% | 963 d | 0 d | 2008-05-30 17:00 | 2008-05-30 17:00 | 2009-01-08 17:00 | 2009-01-08 17:00
199 | 2 | Yes | MBS | Saginaw, MI (MBS) | NA | No | 64% | 631 d | 762 d | 2006-05-10 08:00 | 2008-09-30 17:00 | 2006-05-10 08:00 | 2009-03-29 17:00
200 | 3 | No | MBS | MBS Equipment Delivered to Site | NA | No | 100% | 0 d | 5 d | 2006-05-10 08:00 | 2006-05-16 17:00 | 2006-05-10 08:00 | 2006-05-16 17:00
201 | 3 | No | MBS | Equipment Install and Optimization | NA | No | 100% | 0 d | 131 d | 2006-05-17 08:00 | 2006-11-15 17:00 | 2006-05-17 08:00 | 2006-11-14 17:00
202 | 3 | No | MBS | MBS Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 26 d | 2006-11-16 08:00 | 2006-11-29 17:00 | 2007-02-21 08:00 | 2007-03-26 17:00
203 | 3 | No | MBS | Resolution of Open Items | NA | No | 100% | 0 d | 27 d | 2006-11-30 08:00 | 2007-02-21 17:00 | 2007-03-27 08:00 | 2007-05-01 17:00
204 | 3 | No | MBS | MBS CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-02-21 17:00 | 2007-02-21 17:00 | 2007-05-01 17:00 | 2007-05-01 17:00
205 | 3 | No | MBS | MBS FAA Optimization | NA | No | 100% | 0 d | 43 d | 2007-02-22 08:00 | 2007-06-13 17:00 | 2007-05-02 08:00 | 2007-06-29 17:00
206 | 3 | No | MBS | Field Familiarization | NA | No | 100% | 0 d | 58 d | 2007-06-14 08:00 | 2007-10-03 17:00 | 2007-07-02 08:00 | 2007-09-05 17:00
207 | 3 | No | MBS | MBS Flight Check | NA | No | 100% | 0 d | 1 d | 2007-10-04 08:00 | 2007-10-10 17:00 | 2007-09-06 08:00 | 2007-09-06 17:00
208 | 3 | No | MBS | MBS Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-10-10 17:00 | 2007-10-10 17:00 | 2007-09-13 17:00 | 2007-09-13 17:00
209 | 3 | No | MBS | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 29 d | 2007-10-11 08:00 | 2007-12-12 17:00 | 2007-09-14 08:00 | 2007-10-12 17:00
210 | 3 | No | MBS | MBS Operational Readiness Date (ORD)/Commissioning | 2007-12-31 17:00 | No | 100% | 0 d | 0 d | 2007-12-12 17:00 | 2007-12-12 17:00 | 2007-10-12 17:00 | 2007-10-12 17:00
211 | 3 | No | MBS | MBS Site Dismantle/Deactivation Planning | NA | No | 86% | 0 d | 544 d | 2007-12-13 08:00 | 2008-05-28 17:00 | 2006-06-15 08:00 | 2008-03-30 17:00
212 | 3 | No | MBS | MBS Start Dismantle/Deactivate | 2008-03-31 17:00 | Yes | 0% | 0 d | 0 d | 2008-05-28 17:00 | 2008-05-28 17:00 | 2008-03-31 17:00 | 2008-03-31 17:00
213 | 3 | No | MBS | MBS Dismantle/Deactivate | NA | No | 0% | 883 d | 182 d | 2008-05-29 08:00 | 2008-07-23 17:00 | 2008-03-31 08:00 | 2008-09-28 17:00
214 | 3 | No | MBS | MBS Complete RE Transfer | NA | No | 0% | 883 d | 182 d | 2008-05-29 08:00 | 2008-07-23 17:00 | 2008-09-29 08:00 | 2009-03-29 17:00
215 | 3 | No | MBS | MBS Complete (Latest Finish) | NA | No | 0% | 883 d | 0 d | 2008-09-30 17:00 | 2008-09-30 17:00 | 2009-03-29 17:00 | 2009-03-29 17:00
216 | 2 | Yes | AGS | Augusta, GA (AGS) | NA | No | 50% | 651 d | 823 d | 2006-01-17 08:00 | 2008-11-28 17:00 | 2006-01-17 08:00 | 2009-02-27 17:00
217 | 3 | No | AGS | AGS Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2006-01-17 08:00 | 2006-01-17 08:00 | 2006-01-17 08:00 | 2006-01-17 08:00
218 | 3 | No | AGS | Equipment Install and Optimization | NA | No | 100% | 0 d | 158 d | 2006-01-17 08:00 | 2006-12-18 17:00 | 2006-04-28 08:00 | 2006-12-01 17:00
219 | 3 | No | AGS | AGS Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 10 d | 2006-12-19 08:00 | 2006-12-28 17:00 | 2006-12-12 08:00 | 2006-12-22 17:00
220 | 3 | No | AGS | Resolution of Open Items | NA | No | 100% | 0 d | 26 d | 2006-12-29 08:00 | 2007-02-22 17:00 | 2006-12-25 08:00 | 2007-01-29 17:00
221 | 3 | No | AGS | AGS CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-02-22 17:00 | 2007-02-22 17:00 | 2007-01-29 17:00 | 2007-01-29 17:00
222 | 3 | No | AGS | FAA Optimization | NA | No | 100% | 0 d | 10 d | 2007-02-23 08:00 | 2007-05-17 17:00 | 2007-02-19 08:00 | 2007-03-01 17:00
223 | 3 | No | AGS | Field Familiarization | NA | No | 100% | 0 d | 79 d | 2007-05-18 08:00 | 2007-07-12 17:00 | 2007-03-02 08:00 | 2007-06-18 17:00
224 | 3 | No | AGS | AGS Flight Check | NA | No | 100% | 0 d | 1 d | 2007-07-13 08:00 | 2007-07-19 17:00 | 2007-06-19 08:00 | 2007-06-19 17:00
225 | 3 | No | AGS | AGS Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-07-19 17:00 | 2007-07-19 17:00 | 2007-08-07 17:00 | 2007-08-07 17:00
226 | 3 | No | AGS | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 42 d | 2007-07-20 08:00 | 2007-09-13 17:00 | 2007-08-08 08:00 | 2007-09-18 17:00
227 | 3 | No | AGS | AGS Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-09-13 17:00 | 2007-09-13 17:00 | 2007-09-18 17:00 | 2007-09-18 17:00
228 | 3 | No | AGS | AGS Site Dismantle/Deactivation Planning | NA | No | 40% | 913 d | 255 d | 2007-09-14 08:00 | 2008-06-19 17:00 | 2007-09-19 08:00 | 2008-05-30 17:00
229 | 3 | No | AGS | AGS Start Dismantle/Deactivate | NA | No | 0% | 913 d | 0 d | 2008-06-19 17:00 | 2008-06-19 17:00 | 2008-05-31 17:00 | 2008-05-31 17:00
230 | 3 | No | AGS | AGS Dismantle/Deactivate | NA | No | 0% | 913 d | 91 d | 2008-06-20 08:00 | 2008-08-14 17:00 | 2008-05-31 08:00 | 2008-08-29 17:00
231 | 3 | No | AGS | AGS Complete RE Transfer | NA | No | 0% | 913 d | 182 d | 2008-06-20 08:00 | 2008-08-14 17:00 | 2008-08-30 08:00 | 2009-02-27 17:00
232 | 3 | No | AGS | AGS Complete (Latest Finish) | NA | No | 0% | 913 d | 0 d | 2008-11-28 17:00 | 2008-11-28 17:00 | 2009-02-27 17:00 | 2009-02-27 17:00
233 | 2 | Yes | MYR | Myrtle Beach, SC (MYR) | NA | No | 64% | 589 d | 895 d | 2006-01-03 08:00 | 2008-10-31 17:00 | 2006-01-03 08:00 | 2009-05-26 17:00
234 | 3 | No | MYR | MYR Equipment Delivered to Site | NA | No | 79% | 318 d | 137 d | 2006-01-03 08:00 | 2006-01-03 08:00 | 2006-01-03 08:00 | 2008-07-11 17:00
235 | 3 | No | MYR | Equipment Install and Optimization | NA | No | 100% | 0 d | 216 d | 2006-01-03 08:00 | 2006-12-04 17:00 | 2006-01-03 08:00 | 2006-10-31 17:00
236 | 3 | No | MYR | MYR Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 8 d | 2006-12-05 08:00 | 2006-12-14 17:00 | 2006-10-31 17:00 | 2006-11-10 17:00
237 | 3 | No | MYR | Resolution of Open Items | NA | No | 100% | 0 d | 27 d | 2006-12-15 08:00 | 2007-01-25 17:00 | 2006-11-13 08:00 | 2006-12-15 17:00
238 | 3 | No | MYR | MYR CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-01-25 17:00 | 2007-01-25 17:00 | 2006-12-15 17:00 | 2006-12-15 17:00
239 | 3 | No | MYR | FAA Optimization | NA | No | 100% | 0 d | 11 d | 2007-01-26 08:00 | 2007-03-22 17:00 | 2007-02-27 08:00 | 2007-03-12 17:00
240 | 3 | No | MYR | Field Familiarization | NA | No | 100% | 0 d | 86 d | 2007-03-23 08:00 | 2007-05-17 17:00 | 2007-03-13 08:00 | 2007-07-09 17:00
241 | 3 | No | MYR | MYR Flight Check | NA | No | 100% | 0 d | 2 d | 2007-05-18 08:00 | 2007-05-24 17:00 | 2007-07-10 08:00 | 2007-07-11 17:00
242 | 3 | No | MYR | MYR Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-05-24 17:00 | 2007-05-24 17:00 | 2007-07-17 17:00 | 2007-07-17 17:00
243 | 3 | No | MYR | Operational Suitability Demonstration (OSD) | NA | No | 100% | 0 d | 90 d | 2007-05-25 08:00 | 2007-07-19 17:00 | 2007-07-18 08:00 | 2007-10-19 17:00
244 | 3 | No | MYR | MYR Operational Readiness Date (ORD)/Commissioning | NA | No | 100% | 0 d | 0 d | 2007-07-19 17:00 | 2007-07-19 17:00 | 2007-10-19 17:00 | 2007-10-19 17:00
245 | 3 | No | MYR | MYR Site Dismantle/Deactivation Planning | NA | No | 75% | 0 d | 529 d | 2007-07-20 08:00 | 2008-04-24 17:00 | 2006-10-02 08:00 | 2008-05-31 17:00
246 | 3 | No | MYR | MYR Start Dismantle/Deactivate | 2008-05-31 17:00 | Yes | 0% | 0 d | 0 d | 2008-04-24 17:00 | 2008-04-24 17:00 | 2008-05-31 17:00 | 2008-05-31 17:00
247 | 3 | No | MYR | MYR Dismantle/Deactivate | NA | No | 0% | 825 d | 179 d | 2008-04-25 08:00 | 2008-06-19 17:00 | 2008-05-31 08:00 | 2008-11-25 17:00
248 | 3 | No | MYR | MYR Complete RE Transfer | NA | No | 0% | 825 d | 182 d | 2008-04-25 08:00 | 2008-06-19 17:00 | 2008-11-26 08:00 | 2009-05-26 17:00
249 | 3 | No | MYR | MYR Complete (Latest Finish) | NA | No | 0% | 825 d | 0 d | 2008-10-31 17:00 | 2008-10-31 17:00 | 2009-05-26 17:00 | 2009-05-26 17:00
250 | 2 | Yes | ANC | Anchorage, AK (ANC) | NA | No | 73% | 655 d | 1012 d | 2005-02-10 08:00 | 2007-12-31 17:00 | 2005-04-21 08:00 | 2009-02-23 17:00
251 | 3 | No | ANC | ANC CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2005-02-10 08:00 | 2005-02-10 08:00 | 2005-04-21 08:00 | 2005-04-21 08:00
252 | 3 | No | ANC | FAA Optimization | NA | No | 100% | 0 d | 483 d | 2005-02-10 08:00 | 2007-01-12 17:00 | 2005-05-31 08:00 | 2007-03-29 17:00
253 | 3 | No | ANC | Field Familiarization | NA | No | 100% | 0 d | 29 d | 2007-01-15 08:00 | 2007-02-23 17:00 | 2007-03-31 08:00 | 2007-05-09 17:00
254 | 3 | No | ANC | ANC Flight Check | NA | No | 100% | 0 d | 1 d | 2007-02-26 08:00 | 2007-03-02 17:00 | 2007-05-10 08:00 | 2007-05-10 17:00
255 | 3 | No | ANC | ANC Initial Operating Capability (IOC) | NA | No | 100% | 0 d | 0 d | 2007-03-02 17:00 | 2007-03-02 17:00 | 2007-05-17 17:00 | 2007-05-17 17:00
256 | 3 | No | ANC | Operational Suitability Demonstration (OSD) | NA | No | 56% | 457 d | 386 d | 2007-03-05 08:00 | 2007-04-04 17:00 | 2007-05-18 08:00 | 2008-06-28 17:00
257 | 3 | No | ANC | ANC Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 457 d | 0 d | 2007-04-04 17:00 | 2007-04-04 17:00 | 2008-06-30 17:00 | 2008-06-30 17:00
258 | 3 | No | ANC | ANC Site Dismantle/Deactivation Planning | NA | No | 84% | 918 d | 935 d | 2007-04-05 08:00 | 2007-08-22 17:00 | 2005-04-21 08:00 | 2008-06-29 17:00
259 | 3 | No | ANC | ANC Start Dismantle/Deactivate | NA | No | 0% | 918 d | 0 d | 2007-08-22 17:00 | 2007-08-22 17:00 | 2008-06-30 17:00 | 2008-06-30 17:00
260 | 3 | No | ANC | ANC Dismantle/Deactivate | NA | No | 0% | 917 d | 56 d | 2007-08-23 08:00 | 2007-10-17 17:00 | 2008-07-01 08:00 | 2008-08-25 17:00
261 | 3 | No | ANC | ANC Complete RE Transfer | NA | No | 0% | 917 d | 182 d | 2007-08-23 08:00 | 2007-10-17 17:00 | 2008-08-26 08:00 | 2009-02-23 17:00
262 | 3 | No | ANC | ANC Complete (Latest Finish) | NA | No | 0% | 917 d | 0 d | 2007-12-31 17:00 | 2007-12-31 17:00 | 2009-02-23 17:00 | 2009-02-23 17:00
263 | 2 | Yes | BPT | Beaumont, TX (BPT) | NA | No | 55% | 523 d | 844 d | 2006-08-22 08:00 | 2008-03-31 17:00 | 2006-06-15 08:00 | 2009-08-26 17:00
264 | 3 | No | BPT | BPT CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2006-08-22 08:00 | 2006-08-22 08:00 | 2006-08-24 08:00 | 2006-08-24 08:00
265 | 3 | No | BPT | FAA Optimization | NA | No | 100% | 0 d | 23 d | 2006-08-24 08:00 | 2006-12-13 17:00 | 2006-09-05 08:00 | 2006-10-05 17:00
266 | 3 | No | BPT | Field Familiarization | NA | No | 100% | 0 d | 86 d | 2006-12-14 08:00 | 2007-02-07 17:00 | 2006-10-06 08:00 | 2007-01-29 17:00
267 | 3 | No | BPT | BPT Flight Check | NA | No | 100% | 0 d | 2 d | 2007-02-08 08:00 | 2007-02-14 17:00 | 2007-01-30 08:00 | 2007-01-31 17:00
268 | 3 | No | BPT | BPT ATS Failure Remedy | NA | No | 100% | 0 d | 32 d | 2007-02-01 08:00 | 2007-04-30 17:00 | 2007-02-01 08:00 | 2007-03-14 17:00
269 | 3 | No | BPT | BPT Initial Operating Capability (IOC) | 2007-04-30 17:00 | No | 100% | 0 d | 0 d | 2007-02-14 17:00 | 2007-02-14 17:00 | 2007-03-14 17:00 | 2007-03-14 17:00
270 | 3 | No | BPT | Operational Suitability Demonstration (OSD) | NA | No | 61% | 42 d | 435 d | 2007-02-15 08:00 | 2007-04-11 17:00 | 2007-03-15 08:00 | 2008-06-30 17:00
271 | 3 | No | BPT | BPT Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 42 d | 0 d | 2007-04-11 17:00 | 2007-04-11 17:00 | 2008-06-30 17:00 | 2008-06-30 17:00
272 | 3 | No | BPT | BPT Site Dismantle/Deactivation Planning | NA | No | 70% | 0 d | 698 d | 2007-04-12 08:00 | 2008-01-16 17:00 | 2006-06-15 08:00 | 2008-08-31 17:00
273 | 3 | No | BPT | BPT Start Dismantle/Deactivate | 2008-08-31 17:00 | Yes | 0% | 0 d | 0 d | 2008-01-16 17:00 | 2008-01-16 17:00 | 2008-08-31 17:00 | 2008-08-31 17:00
274 | 3 | No | BPT | BPT Dismantle/Deactivate | NA | No | 0% | 733 d | 179 d | 2008-01-17 08:00 | 2008-03-12 17:00 | 2008-08-31 08:00 | 2009-02-25 17:00
275 | 3 | No | BPT | BPT Complete Real Estate Transfer | NA | No | 0% | 733 d | 182 d | 2008-01-17 08:00 | 2008-03-12 17:00 | 2009-02-26 08:00 | 2009-08-26 17:00
276 | 3 | No | BPT | BPT Complete (Latest Finish) | NA | No | 0% | 733 d | 0 d | 2008-03-31 17:00 | 2008-03-31 17:00 | 2009-08-26 17:00 | 2009-08-26 17:00
277 | 2 | Yes | MOB | Mobile, AL (MOB) | NA | No | 70% | 739 d | 640 d | 2006-05-30 08:00 | 2008-12-31 17:00 | 2006-05-30 08:00 | 2008-10-28 17:00
278 | 3 | No | MOB | MOB Equipment Delivered to Site | NA | No | 100% | 0 d | 45 d | 2006-05-30 08:00 | 2006-07-31 17:00 | 2006-05-30 08:00 | 2006-07-31 17:00
279 | 3 | No | MOB | Equipment Install and Optimization | NA | No | 100% | 0 d | 155 d | 2006-08-01 08:00 | 2007-01-15 17:00 | 2006-08-01 08:00 | 2007-02-26 17:00
280 | 3 | No | MOB | MOB Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 8 d | 2007-01-16 08:00 | 2007-01-25 17:00 | 2007-02-27 08:00 | 2007-03-07 17:00
281 | 3 | No | MOB | Resolution of Open Items | NA | No | 100% | 0 d | 37 d | 2007-01-26 08:00 | 2007-03-22 17:00 | 2007-03-08 08:00 | 2007-04-26 17:00
282 | 3 | No | MOB | MOB CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-03-22 17:00 | 2007-03-22 17:00 | 2007-04-26 17:00 | 2007-04-26 17:00
283 | 3 | No | MOB | MOB IOC Readiness Phase 1 (thru Ph 1 Report Apvl) | NA | No | 100% | 0 d | 113 d | 2007-04-27 08:00 | 2007-09-24 17:00 | 2007-04-27 08:00 | 2007-09-14 17:00
284 | 3 | No | MOB | MOB IOC Readiness Phase 2 (thru Ph 2 Report Apvl) | NA | No | 100% | 0 d | 35 d | 2007-09-25 08:00 | 2007-11-05 17:00 | 2007-09-15 08:00 | 2007-10-19 17:00
285 | 3 | No | MOB | MOB IOC Readiness Phase 3 - before Flight Check | NA | No | 100% | 0 d | 25 d | 2007-11-06 08:00 | 2007-11-26 17:00 | 2007-10-20 08:00 | 2007-11-13 17:00
286 | 3 | No | MOB | MOB Flight Check | NA | No | 100% | 0 d | 1 d | 2007-07-13 08:00 | 2007-07-19 17:00 | 2007-11-14 08:00 | 2007-11-14 17:00
287 | 3 | No | MOB | MOB Initial Operating Capability (IOC) | 2008-01-31 17:00 | No | 100% | 0 d | 0 d | 2007-07-19 17:00 | 2007-07-19 17:00 | 2007-11-28 17:00 | 2007-11-28 17:00
288 | 3 | No | MOB | Operational Suitability Demonstration (OSD) | NA | No | 0% | 75 d | 49 d | 2007-07-20 08:00 | 2007-09-13 17:00 | 2007-11-29 08:00 | 2008-01-16 17:00
289 | 3 | No | MOB | MOB Operational Readiness Date (ORD)/Commissioning | 2008-03-31 17:00 | No | 0% | 75 d | 0 d | 2007-09-13 17:00 | 2007-09-13 17:00 | 2008-01-16 17:00 | 2008-01-16 17:00
290 | 3 | No | MOB | MOB Site Dismantle/Deactivation Planning | NA | No | 89% | 1035 d | 435 d | 2007-09-14 08:00 | 2008-06-19 17:00 | 2006-10-02 08:00 | 2008-02-27 17:00
291 | 3 | No | MOB | MOB Start Dismantle/Deactivate | NA | No | 0% | 1035 d | 0 d | 2008-06-19 17:00 | 2008-06-19 17:00 | 2008-02-28 17:00 | 2008-02-28 17:00
292 | 3 | No | MOB | MOB Dismantle/Deactivate | NA | No | 0% | 1035 d | 63 d | 2008-06-20 08:00 | 2008-08-14 17:00 | 2008-02-28 08:00 | 2008-04-30 17:00
293 | 3 | No | MOB | MOB Complete Real Estate Transfer | NA | No | 0% | 1035 d | 181 d | 2008-06-20 08:00 | 2008-08-14 17:00 | 2008-05-01 08:00 | 2008-10-28 17:00
294 | 3 | No | MOB | MOB Complete (Latest Finish) | NA | No | 0% | 1035 d | 0 d | 2008-12-31 17:00 | 2008-12-31 17:00 | 2008-10-28 17:00 | 2008-10-28 17:00
295 | 2 | Yes | YNG | Youngstown, OH (YNG) | NA | No | 64% | 370 d | 1837 d | 2003-03-27 08:00 | 2008-03-28 17:00 | 2003-03-27 08:00 | 2010-03-29 17:00
296 | 3 | No | YNG | YNG Environmental Studies | NA | No | 100% | 0 d | 410 d | 2003-03-27 08:00 | 2004-10-20 17:00 | 2003-03-27 08:00 | 2004-10-20 17:00
297 | 3 | No | YNG | YNG Real Estate Acquisition | NA | No | 100% | 0 d | 147 d | 2004-07-30 08:00 | 2005-02-21 17:00 | 2004-07-30 08:00 | 2005-02-21 17:00
298 | 3 | No | YNG | YNG Site Construction | NA | No | 100% | 0 d | 131 d | 2005-10-13 08:00 | 2006-04-13 17:00 | 2005-10-13 08:00 | 2006-04-13 17:00
299 | 3 | No | YNG | YNG Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2006-06-29 08:00 | 2006-06-29 08:00 | 2006-06-29 08:00 | 2006-06-29 08:00
300 | 3 | No | YNG | Equipment Install and Optimization | NA | No | 100% | 0 d | 132 d | 2006-07-14 08:00 | 2007-02-01 17:00 | 2006-06-29 08:00 | 2006-12-25 17:00
301 | 3 | No | YNG | YNG Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 9 d | 2007-02-02 08:00 | 2007-02-15 17:00 | 2007-02-06 08:00 | 2007-02-16 17:00
302 | 3 | No | YNG | Resolution of Open Items | NA | No | 100% | 0 d | 8 d | 2007-02-16 08:00 | 2007-04-12 17:00 | 2007-02-19 08:00 | 2007-02-27 17:00
303 | 3 | No | YNG | YNG CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-04-12 17:00 | 2007-04-12 17:00 | 2007-02-27 17:00 | 2007-02-27 17:00
304 | 3 | No | YNG | YNG FAA Optimization | NA | No | 100% | 0 d | 73 d | 2007-04-13 08:00 | 2007-06-21 17:00 | 2007-02-28 08:00 | 2007-06-06 17:00
305 | 3 | No | YNG | YNG Field Familiarization | NA | No | 100% | 0 d | 39 d | 2007-06-22 08:00 | 2007-08-16 17:00 | 2007-06-07 08:00 | 2007-07-31 17:00
306 | 3 | No | YNG | YNG Flight Check | NA | No | 100% | 0 d | 2 d | 2007-08-17 08:00 | 2007-08-23 17:00 | 2007-08-01 08:00 | 2007-08-02 17:00
307 | 3 | No | YNG | YNG Coverage Issue Resolution | NA | No | 88% | 580 d | 170 d | 2007-08-03 08:00 | 2008-01-31 17:00 | 2007-08-03 08:00 | 2008-01-19 17:00
308 | 3 | No | YNG | YNG Initial Operating Capability (IOC) | NA | No | 0% | 580 d | 0 d | 2007-08-23 17:00 | 2007-08-23 17:00 | 2008-01-19 17:00 | 2008-01-19 17:00
309 | 3 | No | YNG | Operational Suitability Demonstration (OSD) | NA | No | 0% | 580 d | 40 d | 2007-08-24 08:00 | 2007-10-25 17:00 | 2008-01-20 08:00 | 2008-02-28 17:00
310 | 3 | No | YNG | YNG Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 580 d | 0 d | 2007-10-25 17:00 | 2007-10-25 17:00 | 2008-02-28 17:00 | 2008-02-28 17:00
311 | 3 | No | YNG | YNG Site Dismantle/Deactivation Planning | NA | No | 43% | 518 d | 890 d | 2007-10-26 08:00 | 2007-12-20 17:00 | 2006-11-15 08:00 | 2009-06-29 17:00
312 | 3 | No | YNG | YNG Start Dismantle/Deactivate | NA | No | 0% | 518 d | 0 d | 2007-12-20 17:00 | 2007-12-20 17:00 | 2009-06-30 17:00 | 2009-06-30 17:00
313 | 3 | No | YNG | YNG Dismantle/Deactivate | NA | No | 0% | 518 d | 91 d | 2007-12-21 08:00 | 2008-02-14 17:00 | 2009-06-30 08:00 | 2009-09-28 17:00
314 | 3 | No | YNG | YNG Complete Real Estate Transfer | NA | No | 0% | 518 d | 182 d | 2007-12-21 08:00 | 2008-02-14 17:00 | 2009-09-29 08:00 | 2010-03-29 17:00
315 | 3 | No | YNG | YNG Complete (Latest Finish) | NA | No | 0% | 518 d | 0 d | 2008-03-28 17:00 | 2008-03-28 17:00 | 2010-03-29 17:00 | 2010-03-29 17:00
316 | 2 | Yes | LIT | Little Rock, AR (LIT) | NA | No | 67% | 676 d | 758 d | 2006-03-15 08:00 | 2009-03-31 17:00 | 2006-03-14 08:00 | 2009-01-24 17:00
317 | 3 | No | LIT | LIT Site Construction | NA | No | 100% | 0 d | 165 d | 2006-03-15 08:00 | 2006-12-04 17:00 | 2006-03-14 08:00 | 2006-10-31 17:00
318 | 3 | No | LIT | LIT Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2006-12-05 08:00 | 2006-12-11 17:00 | 2006-10-31 08:00 | 2006-10-31 08:00
319 | 3 | No | LIT | Equipment Install and Optimization | NA | No | 100% | 0 d | 117 d | 2006-12-12 08:00 | 2007-02-05 17:00 | 2006-10-31 08:00 | 2007-04-02 17:00
320 | 3 | No | LIT | LIT Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 9 d | 2007-02-06 08:00 | 2007-02-19 17:00 | 2007-04-03 08:00 | 2007-04-13 17:00
321 | 3 | No | LIT | Resolution of Open Items | NA | No | 100% | 0 d | 12 d | 2007-02-20 08:00 | 2007-05-14 17:00 | 2007-04-16 08:00 | 2007-05-01 17:00
322 | 3 | No | LIT | LIT CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-05-14 17:00 | 2007-05-14 17:00 | 2007-05-01 17:00 | 2007-05-01 17:00
323 | 3 | No | LIT | LIT IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 100% | 0 d | 82 d | 2007-05-02 08:00 | 2007-08-17 17:00 | 2007-05-02 08:00 | 2007-08-17 17:00
324 | 3 | No | LIT | LIT IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 100% | 0 d | 44 d | 2007-08-18 08:00 | 2007-09-21 17:00 | 2007-08-18 08:00 | 2007-09-30 17:00
325 | 3 | No | LIT | LIT IOC Readiness Phase 3 (before Flight Check) | NA | No | 100% | 0 d | 0 d | 2007-09-22 08:00 | 2007-09-23 17:00 | 2007-09-25 17:00 | 2007-09-25 17:00
326 | 3 | No | LIT | LIT Flight Check | NA | No | 100% | 0 d | 1 d | 2007-10-02 08:00 | 2007-10-08 17:00 | 2007-09-25 08:00 | 2007-09-25 17:00
327 | 3 | No | LIT | LIT Initial Operating Capability (IOC) | 2007-12-31 17:00 | No | 100% | 0 d | 0 d | 2007-10-08 17:00 | 2007-10-08 17:00 | 2007-10-03 17:00 | 2007-10-03 17:00
328 | 3 | No | LIT | Operational Suitability Demonstration (OSD) | NA | No | 74% | 0 d | 119 d | 2007-10-09 08:00 | 2007-12-10 17:00 | 2007-10-04 08:00 | 2008-01-30 17:00
329 | 3 | No | LIT | LIT Operational Readiness Date (ORD)/Commissioning | 2008-01-31 17:00 | Yes | 0% | 0 d | 0 d | 2007-12-10 17:00 | 2007-12-10 17:00 | 2008-01-31 17:00 | 2008-01-31 17:00
330 | 3 | No | LIT | LIT Site Dismantle/Deactivation Planning | NA | No | 75% | 61 d | 416 d | 2007-12-11 08:00 | 2008-05-26 17:00 | 2007-01-15 08:00 | 2008-04-27 17:00
331 | 3 | No | LIT | LIT Start Dismantle/Deactivate | 2008-06-30 17:00 | No | 0% | 61 d | 0 d | 2008-05-26 17:00 | 2008-05-26 17:00 | 2008-04-30 17:00 | 2008-04-30 17:00
332 | 3 | No | LIT | LIT Dismantle/Deactivate | NA | No | 0% | 947 d | 88 d | 2008-05-27 08:00 | 2008-07-21 17:00 | 2008-04-30 08:00 | 2008-07-26 17:00
333 | 3 | No | LIT | LIT Complete Real Estate Transfer | NA | No | 0% | 947 d | 182 d | 2008-05-27 08:00 | 2008-07-21 17:00 | 2008-07-27 08:00 | 2009-01-24 17:00
334 | 3 | No | LIT | LIT Complete (Latest Finish) | NA | No | 0% | 947 d | 0 d | 2009-03-31 17:00 | 2009-03-31 17:00 | 2009-01-24 17:00 | 2009-01-24 17:00
335 | 2 | Yes | CMI | Champaign, IL (CMI) | NA | No | 43% | 501 d | 934 d | 2006-03-13 08:00 | 2008-12-31 17:00 | 2006-03-13 08:00 | 2009-09-26 17:00
336 | 3 | No | CMI | CMI Equipment Delivered to Site | NA | No | 100% | 0 d | 41 d | 2006-03-13 08:00 | 2006-05-08 17:00 | 2006-03-13 08:00 | 2006-05-08 17:00
337 | 3 | No | CMI | Equipment Install and Optimization | NA | No | 100% | 0 d | 43 d | 2006-05-09 08:00 | 2006-10-23 17:00 | 2006-07-03 08:00 | 2006-08-30 17:00
338 | 3 | No | CMI | CMI Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 10 d | 2006-10-24 08:00 | 2006-11-13 17:00 | 2007-03-27 08:00 | 2007-04-06 17:00
339 | 3 | No | CMI | Resolution of Open Items | NA | No | 100% | 0 d | 21 d | 2006-11-14 08:00 | 2007-02-05 17:00 | 2007-04-09 08:00 | 2007-05-07 17:00
340 | 3 | No | CMI | CMI CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-02-05 17:00 | 2007-02-05 17:00 | 2007-05-08 17:00 | 2007-05-08 17:00
341 | 3 | No | AVP | CMI IOC Readiness Phase 1 (thru Ph 1 Report Apvl) | NA | No | 100% | 0 d | 24 d | 2007-05-09 08:00 | 2007-11-16 17:00 | 2007-10-17 08:00 | 2007-11-09 17:00
342 | 3 | No | CMI | CMI IOC Readiness Phase 2 (thru Ph 2 Report Apvl) | NA | No | 100% | 0 d | 28 d | 2007-11-17 08:00 | 2007-12-21 17:00 | 2007-11-10 08:00 | 2007-12-07 17:00
343 | 3 | No | CMI | CMI IOC Readiness Phase 3 - before Flight Check | NA | No | 43% | 54 d | 53 d | 2007-12-22 08:00 | 2008-01-15 17:00 | 2007-12-08 08:00 | 2008-01-29 17:00
344 | 3 | No | CMI | CMI Flight Check | NA | No | 0% | 54 d | 2 d | 2007-06-26 08:00 | 2007-07-02 17:00 | 2008-01-30 08:00 | 2008-01-31 17:00
345 | 3 | No | CMI | CMI Initial Operating Capability (IOC) | 2008-03-31 17:00 | No | 0% | 54 d | 0 d | 2007-07-02 17:00 | 2007-07-02 17:00 | 2008-02-06 17:00 | 2008-02-06 17:00
346 | 3 | No | CMI | Operational Suitability Demonstration (OSD) | NA | No | 0% | 85 d | 30 d | 2007-07-03 08:00 | 2007-09-24 17:00 | 2008-02-07 08:00 | 2008-03-07 17:00
347 | 3 | No | CMI | CMI Operational Readiness Date (ORD)/Commissioning | 2008-05-31 17:00 | No | 0% | 85 d | 0 d | 2007-09-24 17:00 | 2007-09-24 17:00 | 2008-03-07 17:00 | 2008-03-07 17:00
348 | 3 | No | CMI | CMI Site Dismantle/Deactivation Planning | NA | No | 56% | 0 d | 571 d | 2007-09-25 08:00 | 2008-06-30 17:00 | 2007-01-15 08:00 | 2008-09-29 17:00
349 | 3 | No | CMI | CMI Start Dismantle/Deactivate | NA | No | 0% | 702 d | 0 d | 2008-06-30 17:00 | 2008-06-30 17:00 | 2008-09-30 17:00 | 2008-09-30 17:00
350 | 3 | No | CMI | CMI Dismantle/Deactivate | NA | No | 0% | 702 d | 180 d | 2008-07-01 08:00 | 2008-08-25 17:00 | 2008-09-30 08:00 | 2009-03-28 17:00
351 | 3 | No | CMI | CMI Complete Real Estate Transfer | NA | No | 0% | 702 d | 182 d | 2008-07-01 08:00 | 2008-08-25 17:00 | 2009-03-29 08:00 | 2009-09-26 17:00
352 | 3 | No | CMI | CMI Complete (Latest Finish) | NA | No | 0% | 702 d | 0 d | 2008-12-31 17:00 | 2008-12-31 17:00 | 2009-09-26 17:00 | 2009-09-26 17:00
353 | 2 | Yes | LEX | Lexington, KY (LEX) | NA | No | 60% | 481 d | 967 d | 2006-02-22 08:00 | 2008-09-30 17:00 | 2006-02-22 08:00 | 2009-10-24 17:00
354 | 3 | No | LEX | LEX Site Construction | NA | No | 100% | 0 d | 142 d | 2006-02-22 08:00 | 2006-11-13 17:00 | 2006-02-22 08:00 | 2006-09-07 17:00
355 | 3 | No | LEX | LEX Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2006-09-11 08:00 | 2006-09-11 08:00 | 2006-09-11 08:00 | 2006-09-11 08:00
356 | 3 | No | LEX | LEX Equipment Install and Optimization | NA | No | 100% | 0 d | 178 d | 2006-09-11 08:00 | 2006-12-29 17:00 | 2006-09-11 08:00 | 2007-05-07 17:00
357 | 3 | No | LEX | LEX Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 7 d | 2007-01-01 08:00 | 2007-01-12 17:00 | 2007-05-08 08:00 | 2007-05-16 17:00
358 | 3 | No | LEX | LEX Resolution of Open Items | NA | No | 100% | 0 d | 27 d | 2007-01-15 08:00 | 2007-03-23 17:00 | 2007-05-17 08:00 | 2007-06-22 17:00
359 | 3 | No | LEX | LEX CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-03-23 17:00 | 2007-03-23 17:00 | 2007-06-22 17:00 | 2007-06-22 17:00
360 | 3 | No | LEX | LEX IOC Readiness Phase 1 (thru Ph 1 Report Apvl) | NA | No | 100% | 0 d | 33 d | 2007-06-22 08:00 | 2007-11-16 17:00 | 2007-10-15 08:00 | 2007-11-16 17:00
361 | 3 | No | LEX | LEX IOC Readiness Phase 2 (thru Ph 2 Report Apvl) | NA | No | 70% | 292 d | 63 d | 2007-11-17 08:00 | 2007-12-21 17:00 | 2007-11-17 08:00 | 2008-01-18 17:00
362 | 3 | No | LEX | LEX IOC Readiness Phase 3 - before Flight Check | NA | No | 0% | 292 d | 4 d | 2007-12-22 08:00 | 2008-01-22 17:00 | 2008-01-19 08:00 | 2008-01-22 17:00
363 | 3 | No | LEX | LEX Flight Check | NA | No | 0% | 292 d | 2 d | 2007-08-27 08:00 | 2007-08-31 17:00 | 2008-01-23 08:00 | 2008-01-24 17:00
364 | 3 | No | LEX | LEX Initial Operating Capability (IOC) | NA | No | 0% | 292 d | 0 d | 2007-08-31 17:00 | 2007-08-31 17:00 | 2008-02-14 17:00 | 2008-02-14 17:00
365 | 3 | No | LEX | LEX Operational Suitability Demonstration (OSD) | NA | No | 0% | 292 d | 29 d | 2007-09-03 08:00 | 2007-11-02 17:00 | 2008-02-15 08:00 | 2008-03-14 17:00
366 | 3 | No | LEX | LEX Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 292 d | 0 d | 2007-11-02 17:00 | 2007-11-02 17:00 | 2008-03-14 17:00 | 2008-03-14 17:00
367 | 3 | No | LEX | LEX Site Dismantle/Deactivation Planning | NA | No | 69% | 62 d | 838 d | 2007-11-05 08:00 | 2008-04-18 17:00 | 2006-02-22 08:00 | 2008-10-29 17:00
368 | 3 | No | LEX | LEX Start Dismantle/Deactivate | 2008-12-31 17:00 | No | 0% | 62 d | 0 d | 2008-04-18 17:00 | 2008-04-18 17:00 | 2008-10-30 17:00 | 2008-10-30 17:00
369 | 3 | No | LEX | LEX Dismantle/Deactivate | NA | No | 0% | 674 d | 180 d | 2008-04-21 08:00 | 2008-06-13 17:00 | 2008-10-30 08:00 | 2009-04-27 17:00
370 | 3 | No | LEX | LEX Complete Real Estate Transfer | NA | No | 0% | 674 d | 180 d | 2008-04-21 08:00 | 2008-06-13 17:00 | 2009-04-28 08:00 | 2009-10-24 17:00
371 | 3 | No | LEX | LEX Complete (Latest Finish) | NA | No | 0% | 674 d | 0 d | 2008-09-30 17:00 | 2008-09-30 17:00 | 2009-10-24 17:00 | 2009-10-24 17:00
372 | 2 | Yes | MAF | Midland, TX (MAF) | NA | No | 52% | 456 d | 1079 d | 2006-04-26 08:00 | 2009-05-29 17:00 | 2005-10-24 08:00 | 2009-11-28 17:00
373 | 3 | No | MAF | MAF Site Construction | NA | No | 100% | 0 d | 459 d | 2006-04-26 08:00 | 2007-01-15 17:00 | 2005-10-24 08:00 | 2007-07-17 17:00
374 | 3 | No | MAF | MAF Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2007-01-16 08:00 | 2007-01-22 17:00 | 2007-01-31 17:00 | 2007-01-31 17:00
375 | 3 | No | MAF | MAF Equipment Install and Optimization | NA | No | 100% | 0 d | 87 d | 2007-01-23 08:00 | 2007-03-19 17:00 | 2007-02-01 08:00 | 2007-05-29 17:00
376 | 3 | No | MAF | MAF Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 10 d | 2007-03-20 08:00 | 2007-04-02 17:00 | 2007-05-30 08:00 | 2007-06-12 17:00
377 | 3 | No | MAF | MAF Resolution of Open Items | NA | No | 100% | 0 d | 14 d | 2007-04-03 08:00 | 2007-06-25 17:00 | 2007-06-13 08:00 | 2007-07-02 17:00
378 | 3 | No | MAF | MAF CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-06-25 17:00 | 2007-06-25 17:00 | 2007-07-02 17:00 | 2007-07-02 17:00
379 | 3 | No | MAF | MAF IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 91% | 117 d | 192 d | 2007-07-03 08:00 | 2008-02-15 17:00 | 2007-07-03 08:00 | 2008-01-18 17:00
380 | 3 | No | MAF | MAF IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 117 d | 21 d | 2008-02-16 08:00 | 2008-03-21 17:00 | 2008-01-19 08:00 | 2008-02-08 17:00
381 | 3 | No | MAF | MAF IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 117 d | 18 d | 2008-03-22 08:00 | 2008-04-10 17:00 | 2008-02-09 08:00 | 2008-02-26 17:00
382 | 3 | No | MAF | MAF Flight Check | NA | No | 0% | 117 d | 2 d | 2007-12-11 08:00 | 2007-12-17 17:00 | 2008-02-27 08:00 | 2008-02-28 17:00
383 | 3 | No | MAF | MAF Initial Operating Capability (IOC) | 2008-06-30 17:00 | No | 0% | 117 d | 0 d | 2007-12-17 17:00 | 2007-12-17 17:00 | 2008-03-05 17:00 | 2008-03-05 17:00
384 | 3 | No | MAF | MAF Operational Suitability Demonstration (OSD) | NA | No | 0% | 118 d | 30 d | 2007-12-18 08:00 | 2008-02-25 17:00 | 2008-03-06 08:00 | 2008-04-04 17:00
385 | 3 | No | MAF | MAF Operational Readiness Date (ORD)/Commissioning | 2008-07-31 17:00 | No | 0% | 118 d | 0 d | 2008-02-25 17:00 | 2008-02-25 17:00 | 2008-04-04 17:00 | 2008-04-04 17:00
386 | 3 | No | MAF | MAF Site Dismantle/Deactivation Planning | NA | No | 0% | 639 d | 239 d | 2008-02-26 08:00 | 2008-08-11 17:00 | 2008-04-05 08:00 | 2008-11-29 17:00
387 | 3 | No | MAF | MAF Start Dismantle/Deactivate | NA | No | 0% | 639 d | 0 d | 2008-08-11 17:00 | 2008-08-11 17:00 | 2008-11-30 17:00 | 2008-11-30 17:00
388 | 3 | No | MAF | MAF Dismantle/Deactivate | NA | No | 0% | 639 d | 182 d | 2008-08-12 08:00 | 2008-10-06 17:00 | 2008-11-30 08:00 | 2009-05-30 17:00
389 | 3 | No | MAF | MAF Complete Real Estate Transfer | NA | No | 0% | 639 d | 182 d | 2008-08-12 08:00 | 2008-10-06 17:00 | 2009-05-31 08:00 | 2009-11-28 17:00
390 | 3 | No | MAF | MAF Complete (Latest Finish) | NA | No | 0% | 639 d | 0 d | 2009-05-29 17:00 | 2009-05-29 17:00 | 2009-11-28 17:00 | 2009-11-28 17:00
391 | 2 | Yes | RDG | Reading, PA (RDG) | NA | No | 39% | 239 d | 1182 d | 2006-06-05 08:00 | 2009-07-31 17:00 | 2006-03-31 08:00 | 2010-09-28 17:00
392 | 3 | No | RDG | Construction Contract Awarded | NA | No | 100% | 0 d | 0 d | 2006-06-05 08:00 | 2006-06-05 08:00 | 2006-03-31 08:00 | 2006-03-31 08:00
393 | 3 | No | RDG | RDG Site Construction | NA | No | 100% | 0 d | 335 d | 2006-10-02 08:00 | 2007-06-22 17:00 | 2006-03-31 08:00 | 2007-07-03 17:00
394 | 3 | No | RDG | RDG Equipment Delivered to Site | NA | No | 100% | 0 d | 1 d | 2007-06-25 08:00 | 2007-06-29 17:00 | 2007-01-11 08:00 | 2007-01-11 17:00
395 | 3 | No | RDG | Equipment Install and Optimization | NA | No | 100% | 0 d | 141 d | 2007-07-02 08:00 | 2007-09-21 17:00 | 2007-01-12 08:00 | 2007-07-24 17:00
396 | 3 | No | RDG | RDG Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 6 d | 2007-09-24 08:00 | 2007-10-05 17:00 | 2007-07-25 08:00 | 2007-08-01 17:00
397 | 3 | No | RDG | Resolution of Open Items | NA | No | 100% | 0 d | 40 d | 2007-10-08 08:00 | 2007-11-30 17:00 | 2007-08-02 08:00 | 2007-09-10 17:00
398 | 3 | No | RDG | RDG CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-11-30 17:00 | 2007-11-30 17:00 | 2007-09-10 17:00 | 2007-09-10 17:00
399 | 3 | No | RDG | RDG IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 74% | 61 d | 151 d | 2007-09-08 08:00 | 2008-02-08 17:00 | 2007-09-11 08:00 | 2008-02-08 17:00
400 | 3 | No | RDG | RDG IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 61 d | 35 d | 2008-02-09 08:00 | 2008-03-14 17:00 | 2008-02-09 08:00 | 2008-03-14 17:00
401 | 3 | No | RDG | RDG IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 61 d | 18 d | 2008-03-15 08:00 | 2008-04-03 17:00 | 2008-03-15 08:00 | 2008-04-01 17:00
402 | 3 | No | RDG | RDG Flight Check | NA | No | 0% | 61 d | 2 d | 2008-04-21 08:00 | 2008-04-25 17:00 | 2008-04-02 08:00 | 2008-04-03 17:00
403 | 3 | No | RDG | RDG Initial Operating Capability (IOC) | 2008-06-30 17:00 | No | 0% | 61 d | 0 d | 2008-04-25 17:00 | 2008-04-25 17:00 | 2008-04-09 17:00 | 2008-04-09 17:00
404 | 3 | No | RDG | Operational Suitability Demonstration (OSD) | NA | No | 0% | 61 d | 30 d | 2008-04-28 08:00 | 2008-07-04 17:00 | 2008-04-10 08:00 | 2008-05-09 17:00
405 | 3 | No | RDG | RDG Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 61 d | 0 d | 2008-07-04 17:00 | 2008-07-04 17:00 | 2008-05-09 17:00 | 2008-05-09 17:00
406 | 3 | No | RDG | RDG Site Dismantle/Deactivation Planning | NA | No | 0% | 61 d | 508 d | 2008-07-07 08:00 | 2008-12-19 17:00 | 2008-05-10 08:00 | 2009-09-29 17:00
407 | 3 | No | RDG | RDG Start Dismantle/Deactivate | 2009-11-30 17:00 | No | 0% | 61 d | 0 d | 2008-12-19 17:00 | 2008-12-19 17:00 | 2009-09-30 17:00 | 2009-09-30 17:00
408 | 3 | No | RDG | RDG Dismantle/Deactivate | NA | No | 0% | 335 d | 182 d | 2008-12-22 08:00 | 2009-02-13 17:00 | 2009-09-30 08:00 | 2010-03-30 17:00
409 | 3 | No | RDG | RDG Complete Real Estate Transfer | NA | No | 0% | 335 d | 182 d | 2008-12-22 08:00 | 2009-02-13 17:00 | 2010-03-31 08:00 | 2010-09-28 17:00
410 | 3 | No | RDG | RDG Complete (Latest Finish) | NA | No | 0% | 335 d | 0 d | 2009-07-31 17:00 | 2009-07-31 17:00 | 2010-09-28 17:00 | 2010-09-28 17:00
411 | 2 | Yes | SUX | Sioux City, IA (SUX) | NA | No | 42% | 348 d | 1064 d | 2006-04-13 08:00 | 2009-08-31 17:00 | 2006-04-13 08:00 | 2010-04-28 17:00
412 | 3 | No | SUX | Construction Contract Awarded | NA | No | 100% | 0 d | 0 d | 2006-04-13 08:00 | 2006-04-13 08:00 | 2006-04-13 08:00 | 2006-04-13 08:00
413 | 3 | No | SUX | SUX Site Construction | NA | No | 100% | 0 d | 412 d | 2006-10-02 08:00 | 2007-07-06 17:00 | 2006-04-13 08:00 | 2007-10-05 17:00
414 | 3 | No | SUX | SUX Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2007-07-06 17:00 | 2007-07-06 17:00 | 2007-01-12 08:00 | 2007-01-12 08:00
415 | 3 | No | SUX | Equipment Install and Optimization | NA | No | 100% | 0 d | 150 d | 2007-07-09 08:00 | 2007-09-28 17:00 | 2007-01-12 08:00 | 2007-08-04 17:00
416 | 3 | No | SUX | SUX Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 7 d | 2007-10-01 08:00 | 2007-10-12 17:00 | 2007-08-07 08:00 | 2007-08-15 17:00
417 | 3 | No | SUX | Resolution of Open Items | NA | No | 100% | 0 d | 76 d | 2007-10-15 08:00 | 2007-12-07 17:00 | 2007-08-16 08:00 | 2007-10-30 17:00
418 | 3 | No | SUX | SUX CAI/DD250 Signed | 2007-12-31 17:00 | No | 100% | 0 d | 0 d | 2007-12-07 17:00 | 2007-12-07 17:00 | 2007-10-30 17:00 | 2007-10-30 17:00
419 | 3 | No | SUX | SUX IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 61 d | 125 d | 2007-10-21 08:00 | 2008-04-18 17:00 | 2007-11-04 08:00 | 2008-03-07 17:00
420 | 3 | No | SUX | SUX IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 61 d | 28 d | 2008-04-19 08:00 | 2008-05-23 17:00 | 2008-03-08 08:00 | 2008-04-04 17:00
421 | 3 | No | SUX | SUX IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 61 d | 11 d | 2008-05-24 08:00 | 2008-06-12 17:00 | 2008-04-05 08:00 | 2008-04-15 17:00
422 | 3 | No | SUX | SUX Flight Check | NA | No | 0% | 61 d | 2 d | 2008-05-26 08:00 | 2008-05-30 17:00 | 2008-04-16 08:00 | 2008-04-17 17:00
423 | 3 | No | SUX | SUX Initial Operating Capability (IOC) | 2008-08-31 17:00 | No | 0% | 61 d | 0 d | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-04-30 17:00 | 2008-04-30 17:00
424 | 3 | No | SUX | Operational Suitability Demonstration (OSD) | NA | No | 0% | 61 d | 30 d | 2008-06-02 08:00 | 2008-08-08 17:00 | 2008-05-01 08:00 | 2008-05-30 17:00
425 | 3 | No | SUX | SUX Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 61 d | 0 d | 2008-08-08 17:00 | 2008-08-08 17:00 | 2008-05-30 17:00 | 2008-05-30 17:00
426 | 3 | No | SUX | SUX Site Dismantle/Deactivation Planning | NA | No | 0% | 61 d | 334 d | 2008-08-11 08:00 | 2009-01-23 17:00 | 2008-05-31 08:00 | 2009-04-29 17:00
427 | 3 | No | SUX | SUX Start Dismantle/Deactivate | 2009-06-30 17:00 | No | 0% | 61 d | 0 d | 2009-01-23 17:00 | 2009-01-23 17:00 | 2009-04-30 17:00 | 2009-04-30 17:00
428 | 3 | No | SUX | SUX Dismantle/Deactivate | NA | No | 0% | 488 d | 182 d | 2009-01-26 08:00 | 2009-03-20 17:00 | 2009-04-30 08:00 | 2009-10-28 17:00
429 | 3 | No | SUX | SUX Complete Real Estate Transfer | NA | No | 0% | 488 d | 182 d | 2009-01-26 08:00 | 2009-03-20 17:00 | 2009-10-29 08:00 | 2010-04-28 17:00
430 | 3 | No | SUX | SUX Complete (Latest Finish) | NA | No | 0% | 488 d | 0 d | 2009-08-31 17:00 | 2009-08-31 17:00 | 2010-04-28 17:00 | 2010-04-28 17:00
431 | 2 | Yes | AMA | Amarillo, TX (AMA) | NA | No | 42% | 326 d | 1102 d | 2006-03-22 08:00 | 2009-03-31 17:00 | 2006-03-22 08:00 | 2010-05-30 17:00
432 | 3 | No | AMA | AMA Site Construction | NA | No | 100% | 0 d | 160 d | 2006-03-22 08:00 | 2006-12-11 17:00 | 2006-03-22 08:00 | 2006-10-31 17:00
433 | 3 | No | AMA | AMA Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2006-12-12 08:00 | 2006-12-18 17:00 | 2006-10-31 17:00 | 2006-10-31 17:00
434 | 3 | No | AMA | Equipment Install and Optimization | NA | No | 100% | 0 d | 163 d | 2006-12-19 08:00 | 2007-02-12 17:00 | 2006-09-18 08:00 | 2007-04-23 17:00
435 | 3 | No | AMA | AMA Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 9 d | 2007-02-13 08:00 | 2007-02-26 17:00 | 2007-04-24 08:00 | 2007-05-04 17:00
436 | 3 | No | AMA | AMA Resolution of Open Items | NA | No | 100% | 0 d | 34 d | 2007-02-27 08:00 | 2007-05-21 17:00 | 2007-05-07 08:00 | 2007-06-21 17:00
437 | 3 | No | AMA | AMA CAI/DD250 Signed | NA | No | 100% | 0 d | 0 d | 2007-05-21 17:00 | 2007-05-21 17:00 | 2007-06-21 17:00 | 2007-06-21 17:00
438 | 3 | No | AMA | AMA IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 67% | 393 d | 276 d | 2007-06-22 08:00 | 2008-06-20 17:00 | 2007-06-22 08:00 | 2008-04-04 17:00
439 | 3 | No | AMA | AMA IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 393 d | 35 d | 2008-06-21 08:00 | 2008-07-25 17:00 | 2008-04-05 08:00 | 2008-05-09 17:00
440 | 3 | No | AMA | AMA IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 393 d | 9 d | 2008-07-26 08:00 | 2008-08-15 17:00 | 2008-05-10 08:00 | 2008-05-18 17:00
441 | 3 | No | AMA | AMA Flight Check | NA | No | 0% | 393 d | 2 d | 2007-10-09 08:00 | 2007-10-15 17:00 | 2008-05-19 08:00 | 2008-05-20 17:00
442 | 3 | No | AMA | AMA Initial Operating Capability (IOC) | NA | No | 0% | 393 d | 0 d | 2007-10-15 17:00 | 2007-10-15 17:00 | 2008-06-04 17:00 | 2008-06-04 17:00
443 | 3 | No | AMA | Operational Suitability Demonstration (OSD) | NA | No | 0% | 393 d | 29 d | 2007-10-16 08:00 | 2007-12-17 17:00 | 2008-06-05 08:00 | 2008-07-03 17:00
444 | 3 | No | AMA | AMA Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 393 d | 0 d | 2007-12-17 17:00 | 2007-12-17 17:00 | 2008-07-03 17:00 | 2008-07-03 17:00
445 | 3 | No | AMA | AMA Site Dismantle/Deactivation Planning | NA | No | 29% | 0 d | 714 d | 2007-12-18 08:00 | 2008-06-02 17:00 | 2007-05-31 08:00 | 2009-05-31 17:00
446 | 3 | No | AMA | AMA Start Dismantle/Deactivate | 2009-07-31 17:00 | No | 0% | 61 d | 0 d | 2008-06-02 17:00 | 2008-06-02 17:00 | 2009-05-31 17:00 | 2009-05-31 17:00
447 | 3 | No | AMA | AMA Dismantle/Deactivate | NA | No | 0% | 456 d | 182 d | 2008-06-03 08:00 | 2008-07-28 17:00 | 2009-06-01 08:00 | 2009-11-29 17:00
448 | 3 | No | AMA | AMA Complete Real Estate Transfer | NA | No | 0% | 456 d | 182 d | 2008-06-03 08:00 | 2008-07-28 17:00 | 2009-11-30 08:00 | 2010-05-30 17:00
449 | 3 | No | AMA | AMA Complete (Latest Finish) | NA | No | 0% | 456 d | 0 d | 2009-03-31 17:00 | 2009-03-31 17:00 | 2010-05-30 17:00 | 2010-05-30 17:00
450 | 2 | Yes | SPI | Springfield, IL (SPI) | NA | No | 42% | 283 d | 1079 d | 2006-11-30 08:00 | 2009-10-30 17:00 | 2006-06-22 08:00 | 2010-07-28 17:00
451 | 3 | No | SPI | Construction Contract Awarded | NA | No | 100% | 0 d | 0 d | 2006-11-30 08:00 | 2006-11-30 08:00 | 2006-06-22 08:00 | 2006-06-22 08:00
452 | 3 | No | SPI | SPI Site Construction | NA | No | 100% | 0 d | 418 d | 2006-11-30 08:00 | 2007-08-08 17:00 | 2006-06-22 08:00 | 2007-11-30 17:00
453 | 3 | No | SPI | SPI Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2007-08-09 08:00 | 2007-08-15 17:00 | 2007-03-15 17:00 | 2007-03-15 17:00
454 | 3 | No | SPI | Equipment Install and Optimization | NA | No | 100% | 0 d | 182 d | 2007-08-16 08:00 | 2007-11-07 17:00 | 2007-03-16 08:00 | 2007-10-22 17:00
455 | 3 | No | SPI | SPI Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 8 d | 2007-11-08 08:00 | 2007-11-21 17:00 | 2007-10-23 08:00 | 2007-10-30 17:00
456 | 3 | No | SPI | Resolution of Open Items | NA | No | 100% | 0 d | 44 d | 2007-11-22 08:00 | 2008-01-16 17:00 | 2007-10-31 08:00 | 2007-12-13 17:00
457 | 3 | No | SPI | SPI CAI/DD250 Signed | 2008-02-29 17:00 | No | 100% | 0 d | 0 d | 2008-01-16 17:00 | 2008-01-16 17:00 | 2007-12-13 17:00 | 2007-12-13 17:00
458 | 3 | No | SPI | SPI IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 11% | 62 d | 131 d | 2008-01-07 08:00 | 2008-05-16 17:00 | 2007-12-17 08:00 | 2008-04-25 17:00
459 | 3 | No | SPI | SPI IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 62 d | 35 d | 2008-05-17 08:00 | 2008-06-20 17:00 | 2008-04-26 08:00 | 2008-05-30 17:00
460 | 3 | No | SPI | SPI IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 62 d | 18 d | 2008-06-21 08:00 | 2008-07-11 17:00 | 2008-05-31 08:00 | 2008-06-17 17:00
461 | 3 | No | SPI | SPI Flight Check | NA | No | 0% | 62 d | 2 d | 2008-06-05 08:00 | 2008-06-11 17:00 | 2008-06-18 08:00 | 2008-06-19 17:00
462 | 3 | No | SPI | SPI Initial Operating Capability (IOC) | 2008-08-31 17:00 | No | 0% | 62 d | 0 d | 2008-06-11 17:00 | 2008-06-11 17:00 | 2008-06-25 17:00 | 2008-06-25 17:00
463 | 3 | No | SPI | Operational Suitability Demonstration (OSD) | NA | No | 0% | 62 d | 30 d | 2008-06-12 08:00 | 2008-08-20 17:00 | 2008-06-26 08:00 | 2008-07-25 17:00
464 | 3 | No | SPI | SPI Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 62 d | 0 d | 2008-08-20 17:00 | 2008-08-20 17:00 | 2008-07-25 17:00 | 2008-07-25 17:00
465 | 3 | No | SPI | SPI Site Dismantle/Deactivation Planning | NA | No | 0% | 62 d | 369 d | 2008-08-21 08:00 | 2009-02-04 17:00 | 2008-07-26 08:00 | 2009-07-29 17:00
466 | 3 | No | SPI | SPI Start Dismantle/Deactivate | 2009-09-30 17:00 | No | 0% | 62 d | 0 d | 2009-02-04 17:00 | 2009-02-04 17:00 | 2009-07-30 17:00 | 2009-07-30 17:00
467 | 3 | No | SPI | SPI Dismantle/Deactivate | NA | No | 0% | 397 d | 182 d | 2009-02-05 08:00 | 2009-04-01 17:00 | 2009-07-30 08:00 | 2010-01-27 17:00
468 | 3 | No | SPI | SPI Complete Real Estate Transfer | NA | No | 0% | 397 d | 182 d | 2009-02-05 08:00 | 2009-04-01 17:00 | 2010-01-28 08:00 | 2010-07-28 17:00
469 | 3 | No | SPI | SPI Complete (Latest Finish) | NA | No | 0% | 397 d | 0 d | 2009-10-30 17:00 | 2009-10-30 17:00 | 2010-07-28 17:00 | 2010-07-28 17:00
470 | 2 | Yes | MRY | Monterey, CA (MRY) | NA | No | 62% | 391 d | 1808 d | 2003-04-08 08:00 | 2010-02-26 17:00 | 2003-04-08 08:00 | 2010-02-26 17:00
471 | 3 | No | MRY | MRY Environmental Studies | NA | No | 100% | 0 d | 844 d | 2003-04-08 08:00 | 2006-06-30 17:00 | 2003-04-08 08:00 | 2006-06-30 17:00
472 | 3 | No | MRY | MRY Real Estate Acquisition | NA | No | 100% | 0 d | 26 d | 2006-07-03 08:00 | 2007-01-26 17:00 | 2006-07-03 08:00 | 2006-08-07 17:00
473 | 3 | No | MRY | MRY Site Construction | NA | No | 100% | 0 d | 218 d | 2007-01-29 08:00 | 2007-11-30 17:00 | 2006-05-18 08:00 | 2007-03-09 17:00
474 | 3 | No | MRY | MRY Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2007-11-30 17:00 | 2007-11-30 17:00 | 2007-03-12 17:00 | 2007-03-12 17:00
475 | 3 | No | MRY | Equipment Install and Optimization | NA | No | 100% | 0 d | 220 d | 2007-12-03 08:00 | 2008-03-21 17:00 | 2007-03-13 08:00 | 2007-11-26 17:00
476 | 3 | No | MRY | MRY Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 9 d | 2008-03-24 08:00 | 2008-04-04 17:00 | 2007-11-27 08:00 | 2007-12-05 17:00
477 | 3 | No | MRY | Resolution of Open Items | NA | No | 0% | 61 d | 60 d | 2008-04-07 08:00 | 2008-05-30 17:00 | 2007-12-06 08:00 | 2008-02-03 17:00
478 | 3 | No | MRY | MRY CAI/DD250 Signed | NA | No | 0% | 61 d | 0 d | 2008-05-30 17:00 | 2008-05-30 17:00 | 2008-02-03 17:00 | 2008-02-03 17:00
479 | 3 | No | MRY | MRY IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 61 d | 96 d | 2008-01-16 08:00 | 2008-05-29 17:00 | 2008-02-04 08:00 | 2008-05-09 17:00
480 | 3 | No | MRY | MRY IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 61 d | 35 d | 2008-05-30 08:00 | 2008-07-02 17:00 | 2008-05-10 08:00 | 2008-06-13 17:00
481 | 3 | No | MRY | MRY IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 61 d | 18 d | 2008-07-03 08:00 | 2008-07-22 17:00 | 2008-06-14 08:00 | 2008-07-01 17:00
482 | 3 | No | MRY | MRY Flight Check | NA | No | 0% | 61 d | 2 d | 2008-10-20 08:00 | 2008-10-24 17:00 | 2008-07-02 08:00 | 2008-07-03 17:00
483 | 3 | No | MRY | MRY Initial Operating Capability (IOC) | NA | No | 0% | 61 d | 0 d | 2008-10-24 17:00 | 2008-10-24 17:00 | 2008-07-09 17:00 | 2008-07-09 17:00
484 | 3 | No | MRY | Operational Suitability Demonstration (OSD) | NA | No | 0% | 61 d | 30 d | 2008-10-27 08:00 | 2009-01-02 17:00 | 2008-07-10 08:00 | 2008-08-08 17:00
485 | 3 | No | MRY | MRY Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 61 d | 0 d | 2009-01-02 17:00 | 2009-01-02 17:00 | 2008-08-08 17:00 | 2008-08-08 17:00
486 | 3 | No | MRY | MRY Site Dismantle/Deactivation Planning | NA | No | 0% | 61 d | 203 d | 2009-01-05 08:00 | 2009-06-19 17:00 | 2008-08-09 08:00 | 2009-02-27 17:00
487 | 3 | No | MRY | MRY Start Dismantle/Deactivate | 2009-04-30 17:00 | No | 0% | 61 d | 0 d | 2009-06-19 17:00 | 2009-06-19 17:00 | 2009-02-28 17:00 | 2009-02-28 17:00
488 | 3 | No | MRY | MRY Dismantle/Deactivate | NA | No | 0% | 549 d | 182 d | 2009-06-22 08:00 | 2009-08-14 17:00 | 2009-02-28 08:00 | 2009-08-28 17:00
489 | 3 | No | MRY | MRY Complete Real Estate Transfer | NA | No | 0% | 549 d | 182 d | 2009-06-22 08:00 | 2009-08-14 17:00 | 2009-08-29 08:00 | 2010-02-26 17:00
490 | 3 | No | MRY | MRY Complete (Latest Finish) | NA | No | 0% | 549 d | 0 d | 2010-02-26 17:00 | 2010-02-26 17:00 | 2010-02-26 17:00 | 2010-02-26 17:00
491 | 2 | Yes | GPT | Gulfport, MS (GPT) | NA | No | 46% | 411 d | 1013 d | 2006-05-31 08:00 | 2009-09-30 17:00 | 2006-03-28 08:00 | 2010-01-29 17:00
492 | 3 | No | GPT | Construction Contract Awarded | NA | No | 100% | 0 d | 0 d | 2006-05-31 08:00 | 2006-05-31 08:00 | 2006-03-28 08:00 | 2006-03-28 08:00
493 | 3 | No | GPT | GPT Site Construction | NA | No | 100% | 0 d | 407 d | 2006-11-01 08:00 | 2007-08-07 17:00 | 2006-03-28 08:00 | 2007-10-08 17:00
494 | 3 | No | GPT | GPT Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2007-08-07 17:00 | 2007-08-07 17:00 | 2007-04-05 17:00 | 2007-04-05 17:00
495 | 3 | No | GPT | Equipment Install and Optimization | NA | No | 95% | 59 d | 250 d | 2007-08-08 08:00 | 2007-11-27 17:00 | 2007-04-06 08:00 | 2008-01-14 17:00
496 | 3 | No | GPT | GPT Site Acceptance Test (SAT) | NA | No | 0% | 59 d | 11 d | 2007-11-28 08:00 | 2007-12-11 17:00 | 2008-01-15 08:00 | 2008-01-25 17:00
497 | 3 | No | GPT | Resolution of Open Items | NA | No | 0% | 59 d | 34 d | 2007-12-12 08:00 | 2008-02-05 17:00 | 2008-01-26 08:00 | 2008-02-28 17:00
498 | 3 | No | GPT | GPT CAI/DD250 Signed | NA | No | 0% | 59 d | 0 d | 2008-02-05 17:00 | 2008-02-05 17:00 | 2008-02-28 17:00 | 2008-02-28 17:00
499 | 3 | No | GPT | GPT IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 59 d | 92 d | 2008-06-07 08:00 | 2008-07-11 17:00 | 2008-02-29 08:00 | 2008-05-30 17:00
500 | 3 | No | GPT | GPT IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 59 d | 34 d | 2008-07-12 08:00 | 2008-08-15 17:00 | 2008-05-31 08:00 | 2008-07-03 17:00
501 | 3 | No | GPT | GPT IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 59 d | 19 d | 2008-08-16 08:00 | 2008-09-04 17:00 | 2008-07-04 08:00 | 2008-07-22 17:00
502 | 3 | No | GPT | GPT Flight Check | NA | No | 0% | 59 d | 2 d | 2008-06-25 08:00 | 2008-07-01 17:00 | 2008-07-23 08:00 | 2008-07-24 17:00
503 | 3 | No | GPT | GPT Initial Operating Capability (IOC) | NA | No | 0% | 59 d | 0 d | 2008-07-01 17:00 | 2008-07-01 17:00 | 2008-07-30 17:00 | 2008-07-30 17:00
504 | 3 | No | GPT | Operational Suitability Demonstration (OSD) | NA | No | 0% | 59 d | 30 d | 2008-07-02 08:00 | 2008-09-09 17:00 | 2008-07-31 08:00 | 2008-08-29 17:00
505 | 3 | No | GPT | GPT Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 59 d | 0 d | 2008-09-09 17:00 | 2008-09-09 17:00 | 2008-08-29 17:00 | 2008-08-29 17:00
506 | 3 | No | GPT | GPT Site Dismantle/Deactivation Planning | NA | No | 0% | 59 d | 154 d | 2008-09-10 08:00 | 2009-02-24 17:00 | 2008-08-30 08:00 | 2009-01-30 17:00
507 | 3 | No | GPT | GPT Start Dismantle/Deactivate | 2009-03-31 17:00 | No | 0% | 59 d | 0 d | 2009-02-24 17:00 | 2009-02-24 17:00 | 2009-01-31 17:00 | 2009-01-31 17:00
508 | 3 | No | GPT | GPT Dismantle/Deactivate | NA | No | 0% | 577 d | 182 d | 2009-02-25 08:00 | 2009-04-21 17:00 | 2009-01-31 08:00 | 2009-07-31 17:00
509 | 3 | No | GPT | GPT Complete Real Estate Transfer | NA | No | 0% | 577 d | 182 d | 2009-02-25 08:00 | 2009-04-21 17:00 | 2009-08-01 08:00 | 2010-01-29 17:00
510 | 3 | No | GPT | GPT Complete (Latest Finish) | NA | No | 0% | 577 d | 0 d | 2009-09-30 17:00 | 2009-09-30 17:00 | 2010-01-29 17:00 | 2010-01-29 17:00
511 | 2 | Yes | BGM | Binghamton, NY (BGM) | NA | No | 30% | 87 d | 1463 d | 2005-10-13 08:00 | 2010-03-31 17:00 | 2005-10-03 08:00 | 2011-04-28 17:00
512 | 3 | No | BGM | BGM Environmental Studies | NA | No | 100% | 0 d | 218 d | 2005-10-13 08:00 | 2006-08-14 17:00 | 2005-10-13 08:00 | 2006-08-14 17:00
513 | 3 | No | BGM | BGM Real Estate Acquisition | NA | No | 100% | 0 d | 53 d | 2006-08-15 08:00 | 2007-04-02 17:00 | 2005-10-03 08:00 | 2006-09-25 17:00
514 | 3 | No | BGM | BGM Site Construction | NA | No | 100% | 0 d | 165 d | 2007-04-03 08:00 | 2008-02-05 17:00 | 2007-03-26 08:00 | 2007-10-11 17:00
515 | 3 | No | BGM | BGM Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2008-02-05 17:00 | 2008-02-05 17:00 | 2007-10-11 17:00 | 2007-10-11 17:00
516 | 3 | No | BGM | Equipment Install and Optimization | NA | No | 42% | 31 d | 189 d | 2008-02-06 08:00 | 2008-05-27 17:00 | 2007-10-12 08:00 | 2008-04-17 17:00
517 | 3 | No | BGM | BGM Site Acceptance Test (SAT) | NA | No | 0% | 31 d | 11 d | 2008-05-28 08:00 | 2008-06-10 17:00 | 2008-04-18 08:00 | 2008-04-28 17:00
518 | 3 | No | BGM | Resolution of Open Items | NA | No | 0% | 31 d | 60 d | 2008-06-11 08:00 | 2008-08-05 17:00 | 2008-04-29 08:00 | 2008-06-27 17:00
519 | 3 | No | BGM | BGM CAI/DD250 Signed | NA | No | 0% | 31 d | 0 d | 2008-08-05 17:00 | 2008-08-05 17:00 | 2008-06-27 17:00 | 2008-06-27 17:00
520 | 3 | No | BGM | BGM IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 31 d | 49 d | 2008-08-06 08:00 | 2008-09-30 17:00 | 2008-06-28 08:00 | 2008-08-15 17:00
521 | 3 | No | BGM | BGM IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 31 d | 35 d | 2008-10-01 08:00 | 2008-12-23 17:00 | 2008-08-16 08:00 | 2008-09-19 17:00
522 | 3 | No | BGM | BGM IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 31 d | 18 d | 2008-11-16 08:00 | 2008-11-30 17:00 | 2008-09-20 08:00 | 2008-10-07 17:00
523 | 3 | No | BGM | BGM Flight Check | NA | No | 0% | 31 d | 2 d | 2008-12-24 08:00 | 2008-12-30 17:00 | 2008-10-08 08:00 | 2008-10-09 17:00
524 | 3 | No | BGM | BGM Initial Operating Capability (IOC) | 2008-12-31 17:00 | No | 0% | 31 d | 0 d | 2008-12-30 17:00 | 2008-12-30 17:00 | 2008-10-15 17:00 | 2008-10-15 17:00
525 | 3 | No | BGM | Operational Suitability Demonstration (OSD) | NA | No | 0% | 31 d | 30 d | 2008-12-31 08:00 | 2009-03-10 17:00 | 2008-10-16 08:00 | 2008-11-14 17:00
526 | 3 | No | BGM | BGM Operational Readiness Date (ORD)/Commissioning | 2009-01-31 17:00 | No | 0% | 31 d | 0 d | 2009-03-10 17:00 | 2009-03-10 17:00 | 2008-11-14 17:00 | 2008-11-14 17:00
527 | 3 | No | BGM | BGM Site Dismantle/Deactivation Planning | NA | No | 0% | 31 d | 531 d | 2009-03-11 08:00 | 2009-08-25 17:00 | 2008-11-15 08:00 | 2010-04-29 17:00
528 | 3 | No | BGM | BGM Start Dismantle/Deactivate | 2010-05-31 17:00 | Yes | 0% | 31 d | 0 d | 2009-08-25 17:00 | 2009-08-25 17:00 | 2010-04-30 17:00 | 2010-04-30 17:00
529 | 3 | No | BGM | BGM Dismantle/Deactivate | NA | No | 0% | 123 d | 182 d | 2009-08-26 08:00 | 2009-10-20 17:00 | 2010-04-30 08:00 | 2010-10-28 17:00
530 | 3 | No | BGM | BGM Complete Real Estate Transfer | NA | No | 0% | 123 d | 182 d | 2009-08-26 08:00 | 2009-10-20 17:00 | 2010-10-29 08:00 | 2011-04-28 17:00
531 | 3 | No | BGM | BGM Complete (Latest Finish) | NA | No | 0% | 123 d | 0 d | 2010-03-31 17:00 | 2010-03-31 17:00 | 2011-04-28 17:00 | 2011-04-28 17:00
532 | 2 | Yes | ABE | Allentown, PA (ABE) | NA | No | 56% | 173 d | 2146 d | 2002-10-22 08:00 | 2010-09-30 17:00 | 2002-10-22 08:00 | 2010-12-29 17:00
533 | 3 | No | ABE | ABE Environmental Studies | NA | No | 100% | 0 d | 1098 d | 2002-10-22 08:00 | 2007-01-31 17:00 | 2002-10-22 08:00 | 2006-12-29 17:00
534 | 3 | No | ABE | ABE Real Estate Acquisition | NA | No | 100% | 0 d | 371 d | 2007-02-01 08:00 | 2007-10-24 17:00 | 2005-11-02 08:00 | 2007-03-27 17:00
535 | 3 | No | ABE | ABE Site Construction | NA | No | 99% | 284 d | 243 d | 2007-10-25 08:00 | 2008-08-27 17:00 | 2007-04-02 08:00 | 2008-01-03 17:00
536 | 3 | No | ABE | ABE Equipment Delivered to Site | 2007-12-31 17:00 | No | 100% | 0 d | 0 d | 2008-08-27 17:00 | 2008-08-27 17:00 | 2007-10-18 17:00 | 2007-10-18 17:00
537 | 3 | No | ABE | Equipment Install and Optimization | NA | No | 0% | 87 d | 203 d | 2008-08-28 08:00 | 2008-12-17 17:00 | 2007-10-19 08:00 | 2008-05-08 17:00
538 | 3 | No | ABE | ABE Site Acceptance Test (SAT) | NA | No | 0% | 87 d | 11 d | 2008-12-18 08:00 | 2008-12-31 17:00 | 2008-05-09 08:00 | 2008-05-19 17:00
539 | 3 | No | ABE | Resolution of Open Items | NA | No | 0% | 87 d | 60 d | 2009-01-01 08:00 | 2009-02-25 17:00 | 2008-05-20 08:00 | 2008-07-18 17:00
540 | 3 | No | ABE | ABE CAI/DD250 Signed | NA | No | 0% | 87 d | 0 d | 2009-02-25 17:00 | 2009-02-25 17:00 | 2008-07-18 17:00 | 2008-07-18 17:00
541 | 3 | No | ABE | ABE IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 87 d | 33 d | 2009-02-26 08:00 | 2009-04-22 17:00 | 2008-08-04 08:00 | 2008-09-05 17:00
542 | 3 | No | ABE | ABE IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 87 d | 35 d | 2009-04-23 08:00 | 2009-07-15 17:00 | 2008-09-06 08:00 | 2008-10-10 17:00
543 | 3 | No | ABE | ABE IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 87 d | 18 d | 2009-01-13 08:00 | 2009-01-27 17:00 | 2008-10-11 08:00 | 2008-10-28 17:00
544 | 3 | No | ABE | ABE Flight Check | NA | No | 0% | 87 d | 2 d | 2009-07-16 08:00 | 2009-07-22 17:00 | 2008-10-29 08:00 | 2008-10-30 17:00
545 | 3 | No | ABE | ABE Initial Operating Capability (IOC) | 2009-01-31 17:00 | No | 0% | 87 d | 0 d | 2009-07-22 17:00 | 2009-07-22 17:00 | 2008-11-05 17:00 | 2008-11-05 17:00
546 | 3 | No | ABE | Operational Suitability Demonstration (OSD) | NA | No | 0% | 87 d | 28 d | 2009-07-23 08:00 | 2009-09-30 17:00 | 2008-11-06 08:00 | 2008-12-03 17:00
547 | 3 | No | ABE | ABE Operational Readiness Date (ORD)/Commissioning | 2009-02-28 17:00 | No | 0% | 87 d | 0 d | 2009-09-30 17:00 | 2009-09-30 17:00 | 2008-12-03 17:00 | 2008-12-03 17:00
548 | 3 | No | ABE | ABE Site Dismantle/Deactivation Planning | NA | No | 0% | 31 d | 455 d | 2009-10-01 08:00 | 2010-06-09 17:00 | 2008-06-02 08:00 | 2009-08-30 17:00
549 | 3 | No | ABE | ABE Start Dismantle/Deactivate | 2009-09-30 17:00 | Yes | 0% | 31 d | 0 d | 2010-06-09 17:00 | 2010-06-09 17:00 | 2009-08-30 17:00 | 2009-08-30 17:00
550 | 3 | No | ABE | ABE Dismantle/Deactivate | NA | No | 0% | 243 d | 305 d | 2010-06-10 08:00 | 2010-08-04 17:00 | 2009-08-30 08:00 | 2010-06-30 17:00
551 | 3 | No | ABE | ABE Complete Real Estate Transfer | NA | No | 0% | 243 d | 182 d | 2010-06-10 08:00 | 2010-08-04 17:00 | 2010-07-01 08:00 | 2010-12-29 17:00
552 | 3 | No | ABE | ABE Complete (Latest Finish) | NA | No | 0% | 243 d | 0 d | 2010-09-30 17:00 | 2010-09-30 17:00 | 2010-12-29 17:00 | 2010-12-29 17:00
553 | 2 | Yes | FSD | Sioux Falls, SD (FSD) | NA | No | 36% | 66 d | 1608 d | 2005-04-12 08:00 | 2010-08-31 17:00 | 2005-04-12 08:00 | 2011-05-28 17:00
554 | 3 | No | FSD | FSD Environmental Studies | NA | No | 100% | 0 d | 250 d | 2005-04-12 08:00 | 2006-03-28 17:00 | 2005-04-12 08:00 | 2006-03-27 17:00
555 | 3 | No | FSD | FSD Real Estate Acquisition | NA | No | 100% | 0 d | 265 d | 2006-03-29 08:00 | 2007-03-27 17:00 | 2006-03-29 08:00 | 2007-03-26 17:00
556 | 3 | No | FSD | FSD Site Construction | NA | No | 59% | 33 d | 430 d | 2007-03-28 08:00 | 2008-01-29 17:00 | 2007-04-02 08:00 | 2008-07-08 17:00
557 | 3 | No | FSD | FSD Equipment Delivered to Site | 2008-05-31 17:00 | No | 0% | 31 d | 0 d | 2008-01-29 17:00 | 2008-01-29 17:00 | 2008-01-31 17:00 | 2008-01-31 17:00
558 | 3 | No | FSD | Equipment Install and Optimization | NA | No | 0% | 31 d | 90 d | 2008-01-30 08:00 | 2008-05-20 17:00 | 2008-02-01 08:00 | 2008-04-30 17:00
559 | 3 | No | FSD | FSD Site Acceptance Test (SAT) | NA | No | 0% | 31 d | 11 d | 2008-05-21 08:00 | 2008-06-03 17:00 | 2008-05-01 08:00 | 2008-05-11 17:00
560 | 3 | No | FSD | Resolution of Open Items | NA | No | 0% | 31 d | 60 d | 2008-06-04 08:00 | 2008-07-29 17:00 | 2008-05-12 08:00 | 2008-07-10 17:00
561 | 3 | No | FSD | FSD CAI/DD250 Signed | NA | No | 0% | 31 d | 0 d | 2008-07-29 17:00 | 2008-07-29 17:00 | 2008-07-10 17:00 | 2008-07-10 17:00
562 | 3 | No | FSD | FSD IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 31 d | 46 d | 2008-07-30 08:00 | 2008-09-23 17:00 | 2008-07-11 08:00 | 2008-08-25 17:00
563 | 3 | No | FSD | FSD IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 31 d | 35 d | 2008-09-24 08:00 | 2008-12-16 17:00 | 2008-08-26 08:00 | 2008-09-29 17:00
564 | 3 | No | FSD | FSD IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 31 d | 43 d | 2008-11-20 08:00 | 2008-12-04 17:00 | 2008-09-30 08:00 | 2008-11-11 17:00
565 | 3 | No | FSD | FSD Flight Check | NA | No | 0% | 31 d | 2 d | 2008-12-17 08:00 | 2008-12-23 17:00 | 2008-11-12 08:00 | 2008-11-13 17:00
566 | 3 | No | FSD | FSD Initial Operating Capability (IOC) | 2009-03-31 17:00 | No | 0% | 31 d | 0 d | 2008-12-23 17:00 | 2008-12-23 17:00 | 2008-11-19 17:00 | 2008-11-19 17:00
567 | 3 | No | FSD | Operational Suitability Demonstration (OSD) | NA | No | 0% | 31 d | 26 d | 2008-12-24 08:00 | 2009-03-03 17:00 | 2008-11-20 08:00 | 2008-12-15 17:00
568 | 3 | No | FSD | FSD Operational Readiness Date (ORD)/Commissioning | 2009-04-30 17:00 | No | 0% | 31 d | 0 d | 2009-03-03 17:00 | 2009-03-03 17:00 | 2008-12-15 17:00 | 2008-12-15 17:00
569 | 3 | No | FSD | FSD Site Dismantle/Deactivation Planning | NA | No | 0% | 31 d | 530 d | 2009-03-04 08:00 | 2009-11-10 17:00 | 2008-12-16 08:00 | 2010-05-29 17:00
570 | 3 | No | FSD | FSD Start Dismantle/Deactivate | 2010-06-30 17:00 | Yes | 0% | 31 d | 0 d | 2009-11-10 17:00 | 2009-11-10 17:00 | 2010-05-30 17:00 | 2010-05-30 17:00
571 | 3 | No | FSD | FSD Dismantle/Deactivate | NA | No | 0% | 93 d | 182 d | 2009-11-11 08:00 | 2010-01-05 17:00 | 2010-05-30 08:00 | 2010-11-27 17:00
572 | 3 | No | FSD | FSD Complete Real Estate Transfer | NA | No | 0% | 93 d | 182 d | 2009-11-11 08:00 | 2010-01-05 17:00 | 2010-11-28 08:00 | 2011-05-28 17:00
573 | 3 | No | FSD | FSD Complete (Latest Finish) | NA | No | 0% | 93 d | 0 d | 2010-08-31 17:00 | 2010-08-31 17:00 | 2011-05-28 17:00 | 2011-05-28 17:00
574 | 2 | Yes | AVP | Wilkes-Barre, PA (AVP) | NA | No | 64% | 371 d | 1843 d | 2003-03-18 08:00 | 2010-08-31 17:00 | 2003-03-18 08:00 | 2010-03-28 17:00
575 | 3 | No | AVP | AVP Environmental Studies | NA | No | 100% | 0 d | 993 d | 2003-03-18 08:00 | 2007-01-01 17:00 | 2003-03-18 08:00 | 2006-12-29 17:00
576 | 3 | No | AVP | AVP Real Estate Acquisition | NA | No | 100% | 0 d | 176 d | 2006-01-11 08:00 | 2007-01-23 17:00 | 2006-07-26 08:00 | 2007-03-20 17:00
577 | 3 | No | AVP | AVP Site Construction | NA | No | 100% | 0 d | 186 d | 2007-04-04 08:00 | 2008-02-05 17:00 | 2007-03-26 08:00 | 2007-11-01 17:00
578 | 3 | No | AVP | AVP Equipment Delivered to Site | 2008-01-31 17:00 | No | 100% | 0 d | 0 d | 2008-02-05 17:00 | 2008-02-05 17:00 | 2007-11-01 17:00 | 2007-11-01 17:00
579 | 3 | No | AVP | Equipment Install and Optimization | NA | No | 32% | 62 d | 184 d | 2008-02-06 08:00 | 2008-05-27 17:00 | 2007-11-02 08:00 | 2008-05-03 17:00
580 | 3 | No | AVP | AVP Site Acceptance Test (SAT) | NA | No | 0% | 62 d | 11 d | 2008-05-28 08:00 | 2008-06-10 17:00 | 2008-05-04 08:00 | 2008-05-14 17:00
581 | 3 | No | AVP | Resolution of Open Items | NA | No | 0% | 62 d | 60 d | 2008-06-11 08:00 | 2008-08-05 17:00 | 2008-05-15 08:00 | 2008-07-13 17:00
582 | 3 | No | AVP | AVP CAI/DD250 Signed | NA | No | 0% | 62 d | 0 d | 2008-08-05 17:00 | 2008-08-05 17:00 | 2008-07-13 17:00 | 2008-07-13 17:00
583 | 3 | No | AVP | AVP IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 62 d | 47 d | 2008-08-06 08:00 | 2008-09-30 17:00 | 2008-07-14 08:00 | 2008-08-29 17:00
584 | 3 | No | AVP | AVP IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 62 d | 35 d | 2008-10-01 08:00 | 2008-12-23 17:00 | 2008-08-30 08:00 | 2008-10-03 17:00
585 | 3 | No | AVP | AVP IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 62 d | 46 d | 2009-02-15 08:00 | 2009-03-01 17:00 | 2008-10-04 08:00 | 2008-11-18 17:00
586 | 3 | No | AVP | AVP Flight Check | NA | No | 0% | 62 d | 2 d | 2008-12-24 08:00 | 2008-12-30 17:00 | 2008-11-19 08:00 | 2008-11-20 17:00
587 | 3 | No | AVP | AVP Initial Operating Capability (IOC) | 2009-02-28 17:00 | No | 0% | 62 d | 0 d | 2008-12-30 17:00 | 2008-12-30 17:00 | 2008-12-03 17:00 | 2008-12-03 17:00
588 | 3 | No | AVP | Operational Suitability Demonstration (OSD) | NA | No | 0% | 62 d | 49 d | 2008-12-31 08:00 | 2009-03-10 17:00 | 2008-12-04 08:00 | 2009-01-21 17:00
589 | 3 | No | AVP | AVP Operational Readiness Date (ORD)/Commissioning | 2009-03-31 17:00 | No | 0% | 62 d | 0 d | 2009-03-10 17:00 | 2009-03-10 17:00 | 2009-01-21 17:00 | 2009-01-21 17:00
590 | 3 | No | AVP | AVP Site Dismantle/Deactivation Planning | NA | No | 0% | 62 d | 67 d | 2009-03-11 08:00 | 2009-10-20 17:00 | 2009-01-22 08:00 | 2009-03-29 17:00
591 | 3 | No | AVP | AVP Start Dismantle/Deactivate | 2009-05-31 17:00 | No | 0% | 62 d | 0 d | 2009-10-20 17:00 | 2009-10-20 17:00 | 2009-03-30 17:00 | 2009-03-30 17:00
592 | 3 | No | AVP | AVP Dismantle/Deactivate | NA | No | 0% | 519 d | 182 d | 2009-10-21 08:00 | 2009-12-15 17:00 | 2009-03-30 08:00 | 2009-09-27 17:00
593 | 3 | No | AVP | AVP Complete Real Estate Transfer | NA | No | 0% | 519 d | 182 d | 2009-10-21 08:00 | 2009-12-15 17:00 | 2009-09-28 08:00 | 2010-03-28 17:00
594 | 3 | No | AVP | AVP Complete (Latest Finish) | NA | No | 0% | 519 d | 0 d | 2010-08-31 17:00 | 2010-08-31 17:00 | 2010-03-28 17:00 | 2010-03-28 17:00
595 | 2 | Yes | BTR | Baton Rouge, LA (BTR) | NA | No | 54% | 131 d | 2363 d | 2002-02-19 08:00 | 2009-12-31 17:00 | 2002-02-19 08:00 | 2011-02-26 17:00
596 | 3 | No | BTR | BTR Environmental Studies | NA | No | 100% | 0 d | 789 d | 2002-02-19 08:00 | 2005-02-25 17:00 | 2002-02-19 08:00 | 2005-02-25 17:00
597 | 3 | No | BTR | BTR Real Estate Acquisition | NA | No | 100% | 0 d | 153 d | 2004-11-17 08:00 | 2005-06-17 17:00 | 2004-11-17 08:00 | 2005-06-17 17:00
598 | 3 | No | BTR | BTR Site Construction | NA | No | 100% | 0 d | 185 d | 2006-09-14 08:00 | 2007-08-15 17:00 | 2006-09-14 08:00 | 2007-05-21 17:00
599 | 3 | No | BTR | BTR Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2007-08-15 17:00 | 2007-08-15 17:00 | 2007-05-21 17:00 | 2007-05-21 17:00
600 | 3 | No | BTR | Equipment Install and Optimization | NA | No | 91% | 60 d | 225 d | 2007-08-16 08:00 | 2007-12-05 17:00 | 2007-05-22 08:00 | 2008-01-21 17:00
601 | 3 | No | BTR | BTR Site Acceptance Test (SAT) | NA | No | 0% | 60 d | 11 d | 2007-12-06 08:00 | 2007-12-19 17:00 | 2008-01-22 08:00 | 2008-02-01 17:00
602 | 3 | No | BTR | Resolution of Open Items | NA | No | 0% | 60 d | 60 d | 2007-12-20 08:00 | 2008-02-13 17:00 | 2008-02-02 08:00 | 2008-04-01 17:00
603 | 3 | No | BTR | BTR CAI/DD250 Signed | 2008-05-31 17:00 | No | 0% | 60 d | 0 d | 2008-02-13 17:00 | 2008-02-13 17:00 | 2008-04-01 17:00 | 2008-04-01 17:00
604 | 3 | No | BTR | BTR IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 91 d | 243 d | 2008-02-14 08:00 | 2008-04-09 17:00 | 2008-04-02 08:00 | 2008-11-30 17:00
605 | 3 | No | BTR | BTR IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 91 d | 47 d | 2008-04-10 08:00 | 2008-07-02 17:00 | 2008-12-01 08:00 | 2009-01-16 17:00
606 | 3 | No | BTR | BTR IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 91 d | 5 d | 2009-01-29 08:00 | 2009-02-12 17:00 | 2009-01-17 08:00 | 2009-01-21 17:00
607 | 3 | No | BTR | BTR Flight Check | NA | No | 0% | 91 d | 2 d | 2008-07-03 08:00 | 2008-07-09 17:00 | 2009-01-22 08:00 | 2009-01-23 17:00
608 | 3 | No | BTR | BTR Initial Operating Capability (IOC) | 2009-04-30 17:00 | No | 0% | 91 d | 0 d | 2008-07-09 17:00 | 2008-07-09 17:00 | 2009-01-29 17:00 | 2009-01-29 17:00
609 | 3 | No | BTR | Operational Suitability Demonstration (OSD) | NA | No | 0% | 92 d | 30 d | 2008-07-10 08:00 | 2008-09-17 17:00 | 2009-01-30 08:00 | 2009-02-28 17:00
610 | 3 | No | BTR | BTR Operational Readiness Date (ORD)/Commissioning | 2009-05-31 17:00 | No | 0% | 92 d | 0 d | 2008-09-17 17:00 | 2008-09-17 17:00 | 2009-02-28 17:00 | 2009-02-28 17:00
611 | 3 | No | BTR | BTR Site Dismantle/Deactivation Planning | NA | No | 0% | 184 d | 364 d | 2008-09-18 08:00 | 2009-03-04 17:00 | 2009-03-01 08:00 | 2010-02-27 17:00
612 | 3 | No | BTR | BTR Start Dismantle/Deactivate | 2010-11-30 17:00 | No | 0% | 184 d | 0 d | 2009-03-04 17:00 | 2009-03-04 17:00 | 2010-02-28 17:00 | 2010-02-28 17:00
613 | 3 | No | BTR | BTR Dismantle/Deactivate | NA | No | 0% | 184 d | 182 d | 2009-03-05 08:00 | 2009-04-29 17:00 | 2010-02-28 08:00 | 2010-08-28 17:00
614 | 3 | No | BTR | BTR Complete Real Estate Transfer | NA | No | 0% | 184 d | 182 d | 2009-03-05 08:00 | 2009-04-29 17:00 | 2010-08-29 08:00 | 2011-02-26 17:00
615 | 3 | No | BTR | BTR Complete (Latest Finish) | NA | No | 0% | 184 d | 0 d | 2009-12-31 17:00 | 2009-12-31 17:00 | 2011-02-26 17:00 | 2011-02-26 17:00
616 | 2 | Yes | CRP | Corpus Christi, TX (CRP) | NA | No | 34% | 109 d | 1493 d | 2005-07-21 08:00 | 2009-11-30 17:00 | 2005-07-21 08:00 | 2011-03-29 17:00
617 | 3 | No | CRP | CRP Environmental Studies | NA | No | 100% | 0 d | 96 d | 2005-07-21 08:00 | 2005-12-01 17:00 | 2005-07-21 08:00 | 2005-12-01 17:00
618 | 3 | No | CRP | CRP Real Estate Acquisition | NA | No | 100% | 0 d | 63 d | 2005-12-02 08:00 | 2006-02-28 17:00 | 2005-12-02 08:00 | 2006-02-28 17:00
619 | 3 | No | CRP | CRP Site Construction | NA | No | 100% | 0 d | 289 d | 2007-01-08 08:00 | 2007-09-28 17:00 | 2006-05-18 08:00 | 2007-06-15 17:00
620 | 3 | No | CRP | CRP Equipment Delivered to Site | NA | No | 100% | 0 d | 0 d | 2007-09-28 17:00 | 2007-09-28 17:00 | 2007-06-13 17:00 | 2007-06-13 17:00
621 | 3 | No | CRP | Equipment Install and Optimization | NA | No | 100% | 0 d | 159 d | 2007-10-01 08:00 | 2008-01-18 17:00 | 2007-06-14 08:00 | 2007-12-03 17:00
622 | 3 | No | CRP | CRP Site Acceptance Test (SAT) | NA | No | 100% | 0 d | 10 d | 2008-01-21 08:00 | 2008-02-01 17:00 | 2007-12-04 08:00 | 2007-12-13 17:00
623 | 3 | No | CRP | Resolution of Open Items | NA | No | 0% | 64 d | 61 d | 2008-02-04 08:00 | 2008-03-28 17:00 | 2007-12-14 08:00 | 2008-02-12 17:00
624 | 3 | No | CRP | CRP CAI/DD250 Signed | 2008-05-31 17:00 | No | 0% | 64 d | 0 d | 2008-03-28 17:00 | 2008-03-28 17:00 | 2008-02-12 17:00 | 2008-02-12 17:00
625 | 3 | No | CRP | CRP IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 64 d | 303 d | 2008-03-31 08:00 | 2008-05-23 17:00 | 2008-02-13 08:00 | 2008-12-11 17:00
626 | 3 | No | CRP | CRP IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 64 d | 48 d | 2008-05-26 08:00 | 2008-08-15 17:00 | 2008-12-12 08:00 | 2009-01-28 17:00
627 | 3 | No | CRP | CRP IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 64 d | 20 d | 2009-01-08 08:00 | 2009-01-22 17:00 | 2009-01-29 08:00 | 2009-02-17 17:00
628 | 3 | No | CRP | CRP Flight Check | NA | No | 0% | 64 d | 1 d | 2008-08-18 08:00 | 2008-08-22 17:00 | 2009-02-18 08:00 | 2009-02-18 17:00
629 | 3 | No | CRP | CRP Initial Operating Capability (IOC) | 2009-04-30 17:00 | No | 0% | 64 d | 0 d | 2008-08-22 17:00 | 2008-08-22 17:00 | 2009-02-25 17:00 | 2009-02-25 17:00
630 | 3 | No | CRP | Operational Suitability Demonstration (OSD) | NA | No | 0% | 65 d | 30 d | 2008-08-25 08:00 | 2008-10-31 17:00 | 2009-02-26 08:00 | 2009-03-27 17:00
631 | 3 | No | CRP | CRP Operational Readiness Date (ORD)/Commissioning | 2009-05-31 17:00 | No | 0% | 65 d | 0 d | 2008-10-31 17:00 | 2008-10-31 17:00 | 2009-03-27 17:00 | 2009-03-27 17:00
632 | 3 | No | CRP | CRP Site Dismantle/Deactivation Planning | NA | No | 0% | 153 d | 368 d | 2008-11-03 08:00 | 2009-04-17 17:00 | 2009-03-28 08:00 | 2010-03-30 17:00
633 | 3 | No | CRP | CRP Start Dismantle/Deactivate | 2010-12-31 17:00 | No | 0% | 153 d | 0 d | 2009-04-17 17:00 | 2009-04-17 17:00 | 2010-03-31 17:00 | 2010-03-31 17:00
634 | 3 | No | CRP | CRP Dismantle/Deactivate | NA | No | 0% | 153 d | 182 d | 2009-04-20 08:00 | 2009-06-12 17:00 | 2010-03-31 08:00 | 2010-09-28 17:00
635 | 3 | No | CRP | CRP Complete Real Estate Transfer | NA | No | 0% | 153 d | 182 d | 2009-04-20 08:00 | 2009-06-12 17:00 | 2010-09-29 08:00 | 2011-03-29 17:00
636 | 3 | No | CRP | CRP Complete (Latest Finish) | NA | No | 0% | 153 d | 0 d | 2009-11-30 17:00 | 2009-11-30 17:00 | 2011-03-29 17:00 | 2011-03-29 17:00
637 | 2 | Yes | MLB | Melbourne, FL (MLB) | NA | No | 39% | 152 d | 1355 d | 2005-12-01 08:00 | 2010-06-30 17:00 | 2005-12-01 08:00 | 2011-01-27 17:00
638 | 3 | No | MLB | MLB Environmental Studies | NA | No | 100% | 0 d | 330 d | 2005-12-01 08:00 | 2006-12-27 17:00 | 2005-12-01 08:00 | 2007-02-28 17:00
639 | 3 | No | MLB | MLB Real Estate Acquisition | NA | No | 100% | 0 d | 155 d | 2006-09-27 08:00 | 2007-04-10 17:00 | 2006-09-27 08:00 | 2007-04-20 17:00
640 | 3 | No | MLB | MLB Site Construction | NA | No | 58% | 104 d | 406 d | 2007-04-11 08:00 | 2008-02-13 17:00 | 2007-04-24 08:00 | 2008-06-30 17:00
641 | 3 | No | MLB | MLB Equipment Delivered to Site | NA | No | 0% | 104 d | 0 d | 2008-02-13 17:00 | 2008-02-13 17:00 | 2008-06-30 17:00 | 2008-06-30 17:00
642 | 3 | No | MLB | Equipment Install and Optimization | NA | No | 0% | 104 d | 85 d | 2008-02-14 08:00 | 2008-06-04 17:00 | 2008-07-01 08:00 | 2008-09-23 17:00
643 | 3 | No | MLB | MLB Site Acceptance Test (SAT) | NA | No | 0% | 104 d | 11 d | 2008-06-05 08:00 | 2008-06-18 17:00 | 2008-09-24 08:00 | 2008-10-04 17:00
644 | 3 | No | MLB | Resolution of Open Items | NA | No | 0% | 104 d | 60 d | 2008-06-19 08:00 | 2008-08-13 17:00 | 2008-10-05 08:00 | 2008-12-03 17:00
645 | 3 | No | MLB | MLB CAI/DD250 Signed | NA | No | 0% | 104 d | 0 d | 2008-08-13 17:00 | 2008-08-13 17:00 | 2008-12-03 17:00 | 2008-12-03 17:00
646 | 3 | No | MLB | MLB IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 104 d | 75 d | 2008-08-14 08:00 | 2008-10-08 17:00 | 2008-12-04 08:00 | 2009-02-16 17:00
647 | 3 | No | MLB | MLB IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 104 d | 35 d | 2008-10-09 08:00 | 2008-12-31 17:00 | 2009-02-17 08:00 | 2009-03-23 17:00
648 | 3 | No | MLB | MLB IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 104 d | 18 d | 2009-02-12 08:00 | 2009-02-26 17:00 | 2009-03-24 08:00 | 2009-04-10 17:00
649 | 3 | No | MLB | MLB Flight Check | NA | No | 0% | 104 d | 2 d | 2009-01-01 08:00 | 2009-01-07 17:00 | 2009-04-11 08:00 | 2009-04-12 17:00
650 | 3 | No | MLB | MLB Initial Operating Capability (IOC) | 2009-07-31 17:00 | No | 0% | 104 d | 0 d | 2009-01-07 17:00 | 2009-01-07 17:00 | 2009-04-18 17:00 | 2009-04-18 17:00
651 | 3 | No | MLB | Operational Suitability Demonstration (OSD) | NA | No | 0% | 105 d | 30 d | 2009-01-08 08:00 | 2009-03-18 17:00 | 2009-04-19 08:00 | 2009-05-18 17:00
652 | 3 | No | MLB | MLB Operational Readiness Date (ORD)/Commissioning | 2009-08-31 17:00 | No | 0% | 105 d | 0 d | 2009-03-18 17:00 | 2009-03-18 17:00 | 2009-05-18 17:00 | 2009-05-18 17:00
653 | 3 | No | MLB | MLB Site Dismantle/Deactivation Planning | NA | No | 0% | 214 d | 257 d | 2009-03-19 08:00 | 2009-10-28 17:00 | 2009-05-19 08:00 | 2010-01-30 17:00
654 | 3 | No | MLB | MLB Start Dismantle/Deactivate | 2010-12-31 17:00 | No | 0% | 214 d | 0 d | 2009-10-28 17:00 | 2009-10-28 17:00 | 2010-01-31 17:00 | 2010-01-31 17:00
655 | 3 | No | MLB | MLB Dismantle/Deactivate | NA | No | 0% | 214 d | 180 d | 2009-10-29 08:00 | 2009-12-23 17:00 | 2010-01-31 08:00 | 2010-07-29 17:00
656 | 3 | No | MLB | MLB Complete Real Estate Transfer | NA | No | 0% | 214 d | 182 d | 2009-10-29 08:00 | 2009-12-23 17:00 | 2010-07-30 08:00 | 2011-01-27 17:00
657 | 3 | No | MLB | MLB Complete (Latest Finish) | NA | No | 0% | 214 d | 0 d | 2010-06-30 17:00 | 2010-06-30 17:00 | 2011-01-27 17:00 | 2011-01-27 17:00
658 | 2 | Yes | OGG | Kahului, HI (OGG) | NA | No | 65% | 196 d | 2973 d | 1999-07-20 08:00 | 2010-01-29 17:00 | 1999-07-20 08:00 | 2010-11-26 17:00
659 | 3 | No | OGG | OGG Environmental Studies | NA | No | 100% | 0 d | 453 d | 1999-07-20 08:00 | 2001-04-12 17:00 | 1999-07-20 08:00 | 2001-04-12 17:00
660 | 3 | No | OGG | OGG Real Estate Acquisition | NA | No | 100% | 0 d | 963 d | 2001-04-13 08:00 | 2004-12-21 17:00 | 2001-04-13 08:00 | 2004-12-21 17:00
661 | 3 | No | OGG | OGG Site Construction | NA | No | 84% | 0 d | 642 d | 2007-01-31 08:00 | 2007-11-06 17:00 | 2006-03-14 08:00 | 2008-04-30 17:00
662 | 3 | No | OGG | OGG Equipment Delivered to Site | NA | No | 0% | 0 d | 0 d | 2007-11-06 17:00 | 2007-11-06 17:00 | 2008-04-30 17:00 | 2008-04-30 17:00
663 | 3 | No | OGG | Equipment Install and Optimization | NA | No | 0% | 0 d | 234 d | 2007-11-07 08:00 | 2008-02-26 17:00 | 2008-05-01 08:00 | 2008-12-20 17:00
664 | 3 | No | OGG | OGG Site Acceptance Test (SAT) | NA | No | 0% | 0 d | 11 d | 2008-02-27 08:00 | 2008-03-11 17:00 | 2008-12-21 08:00 | 2008-12-31 17:00
665 | 3 | No | OGG | Resolution of Open Items | NA | No | 0% | 0 d | 60 d | 2008-03-12 08:00 | 2008-05-06 17:00 | 2009-01-01 08:00 | 2009-03-01 17:00
666 | 3 | No | OGG | OGG CAI/DD250 Signed | NA | No | 0% | 0 d | 0 d | 2008-05-06 17:00 | 2008-05-06 17:00 | 2009-03-01 17:00 | 2009-03-01 17:00
667 | 3 | No | OGG | OGG IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 0 d | 47 d | 2008-05-07 08:00 | 2008-07-01 17:00 | 2009-03-02 08:00 | 2009-04-17 17:00
668 | 3 | No | OGG | OGG IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 0 d | 35 d | 2008-07-02 08:00 | 2008-09-23 17:00 | 2009-04-18 08:00 | 2009-05-22 17:00
669 | 3 | No | OGG | OGG IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 0 d | 18 d | 2006-10-02 08:00 | 2006-10-20 17:00 | 2009-05-23 08:00 | 2009-06-09 17:00
670 | 3 | No | OGG | OGG Flight Check | NA | No | 0% | 0 d | 2 d | 2008-09-24 08:00 | 2008-09-30 17:00 | 2009-06-10 08:00 | 2009-06-11 17:00
671 | 3 | No | OGG | OGG Initial Operating Capability (IOC) | NA | No | 0% | 0 d | 0 d | 2008-09-30 17:00 | 2008-09-30 17:00 | 2009-06-17 17:00 | 2009-06-17 17:00
672 | 3 | No | OGG | Operational Suitability Demonstration (OSD) | NA | No | 0% | 0 d | 30 d | 2008-10-01 08:00 | 2008-12-09 17:00 | 2009-06-18 08:00 | 2009-07-17 17:00
673 | 3 | No | OGG | OGG Operational Readiness Date (ORD)/Commissioning | 2009-09-30 17:00 | No | 0% | 0 d | 0 d | 2008-12-09 17:00 | 2008-12-09 17:00 | 2009-07-17 17:00 | 2009-07-17 17:00
674 | 3 | No | OGG | OGG Site Dismantle/Deactivation Planning | NA | No | 0% | 0 d | 135 d | 2008-12-10 08:00 | 2009-05-26 17:00 | 2009-07-18 08:00 | 2009-11-29 17:00
675 | 3 | No | OGG | OGG Start Dismantle/Deactivate | 2009-11-30 17:00 | Yes | 0% | 0 d | 0 d | 2009-05-26 17:00 | 2009-05-26 17:00 | 2009-11-30 17:00 | 2009-11-30 17:00
676 | 3 | No | OGG | OGG Dismantle/Deactivate | NA | No | 0% | 276 d | 180 d | 2009-05-27 08:00 | 2009-07-21 17:00 | 2009-11-30 08:00 | 2010-05-28 17:00
677 | 3 | No | OGG | OGG Complete Real Estate Transfer | NA | No | 0% | 276 d | 182 d | 2009-05-27 08:00 | 2009-07-21 17:00 | 2010-05-29 08:00 | 2010-11-26 17:00
678 | 3 | No | OGG | OGG Complete (Latest Finish) | NA | No | 0% | 276 d | 0 d | 2010-01-29 17:00 | 2010-01-29 17:00 | 2010-11-26 17:00 | 2010-11-26 17:00
679 | 2 | Yes | MLI | Moline, IL (MLI) | NA | No | 19% | 45 d | 1418 d | 2006-02-01 08:00 | 2010-03-31 17:00 | 2006-02-01 08:00 | 2011-06-27 17:00
680 | 3 | No | MLI | MLI Environmental Studies | NA | No | 100% | 0 d | 126 d | 2006-02-01 08:00 | 2006-07-26 17:00 | 2006-02-01 08:00 | 2006-07-26 17:00
681 | 3 | No | MLI | MLI Real Estate Acquisition | NA | No | 100% | 0 d | 154 d | 2006-07-06 08:00 | 2007-01-31 17:00 | 2006-07-06 08:00 | 2007-01-31 17:00
682 | 3 | No | MLI | MLI Start Site Construction | NA | No | 100% | 0 d | 0 d | 2007-04-12 08:00 | 2007-04-12 08:00 | 2007-09-10 17:00 | 2007-09-10 17:00
683 | 3 | No | MLI | MLI Site Construction | NA | No | 34% | -150 d | 329 d | 2007-04-12 08:00 | 2008-02-14 17:00 | 2007-09-10 08:00 | 2008-08-03 17:00
684 | 3 | No | MLI | MLI Equipment Delivered to Site | NA | No | 0% | -150 d | 0 d | 2008-02-14 17:00 | 2008-02-14 17:00 | 2008-08-03 17:00 | 2008-08-03 17:00
685 | 3 | No | MLI | Equipment Install and Optimization | NA | No | 0% | -16 d | 161 d | 2008-02-15 08:00 | 2008-06-05 17:00 | 2008-08-04 08:00 | 2009-01-11 17:00
686 | 3 | No | MLI | MLI Site Acceptance Test (SAT) | NA | No | 0% | -16 d | 11 d | 2008-06-06 08:00 | 2008-06-19 17:00 | 2009-01-12 08:00 | 2009-01-22 17:00
687 | 3 | No | MLI | Resolution of Open Items | NA | No | 0% | -16 d | 129 d | 2008-06-20 08:00 | 2008-08-14 17:00 | 2009-01-23 08:00 | 2009-05-31 17:00
688 | 3 | No | MLI | MLI CAI/DD250 Signed | NA | No | 0% | -16 d | 0 d | 2008-08-14 17:00 | 2008-08-14 17:00 | 2009-05-31 17:00 | 2009-05-31 17:00
689 | 3 | No | MLI | MLI IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | -16 d | 47 d | 2008-08-15 08:00 | 2008-10-09 17:00 | 2009-06-01 08:00 | 2009-07-17 17:00
690 | 3 | No | MLI | MLI IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | -16 d | 35 d | 2008-10-10 08:00 | 2009-01-01 17:00 | 2009-07-18 08:00 | 2009-08-21 17:00
691 | 3 | No | MLI | MLI IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | -16 d | 18 d | 2009-06-11 08:00 | 2009-06-25 17:00 | 2009-08-22 08:00 | 2009-09-08 17:00
692 | 3 | No | MLI | MLI Flight Check | NA | No | 0% | -16 d | 2 d | 2009-01-02 08:00 | 2009-01-08 17:00 | 2009-09-09 08:00 | 2009-09-10 17:00
693 | 3 | No | MLI | MLI Initial Operating Capability (IOC) | NA | No | 0% | -16 d | 0 d | 2009-01-08 17:00 | 2009-01-08 17:00 | 2009-09-16 17:00 | 2009-09-16 17:00
694 | 3 | No | MLI | Operational Suitability Demonstration (OSD) | NA | No | 0% | -16 d | 30 d | 2009-01-09 08:00 | 2009-03-19 17:00 | 2009-09-17 08:00 | 2009-10-16 17:00
695 | 3 | No | MLI | MLI Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | -16 d | 0 d | 2009-03-19 17:00 | 2009-03-19 17:00 | 2009-10-16 17:00 | 2009-10-16 17:00
696 | 3 | No | MLI | MLI Site Dismantle/Deactivation Planning | NA | No | 0% | -150 d | 696 d | 2009-03-20 08:00 | 2009-09-03 17:00 | 2008-08-04 08:00 | 2010-06-30 17:00
697 | 3 | No | MLI | MLI Start Dismantle/Deactivate | 2010-01-31 17:00 | Yes | 0% | -150 d | 0 d | 2009-09-03 17:00 | 2009-09-03 17:00 | 2010-06-30 17:00 | 2010-06-30 17:00
698 | 3 | No | MLI | MLI Dismantle/Deactivate | NA | No | 0% | 63 d | 181 d | 2009-09-04 08:00 | 2009-10-29 17:00 | 2010-06-30 08:00 | 2010-12-27 17:00
699 | 3 | No | MLI | MLI Complete Real Estate Transfer | NA | No | 0% | 63 d | 182 d | 2009-09-04 08:00 | 2009-10-29 17:00 | 2010-12-28 08:00 | 2011-06-27 17:00
700 | 3 | No | MLI | MLI Complete (Latest Finish) | NA | No | 0% | 63 d | 0 d | 2010-03-31 17:00 | 2010-03-31 17:00 | 2011-06-27 17:00 | 2011-06-27 17:00
701 | 2 | Yes | GRB | Green Bay, WI (GRB) | NA | No | 54% | 22 d | 2362 d | 2002-07-23 08:00 | 2010-05-31 17:00 | 2002-07-23 08:00 | 2011-07-28 17:00
702 | 3 | No | GRB | GRB Environmental Studies | NA | No | 100% | 0 d | 612 d | 2002-07-23 08:00 | 2004-11-24 17:00 | 2002-07-23 08:00 | 2004-11-24 17:00
703 | 3 | No | GRB | GRB Real Estate Acquisition | NA | No | 95% | -158 d | 929 d | 2004-11-10 08:00 | 2007-02-27 17:00 | 2004-11-10 08:00 | 2008-02-28 17:00
704 | 3 | No | GRB | GRB Real Estate Acquisition Complete | 2008-04-30 17:00 | No | 0% | -116 d | 0 d | NA | NA | 2008-02-28 17:00 | 2008-02-28 17:00
705 | 3 | No | GRB | GRB Start Site Construction | NA | No | 0% | -158 d | 0 d | 2007-02-28 08:00 | 2008-01-02 17:00 | 2008-03-30 17:00 | 2008-03-30 17:00
706 | 3 | No | GRB | GRB Site Construction | NA | No | 0% | -158 d | 151 d | 2007-02-28 08:00 | 2008-01-02 17:00 | 2008-03-30 08:00 | 2008-08-27 17:00
707 | 3 | No | GRB | GRB Equipment Delivered to Site | NA | No | 0% | -158 d | 0 d | 2008-01-02 17:00 | 2008-01-02 17:00 | 2008-08-27 17:00 | 2008-08-27 17:00
708 | 3 | No | GRB | Equipment Install and Optimization | NA | No | 0% | -158 d | 372 d | 2008-01-03 08:00 | 2008-04-23 17:00 | 2008-08-28 08:00 | 2009-09-03 17:00
709 | 3 | No | GRB | GRB Site Acceptance Test (SAT) | NA | No | 0% | -158 d | 11 d | 2008-04-24 08:00 | 2008-05-07 17:00 | 2009-09-04 08:00 | 2009-09-14 17:00
710 | 3 | No | GRB | Resolution of Open Items | NA | No | 0% | -158 d | 15 d | 2008-05-08 08:00 | 2008-07-02 17:00 | 2009-09-15 08:00 | 2009-09-29 17:00
711 | 3 | No | GRB | GRB CAI/DD250 Signed | NA | No | 0% | -158 d | 0 d | 2008-07-02 17:00 | 2008-07-02 17:00 | 2009-09-29 17:00 | 2009-09-29 17:00
712 | 3 | No | GRB | GRB IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | -158 d | 76 d | 2008-07-03 08:00 | 2008-08-27 17:00 | 2009-09-30 08:00 | 2009-12-14 17:00
713 | 3 | No | GRB | GRB IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | -158 d | 35 d | 2008-08-28 08:00 | 2008-11-19 17:00 | 2009-12-15 08:00 | 2010-01-18 17:00
714 | 3 | No | GRB | GRB IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | -158 d | 15 d | 2010-01-12 08:00 | 2010-02-01 17:00 | 2010-01-19 08:00 | 2010-02-02 17:00
715 | 3 | No | GRB | GRB Flight Check | NA | No | 0% | -158 d | 2 d | 2008-11-20 08:00 | 2008-11-26 17:00 | 2010-02-03 08:00 | 2010-02-04 17:00
716 | 3 | No | GRB | GRB Initial Operating Capability (IOC) | 2010-04-30 17:00 | No | 0% | -158 d | 0 d | 2008-11-26 17:00 | 2008-11-26 17:00 | 2010-02-07 17:00 | 2010-02-07 17:00
717 | 3 | No | GRB | Operational Suitability Demonstration (OSD) | NA | No | 0% | -158 d | 28 d | 2008-11-27 08:00 | 2009-02-04 17:00 | 2010-02-08 08:00 | 2010-03-07 17:00
718 | 3 | No | GRB | GRB Operational Readiness Date (ORD)/Commissioning | 2010-05-31 17:00 | No | 0% | -158 d | 0 d | 2009-02-04 17:00 | 2009-02-04 17:00 | 2010-03-07 17:00 | 2010-03-07 17:00
719 | 3 | No | GRB | GRB Site Dismantle/Deactivation Planning | NA | No | 0% | 32 d | 144 d | 2009-02-05 08:00 | 2009-07-22 17:00 | 2010-03-08 08:00 | 2010-07-29 17:00
720 | 3 | No | GRB | GRB Start Dismantle/Deactivate | 2010-08-31 17:00 | Yes | 0% | 32 d | 0 d | 2009-07-22 17:00 | 2009-07-22 17:00 | 2010-07-30 17:00 | 2010-07-30 17:00
721 | 3 | No | GRB | GRB Dismantle/Deactivate | NA | No | 0% | 32 d | 182 d | 2009-07-23 08:00 | 2009-09-16 17:00 | 2010-07-30 08:00 | 2011-01-27 17:00
722 | 3 | No | GRB | GRB Complete Real Estate Transfer | NA | No | 0% | 32 d | 182 d | 2009-07-23 08:00 | 2009-09-16 17:00 | 2011-01-28 08:00 | 2011-07-28 17:00
723 | 3 | No | GRB | GRB Complete (Latest Finish) | NA | No | 0% | 32 d | 0 d | 2010-05-31 17:00 | 2010-05-31 17:00 | 2011-07-28 17:00 | 2011-07-28 17:00
724 | 2 | Yes | PIA | Peoria, IL (PIA) | NA | No | 49% | 0 d | 2959 d | 2000-05-09 08:00 | 2010-09-30 17:00 | 2000-05-09 08:00 | 2011-08-29 17:00
725 | 3 | No | PIA | PIA Environmental Studies | NA | No | 100% | 0 d | 939 d | 2000-05-09 08:00 | 2003-12-12 17:00 | 2000-05-09 08:00 | 2003-12-12 17:00
726 | 3 | No | PIA | PIA Real Estate Acquisition | NA | No | 100% | 0 d | 408 d | 2006-04-06 08:00 | 2007-01-31 17:00 | 2006-04-06 08:00 | 2007-09-26 17:00
727 | 3 | No | PIA | PIA Real Estate Acquisition Complete | NA | No | 100% | 0 d | 0 d | 2006-04-06 08:00 | 2007-01-31 17:00 | 2007-09-26 17:00 | 2007-09-26 17:00
728 | 3 | No | PIA | PIA Start Site Construction | NA | No | 100% | 0 d | 0 d | 2007-11-08 08:00 | 2008-08-13 17:00 | 2007-12-21 17:00 | 2007-12-21 17:00
729 | 3 | No | PIA | PIA Site Construction | NA | No | 0% | -173 d | 348 d | 2007-11-08 08:00 | 2008-08-13 17:00 | 2007-12-21 08:00 | 2008-12-02 17:00
730 | 3 | No | PIA | PIA Equipment Delivered to Site | NA | No | 0% | -173 d | 0 d | 2008-08-13 17:00 | 2008-08-13 17:00 | 2008-09-10 17:00 | 2008-09-10 17:00
731 | 3 | No | PIA | Equipment Install and Optimization | NA | No | 0% | -173 d | 350 d | 2008-08-14 08:00 | 2008-12-03 17:00 | 2008-09-11 08:00 | 2009-08-26 17:00
732 | 3 | No | PIA | PIA Site Acceptance Test (SAT) | NA | No | 0% | -173 d | 11 d | 2008-12-04 08:00 | 2008-12-17 17:00 | 2009-08-27 08:00 | 2009-09-06 17:00
733 | 3 | No | PIA | Resolution of Open Items | NA | No | 0% | -173 d | 23 d | 2008-12-18 08:00 | 2009-02-11 17:00 | 2009-09-07 08:00 | 2009-09-29 17:00
734 | 3 | No | PIA | PIA CAI/DD250 Signed | NA | No | 0% | -173 d | 0 d | 2009-02-11 17:00 | 2009-02-11 17:00 | 2009-09-29 17:00 | 2009-09-29 17:00
735 | 3 | No | PIA | PIA IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | -173 d | 90 d | 2009-02-12 08:00 | 2009-04-08 17:00 | 2009-09-30 08:00 | 2009-12-28 17:00
736 | 3 | No | PIA | PIA IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | -173 d | 35 d | 2009-04-09 08:00 | 2009-07-01 17:00 | 2009-12-29 08:00 | 2010-02-01 17:00
737 | 3 | No | PIA | PIA IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | -173 d | 15 d | 2010-04-08 08:00 | 2010-04-22 17:00 | 2010-02-02 08:00 | 2010-02-16 17:00
738 | 3 | No | PIA | PIA Flight Check | NA | No | 0% | -173 d | 2 d | 2009-07-02 08:00 | 2009-07-08 17:00 | 2010-02-17 08:00 | 2010-02-18 17:00
739 | 3 | No | PIA | PIA Initial Operating Capability (IOC) | NA | No | 0% | -173 d | 0 d | 2009-07-08 17:00 | 2009-07-08 17:00 | 2010-02-22 17:00 | 2010-02-22 17:00
740 | 3 | No | PIA | Operational Suitability Demonstration (OSD) | NA | No | 0% | -173 d | 28 d | 2009-07-09 08:00 | 2009-09-16 17:00 | 2010-02-23 08:00 | 2010-03-22 17:00
741 | 3 | No | PIA | PIA Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | -173 d | 0 d | 2009-09-16 17:00 | 2009-09-16 17:00 | 2010-03-22 17:00 | 2010-03-22 17:00
742 | 3 | No | PIA | PIA Site Dismantle/Deactivation Planning | NA | No | 0% | 0 d | 161 d | 2009-09-17 08:00 | 2010-06-23 17:00 | 2010-03-23 08:00 | 2010-08-30 17:00
743 | 3 | No | PIA | PIA Start Dismantle/Deactivate | NA | No | 0% | 1 d | 0 d | 2010-06-23 17:00 | 2010-06-23 17:00 | 2010-08-30 17:00 | 2010-08-30 17:00
744 | 3 | No | PIA | PIA Dismantle/Deactivate | NA | No | 0% | 0 d | 182 d | 2010-06-24 08:00 | 2010-08-18 17:00 | 2010-08-31 08:00 | 2011-02-28 17:00
745 | 3 | No | PIA | PIA Complete Real Estate Transfer | NA | No | 0% | 0 d | 182 d | 2010-06-24 08:00 | 2010-08-18 17:00 | 2011-03-01 08:00 | 2011-08-29 17:00
746 | 3 | No | PIA | PIA Complete (Latest Finish) | NA | No | 0% | 0 d | 0 d | 2010-09-30 17:00 | 2010-09-30 17:00 | 2011-08-29 17:00 | 2011-08-29 17:00
747 | 2 | Yes | Site 65 TBD | Site 65 (formerly RFD) | NA | No | 89% | 824 d | 1540 d | 2002-08-20 08:00 | 2010-01-29 17:00 | 2002-08-20 08:00 | 2008-07-01 17:00
748 | 3 | No | Site 65 | Site 65 Environmental Studies | NA | No | 100% | 0 d | 591 d | 2002-08-20 08:00 | 2004-11-23 17:00 | 2002-08-20 08:00 | 2004-11-23 17:00
749 | 3 | No | Site 65 | Site 65 Real Estate Acquisition (Prel) | NA | No | 100% | 0 d | 726 d | 2004-11-30 08:00 | 2006-12-01 17:00 | 2004-11-30 08:00 | 2007-08-31 17:00
750 | 3 | No | Site 65 | Deployment Decision for this System on Hold | NA | No | 40% | 456 d | 305 d | 2007-08-31 08:00 | 2007-09-27 17:00 | 2007-09-01 08:00 | 2008-07-01 17:00
751 | 3 | No | Site 65 | Site 65 Start Site Construction | NA | No | 0% | 456 d | 0 d | 2007-01-29 08:00 | 2007-11-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
752 | 3 | No | Site 65 | Site 65 Site Construction | NA | No | 0% | 456 d | 0 d | 2007-01-29 08:00 | 2007-11-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
753 | 3 | No | Site 65 | Site 65 Equipment Delivered to Site | NA | No | 0% | 456 d | 0 d | 2007-11-02 17:00 | 2007-11-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
754 | 3 | No | Site 65 | Site 65 Equipment Install and Optimization | NA | No | 0% | 456 d | 0 d | 2007-11-05 08:00 | 2008-02-22 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
755 | 3 | No | Site 65 | Site 65 Site Acceptance Test (SAT) | NA | No | 0% | 456 d | 0 d | 2008-02-25 08:00 | 2008-03-07 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
756 | 3 | No | Site 65 | Site 65 Resolution of Open Items | NA | No | 0% | 456 d | 0 d | 2008-03-10 08:00 | 2008-05-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
757 | 3 | No | Site 65 | Site 65 CAI/DD250 Signed | NA | No | 0% | 456 d | 0 d | 2008-05-02 17:00 | 2008-05-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
758 | 3 | No | Site 65 | Site 65 IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 456 d | 0 d | 2008-05-05 08:00 | 2008-06-27 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
759 | 3 | No | Site 65 | Site 65 IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 456 d | 0 d | 2008-06-30 08:00 | 2008-09-19 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
760 | 3 | No | Site 65 | Site 65 IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 456 d | 0 d | 2007-12-01 17:00 | 2007-12-01 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
761 | 3 | No | Site 65 | Site 65 Flight Check | NA | No | 0% | 456 d | 0 d | 2008-09-22 08:00 | 2008-09-26 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
762 | 3 | No | Site 65 | Site 65 Initial Operating Capability (IOC) | NA | No | 0% | 456 d | 0 d | 2008-09-26 17:00 | 2008-09-26 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
763 | 3 | No | Site 65 | Site 65 Operational Suitability Demonstration (OSD) | NA | No | 0% | 456 d | 0 d | 2008-09-29 08:00 | 2008-12-05 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
764 | 3 | No | Site 65 | Site 65 Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 456 d | 0 d | 2008-12-05 17:00 | 2008-12-05 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
765 | 3 | No | Site 65 | Site 65 Site Dismantle/Deactivation Planning | NA | No | 0% | 1154 d | 0 d | 2008-12-08 08:00 | 2009-05-22 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
766 | 3 | No | Site 65 | Site 65 Start Dismantle/Deactivate | NA | No | 0% | 1154 d | 0 d | 2009-05-22 17:00 | 2009-05-22 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
767 | 3 | No | Site 65 | Site 65 Dismantle/Deactivate | NA | No | 0% | 1154 d | 0 d | 2009-05-25 08:00 | 2009-07-17 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
768 | 3 | No | Site 65 | Site 65 Complete Real Estate Transfer | NA | No | 0% | 1154 d | 0 d | 2009-05-25 08:00 | 2009-07-17 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
769 | 3 | No | Site 65 | Site 65 Complete (Latest Finish) | NA | No | 0% | 1154 d | 0 d | 2010-01-29 17:00 | 2010-01-29 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
770 | 2 | Yes | Site 66 TBD | Site 66 (formerly FWA) | NA | No | 89% | 0 d | 1540 d | 2002-08-20 08:00 | 2010-01-29 17:00 | 2002-08-20 08:00 | 2008-07-01 17:00
771 | 3 | No | Site 66 | Site 66 Environmental Studies | NA | No | 100% | 0 d | 591 d | 2002-08-20 08:00 | 2004-11-23 17:00 | 2002-08-20 08:00 | 2004-11-23 17:00
772 | 3 | No | Site 66 | Site 66 Real Estate Acquisition (Prel) | NA | No | 100% | 0 d | 726 d | 2004-11-30 08:00 | 2006-12-01 17:00 | 2004-11-30 08:00 | 2007-08-31 17:00
773 | 3 | No | Site 66 | Deployment Decision for this System on Hold | NA | No | 40% | 0 d | 305 d | 2007-08-31 08:00 | 2007-09-27 17:00 | 2007-09-01 08:00 | 2008-07-01 17:00
774 | 3 | No | Site 66 | Site 66 Start Site Construction | NA | No | 0% | 0 d | 0 d | 2007-01-29 08:00 | 2007-11-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
775 | 3 | No | Site 66 | Site 66 Site Construction | NA | No | 0% | 0 d | 0 d | 2007-01-29 08:00 | 2007-11-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
776 | 3 | No | Site 66 | Site 66 Equipment Delivered to Site | NA | No | 0% | 0 d | 0 d | 2007-11-02 17:00 | 2007-11-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
777 | 3 | No | Site 66 | Site 66 Equipment Install and Optimization | NA | No | 0% | 0 d | 0 d | 2007-11-05 08:00 | 2008-02-22 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
778 | 3 | No | Site 66 | Site 66 Site Acceptance Test (SAT) | NA | No | 0% | 0 d | 0 d | 2008-02-25 08:00 | 2008-03-07 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
779 | 3 | No | Site 66 | Site 66 Resolution of Open Items | NA | No | 0% | 0 d | 0 d | 2008-03-10 08:00 | 2008-05-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
780 | 3 | No | Site 66 | Site 66 CAI/DD250 Signed | NA | No | 0% | 0 d | 0 d | 2008-05-02 17:00 | 2008-05-02 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
781 | 3 | No | Site 66 | Site 66 IOC Readiness Phase 1 (thru Ph 1 Report Approval) | NA | No | 0% | 0 d | 0 d | 2008-05-05 08:00 | 2008-06-27 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
782 | 3 | No | Site 66 | Site 66 IOC Readiness Phase 2 (thru Ph 2 Report Approval) | NA | No | 0% | 0 d | 0 d | 2008-06-30 08:00 | 2008-09-19 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
783 | 3 | No | Site 66 | Site 66 IOC Readiness Phase 3 (before Flight Check) | NA | No | 0% | 0 d | 0 d | 2007-12-01 17:00 | 2007-12-01 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
784 | 3 | No | Site 66 | Site 66 Flight Check | NA | No | 0% | 0 d | 0 d | 2008-09-22 08:00 | 2008-09-26 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
785 | 3 | No | Site 66 | Site 66 Initial Operating Capability (IOC) | NA | No | 0% | 0 d | 0 d | 2008-09-26 17:00 | 2008-09-26 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
786 | 3 | No | Site 66 | Site 66 Operational Suitability Demonstration (OSD) | NA | No | 0% | 0 d | 0 d | 2008-09-29 08:00 | 2008-12-05 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
787 | 3 | No | Site 66 | Site 66 Operational Readiness Date (ORD)/Commissioning | NA | No | 0% | 0 d | 0 d | 2008-12-05 17:00 | 2008-12-05 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
788 | 3 | No | Site 66 | Site 66 Site Dismantle/Deactivation Planning | NA | No | 0% | 0 d | 0 d | 2008-12-08 08:00 | 2009-05-22 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
789 | 3 | No | Site 66 | Site 66 Start Dismantle/Deactivate | NA | No | 0% | 0 d | 0 d | 2009-05-22 17:00 | 2009-05-22 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
790 | 3 | No | Site 66 | Site 66 Dismantle/Deactivate | NA | No | 0% | 0 d | 0 d | 2009-05-25 08:00 | 2009-07-17 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
791 | 3 | No | Site 66 | Site 66 Complete Real Estate Transfer | NA | No | 0% | 0 d | 0 d | 2009-05-25 08:00 | 2009-07-17 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
792 | 3 | No | Site 66 | Site 66 Complete (Latest Finish) | NA | No | 0% | 0 d | 0 d | 2010-01-29 17:00 | 2010-01-29 17:00 | 2008-07-01 17:00 | 2008-07-01 17:00
Note on G1: Susan Barton: "Yes" if current Forecasted Start is 45 days or less away from Goal in Column F. Start is highlighted in Red if it surpasses this target da