## WBS_Master
T | BOTH | Actual price | Argonne National Laboratory
F | DOE | Catalog price | Brookhaven Software
| NSF | Vendor quotation | Brookhaven Facilities
|  | Engineering judgement | Lawrence Berkeley Laboratory
|  | Parametric estimate | Indiana University
|  | Physicist estimate | University of Chicago
|  | Level of Effort | Composite University rate
|  | In Contract | UC-Berkeley
Based on actual labor rates
|  |  |  | mm/dd/yy | mm/dd/yy
WBSNo | PBS Number | Description | Atlas Num Ref | Task Start Date | Task End Date | WBS Dictionary | Funded By | Institution | Sub System Manager | Contact | Contact Phone | Contact Fax | Contact Email | CORE Value | Details of Estimate | Tech Risk | Cost Risk | Schedule Risk | DesignRisk | Tech Weight | Cost Weight | Schedule Weight | BasisofEst | Complete (T/F)
2 |  | KOPIO
2.1 |  | Calorimeter System |  |  |  | The calorimeter system consists of 2235 Shashlyk modules assembled into a calorimeter (2.1.1), readout electronics (2.1.2), and monitoring system (2.1.3), and the effort necessary to design, prototype, fabricate, install, and commission the calorimeter system. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.1 |  | Photon Calorimeter |  |  |  | 2285 Shashlyk modules will be designed, prototyped, and fabricated. The modules are sandwiches consisting of 240 layers of alternating scintillator (1.5 mm thick) and lead (0.35 mm thick) read out by 72 wave length shifting fibers passing through holes in the scintillator. Calibration will be performed for a finite number of modules. Oboard electronics will be designed, prototyped, and procured, then installed with the Modules in the mechanics. Mechanics will house the modules and electronics in two structures installed in the pit. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.1.1 |  | Modules |  |  |  | This effort encompasses the design, prototype, fabrication, shipping, calibration, and installation of 2285 Shashlyk modules. G82
2.1.1.1.1 |  | Prototyping of Shashlyk Modules |  |  |  | x number of modules will be manufactured and tested to validate final production configuration. This effort will include fabrication of x number of modules, shipping to the US, and test and inspection to determine compliance with the specification. Test and inspection equipment not developed for production is included in this effort. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.1.1.1.1 |  | R & D of Polystyrene Based Scintillator |  |  |  | This effort will test different doping to match scintillator emissions to wavelength shifting fiber response. It includes test equipment and labor.
2.1.1.1.1.2 |  | Design of Prototype Module and Tooling |  |  |  | The prototyping effort will include design of the full-scale module and production tooling. A full-scale module will be produced under this effort to validate design and procedures. It includes drawings, specifications, and procedures.
2.1.1.1.1.3 |  | Fabrication of Experimental Batch of 25 Modules and Shipping to BNL |  |  |  | An Experimental Batch of 25 Modules will be fabricated at IHAP and Shipped to BNL for testing. It includes materials, labor, packing, shipping, and rigging.
2.1.1.1.1.4 |  | Testing of Modules with Different Photodetectors. |  |  |  | A specification will be jointly developed with the Russian Collaboration for final production of the Shashlyk modules.
2.1.1.1.2 |  | Design of Shashlyk Module |  |  |  | The final production design of the modules will be completed under this WBS . This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.1.1.2.1 |  | Design of Module |  |  |  | A specification will be jointly developed with the Russian Collaboration for final production of the Shashlyk modules. This effort includes labor.
2.1.1.1.2.2 |  | Design of Production Tools |  |  |  | Production tools not developed during the prototyping effort will be designed under this effort. It includes labor to develop specifications and drawings.
2.1.1.1.2.3 |  | Design of a Module Photo-Readout. |  |  |  | This effort will design the photodetector mounting. It includes labor for drawings and specifications.
2.1.1.1.3 |  | Fabrication/Production of Shashlyk Modules |  |  |  | 2285 Shashlyk modules will be produced by the Russian collaboration and shipped to the US. Modules will be unpacked, tested and inspected. Test and inspection equipment is included in this effort.
2.1.1.1.3.1 |  | Documentation |  |  |  | Documentation for the fabrication of the modules will be performed under this WBS. It includes drawings, specifications, procedures, QA and database for the production modules.
2.1.1.1.3.2 |  | Purchase of Module Components |  |  |  | The modules will fabricated by contract with IHAP.
2.1.1.1.3.3 |  | Purchase of Photo Readout Components |  |  |  | The photo readout components will be procured. This effort includes specifications, drawings and other documentation for bid packages, bid evaluation, vendor oversight, and acceptance testing. It includes material and labor.
2.1.1.1.3.4 |  | Assembling of Modules (Includes Fiber Installation) |  |  |  | This is the effort required to install the fibers and photodetectors onto the modules.
2.1.1.1.3.5 |  | Design and Assembling of Setup for Acceptance Test of Modules |  |  |  | This effort includes fabrication of test equipment and other facilities for testing modules. It includes labor and materials.
2.1.1.1.3.6 |  | Acceptance Test of Modules |  |  |  | Modules will be acceptance tested in the US. This effort includes labor for testing.
2.1.1.1.3.7 |  | Shipping of Modules (4 Batches) to BNL |  |  |  | Modules will be shipped to the US. This effort includes rigging, packing, shipping and storage.
2.1.1.1.4 |  | Testing/Calibration of Modules |  |  |  | A percentage of modules will be calibrated in a test beam to be performed in the US at an accelerator facility. This effort includes special test apparatus and electronics to obtain the calibration data, and fees for machine time. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.1.1.4.1 |  | Pre-Install Test of Modules (Cosmic Ray Test) |  |  |  | This testing will verify correct installation of equipment on modules before installation into the detector. It includes test equipment and labor for setup and testing.
2.1.1.1.4.2 |  | Beam Test of 100 Modules from each Shipping Batch |  |  |  | This effort includes special test apparatus and electronics to obtain the calibration data, and fees for machine time.
2.1.1.2 |  | Readout Electronics |  |  |  | The readout electronics will be designed, prototyped and tested, and procured and assembled for the calorimeter modules. It is the interface for the 2200 channels of photodetectors for the calorimeter. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.1.2.1 |  | Evaluate Analog and Timing Chips |  |  |  | Various chips will be evaluated to determine their suitability for use in the readout electronics. This effort includes labor.
2.1.1.2.2 |  | Design of Readout Board |  |  |  | Engineering and design for the readout electronics. Final drawings and specifications will be produced.
2.1.1.2.3 |  | Test Prototype of Readout Board |  |  |  | Prototype boards will be produced to determine their sensitivity and timing and suitability for use in the calorimeter. This effort includes labor and materials for fabrication and procurement of test boards, test equipment, and testing.
2.1.1.2.4 |  | Fabrication/Production of Readout Boards |  |  |  | This effort is the labor and materials necessary to procure components and fabricate the boards for use in the calorimeter. It includes labor for purchase order and bid package preparation, vendor oversight, procedures for fabrication, fabrication labor, and final testing, as well as materials for the components, assembly tools and equipment, and test equipment.
2.1.1.2.5 |  | Pre-Install Test of Readout Boards |  |  |  | This effort is the labor and test equipment for testing of the boards prior to installation at BNL into t he calorimeter.
2.1.1.2.6 |  | System Test of Readout System |  |  |  | The readout electronics will be system tested prior to calorimeter and detector commissioning.
2.1.1.3 |  | Mechanics (Support Frame of Calorimeter & Other Support System) |  |  |  | Frames will mount the completed modules, onboard electronics and monitoring system in the calorimeter. This effort will include the design, prototype, fabrication, shipping and installation of the mechanics in the calorimeter pit. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.1.3.1 |  | Design of Calorimeter Support Frame |  |  |  | Engineering to design the mechanics for the calorimeter. Final design drawings will be produced.
2.1.1.3.2 |  | Design of Railway System |  |  |  | This effort will design the railway system for the moving supports of the calorimeter system. It includes labor for drawings and specifications.
2.1.1.3.3 |  | Design of Assembling and Servicing System |  |  |  | This effort will design the Assembling and Servicing System. This system is the structure and platforms necessary to assemble and service the calorimeter. This effort includes labor for drawings and specifications.
2.1.1.3.4 |  | Manufacture of Calorimeter Support Frame |  |  |  | The structure will be manufactured in IHAP. This effort is the labor and materials for fabrication, QA, oversight, rigging, packing, shipping and storage.
2.1.1.3.5 |  | Manufacture of Railway System |  |  |  | This is the labor and materials necessary to fabricate, pack, ship and rig the railway system at BNL.
2.1.1.3.6 |  | Manufacture of Assembling & Servicing System |  |  |  | This is the labor and materials necessary to fabricate, pack, ship and rig the assembling and servicing system at BNL.
2.1.2 |  | Cabling |  |  |  | This includes the readout electronics and cables between t he calorimeter and the counting house. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.2.1 |  | Design |  |  |  | Engineering and design for the readout electronics. Final drawings will be produced.
2.1.2.2 |  | Manufacture |  |  |  | 2 ADC and 2 TDC crates will be assembled from existing equipment. Cables, connectors, cable tray, and miscellaneous hardware will be procured. Some software development.
2.1.3 |  | Monitoring and Calibration System |  |  |  | A laser monitoring system will be designed, prototyped, fabricated and installed for the calorimeter system. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.3.1 |  | Design of Monitoring and Calibration System |  |  |  | Engineering necessary to design a laser and readout system to monitor the calorimeter modules. Final drawings will be produced. Interface with the mechanics design to accommodate the monitoring system.
2.1.3.2 |  | Prototyping of a Monitoring and Calibration System |  |  |  | Design, procurement and fabrication, and test of prototype devices to demonstrate performance of monitoring system concept.
2.1.3.3 |  | Fabrication /Prod of Monitoring and Calibration System (as a whole) |  |  |  | Specifications and statements of work for procurement of the components for the monitoring system. RFP, bid evaluation, and vendor oversight. Assembly and test of monitoring system devices.
2.1.4 |  | Assembling and Installation Calorimeter |  |  |  | The components of the calorimeter will be staged for installation at BNL. It includes labor and materials for tooling, rigging, survey, assembly, adjustment and clean-up. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.4.1 |  | Mounting of Railway and Cabling Systems |  |  |  | This is the labor and materials necessary to rig, position, and install the railway system at BNL.
2.1.4.2 |  | Installation of Calorimeter Support Frame |  |  |  | This is the labor and materials necessary to rig, position, and install the Calorimeter support frame at BNL.
2.1.4.3 |  | Installation of Assembling and Service System |  |  |  | This is the labor and materials necessary to rig, position, assemble and install the assembling and servicing system at BNL.
2.1.4.4 |  | Assembling of Modules into Calorimeter Frame |  |  |  | This is the labor and materials necessary to rig, position, and install the modules into the calorimeter support frame at BNL.
2.1.4.5 |  | Installation of Monitoring and Calibration System |  |  |  | This is the labor and materials necessary to install and connect the monitoring and calibration system into the calorimeter at BNL.
2.1.4.6 |  | Installation of Readout Boards |  |  |  | This is the labor and materials necessary to install and connect the readout system into the calorimeter at BNL.
2.1.4.7 |  | Cabling |  |  |  | This is the labor and materials necessary to install the cabling for the calorimeter at BNL.
2.1.5 |  | Commissioning |  |  |  | Labor and testing to commission the calorimeter system. This includes run time at AGS [or other test methodology] to demonstrate performance. Adjustment and final tuning of the calorimeter system. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.1.5.1 |  | Test of Moving System |  |  |  | This is the labor and materials necessary to rig, position, install and checkout the Calorimeter moving system at BNL.
2.1.5.2 |  | Complete Test of Calorimeter (Engineering Run) |  |  |  | [I don't think this really belongs here, I think this is maybe even it's own level 2.]
2.2 |  | Preradiator |  |  |  | The Preradiator consists of 32 modules containing and inactive converter material, a dual coordinate drift chamber, and a scintillator, with all necessary electronics for read out and data transmission. The effort is distributed between Chamber System (2.2.1), scintillator system (2.2.2) and mechanics (2.2.3), and the effort necessary to design, prototype, fabricate, install, and commission the Preradiator system. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.1 |  | Chamber System |  |  |  | The chamber system consists of 288 dual coordinate drift chambers and associated electronics for read out. This WBS describes the effort necessary to design, prototype, fabricate, and assemble the Chamber system. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.1.1 |  | Chambers |  |  |  | The 288 dual coordinate drift chambers will be fabricated at TRIUMF. This WBS describes the effort necessary to design, prototype, fabricate, and assemble the Chambers into Preradiator Modules. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.1.1.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the chambers for prototyping, in-house fabrication, testing, packing, shipping, and installation at BNL. Drawings and specifications will be developed for in-house production of the chamber mechanical structure, high voltage distribution, and signal transmission.
2.2.1.1.2 |  | Prototype |  |  |  | A substantial, five level prototype effort is planned for the chambers. It will include operational, electronics design, beam test and pre-production prototypes to validate the electronics performance and develop the fabrication procedure. Tooling for production and test equipment are included in this effort.
2.2.1.1.3 |  | Fabrication/Production |  |  |  | TRIUMF will produce 288 chambers. This effort includes labor and materials.
2.2.1.1.4 |  | Installation |  |  |  | Chambers will be assembled into Preradiator Modules.
2.2.1.2 |  | Analog Electronics |  |  |  | The analog electronics consists of 90,000 channels of ADCs for the dual coordinate drift chambers. This WBS describes the effort necessary to design, prototype, fabricate or procure, and assemble the analog electronics into Preradiator Modules. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.1.2.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the analog electronics for prototyping, in-house fabrication or procurement, testing, and installation into Preradiator modules. Drawings and specifications will be developed. Fabrication procedures will be developed for in-house production, or bid packages will be prepared for outside procurement. This effort will include a make vs. buy trade study.
2.2.1.2.2 |  | Prototype |  |  |  | A substantial, five level prototype effort is planned for the analog electronics for the chambers. It will include operational, electronics design, beam test and pre-production prototypes to validate the electronics performance and develop the fabrication procedure. Tooling for production and test equipment, in addition to the chamber test equipment, are included in this effort.
2.2.1.2.3 |  | Fabrication/Production |  |  |  | TRIUMF will produce or procure analog electronics for 288 chambers, including final test or acceptance test. This effort includes labor and materials.
2.2.1.2.4 |  | Installation |  |  |  | analog electronics will be assembled onto chambers and installed into Preradiator Modules.
2.2.1.3 |  | Timing Electronics |  |  |  | The timing electronics consists of 90,000 channels of TDCs for the dual coordinate drift chambers. This WBS describes the effort necessary to design, prototype, fabricate or procure, and assemble the timing electronics into Preradiator Modules. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.1.3.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the timing electronics for prototyping, in-house fabrication or procurement, testing, and installation into Preradiator modules. Drawings and specifications will be developed. Fabrication procedures will be developed for in-house production, or bid packages will be prepared for outside procurement. This effort will include a make vs. buy trade study.
2.2.1.3.2 |  | Prototype |  |  |  | A substantial, five level prototype effort is planned for the timing electronics for the chambers. It will include operational, electronics design, beam test and pre-production prototypes to validate the electronics performance and develop the fabrication procedure. Tooling for production and test equipment, in addition to the chamber test equipment, are included in this effort.
2.2.1.3.3 |  | Fabrication/Production |  |  |  | TRIUMF will produce or procure timing electronics for 288 chambers, including final test or acceptance test. This effort includes labor and materials.
2.2.1.3.4 |  | Installation |  |  |  | Timing electronics will be assembled onto chambers and installed into Preradiator Modules.
2.2.1.4 |  | High Voltage Electronics |  |  |  | The high voltage electronics consists of high voltage power supplies and cables for the dual coordinate drift chambers. This WBS describes the effort necessary to design, procure, and assemble the high voltage electronics into Preradiator Modules. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.1.4.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the high voltage for procurement, testing, and installation into Preradiator modules. Drawings and specifications will be developed. Bid packages will be prepared for outside procurement.
2.2.1.4.3 |  | Fabrication/Production |  |  |  | TRIUMF will procure high voltage electronics for 288 chambers, including acceptance test. This effort includes labor and materials.
2.2.1.4.4 |  | Installation |  |  |  | High voltage electronics will be assembled onto chambers and installed into Preradiator Modules.
2.2.1.5 |  | Gas System |  |  |  | The dual coordinate drift chambers operate with an Argon/CF4 gas supply and recirculating system at atmospheric pressure. This WBS describes the effort necessary to design, procure, and assemble the gas system. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.1.5.1 |  | Design |  |  |  | This effort includes the tasks necessary to design an Argon/CF4 gas supply and recirculating system operating at atmospheric pressure for the chambers. Drawings and specifications will be developed. Fabrication procedures will be developed for in-house assembly, and bid packages and purchase orders will be prepared for outside procurement.
2.2.1.5.3 |  | Fabrication/Production |  |  |  | TRIUMF will procure and assemble components for the gas system for the 288 chambers. This effort includes labor and materials, and final test of the system at TRIUMF.
2.2.1.5.4 |  | Installation |  |  |  | The gas system will be broken down, packed and shipped to BNL, where it will be reassembled and installed in the experiment.
2.2.1.6 |  | Readout/DAQ |  |  |  | The Readout/DAQ consists of 180,000 channels of optical cables, data transmission and slow controls for the dual coordinate drift chamber electronics. This WBS describes the effort necessary to design, prototype, fabricate or procure, and assemble the Readout/DAQ for the Preradiator chamber electronics. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.1.6.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the Readout/DAQ for prototyping, in-house fabrication and procurement, testing, and assembly for use with the Preradiator electronics. Drawings and specifications will be developed. Fabrication procedures will be developed for in-house production, and bid packages and purchase orders will be prepared for outside procurement.
2.2.1.6.2 |  | Prototype |  |  |  | A 100 channel prototype effort is planned for the Readout/DAQ to validate the electronics performance and speed for the Preradiator chamber system. A throughput of 50Mb/second is essential for performance of the experiment. Test equipment is included in this effort, in addition to labor and materials.
2.2.1.6.3 |  | Fabrication/Production |  |  |  | TRIUMF will produce Readout/DAQ electronics for 288 chambers, including final test and acceptance test. This effort includes labor and materials.
2.2.1.6.4 |  | Installation |  |  |  | Readout/DAQ electronics will be assembled near the Preradiator equipment on the experimental floor.
2.2.2 |  | Scintillator System |  |  |  | The scintillator system consists of 288 scintillator modules and associated electronics for read out. This WBS describes the effort necessary to design, prototype, fabricate, and assemble the scintillator system. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.2.1 |  | Scintillator Plates |  |  |  | The 288 scintillator modules will be fabricated at TRIUMF. This WBS describes the effort necessary to design, prototype, fabricate, and assemble the scintillators into Preradiator Modules. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.2.1.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the scintillators for prototyping, material and equipment procurement, in-house fabrication, testing, and assembly into Preradiator Modules. It includes evaluation of necessary tolerances. Drawings and specifications will be developed for in-house production as well as bid packages and evaluation for material procurement of the scintillator.
2.2.2.1.2 |  | Prototype |  |  |  | A substantial, five level prototype effort is planned for the scintillators, to be conducted in tandem with the chamber prototyping. It will include operational, electronics design, beam test and pre-production prototypes to validate the electronics performance and develop the fabrication procedure. Tooling for production and test equipment are included in this effort.
2.2.2.1.3 |  | Fabrication/Production |  |  |  | TRIUMF will procure scintillators to construct 288 module elements. This effort includes labor for vendor oversight and receiving inspection, and materials for scintillator and test equipment to monitor light output and uniformity which is critical to the performance of this element.
2.2.2.1.4 |  | Installation |  |  |  | Scintillators will be assembled into Preradiator Modules.
2.2.2.2 |  | Wavelength Shifter Fibers |  |  |  | The 288 scintillator modules will be instrumented with wavelength shifting fibers at TRIUMF. This WBS describes the effort necessary to design, prototype, procure and assemble the fibers into the scintillator system. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.2.1.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the wavelength shifting fibers for prototyping, material and equipment procurement, in-house fabrication, testing, and assembly into the scintillator system. It includes evaluation of necessary tolerances. Drawings and specifications will be developed for in-house production as well as bid packages and evaluation for material procurement of the fibers.
2.2.2.1.2 |  | Prototype |  |  |  | A substantial, five level prototype effort is planned for the wavelength shifting fibers, to be conducted in tandem with the chamber prototyping. It will include operational, electronics design, beam test and pre-production prototypes to validate the electronics performance and develop the fabrication procedure. Tooling for production and test equipment are included in this effort.
2.2.2.1.3 |  | Fabrication/Production |  |  |  | TRIUMF will procure wavelength shifting fibers to construct 288 module elements. This effort includes labor for vendor oversight and receiving inspection, and materials for scintillator and test equipment to monitor light output and uniformity which is critical to the performance of this element.
2.2.2.1.4 |  | Installation |  |  |  | Wavelength shifting fibers will be assembled into the scintillator system.
2.2.2.3 |  | Scintillator Instrumentation |  |  |  | The 288 scintillator modules will be fabricated at TRIUMF. This WBS describes the effort necessary to design, prototype, procure and/or fabricate, and assemble the scintillator instrumentation into the scintillator system. The instrumentation system will be composed of photomultiplier tubes, and ADC and TDC electronics to read them out. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.2.3.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the scintillator instrumentation for prototyping, material and equipment procurement, in-house fabrication, testing, and assembly into the scintillator system. It includes evaluation of PMTs and trade study to determine whether the chamber ADC/TDC can be used, or make/buy will be the equipment used. Drawings and specifications will be developed for in-house production as well as bid packages and evaluation for material procurement of the PMTs, ADCs and TDCs.
2.2.2.3.2 |  | Prototype |  |  |  | A two level prototype effort is planned for the scintillator instrumentation, and will be integrated with higher level chamber prototyping. It will include operational, electronics design, beam test and pre-production prototypes to validate the electronics performance and develop the fabrication procedure. Tooling for production is included in this effort.
2.2.2.3.3 |  | Fabrication/Production |  |  |  | TRIUMF will procure scintillator instrumentation to construct 288 module elements. This effort includes labor for trade studies, bid evaluation and vendor oversight, and receiving inspection, and materials for PMT, ADC, and TDC testing.
2.2.2.3.4 |  | Installation |  |  |  | Scintillator instrumentation will be assembled into Preradiator Modules.
2.2.3 |  | Mechanics |  |  |  | The 32 Preradiator Modules will be fabricated at TRIUMF on a module structure. The modules will be installed at BNL on a Support Structure which consists of frames and cables. This WBS describes the effort necessary to design, prototype, fabricate, and assemble the structure for the Preradiator Modules. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.2.3.1 |  | Design |  |  |  | This effort includes the tasks necessary to design the module structure and support structure for prototyping, and in-house fabrication, packing, shipping, and installation at BNL. Module structure is composed of layers of aluminum and lead. Drawings and specifications will be developed for production of the module mechanical structure and Preradiator support structure.
2.2.3.2 |  | Prototype |  |  |  | A two level prototype effort is planned for the Module structure. A 50cm x 50cm x 8 layers deep prototype will be constructed, followed by a full scale, pre-production, 8 layer prototype. Tooling for production and test equipment are included in this effort.
2.2.3.3 |  | Fabrication/Production |  |  |  | TRIUMF will module structures for 32 modules. This effort includes labor and materials.
2.2.3.4 |  | Installation |  |  |  | Module structures will be assembled into Preradiator Modules with the other Preradiator components. These will be packed and shipped to BNL. Preradiator support structure will be built at BNL. This effort includes packing, shipping, rigging at BNL and TRIUMF, installation of the modules at BNL, and construction of the Preradiator support structure at BNL.
2.3 |  | Photon Veto |  |  |  | The Photon Veto system consists of a lead/scintillator sandwich that is read out by wavelength-shifting fibers and phototubes at each end. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.1 |  | Module |  |  |  | The photon veto system module is a Pb scintillator sandwich consisting of 23 7 mm thick, 15 cm wide scintillator plates interspersed with 1 mm of Pb. The length of each element depends on its specific location in the apparatus, with the longest element being 4 m. The scintillators are extruded, with 1 mm grooves placed 10 mm apart running their full length. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.1.1 |  | Design |  |  |  | This effort includes the design of the modules and preparation of drawings for production/fabrication.
2.3.1.2 |  | Prototype |  |  |  | A prototype has already been completed.
2.3.1.3 |  | Fabrication/Production |  |  |  | The photon veto modules will be fabricated at INR Moscow. This effort includes oversight of the fabrication and testing at the institute. The modules will be shipped to the US. They will be received, assembled and tested in preparation for their installation into the experiment. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.1.3.1 |  | Fabrication |  |  |  | This effort is for module fabrication by an outside vendor with oversight by INR Moscow. It includes contracting expenses for the vendor to produce the modules, testing at the institute, and a level of effort for oversight.
2.3.1.3.2 |  | Shipping to US |  |  |  | This WBS includes the shipping to the US from Moscow.
2.3.1.3.3 |  | Receiving Test & Assembly |  |  |  | This is the effort necessary to receive, test and assemble the modules prior to installation in the experiment. It includes test equipment.
2.3.1.4 |  | Installation |  |  |  | This is the labor and equipment necessary to install the Modules into the experiment. It includes rigging labor and equipment, as well as technician labor and equipment for their installation.
2.3.2 |  | Instrumentation |  |  |  | This element is the read out of the Modules. It includes all effort to design, prototype, produce, install and test the read out equipment. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.2.1 |  | Design |  |  |  | This effort includes the design of the photo-multiplier tubes (PMT) and the dividers, and preparation of drawings for production/fabrication. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.2.2 |  | Prototype |  |  |  | A full length prototype will be constructed and tested to validate the design. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.2.2.1 |  | Construction |  |  |  | A full length prototype will be constructed for testing. These costs include labor and materials to construct one module.
2.3.2.2.2 |  | Beam Test |  |  |  | The prototype will be tested in a beam. This effort includes labor and materials to install the prototype in the beam, operate the beam, read out the prototype, and reduce the data to determine the performance of the prototype and its suitability for the Kopio experiment.
2.3.2.2.3 |  | Test Equipment |  |  |  | This is the test equipment necessary for the construction and beam test of the read out prototype.
2.3.2.3 |  | Fabrication/Production |  |  |  | The PMT and dividers will be fabricated at INR Moscow. This effort includes oversight of the fabrication and testing at the institute. The PMT and dividers will be shipped to the US. They will be received, assembled and tested in preparation for their installation into the experiment. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.2.3.1 |  | Fabrication |  |  |  | This effort is for PMT and divider fabrication by an outside vendor with oversight by INR Moscow. It includes contracting expenses for the vendor to produce the PMTs and dividers, testing at the institute, and a level of effort for oversight.
2.3.2.3.2 |  | Shipping to US |  |  |  | This WBS includes the shipping to the US from Moscow.
2.3.2.3.3 |  | Receiving Test & Assembly |  |  |  | This is the effort necessary to receive, test and assemble the read out prior to installation in the experiment. It includes test equipment.
2.3.2.4 |  | Installation |  |  |  | This is the labor and equipment necessary to install the read out into the experiment, and perform testing to verify function prior to commissioning.
2.3.3 |  | Crack Fillers
2.3.3.1 |  | Design
2.3.3.2 |  | Prototype
2.3.3.3 |  | Fabrication/Production
2.3.3.4 |  | Installation
2.3.3.5 |  | Commissioning
2.3.4 |  | Downstream Photon Veto
2.3.4.1 |  | Design
2.3.4.2 |  | Prototype
2.3.4.3 |  | Fabrication/Production
2.3.4.4 |  | Installation
2.3.4.5 |  | Commissioning
2.3.5 |  | Calibration & monitoring |  |  |  | This WBS is the calibration and monitoring system for the photon veto system. It provides real-time verification and adjustment during operation to assure performance. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.5.1 |  | Design |  |  |  | Engineering necessary to design a calibration and monitoring system to monitor the photon veto modules and read out. Final drawings will be produced. Interface with the mechanics design to accommodate the monitoring system.
2.3.5.2 |  | Prototype |  |  |  | Design, procurement and fabrication, and test of prototype devices to demonstrate performance of monitoring system concept.
2.3.5.3 |  | Fabrication/Production |  |  |  | Specifications and statements of work for procurement of the components for the monitoring system. RFP, bid evaluation, and vendor oversight. Assembly and test of x number of monitoring system devices.
2.3.5.4 |  | Installation |  |  |  | Labor and tooling necessary for installation of the monitoring system in the veto mechanics. Labor and contract labor to install hardware and cables.
2.3.5.5 |  | Pre-Commissioning Testing |  |  |  | Labor and testing to commission the calorimeter system. This includes x amount of run time at AGS [or other test methodology] to demonstrate performance. Adjustment and final tuning of the calorimeter system.
2.3.6 |  | Mechanics |  |  |  | The photon veto system mechanics will support the Pb/scintillator modules. Straight modules span the roof, floor and upstream parts of the enclosure, while curved modules make up the sides. The top modules span a 3.5m width and must be supported by an external truss structure. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.6.1 |  | Design |  |  |  | This effort includes the design of the mechanics and preparation of drawings in the US for production/fabrication in INR Moscow.
2.3.6.2 |  | Prototype |  |  |  | A prototype structure will be developed to validate the design. This effort includes labor, material and testing.
2.3.6.3 |  | Fabrication/Production |  |  |  | The photon veto mechanics will be fabricated at INR Moscow. This effort includes oversight of the fabrication, tooling, labor, materials and testing at the institute. The modules will be shipped to the US. They will be received, and staged in preparation for their installation into the experiment. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.6.3.1 |  | Fabrication |  |  |  | This effort is for mechanics fabrication by an outside vendor with oversight by INR Moscow. It includes contracting expenses for the vendor to produce the mechanics tooling, labor, materials and acceptance at the institute, and a level of effort for oversight.
2.3.6.3.2 |  | Shipping to US |  |  |  | This WBS includes the shipping to the US from Moscow.
2.3.6.3.3 |  | Receiving & Acceptance |  |  |  | This is the effort necessary to receive and accept the modules prior to installation in the experiment. It includes inspection equipment and rigging.
2.3.6.4 |  | Installation |  |  |  | This is the labor and equipment necessary to install the mechanics into the experiment. It includes rigging labor and equipment, as well as technician labor and equipment for their installation.
2.3.7 |  | System Design |  |  |  | This element is the electronics and other infrastructure to collect and analyze the data for the photon veto system. It includes all effort to design, prototype, produce, install and test the photon veto system. It is anticipated that the system will include preamps, ADC & TDC, high voltage power supplies, digitizers and cables. This WBS is a summary level, detail description and cost estimation are completed at lower levels.
2.3.7.1 |  | Design |  |  |  | This effort includes the design of the electronics and infrastructure and preparation of drawings and specifications for production/fabrication and procurement.
2.3.7.2 |  | Prototype |  |  |  | A prototype of the electronics system will be constructed and tested to validate the design. This WBS includes labor and material.
2.3.7.3 |  | Fabrication/Production |  |  |  | This effort includes preamps, ADC & TDC, high voltage power supplies, digitizers and cables that will be procured and/or fabricated. It includes cable tray and cable procurement and potentially contracting for installation.
2.3.7.4 |  | Installation |  |  |  | This is the labor, material and equipment necessary to install the system electronics and infrastructure into the experiment. It includes cable tray and cable installation.
2.3.7.5 |  | Pre-Commissioning Testing |  |  |  | This is the labor and equipment necessary to perform functional checks on the installed equipment prior to commissioning.
2.4 |  | Charged Part. Veto System
2.4.1 |  | Barrel Charged Part. Veto
2.4.1.1 |  | Scintillation Counter Modules
2.4.1.1.1 |  | Research & Development/Proto |  |  |  | At Zurich and at PSI including prototypes manufactured by Russian colleagues at BNL and in Moscow.
2.4.1.1.2 |  | Manufacture |  |  |  | At University of Zurich shops and in Swiss Industry.
2.4.1.1.3 |  | Tests |  |  |  | At University of Zurich and at PSI
2.4.1.2 |  | On-Detector Electronics
2.4.1.2.1 |  | Research & Development/Proto |  |  |  | At Zurich and at PSI including prototypes manufactured by Russian colleagues at BNL and in Moscow.
2.4.1.2.2 |  | Manufacture |  |  |  | At University of Zurich shops and in Swiss Industry.
2.4.1.3 |  | Detector Mechanics
2.4.1.3.1 |  | Design
2.4.1.3.2 |  | Manufacture |  |  |  | At University of Zurich shops and in Swiss Industry.
2.4.1.4 |  | Detector Assembly |  |  |  | At University of Zurich shops
2.4.1.5 |  | Calibration System
2.4.1.5.1 |  | Research & Development/Proto
2.4.1.5.2 |  | Manufacture
2.4.1.6 |  | Detector Test
2.4.1.7 |  | Integration into Vacuum System
2.4.1.7.1 |  | Overall Design |  |  |  | BNL and Yale in contact with University of Zurich
2.4.1.7.2 |  | Design (Signal, Supply Voltage & Cooling FTs) |  |  |  | University of Zurich in contact with BNL and Yale
2.4.1.7.3 |  | Manufacture (Signal, Supply Voltage & Cooling FTs) |  |  |  | American industry and University of Zurich shops
2.4.1.7.4 |  | Mechanics Design
2.4.1.7.5 |  | Mechanics Manufacture |  |  |  | American industry and University of Zurich shops
2.4.1.7.6 |  | Assembly (at BNL) |  |  |  | At BNL
2.4.1.7.7 |  | System Test
2.4.1.8 |  | Assembly (at BNL) |  |  |  | At BNL
2.4.2 |  | Downstream Charged Part. Veto
2.4.2.1 |  | Scintillation Counter Modules
2.4.2.1.1 |  | Research & Development/Proto |  |  |  | Yale and Russian colleagues at BNL and in Moscow
2.4.2.1.2 |  | Manufacture |  |  |  | Yale
2.4.2.1.3 |  | Tests |  |  |  | At BNL and at PSI
2.4.2.2 |  | On-Detector Electronics
2.4.2.2.1 |  | Research & Development/Proto |  |  |  | Yale and Russian colleagues at BNL and in Moscow
2.4.2.2.2 |  | Manufacture
2.4.2.3 |  | Detector Mechanics
2.4.2.3.1 |  | Design
2.4.2.3.2 |  | Manufacture
2.4.2.4 |  | Detector Assembly
2.4.2.5 |  | Calibration System
2.4.2.5.1 |  | Research & Development/Proto
2.4.2.5.2 |  | Manufacture
2.4.2.6 |  | Detector Test
2.4.2.7 |  | Integration into Vacuum System
2.4.2.7.1 |  | Overall Design
2.4.2.7.2 |  | Signal FTS
2.4.2.7.3 |  | Mechanics
2.4.2.7.4 |  | Manufacture
2.4.2.7.5 |  | Assembly (at BNL)
2.4.2.7.6 |  | System Test
2.4.3 |  | Beam Pipe Internal Veto
2.4.3.1 |  | Design
2.4.3.2 |  | Prototype
2.4.3.3 |  | Fabrication/Production
2.4.3.4 |  | Installation
2.4.3.5 |  | Commissioning
2.4.4 |  | CsI Upstream Veto
2.4.4.1 |  | Design
2.4.4.2 |  | Prototype
2.4.4.3 |  | Fabrication/Production
2.4.4.4 |  | Installation
2.4.4.5 |  | Commissioning
2.4.5 |  | Off-Detector Elec.'s (Readout & Data Acquistion)
2.4.5.1 |  | Cabling
2.4.5.2 |  | Low Voltage Supplies
2.4.5.3 |  | HV Supplies
2.4.5.4 |  | Readout
2.4.5.5 |  | Triggering
2.4.5.6 |  | Subsystem Data Acquistion
2.1.2 |  | Beam Hole Liner Counters
2.1.2.1 |  | Upstream
2.1.2.1.1 |  | Design
2.1.2.1.2 |  | Prototype
2.1.2.1.3 |  | Fabrication/Production
2.1.2.1.4 |  | Installation
2.1.2.1.5 |  | Commissioning
2.1.2.2 |  | Downstream
2.1.2.2.1 |  | Design
2.1.2.2.2 |  | Prototype
2.1.2.2.3 |  | Fabrication/Production
2.1.2.2.4 |  | Installation
2.1.2.2.5 |  | Commissioning
2.5 |  | Beam Catcher System |  |  |  | The beam catcher system consists of 512 aerogel Cherenkov counter modules assembled into distributed-aerogel counter (2.5.1), read out electronics (2.5.2), and monitoring system (2.5.3), and the effort necessary to desgn, prototype, fabricate, install, and commission the beam catcher system. This WBS is a summary level, detail description and cost estimate are completed at lower levels.
2.5.1 |  | Aerogel Counter |  |  |  | Each aerogel Cherenkov counter module consists of 2mm thick lead, 50mm thick aerogel, a light-collection mirror and funnel, and a 5" photomultiplier tube. Its cross section is 20cm (height) by 20cm (width). These modules are arrayed into 25 rows of 20 (or 21) modules, with rows separated by 35cm. Calibration will be performed for a finite number of modules.
2.5.1.1 |  | Modules |  |  |  | This effort includes the design, fabrication,shipping, calibration, and installation of the modules.
2.5.1.1.1 |  | Design |  |  |  | Design work will be jointly carried out by the Japanese Collaboration and members of VPI
2.5.1.1.2 |  | Prototype |  |  |  | 2-5 of modules will be manufactured and tested to validate final production configuration. This effort includes fabrication and testing of 2-5 modules.
2.5.1.1.3 |  | Fabrication/Production |  |  |  | 512 modules will be produced by the Japanese Collaboration and shipped to the U.S. Modules will be unpacked, tested and inspected. Test and inspection equipment is included in this effort.
2.5.1.1.4 |  | Calibration |  |  |  | 5-10 modules will be calibrated in a test beam to be performed at KEK or SPring-8 in Japan. This effort includes special test apparatus and electronics to obtain the calibration data.
2.5.1.1.5 |  | Installation |  |  |  | This is the labor and tooling necessary to install the modules into the mechanics.
2.5.1.2 |  | Support Frame |  |  |  | The support frame will mount the aerogel Cherenkov counter modules including calibration system. This effort includes the design, fabrication, shipping and installation of the mechanics in the beam catcher pit.
2.5.1.2.1 |  | Design |  |  |  | Engineering to design the mechanics for the beam catcher. Final design drawings will be produced.
2.5.1.2.2 |  | Fabrication/Production |  |  |  | A drawing package and specification will be provided by the Japanese Collaboration. The mechanics will be shipped to the U.S. The mechanics will be received and tested.
2.5.1.2.3 |  | Installation |  |  |  | The mechanics will be assembled at BNL in the beam catcher pit.
2.5.2 |  | Readout Electronics |  |  |  | The readout electronics include HV power supply, wave form digitizer, ADC, TDC and cables.
2.5.2.1 |  | HV Power Supply |  |  |  | A specification will be provided for manufacture of the HV power supply by the Japanese Collaboration. The HV power supply will be shipped to the U.S. The HV power supply will be received and inspected.
2.5.2.2 |  | Wave Form Digitizer |  |  |  | Specification, common to all KOPIO phototubes, will be provided for manufacture of wave form digitizer.
2.5.2.3 |  | ADCs |  |  |  | Specifications, common to all KOPIO phototubes, will be provided for manufacture of ADCs. As part of necessary ADCs will be reused from the past experiments.
2.5.2.4 |  | TDCs |  |  |  | Specifications, common to all KOPIO phototubes, will be provided for manufacture of TDCs. As part of necessary TDCs will be reused from the past experiments.
2.5.2.5 |  | Cables |  |  |  | Specifications, common to all KOPIO phototubes, will be provided for manufacture of cables. As part of necessary cables will be reused from the past experiments.
2.5.3 |  | Monitoring System |  |  |  | A LED-based monitoring system will be designed, prototyped, fabricated and installed for the aerogel-distributed counter.
2.5.3.1 |  | Design |  |  |  | Engineering necessary to desing a LED pulser and readout system to monitor the aerogel counter modules.
2.5.3.2 |  | Fabrication/Production |  |  |  | Specification will be provided for manufacturer of wave form digitizer. Assembly and test of the monitoring system is included in this effort.
2.5.3.3 |  | Installation |  |  |  | Labor necessary for installation of the monitoring system in the catcher. This work will be done concurrently with the fabrication of the aerogel counter modules.
2.5.4 |  | Commissioning |  |  |  | Labor and testing to commission the beam catcher system. Commissioning will be jointly be carried out by the Japanese Collaboration and members of VPI
2.6 |  | Vacuum
2.6.1 |  | High Vacuum Vessel
2.6.1.1 |  | Design
2.6.1.2 |  | Prototype
2.6.1.3 |  | Fabrication/Production
2.6.1.4 |  | Installation
2.6.1.5 |  | Commissioning
2.6.2 |  | Downstream Tank
2.6.2.1 |  | Design
2.6.2.2 |  | Prototype
2.6.2.3 |  | Fabrication/Production
2.6.2.4 |  | Installation
2.6.2.5 |  | Commissioning
2.6.3 |  | Testing
2.6.3.1 |  | Design
2.6.3.2 |  | Prototype
2.6.3.3 |  | Fabrication/Production
2.6.3.4 |  | Installation
2.6.3.5 |  | Commissioning
2.6.4 |  | Transport & Installation
2.6.4.1 |  | Design
2.6.4.2 |  | Prototype
2.6.4.3 |  | Fabrication/Production
2.6.4.4 |  | Installation
2.6.4.5 |  | Commissioning
2.6.5 |  | Piping
2.6.5.1 |  | Design
2.6.5.2 |  | Prototype
2.6.5.3 |  | Fabrication/Production
2.6.5.4 |  | Installation
2.6.5.5 |  | Commissioning
2.6.6 |  | Mechanics
2.6.6.1 |  | Design
2.6.6.2 |  | Prototype
2.6.6.3 |  | Fabrication/Production
2.6.6.4 |  | Installation
2.6.6.5 |  | Commissioning
2.6.7 |  | Pumps
2.6.7.1 |  | Design
2.6.7.2 |  | Prototype
2.6.7.3 |  | Fabrication/Production
2.6.7.4 |  | Installation
2.6.7.5 |  | Commissioning
2.7 |  | Trigger
2.7.1 |  | Calorimeter Module
2.7.1.1 |  | Design
2.7.1.2 |  | Prototype
2.7.1.3 |  | Fabrication/Production
2.7.1.4 |  | Installation
2.7.1.5 |  | Commissioning
2.7.2 |  | Prerad Lookup Trigger
2.7.2.1 |  | Design
2.7.2.2 |  | Prototype
2.7.2.3 |  | Fabrication/Production
2.7.2.4 |  | Installation
2.7.2.5 |  | Commissioning
2.7.3 |  | Veto Trigger System
2.7.3.1 |  | Design
2.7.3.2 |  | Prototype
2.7.3.3 |  | Fabrication/Production
2.7.3.4 |  | Installation
2.7.3.5 |  | Commissioning
2.7.4 |  | Ch. Veto Trigger System
2.7.4.1 |  | Design
2.7.4.2 |  | Prototype
2.7.4.3 |  | Fabrication/Production
2.7.4.4 |  | Installation
2.7.4.5 |  | Commissioning
2.7.5 |  | Trigger Module
2.7.5.1 |  | Design
2.7.5.2 |  | Prototype
2.7.5.3 |  | Fabrication/Production
2.7.5.4 |  | Installation
2.7.5.5 |  | Commissioning
2.8 |  | Electronics Infra.
2.8.1 |  | Design
2.8.2 |  | Prototype
2.8.3 |  | Fabrication/Production
2.8.4 |  | Installation
2.8.5 |  | Commissioning
2.9 |  | DAQ
2.9.1 |  | Design
2.9.2 |  | Prototype
2.9.3 |  | Fabrication/Production
2.9.4 |  | Installation
2.9.5 |  | Commissioning
2.10. |  | AGS Mods
2.10.1 |  | 25MHz ubunch cavity
2.10.1.1 |  | Cavity
2.10.1.1.1 |  | Design
2.10.1.1.2 |  | Prototype
2.10.1.1.3 |  | Fabrication/Production
2.10.1.1.4 |  | Installation
2.10.1.1.5 |  | Commissioning
2.10.1.2 |  | Tuner
2.10.1.2.1 |  | Design
2.10.1.2.2 |  | Prototype
2.10.1.2.3 |  | Fabrication/Production
2.10.1.2.4 |  | Installation
2.10.1.2.5 |  | Commissioning
2.10.1.3 |  | Vacuum Pump
2.10.1.3.1 |  | Design
2.10.1.3.2 |  | Prototype
2.10.1.3.3 |  | Fabrication/Production
2.10.1.3.4 |  | Installation
2.10.1.3.5 |  | Commissioning
2.10.1.4 |  | Power Amplifier
2.10.1.4.1 |  | Design
2.10.1.4.2 |  | Prototype
2.10.1.4.3 |  | Fabrication/Production
2.10.1.4.4 |  | Installation
2.10.1.4.5 |  | Commissioning
2.10.1.5 |  | Driver
2.10.1.5.1 |  | Design
2.10.1.5.2 |  | Prototype
2.10.1.5.3 |  | Fabrication/Production
2.10.1.5.4 |  | Installation
2.10.1.5.5 |  | Commissioning
2.10.1.6 |  | Low Level
2.10.1.6.1 |  | Design
2.10.1.6.2 |  | Prototype
2.10.1.6.3 |  | Fabrication/Production
2.10.1.6.4 |  | Installation
2.10.1.6.5 |  | Commissioning
2.10.1.7 |  | Controls
2.10.1.7.1 |  | Design
2.10.1.7.2 |  | Prototype
2.10.1.7.3 |  | Fabrication/Production
2.10.1.7.4 |  | Installation
2.10.1.7.5 |  | Commissioning
2.10.1.8 |  | Damper
2.10.1.8.1 |  | Design
2.10.1.8.2 |  | Prototype
2.10.1.8.3 |  | Fabrication/Production
2.10.1.8.4 |  | Installation
2.10.1.8.5 |  | Commissioning
2.10.2 |  | 100MHz booster cavity
2.10.2.1 |  | Cavity
2.10.2.1.1 |  | Design
2.10.2.1.2 |  | Prototype
2.10.2.1.3 |  | Fabrication/Production
2.10.2.1.4 |  | Installation
2.10.2.1.5 |  | Commissioning
2.10.2.2 |  | Tuner
2.10.2.2.1 |  | Design
2.10.2.2.2 |  | Prototype
2.10.2.2.3 |  | Fabrication/Production
2.10.2.2.4 |  | Installation
2.10.2.2.5 |  | Commissioning
2.10.2.3 |  | Vacuum Pump
2.10.2.3.1 |  | Design
2.10.2.3.2 |  | Prototype
2.10.2.3.3 |  | Fabrication/Production
2.10.2.3.4 |  | Installation
2.10.2.3.5 |  | Commissioning
2.10.2.4 |  | Power Amplifier
2.10.2.4.1 |  | Design
2.10.2.4.2 |  | Prototype
2.10.2.4.3 |  | Fabrication/Production
2.10.2.4.4 |  | Installation
2.10.2.4.5 |  | Commissioning
2.10.2.5 |  | Driver
2.10.2.5.1 |  | Design
2.10.2.5.2 |  | Prototype
2.10.2.5.3 |  | Fabrication/Production
2.10.2.5.4 |  | Installation
2.10.2.5.5 |  | Commissioning
2.10.2.6 |  | Low Level
2.10.2.6.1 |  | Design
2.10.2.6.2 |  | Prototype
2.10.2.6.3 |  | Fabrication/Production
2.10.2.6.4 |  | Installation
2.10.2.6.5 |  | Commissioning
2.10.2.7 |  | Controls
2.10.2.7.1 |  | Design
2.10.2.7.2 |  | Prototype
2.10.2.7.3 |  | Fabrication/Production
2.10.2.7.4 |  | Installation
2.10.2.7.5 |  | Commissioning
2.10.2.8 |  | Damper
2.10.2.8.1 |  | Design
2.10.2.8.2 |  | Prototype
2.10.2.8.3 |  | Fabrication/Production
2.10.2.8.4 |  | Installation
2.10.2.8.5 |  | Commissioning
2.10.3 |  | A5 Kicker Modification
2.11 |  | Beam
2.11.1 |  | Project Support
2.11.1.1 |  | Engineering Supervision
2.11.1.2 |  | Physicist Supervision
2.11.2 |  | Neutral beam
2.11.2.1 |  | Target Station
2.11.2.1.1 |  | Design
2.11.2.1.2 |  | Prototype
2.11.2.1.3 |  | Fabrication/Production
2.11.2.2 |  | Sweeper #1
2.11.2.2.1 |  | Design
2.11.2.2.3 |  | Fabrication/Production
2.11.2.3 |  | Sweeper #2
2.11.2.3.1 |  | Design
2.11.2.3.3 |  | Fabrication/Production
2.11.2.4 |  | Collimators
2.11.2.4.1 |  | Sweeper #1
2.11.2.4.1.1 |  | Design
2.11.2.4.1.2 |  | Prototype
2.11.2.4.1.3 |  | Fabrication/Production
2.11.2.4.2 |  | Sweeper #2
2.11.2.4.2.1 |  | Design
2.11.2.4.2.2 |  | Prototype
2.11.2.4.2.3 |  | Fabrication/Production
2.11.2.4.3 |  | 2" liner
2.11.2.4.3.1 |  | Design
2.11.2.4.3.3 |  | Fabrication/Production
2.11.2.5 |  | Steel & Pb shielding
2.11.2.5.1 |  | Design
2.11.2.5.3 |  | Fabrication/Production
2.11.2.6 |  | Vacuum Box
2.11.2.6.1 |  | Design
2.11.2.6.3 |  | Fabrication/Production
2.11.2.7 |  | Upgrade 2 Power Supplies
2.11.2.7.1 |  | Design
2.11.2.7.3 |  | Fabrication/Production
2.11.3 |  | Modify C3 Beam (Primary Beam)
2.11.3.1 |  | Magnets
2.11.3.1.1 |  | Fab. New 5Q36
2.11.3.1.1.1 |  | Design
2.11.3.1.1.3 |  | Fabrication/Production
2.11.3.1.2 |  | Fab. 2 Trim Magnets
2.11.3.1.2.1 |  | Design
2.11.3.1.2.3 |  | Fabrication/Production
2.11.3.1.3 |  | Rebuild N3Q36
2.11.3.1.3.1 |  | Design
2.11.3.1.3.3 |  | Fabrication/Production
2.11.3.1.4 |  | Rebuild 18D72
2.11.3.1.4.1 |  | Design
2.11.3.1.4.3 |  | Fabrication/Production
2.11.3.2 |  | C3 Collimator
2.11.3.2.1 |  | Design
2.11.3.2.3 |  | Fabrication/Production
2.11.3.3 |  | Vacuum
2.11.3.3.1 |  | 18D72 Vacuum Box
2.11.3.3.1.1 |  | Design
2.11.3.3.1.3 |  | Fabrication/Production
2.11.3.3.2 |  | 300' Vacuum Pipe
2.11.3.3.2.1 |  | Design
2.11.3.3.2.3 |  | Fabrication/Production
2.11.3.3.3 |  | Flanges
2.11.3.3.3.1 |  | Design
2.11.3.3.3.3 |  | Fabrication/Production
2.11.3.3.4 |  | Bellows
2.11.3.3.4.1 |  | Design
2.11.3.3.4.3 |  | Fabrication/Production
2.11.3.3.5 |  | Quad Assemblies
2.11.3.3.5.1 |  | Design
2.11.3.3.5.3 |  | Fabrication/Production
2.11.3.3.6 |  | Pump Fittings
2.11.3.3.6.1 |  | Design
2.11.3.3.6.3 |  | Fabrication/Production
2.11.3.3.7 |  | Stands
2.11.3.3.7.1 |  | Design
2.11.3.3.7.3 |  | Fabrication/Production
2.11.3.4 |  | Upgrade 4 Power Supplies
2.11.3.4.1 |  | Design
2.11.3.4.3 |  | Fabrication/Production
2.11.3.5 |  | Controls
2.11.3.5.1 |  | Vac PLC
2.11.3.5.1.1 |  | Design
2.11.3.5.1.3 |  | Fabrication/Production
2.11.3.5.2 |  | 300' Vacuum Pipe
2.11.3.5.2.1 |  | Design
2.11.3.5.2.3 |  | Fabrication/Production
2.11.3.6 |  | Shielding: 30A's + 18 Specials
2.11.3.6.1 |  | Design
2.11.3.6.3 |  | Fabrication/Production
2.11.3.7 |  | Instrumentation
2.11.3.7.1 |  | Remove Existing
2.11.3.7.1.1 |  | Design
2.11.3.7.1.2 |  | Prototype
2.11.3.7.1.3 |  | Fabrication/Production
2.11.3.7.2 |  | Fab New SEC
2.11.3.7.2.1 |  | Design
2.11.3.7.2.2 |  | Prototype
2.11.3.7.2.3 |  | Fabrication/Production
2.11.3.7.3 |  | Target Monitor (temp)
2.11.3.7.3.1 |  | Design
2.11.3.7.3.2 |  | Prototype
2.11.3.7.3.3 |  | Fabrication/Production
2.11.3.7.4 |  | Target Monitor (beam)
2.11.3.7.4.1 |  | Design
2.11.3.7.4.2 |  | Prototype
2.11.3.7.4.3 |  | Fabrication/Production
2.11.3.7.5 |  | Fab New SWIC
2.11.3.7.5.1 |  | Design
2.11.3.7.5.2 |  | Prototype
2.11.3.7.5.3 |  | Fabrication/Production
2.11.3.7.6 |  | Loss Monitor System
2.11.3.7.6.1 |  | Design
2.11.3.7.6.2 |  | Prototype
2.11.3.7.6.3 |  | Fabrication/Production
2.11.4 |  | Experimental Area
2.11.4.1 |  | 48D48
2.11.4.1.1 |  | Design
2.11.4.1.3 |  | Fabrication/Production
2.11.4.2 |  | Upgrade Power Supply - 48D48
2.11.4.2.1 |  | Design
2.11.4.2.3 |  | Fabrication/Production
2.11.4.3 |  | LI Concrete shielding
2.11.4.3.1 |  | Design
2.11.4.3.3 |  | Fabrication/Production
2.11.5 |  | Construction
2.11.5.1 |  | Pit for Exp. Detector
2.11.5.1.1 |  | Design
2.11.5.1.3 |  | Fabrication/Production
2.11.5.2 |  | Fast Elec House
2.11.5.2.1 |  | Design
2.11.5.2.3 |  | Fabrication/Production
2.11.5.3 |  | Counting House
2.11.5.3.1 |  | Design
2.11.5.3.3 |  | Fabrication/Production
2.11.5.4 |  | Modifications to Facility Power
2.11.5.4.1 |  | Design
2.11.5.4.2 |  | Production
2.11.6 |  | Beam Installation
2.11.6.1 |  | Neutral Beam Installation
2.11.6.1.1 |  | Sweeper # 1 Installation
2.11.6.1.1.1 |  | Design
2.11.6.1.1.2 |  | Installation
2.11.6.1.2 |  | Sweeper #2 Installation
2.11.6.1.2.1 |  | Design
2.11.6.1.2.2 |  | Installation
2.11.6.1.3 |  | Collimators Installation
2.11.6.1.3.1 |  | Design
2.11.6.1.3.2 |  | Installation
2.11.6.1.4 |  | Steel & Pb Shielding Install
2.11.6.1.4.1 |  | Design
2.11.6.1.4.2 |  | Installation
2.11.6.1.5 |  | Vacuum Box Installation
2.11.6.1.5.1 |  | Design
2.11.6.1.5.2 |  | Installation
2.11.6.1.6 |  | 2 Power Supplies Install
2.11.6.1.6.1 |  | Design
2.11.6.1.6.2 |  | Installation
2.11.6.2 |  | C3 Beam Installation
2.11.6.2.1 |  | Remove LESBII
2.11.6.2.1.1 |  | Design
2.11.6.2.1.2 |  | Removal/Clean-up
2.11.6.2.1.3 |  | RAD Waste Removal
2.11.6.2.2 |  | C3 Magnets Installation
2.11.6.2.2.1 |  | Design
2.11.6.2.2.2 |  | Installation
2.11.6.2.3 |  | C3 Collimators Installation
2.11.6.2.3.1 |  | Design
2.11.6.2.3.2 |  | Installation
2.11.6.2.4 |  | Vacuum Installation
2.11.6.2.4.1 |  | Design
2.11.6.2.4.2 |  | Installation
2.11.6.2.5 |  | 4 Power Supplies Installation
2.11.6.2.5.1 |  | Design
2.11.6.2.5.2 |  | Installation
2.11.6.2.6 |  | Controls Installation
2.11.6.2.6.1 |  | Design
2.11.6.2.6.2 |  | Installation
2.11.6.2.7 |  | Shielding Installation
2.11.6.2.7.1 |  | Design
2.11.6.2.7.2 |  | Installation
2.11.6.2.8 |  | Instrumentation Installation
2.11.6.2.8.1 |  | Design
2.11.6.2.8.2 |  | Installation
2.11.6.2.9 |  | Target Station Installation
2.11.6.2.9.1 |  | Design
2.11.6.2.9.2 |  | Installation
2.11.6.3 |  | Experimental Area Installation
2.11.6.3.1 |  | 48D48 Installation
2.11.6.3.1.1 |  | Design
2.11.6.3.1.2 |  | Installation
2.11.6.3.2 |  | 48D48 Power Supply Installation
2.11.6.3.2.1 |  | Design
2.11.6.3.2.2 |  | Installation
2.11.6.3.3 |  | LI Concrete Shielding Installation
2.11.6.3.3.1 |  | Design
2.11.6.3.3.2 |  | Installation
2.12 |  | Detector Installation
2.12.1 |  | Calorimeter Installation
2.12.2 |  | Preradiator Installation
2.12.3 |  | Photon Veto Installation
2.12.4 |  | Charged Part. Veto Installation
2.12.5 |  | Catcher Installation
2.12.6 |  | Vacuum Installation
2.12.7 |  | Trigger Installation
2.12.8 |  | Elec. Infrastructure Installation
2.12.9 |  | DAQ Imstallation
2.13 | Project Management | Project Services
2.13.1 |  | Project Management
2.13.2 | Proj. Manager | Cost/Schedules
2.13.3 | Proj. Engineer | QA
2.13.4 | Proj. Assistant | Safety