## KA03; 110-95
NOAA SHIP KA'IMIMOANA
KA-03-02
24 MARCH - 27 APRIL 2003
TAO ARRAY: 110W & 95W
GP2-03-KA
| Activity |  | Latitude |  |  | Longitude |  | Deployed | Distance | Speed | Transit | On Sta. | Arrive | Depart | CUMULATIVE |  |  |  |  | SWAP | DEPLOY | LAT | LONG
|  | Deg. | Minutes |  | Deg. | Minutes |  | (mos) | (nmi) | (kts) | (hrs) | (hrs) | Date / Time | Date / Time | (hrs) | (days) | RECOVER | VISIT | REPAIR | OUT | ONLY | CORR | CORR |  |  |  |  | AT SITE | LAST RECOV | DIFFERENCE
| SAN DIEGO, CA | 32 | 43 | N | 117 | 11 | W | [6 empty] | 2003-03-24 16:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 32 | N | 117 | 0 | 0 |  | 0
R | /D TAUT-NG, AVOID HAURUPHONE & CTD | 8 | 0 | N | 110 | 0 | W | 5.2591 | 1535.8835 | 9.5 | 161.6719 | 16 | 2003-03-31 09:40 | 2003-04-01 01:40 | 177.6719 | 7.403 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 8 | N | 110 | R | 36249.403 | 2002-10-22 | 5.2591
| CTD | 7 | 0 | N | 110 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-01 07:59 | 2003-04-01 08:59 | 184.9877 | 7.7078 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | N | 110 | 0 | 0 |  | 0
| CTD | 6 | 0 | N | 110 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-01 15:18 | 2003-04-01 16:18 | 192.3035 | 8.0126 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6 | N | 110 | 0 | 0 |  | 0
V | ISIT TAUT-NG & CTD | 5 | 0 | N | 110 | 0 | W | 5.3096 | 60 | 9.5 | 6.3158 | 4 | 2003-04-01 22:37 | 2003-04-02 02:37 | 202.6193 | 8.4425 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 5 | N | 110 | V | 36250.9425 | 2002-10-22 | 5.3096
| CTD | 4 | 0 | N | 110 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-02 08:56 | 2003-04-02 09:56 | 209.9351 | 8.7473 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | N | 110 | 0 | 0 |  | 0
| CTD | 3 | 0 | N | 110 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-02 16:15 | 2003-04-02 17:15 | 217.2509 | 9.0521 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | N | 110 | 0 | 0 |  | 0
| CTD | 2 | 30 | N | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-02 20:25 | 2003-04-02 21:25 | 221.4088 | 9.2254 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 110 | 0 | 0 |  | 0
R | /D TAUT-NG (INSERT/FAIRED) & CTD | 2 | 0 | N | 110 | 0 | W | 5.345 | 30 | 9.5 | 3.1579 | 19 | 2003-04-03 00:34 | 2003-04-03 19:34 | 243.5667 | 10.1486 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 110 | R | 36252.0236 | 2002-10-22 | 5.345
| CTD | 1 | 30 | N | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-03 22:43 | 2003-04-03 23:43 | 247.7246 | 10.3219 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 110 | 0 | 0 |  | 0
| CTD | 1 | 0 | N | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-04 02:53 | 2003-04-04 03:53 | 251.8825 | 10.4951 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 110 | 0 | 0 |  | 0
| CTD | 0 | 30 | N | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-04 07:02 | 2003-04-04 08:02 | 256.0404 | 10.6683 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | N | 110 | 0 | 0 |  | 0
R | /D TAUT-NG (INSERT/FAIRED) & CTD | 0 | 0 |  | 110 | 0 | W | 5.3923 | 30 | 9.5 | 3.1579 | 12 | 2003-04-04 11:12 | 2003-04-04 23:12 | 271.1983 | 11.2999 | 1 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | 0 | 110 | R | 36253.4666 | 2002-10-22 | 5.3923
D | EPLOY broadband SS ADCP alongside existing ADCP | 0 | 0 |  | 110 | 0 | W | 5.4087 | 0 | 9.5 | 0 | 13 | 2003-04-04 23:12 | 2003-04-05 12:12 | 284.1983 | 11.8416 | 0 | 0 | 0 | 0 | 1 | -1 | 1 | 0 | 0 | 110 | 0 | 36253.9666 | 2002-10-22 | 5.4087
| CTD | 0 | 30 | S | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-05 15:21 | 2003-04-05 16:21 | 288.3562 | 12.0148 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | S | 110 | 0 | 0 |  | 0
| CTD | 1 | 0 | S | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-05 19:31 | 2003-04-05 20:31 | 292.5141 | 12.1881 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 110 | 0 | 0 |  | 0
| CTD | 1 | 30 | S | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-05 23:40 | 2003-04-06 00:40 | 296.6719 | 12.3613 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 110 | 0 | 0 |  | 0
R E | EPAIR TAUT-NG & CTD | 2 | 0 | S | 110 | 0 | W | 5.4479 | 30 | 9.5 | 3.1579 | 8.5 | 2003-04-06 03:50 | 2003-04-06 12:20 | 308.3298 | 12.8471 | 0 | 0 | 1 | 0 | 0 | -1 | 1 | 2 | S | 110 | 0 | 36255.1596 | 2002-10-22 | 5.4479
| CTD | 2 | 30 | S | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-06 15:29 | 2003-04-06 16:29 | 312.4877 | 13.0203 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | S | 110 | 0 | 0 |  | 0
| CTD | 3 | 0 | S | 110 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-06 19:39 | 2003-04-06 20:39 | 316.6456 | 13.1936 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 3 | S | 110 | 0 | 0 |  | 0
| CTD | 4 | 0 | S | 110 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-07 02:58 | 2003-04-07 03:58 | 323.9614 | 13.4984 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 4 | S | 110 | 0 | 0 |  | 0
V | ISIT TAUT-NG & CTD | 5 | 0 | S | 110 | 0 | W | 5.4894 | 60 | 9.5 | 6.3158 | 4 | 2003-04-07 10:17 | 2003-04-07 14:17 | 334.2772 | 13.9282 | 0 | 1 | 0 | 0 | 0 | -1 | 1 | 5 | S | 110 | V | 36256.4282 | 2002-10-22 | 5.4894
| CTD | 6 | 0 | S | 110 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-07 20:36 | 2003-04-07 21:36 | 341.593 | 14.233 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 6 | S | 110 | 0 | 0 |  | 0
| CTD | 7 | 0 | S | 110 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-08 03:55 | 2003-04-08 04:55 | 348.9088 | 14.5379 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 7 | S | 110 | 0 | 0 |  | 0
R | /D TAUT-NG & CTD | 8 | 0 | S | 110 | 0 | W | 5.5235 | 60 | 9.5 | 6.3158 | 10 | 2003-04-08 11:13 | 2003-04-08 21:13 | 365.2246 | 15.2177 | 1 | 0 | 0 | 0 | 0 | -1 | 1 | 8 | S | 110 | R | 36257.4677 | 2002-10-22 | 5.5235
R | /D TAUT-NG | 8 | 0 | S | 95 | 0 | W | 5.6653 | 891.1916 | 9.5 | 93.8096 | 23 | 2003-04-12 19:02 | 2003-04-13 18:02 | 482.0342 | 20.0848 | 1 | 0 | 0 | 0 | 0 | -1 | 1 | 8 | S | 95 | R | 36261.7931 | 2002-10-22 | 5.6653
| CTD | 7 | 0 | S | 95 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-14 00:21 | 2003-04-14 01:21 | 489.35 | 20.3896 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 7 | S | 95 | 0 | 0 |  | 0
| CTD | 6 | 0 | S | 95 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-14 07:40 | 2003-04-14 08:40 | 496.6658 | 20.6944 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 6 | S | 95 | 0 | 0 |  | 0
R E | EPAIR TAUT-NG-E & CTD | 5 | 0 | S | 95 | 0 | W | 5.7254 | 60 | 9.5 | 6.3158 | 6 | 2003-04-14 14:59 | 2003-04-14 20:59 | 508.9816 | 21.2076 | 0 | 0 | 1 | 0 | 0 | -1 | 1 | 5 | S | 95 | 0 | 36263.6242 | 2002-10-22 | 5.7254
| CTD | 4 | 0 | S | 95 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-15 03:18 | 2003-04-15 04:18 | 516.2974 | 21.5124 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 4 | S | 95 | 0 | 0 |  | 0
| CTD | 3 | 0 | S | 95 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-15 10:37 | 2003-04-15 11:37 | 523.6132 | 21.8172 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 3 | S | 95 | 0 | 0 |  | 0
| CTD | 2 | 30 | S | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-15 14:46 | 2003-04-15 15:46 | 527.7711 | 21.9905 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | S | 95 | 0 | 0 |  | 0
R | /D TAUT-NG & CTD | 2 | 0 | S | 95 | 0 | W | 5.7636 | 30 | 9.5 | 3.1579 | 23 | 2003-04-15 18:56 | 2003-04-16 17:56 | 553.929 | 23.0804 | 1 | 0 | 0 | 0 | 0 | -1 | 1 | 2 | S | 95 | R | 36264.7887 | 2002-10-22 | 5.7636
| CTD | 1 | 30 | S | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-16 21:05 | 2003-04-16 22:05 | 558.0869 | 23.2536 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 95 | 0 | 0 |  | 0
| CTD | 1 | 0 | S | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-17 01:15 | 2003-04-17 02:15 | 562.2448 | 23.4269 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 1 | S | 95 | 0 | 0 |  | 0
| CTD | 0 | 30 | S | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-17 05:24 | 2003-04-17 06:24 | 566.4026 | 23.6001 | 0 | 0 | 0 | 0 | 0 | -1 | 1 | 0 | S | 95 | 0 | 0 |  | 0
R E | EPAIR TAUT-NG-E (INSERT/FAIR), AVOID HARUPHONE & CTD | 0 | 0 |  | 95 | 0 | W | 5.8163 | 30 | 9.5 | 3.1579 | 6 | 2003-04-17 09:34 | 2003-04-17 15:34 | 575.5605 | 23.9817 | 0 | 0 | 1 | 0 | 0 | -1 | 1 | 0 | 0 | 95 | 0 | 36266.3984 | 2002-10-22 | 5.8163
| CTD | 0 | 30 | N | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-17 18:43 | 2003-04-17 19:43 | 579.7184 | 24.1549 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | N | 95 | 0 | 0 |  | 0
| CTD | 1 | 0 | N | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-17 22:53 | 2003-04-17 23:53 | 583.8763 | 24.3282 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 95 | 0 | 0 |  | 0
| CTD | 1 | 30 | N | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-18 03:02 | 2003-04-18 04:02 | 588.0342 | 24.5014 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | N | 95 | 0 | 0 |  | 0
R | /D TAUT-NG-E (INSERT/FAIR) & CTD | 2 | 0 | N | 95 | 0 | W | 5.8459 | 30 | 9.5 | 3.1579 | 12 | 2003-04-18 07:12 | 2003-04-18 19:12 | 603.1921 | 25.133 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 95 | R | 36267.2997 | 2002-10-22 | 5.8459
| CTD | 2 | 30 | N | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-18 22:21 | 2003-04-18 23:21 | 607.35 | 25.3063 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | N | 95 | 0 | 0 |  | 0
| CTD | 3 | 0 | N | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-19 02:30 | 2003-04-19 03:30 | 611.5079 | 25.4795 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | N | 95 | 0 | 0 |  | 0
V | ISIT TAUT NX (INSERT AND FAIR) & CTD | 3 | 30 | N | 95 | 0 | W | 5.878 | 30 | 9.5 | 3.1579 | 4 | 2003-04-19 06:40 | 2003-04-19 10:40 | 618.6658 | 25.7777 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3 | N | 95 | V | 36268.2777 | 2002-10-22 | 5.878
| CTD | 4 | 0 | N | 95 | 0 | W |  | 30 | 9.5 | 3.1579 | 1 | 2003-04-19 13:49 | 2003-04-19 14:49 | 622.8237 | 25.951 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4 | N | 95 | 0 | 0 |  | 0
R | /D TAUT-NG-E & CTD | 5 | 0 | N | 95 | 0 | W | 5.8977 | 60 | 9.5 | 6.3158 | 21 | 2003-04-19 21:08 | 2003-04-20 18:08 | 650.1395 | 27.0891 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 5 | N | 95 | R | 36268.8808 | 2002-10-22 | 5.8977
| CTD | 6 | 0 | N | 95 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-21 00:27 | 2003-04-21 01:27 | 657.4553 | 27.394 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 6 | N | 95 | 0 | 0 |  | 0
| CTD | 7 | 0 | N | 95 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-21 07:46 | 2003-04-21 08:46 | 664.7711 | 27.6988 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | N | 95 | 0 | 0 |  | 0
R | /D TAUT-NG-E, AVOID HARUPHONE & CTD | 8 | 0 | N | 95 | 0 | W | 5.955 | 60 | 9.5 | 6.3158 | 10 | 2003-04-21 15:05 | 2003-04-22 01:05 | 681.0869 | 28.3786 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 8 | N | 95 | R | 36270.6286 | 2002-10-22 | 5.955
| CTD | 9 | 0 | N | 95 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-22 07:24 | 2003-04-22 08:24 | 688.4026 | 28.6834 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9 | N | 95 | 0 | 0 |  | 0
V | ISIT TAUT-NG (CHECK RAIN), AVOID HARUPHONE & CTD | 10 | 0 | N | 95 | 0 | W | 5.9873 | 60 | 9.5 | 6.3158 | 4 | 2003-04-22 14:43 | 2003-04-22 18:43 | 698.7184 | 29.1133 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 10 | N | 95 | V | 36271.6133 | 2002-10-22 | 5.9873
| CTD | 11 | 0 | N | 95 | 0 | W |  | 60 | 9.5 | 6.3158 | 1 | 2003-04-23 01:02 | 2003-04-23 02:02 | 706.0342 | 29.4181 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11 | N | 95 | 0 | 0 |  | 0
V | ISIT TAUT-NG (CHECK RAIN), AVOID HARUPHONE & CTD | 12 | 0 | N | 95 | 0 | W | 6.0114 | 60 | 9.5 | 6.3158 | 16 | 2003-04-23 08:21 | 2003-04-24 00:21 | 728.35 | 30.3479 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 12 | N | 95 | V | 36272.3479 | 2002-10-22 | 6.0114
| MANZANILLO, MX | 19 | 3 | N | 104 | 20 | W |  | 685.2469 | 9 | 76.1385 |  | 2003-04-27 04:29 |  | 804.4886 | 33.5204 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 19 | N | 104 | 0 | 0 |  | 0
[17 empty] | 9 | 5 | 3 | 0 | 1
| RECOVER TAUT NG = |  | 6
| DEPLOY TAUT NG = |  | 6
[13 empty] | Days At Sea | Nautical Miles
| RECOVER TAUT NG (INSERT/FAIRED) = |  | 3 |  |  |  | Transit | On Station |  |  | 110W = |  | 9.4814 | 960
| DEPLOY TAUT NG (INSERT/FAIRED) = |  | 3 |  |  |  | hrs | hrs |  |  | 95W = |  | 12.2215 | 1200
[7 empty] | 558.9886 | 245.5 |  |  | Transit = |  | 13.8175 | 3112.322 |  |  | nmi check
| REPAIR TAUT-NG (BUOY RIDE) = |  | 3 | [7 empty] | TOTALS = |  | 35.5204 | 5272.322 |  |  | 5272.322
| VISIT TAUT-NG = |  | 5
| DEPLOY SUBSURFACE ADCP (NO RECOVERY) = |  | 1 |  | Six hrs of ops time added for CTD's at 12N, 11N, 10N & 9N along trackline from San Diego to 8N/110W
| RECOVER/DEPLOY SUBSURFACE HARUPHONES = |  | 0 |  |  | Twelve hrs of CTD/Sensor Calibration Ops added at 12N/95W Station
ALL TIMES ARE PACIFIC STANDARD TIME (-8 GMT)
Formulas:
Arrive = [Depart, row above]+[Transit]/24
Arrive = O33+[Transit]/24
Depart = [Arrive]+[On Sta.]/24