| CURRENT STATUS (As of June 30, 2007) | PROGRESS Third Quarter, FY 2007 | COMMENTS |
| --- | --- | --- |
| Initiative: Human Capital Bureau Lead: Eduardo Ribas | Yellow | Comprehensive human capital plan X developed, etc. on (Q4/FY03) X results analyzed & used (Q3/05) Organizational structures X current structure analyzed and restructuring begun (Q3/FY02) X structure in place & addressing future challenges (Q3/02) Succession strategies X succession plan approved (Q3/FY02) X continuously updated talent pool assured (Q3/02) Performance appraisal plans adhere to merit system principles, etc. X SES & mgrs. (Q1/FY03) __ beta site completed (Q2/08) X 60%+ of agency __beta site expanded (Q2/08) Under representation X implemented strategies to address (Q2/07) __ reduced & established process to sustain diversity (TBD) Skill gaps X workforce planning system implemented (Q1/FY07) X identifies and sets competency targets (Q4/FY06) _X_ significant reduction in mission critical occupation gaps (Q3/07) X meets competency gap targets (Q3/07) Improve Hiring X collects data & sets standard (Q3/FY03) X meets standard (Q4/FY05) __meets target for improvement (Q1/08) Accountability system and reviews X system developed (Q4/FY06) X conducts reviews & takes corrective action ongoing __ provided annual report (Q1/FY08) __HR service delivery target met (next survey data available Q1/FY08) | Green | Performance appraisal plans adhere to merit system principles: Signed MOU with unions on multi-tier performance management system. NOAA will submit sample performance plans for review by DOC, when requested. Under representation: Identified under representation challenges across NOAA Researched best practices to combat under representation Will develop a NOAA-wide process to sustain diversity (FY08) Continue to measure and evaluate outcomes Selected 15 students who attend Minority Serving Institutions to participate in the Educational Partnership Program - Undergraduate Scholarship Program. Conducted workforce analysis for each Line Office to include comparative analysis of demographic data with civilian labor force data. Conducted extensive interviews with line and staff office resource and diversity managers to determine kind and extent of outreach and recruiting activities in preparation for proposing a corporate recruitment strategy that will include strategies to reach diverse applicants. Improve Hiring: DOC will provide results of the OPM Hiring Manager’s Satisfaction Survey. NOAA will analyze and set targets for improvements, if necessary. Accountability system and reviews: DOC will provide guidance on content and format of annual report. DOC employee survey will be administered in Q4 FY07. NOAA data will be available in Q1 FY08 for analysis and action planning. Completed the Workforce Management Program Operating Plan for the Planning, Programming, Budget, Execution System (PPBES) for FY10 – FY14. Supported BPR team in implementing resourced actions for hiring cycle and training/development processes. Reorganized the OAR Office of Chief Financial Officer/Chief Administrative Officer. Identified priority HR competencies and submitted an Improvement Plan to DOC. Completed Leadership Development: 1) The 40-hour NOAA Leadership Training Program for new first-line supervisors was given to 13 employees; 2) The 9-day Executive Leadership Seminar targeted for managers at GS-13-15 was given to 25 employees; 3) The 80-hour Management and Supervision course for new supervisors was given to 27 employees. Conducted NOAA Honor Awards Ceremony recognizing more than 800 NOAA employees. Provided report to address the results of the OPM delegated examining unit audit of Norfolk office, including recommended and required actions. Planned Actions for Next Quarter Conduct training sessions on multi-tier performance management system in preparation for migration of remaining 3,967 employees in Q1/07. Continue to meet/surpass the OPM non-SES hiring target of 45-days. Continue to implement actions to address 2006 Federal Human Capital Survey results. Provide NOAA Leadership Training Program for new first-line supervisors. Improve process to meet the OPM SES hiring target. | In order to earn a green score in status, NOAA must move the remaining 3,967 employees to the 5-tier performance appraisal system that makes meaningful distinctions in levels of performance, continue to reduce under representation, and raise the overall satisfaction score for HR service delivery on the HR Performance Management Survey to at least the Department’s overall satisfaction score of 68.2%. NOAA conducted workforce analysis for each Line Office to include comparative analysis of NOAA demographic data with civilian labor force data. NOAA selected 15 students who attend Minority Serving Institutions to participate in the Educational Partnership Program - Undergraduate Scholarship Program. |
| Initiative: Competitive Sourcing Bureau Lead: William Broglie | Yellow | Approved competition plan __ “yellow” plan (date) X “green” plan on (11/04) Standard competitions X one completed OR announced one > “yellow” plan FTEs (Y) (1/04), NWS Telecommunications Gateway __ announced in accordance with “green” plan schedule (G) (date) __ completed ≥ 90% in A-76 timeframe past 4 Qs (G) (date) Standard and streamlined competitions X at least 10 or sufficiently large completed since Jan. 2001 (G)(4/04) __ encourage participation by private and public sectors (G) (date) X reviewed once implemented (NWS Gateway study(3/05) (OAR GFDL (8/05) Streamlined competitions completed in Circular timeframe __ ≥ 75% during the past 2 Qs (date) __ ≥ 95% during the past 4 Qs Announced competitions cancelled __ ( 20% in past two Qs __ (10% in past year (date) X Justifications for all commercial activities exempt from competition (G)(5/06) Savings X anticipated net savings for past 2 Qs (Y) (4/06) (OAR, NWS) __ anticipated for past 3 Qs (G+) (Y) (9.06) (OAR, NWS) __ independently validated (G+) | Green | Actions taken this quarter: The OCAO Competitive Sourcing Team completed NOAA’s FY 2007 FAIR Act Inventory and submitted it to DOC on 5/18/2007. Overall statistics are virtually unchanged from FY 2006, with 72% of employees coded as inherently governmental and 28% as commercial. NOAA has 3,100 contractor employees on board and support contracts totaling over $400M. Feasibility Studies In Progress: Line Office Start Complete NOS R & D Admin. (13 FTE) 5/14/07 8/13/07 NMAO Relief Pool (36 FTE) 3/29/07 6/30/07 NMAO Admin (8 FTE) 6/04/07 8/30/07 NMFS Admin. ( 56 FTE) 6/04/07 8/13/07 All studies are on track for completion in FY 2007. Most studies are in the general assessment phase which includes an assessment of current operations and a determination of market interest. The NMAO Relief Pool study has been completed and is undergoing an internal management review prior to formal submission. Planned actions for next quarter: Completion of all FY 2007 feasibility studies. Finalization of FY 2008 feasibility study schedule. Independent validation cost savings for a selected MEO, as required by DOC. | DOC, in its Organizational Assessment of Performance for the 4th Quarter, FY 2006, President’s Management Agenda, Competitive Sourcing, stated “NOAA must study an activity or function in FY 2007 that will result in preplanning for competition.” We understand this language is intended to reflect that even if NOAA conducts the FY 2007 feasibility studies as planned, unless one of these studies leads to pre-planning for competition, NOAA will remain at “Yellow” for Current Status on this initiative. It is unlikely that the currently scheduled feasibility studies will result in economically viable candidates for preplanning—largely due to geographically-dispersed functions with small “cell” sizes in each location. |
| Initiative: Financial Performance Bureau Lead: Jon Alexander | Green | GREEN STANDARDS X Meets all yellow standards (2/05) X Uses financial info to drive results in key areas (ongoing) X Expands routine data use (ongoing) YELLOW STANDARDS X Clean annual audit (12/04) __ qualified (date if relevant) __ disclaimer (date if relevant) X Meets reporting deadlines (ongoing) X FFMIA compliance reported (FY 2004, Qtr. 4) X No chronic or significant Anti-Deficiency Act Violations X No material auditor-reported internal control weaknesses __ new (enter # if applicable) __ repeat (enter # if applicable) X No material non-compliance with laws or regulations X No material weaknesses in FMFIA (FY 2004, Qtr. 4) __ for Section 2 (enter # if __ for Section 4 applicable) | Green | Actions taken last quarter: Prepared and submitted Q2, FY07 Financial Statement package to DoC OFM by the due dates. Complete internal control reviews for three NOAA ship imprest funds. Substantially complete testing of internal controls on financial reporting (A-123, Appendix) through Phase I (March 31, 2007). No material weaknesses have been identified to date. Substantially complete A-123, Appendix A cycle memos for remaining cycles that will be not be tested in FY 07. Conduct status meetings with Line and Staff Offices to ensure that the Management Control Reviews (self-assessments) are on schedule for completion by July 31, 2007 deadline. Complete internal control review of travel gifts and issue draft report. Developed standard NOAA-wide procedures for processing reimbursable interagency agreements. Developed and provided training for processing reimbursable interagency agreements according to the new policies and procedures. Planned actions for next quarter: Prepare and submit Q3, FY07 Financial Statement package to DoC OFM by the due dates and monitor implementation of the corrective action plans. Complete testing of internal controls on financial reporting (A-123, Appendix) through Phase II (June 30, 2007). Complete A-123, Appendix A cycle memos for remaining cycles that will be not be tested in FY 07. Conduct exit conference with Line and Staff Offices for Management Control Reviews. Compile information for FMFIA report to be included in DOC Performance and Accountability Report (PAR). Issue final report on travel gifts. Complete internal control review for fourth NOAA ship imprest fund and issue final report. Continue to work with the NOAA-wide Reimbursable Workgroup to improve processing of reimbursable interagency agreements. Continue to improve the process for making payments until the Central Contractor Registry data base is stabilized. | NOAA continues to actively support DoC led initiatives to improve the financial management practices agency wide |
| Initiative: E-Government Bureau Lead: Joseph Klimavicz | Yellow | Enterprise Architecture _ Has 4 in Completion and 3 in Use or Results (Y) date X Has 4 in Completion & 3 in both Use & Results (G) 02/28/2007 Acceptable business cases for major systems for more than 50% (Y) date X for all (G) 06/05 Cost/schedule/performance adherence for major IT overruns/shortfalls < 30% (Y) date X EVMS shows overruns/ shortfalls <10% (G) 03/30/2005 Security of all IT systems __ 80% secured or IG verifies effectiveness (Y) 3/30/2007 X 90% secured (G) date IG or Agency head verifies effective & rates certification as Satisfactory (G) date E-Gov implementation X has current plan in place (Y) 12/08/2004 X adheres to agency-accepted and OMB approved implementation plan (G) 06/30/2007 | Green | Actions taken this quarter: Completed two Privacy Impact Assessments (PIAs) for NMFS Permits Program and the NOS Management and Budget Office Web Application. Certified and Accredited 37 NOAA systems. NOAA IT Review Board conducted 2 System Reviews and 1 budget initiative. Updated IT Security Manual. Achieved 100% compliance in DOC laptop encryption policy. Established NOAA EA life-cycle, management processes and governance model. Completed integrated NOAA staff directory. Met Q3 milestone for Geospatial Line of Business. Planned actions for next quarter: Certify and Accredit 20 NOAA systems. Complete 1 PIA for NOS Domain Subsystem. NITRB will conduct 2 System Reviews and review 3 Designations of Procurement Authority (DPA). Complete Strategic IT Plan. Submit semi-annual IT inventory. Complete Annual Federal Information Security Management Act (FISMA) Report. Produce NOAA Enterprise Architecture (EA) Technical Reference Model. | NOAA is committed to a schedule to complete Certifications and Accreditations (C&As) for all operational systems by the end of FY2007. NOAA processes have been strengthened to address IG concerns of auditability, inventory, and testing. |
| Initiative: Budget & Performance Integration Bureau Lead: Steven Gallagher | Green | Improved results/use of perf info X uses perf info. to improve perf (Sept 2004) Strategic and annual plans X limited # of goals & use PART measures (June 2004) X AND focus on info used in senior mgmt. report (Q2 2005) Cost of achieving performance goals X full cost reported (Sept 2004) X AND marginal cost reported __ uses marginal cost to inform resource allocations At least one efficiency measure per PARTed program X for ≥50% X for all (Q2 2006 – see comments) Use of PART ratings _X_ to justify requests, etc. and hold program managers accountable (2003) X direct improvements justify requests, etc (Nov 2003) % of PARTed programs rated Results Not Demonstrated for 2 yrs in a row _X_ less than 10% (2003) _X_ no more than 50% (2003) | Green | Actions taken this quarter: Prepared narratives and performance information to support proposed program increases in the Annual Performance Plan and submitted the exhibit with the FY 2008 Secretarial Budget. Submitted a performance-based budget request for FY 2009. Completed the PART reassessment of NMFS and the assessment of the NOAA Hydrology Program. NMFS received an improved rating from its initial score of 55% (Adequate) in 2002 to 72% (Moderately Effective) during the 2007 reassessment. Hydrology received a rating of 74% (Moderately Effective). Submitted efficiency measures for both of the PARTed programs, with OMB acceptance. Provided Spring 2007 updates to OMB on the PART Recommendations (a.k.a. “PART Improvement Plans”), PART performance measures, and funding levels through PARTWeb. Worked with the NOAA R&D programs that are scheduled for a PART review in 2009 (Science, Technology & Infusion and Climate) and 2010 (Ecosystem Research Program) to identify, address and work on the key elements of the PART instrument. Important milestones for each quarter leading up to the actual year of assessment will be tracked to ensure the continued efforts at NOAA for enhancing the likelihood of receiving a high rating from OMB. Developed and submitted a 5-year PART review schedule to OMB. Submitted content for “This Week in Budget (TWiB)” newsletter for enhanced communication within the NOAA Budget community. Planned actions for next quarter: Prepare the FY 2007 Performance and Accountability Report (PAR). Prepare FY 2007 NOAA Business Report, which highlights major accomplishments, management improvements, provides updates to NOAA operations, products, and services. Continue to implement the Commerce Learning Management System (LMS) Phase I for NOAA Budget training needs. |  |
| Initiative: R&D INVESTMENT CRITERIA Agency Lead: Richard Spinrad | Yellow Next ( in 2009) | Senior R&D managers across the agency: X have practices that promote quality, relevance, and performance of R&D activities (ongoing 2006) X meet at least quarterly to plan, coordinate, assess, and redirect agency R&D activities as appropriate (bi-monthly 2005 and 2006) Of R&D programs assessed by the R&D PART, X at least 50% are found to be “Moderately Effective” or better at least 75% are found to be “Moderately Effective” or better (date) Agency budget proposals: X to OMB use the R&D criteria (9/2005) X to OMB and Congress use the R&D criteria and document how the criteria have successfully influenced budget decisions and management changes (9/2005). | Green | Actions taken this quarter: Updated the 5-Year Research Plan based on NEP/NEC comments and released for public comment. Released guidance for NOAA-wide review and monitoring of future Climate Change Science Program (CCSP) Synthesis and Assessment Product (SAP) and Prospectus documents. Reviewed CCSP SAP 3.1 on Climate Modeling. Created Terms of Reference for a standing Monitoring of Research Committee and solicited nominations for members. Briefed CFO Council representatives on future database requirements for monitoring research activities. Reviewed FY 2010 Program Operating Plans (POPs). Produced draft versions of 5 State of the Science Fact Sheets. Briefed NOAA leadership on plan for determining the optimal balance of research and operations and their funding in NOAA. Continued work on Hurricane Intensity Research Working Group (HIRWG) and External Ecosystem Task Team (eETT) responses for Science Advisory Board (SAB). Finalized R&D PART planning for programs scheduled for review in FY 2009. Will begin implementing actions with Program Mangers to ensure that key elements of the PART, such as long-term, annual, and efficiency (outcome) performance measures, independent evaluations, and collaboration with partners are well established and documented. Planned actions for next quarter: Update the 5-Year Research Plan based on public comment and present to the NEP/NEC for final approval. Brief NOAA CFO on future database requirements for monitoring research. Request NEC approval for corporate concept of monitoring research and appointing a Monitoring Research Committee. Strategic review of FY 2010 Strategic Portfolio Analyses. Produce final versions of 5 State of the Science Fact Sheets. Develop a follow-up statement regarding the balance and under-funding of R&D within NOAA for the NEP. Finish work on HIRWG and eETT responses for the SAB. Work with staff from the Ecosystems Research Program and Climate Program Office to develop specific milestones to ensure that key elements of the PART are well established and documented. ST&I Coordinator will act on five identified action items to prepare for mock PART scheduled for early FY08 (prepare ST&I 101 PowerPoint, review/update program charter, identify current sources of customer feedback, identify mechanism to initiate independent program review/evaluation, provide list of current performance measures). | In order to acquire a “Green” rating for Current Status, at least 75% of the R&D Programs that have been assessed by the R&D PART must be found to be “Moderately Effective” or better. NOAA has proposed a 5-year PART review schedule to OMB (pending approval). There are two R&D reviews (Weather & Water and Climate) in the plan, both of which will occur in 2009. |