## Total $s
Long Baseline Neutrinos + PDK Proposal $s (schedule 2)
Revised Proposal total
Original Proposal Budget (FY05 $s) |  |  |  | Revised Proposal Budget (FY07$s) |  |  |  |  | without discount
|  |  |  | Chamber R&D |  | 200000 | 200000 | New Item | 200000
Chambers |  | One Module | Three Modules | Chambers |  | One Module | Three Modules
Labor & benefits |  | 6060000 | 12030000 | Labor & benefits |  | 6423600 | 12751800 |  | 19270800 | no discount
Mining equipment operation |  | 1430000 | 4279000 | Mining equipment operation |  | 1515800 | 4535740 |  | 4547400 | no discount
Supplies |  | 4961000 | 14685000 | Supplies |  | 5258660 | 15566100 |  | 15775980 | no discount
Precast concrete liner |  | 3575000 | 10725000 | Precast concrete liner |  | 3789500 | 11368500 |  | 11368500
Outside contractor |  | 132000 | 396000 | Outside contractor |  | 139920 | 419760 |  | 419760
Plastic liner |  | 250000 | 750000 | Plastic liner |  | 265000 | 795000 |  | 795000
Rock removal |  | 1000000 | 3000000 | Rock removal |  | 1060000 | 3180000 |  | 3180000
Mining equipment |  | 5000000 | 5000000 | Mining equipment |  | 5300000 | 5300000 |  | 5300000
Contingency - 30% |  | 6722400 | 15259500 | Contingency - 30% |  | 7125744 | 16175070 |  | 18197232
Chamber construction-subtotal |  | 29130400 | 66124500 | Chamber construction-subtotal |  | 30878224 | 70091970 |  | 78854672
|  |  |  | PM R&D |  | 2100000 | 2100000 | New Item | 2100000
Photomultipliers |  |  |  | Photomultipliers
PM tube | 880 |  |  | PM tube | 932.8 |  |  |  | 139920000
PM installation | 165 |  |  | PM installation | 174.9 |  |  |  | 26235000
Readout electronics | 120 |  |  | Readout electronics | 127.2 |  |  |  | 19080000
Cables | 77 |  |  | Cables | 81.62 |  |  |  | 12243000
PM subtotal per tube | 1242 | 62100000 | 186300000 | PM subtotal per tube | 1316.52 | 65826000 | 197478000 |  | 197478000
|  |  |  | PM Testing |  |  |  | New Item
|  |  |  | Test Facility |  | 2000000 | 2000000 |  | 2000000
|  |  |  | Testing |  | 7500000 | 7500000 |  | 7500000 | see worksheet
|  |  |  | Calibration Equipment R&D |  | 42400 | 42400 | New Item | 42400
Other |  |  |  | Other
Calibration equipment | 400000 |  |  | Calibration equipment | 424000 |  |  |  | 424000
Development labor | 3000000 |  |  | Development labor | 3180000 |  |  |  | 3180000
Water purification | 4500000 |  |  | Water purification | 4770000 |  |  |  | 2250000 | new estimate
Other-subtotal | 7900000 | 7800000 | 7800000 | Other-subtotal | 8374000 | 8374000 | 8374000 |  | 5854000
Total - pm and other |  | 69900000 | 194100000 | Total - pm and other |  | 74200000 | 205852000 |  | 203332000
Contingency - 25% (pm & other) |  | 17475000 | 48525000 | Contingency - 25% (pm & other) |  | 18550000 | 51463000 |  | 50833000
Grand total |  | 116505400 | 308749500 | Grand total |  | 135470624 | 339249370 |  | 344862072

## Profile
Long Baseline Neutrinos + PDK Profile $s (3 Modules) (schedule 2)
| Total Project $s | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | Total
Chamber R&D (coring) | 200000 | 50000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 200000
Chambers
Labor & benefits | 19270800 | 0 | 401475 | 2007375 | 3613275 | 4817700 | 4416225 | 2810325 | 1204425 | 0 | 0 | 0 |  |  | 19270800
Mining equipment operation | 4547400 | 0 | 94737.5 | 473687.5 | 852637.5 | 1136850 | 1042112.5 | 663162.5 | 284212.5 | 0 | 0 | 0 |  |  | 4547400
Supplies | 15775980 | 0 | 328666.25 | 1643331.25 | 2957996.25 | 3943995 | 3615328.75 | 2300663.75 | 985998.75 | 0 | 0 | 0 |  |  | 15775980
Precast concrete liner | 11368500 | 0 | 236843.75 | 1184218.75 | 2131593.75 | 2842125 | 2605281.25 | 1657906.25 | 710531.25 | 0 | 0 | 0 |  |  | 11368500
Outside contractor | 419760 | 0 | 8745 | 43725 | 78705 | 104940 | 96195 | 61215 | 26235 | 0 | 0 | 0 |  |  | 419760
Plastic liner | 795000 | 0 | 16562.5 | 82812.5 | 149062.5 | 198750 | 182187.5 | 115937.5 | 49687.5 | 0 | 0 | 0 |  |  | 795000
Rock removal | 3180000 | 0 | 66250 | 331250 | 596250 | 795000 | 728750 | 463750 | 198750 | 0 | 0 | 0 |  |  | 3180000
Mining equipment | 5300000 | 0 | 5300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5300000
Contingency - 30% | 18197232 | 0 | 1935984 | 1729920 | 3113856 | 4151808 | 3805824 | 2421888 | 1037952 | 0 | 0 | 0 |  |  | 18197232
Chamber construction-subtotal | 78854672 | 0 | 8389264 | 7496320 | 13493376 | 17991168 | 16491904 | 10494848 | 4497792 | 0 | 0 | 0 |  |  | 78854672
PM R&D | 2100000 | 0 | 0 | 1050000 | 1050000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2100000
Photomultipliers
PM tube | 932.8 | 0 | 0 | 0 | 0 | 18656000 | 37312000 | 37312000 | 37312000 | 9328000 | 0 | 0 | 0 | 0 | 139920000
PM installation | 174.9 | 0 | 0 | 0 | 0 | 0 | 0 | 8016192 | 8745000 | 8745000 | 728808 | 0 | 0 | 0 | 26235000
Readout electronics | 127.2 | 0 | 0 | 0 | 0 | 2544000 | 5088000 | 5088000 | 5088000 | 1272000 | 0 | 0 | 0 | 0 | 19080000
Cables | 81.62 | 0 | 0 | 0 | 0 | 1632400 | 3264800 | 3264800 | 3264800 | 816200 | 0 | 0 | 0 | 0 | 12243000
PM subtotal per tube | 1316.52
PM subtotal (3 Modules) | 197478000 |  |  | 0 | 0 | 22832400 | 45664800 | 53680992 | 54409800 | 20161200 | 728808 | 0 | 0 | 0 | 197478000
PM Testing
Test Facility | 2000000 | 0 | 0 | 0 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2000000
Testing | 7500000 |  |  | 0 | 0 | 1000000 | 2000000 | 2000000 | 2000000 | 500000 | 0 | 0 | 0 | 0 | 7500000
Calibration Equipment R&D | 42400 | 0 | 0 | 0 | 0 | 42400 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 42400
Other
Calibration equipment | 424000 | 0 | 0 | 0 | 0 | 0 | 212000 | 212000 | 0 | 0 |  | 0 |  |  | 424000
Development labor | 3180000 | 0 | 1590000 | 1590000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3180000
Water purification | 4770000 | 0 | 0 | 0 | 0 | 0 | 2250000 | 0 | 0 | 0 |  |  |  |  | 2250000
Other-subtotal | 8374000 | 0 | 1590000 | 1590000 | 0 | 0 | 2462000 | 212000 | 0 | 0 | 0 | 0 | 0 |  | 5854000
Total - pm and other | 205852000 | 0 | 1590000 | 1590000 | 0 | 22832400 | 48126800 | 53892992 | 54409800 | 20161200 | 728808 | 0 | 0 | 0 | 203332000
Contingency - 25% (pm & other) | 51463000 | 0 | 397500 | 397500 | 0 | 5708100 | 12031700 | 13473248 | 13602450 | 5040300 | 182202 | 0 | 0 | 0 | 50833000
Grand total (FY07$s) | 348012072 | 1100000 | 11576764 | 9483820 | 15493376 | 47574068 | 78650404 | 79861088 | 74510042 | 25701500 | 911010 | 0 | 0 | 0 | 344862072
escalation rates |  | 1 | 1.026 | 1.0527 | 1.08 | 1.1081 | 1.1369 | 1.1665 | 1.1968 | 1.2279 | 1.2599 | 1.2926 | 1.3262 | 1.3607
Grand total (AY$s) |  | 1100000 | 11877759.864 | 9983617.314 | 16732846.08 | 52716824.7508 | 89417644.3076 | 93157959.152 | 89173618.2656 | 31558871.85 | 1147781.499 | 0 | 0 | 0 | 396866923.083

## Chamber Costs breakout
Chamber Construction (schedule 2)
Chamber 1 |  | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | Total
Labor & benefits | 6423600 | 0 | 401475 | 1605900 | 1605900 | 1605900 | 1204425 | 0 | 0 | 0 | 0 | 0 | 6423600
Mining equipment operation | 1515800 | 0 | 94737.5 | 378950 | 378950 | 378950 | 284212.5 | 0 | 0 | 0 | 0 | 0 | 1515800
Supplies | 5258660 | 0 | 328666.25 | 1314665 | 1314665 | 1314665 | 985998.75 | 0 | 0 | 0 | 0 | 0 | 5258660
Precast concrete liner | 3789500 | 0 | 236843.75 | 947375 | 947375 | 947375 | 710531.25 | 0 | 0 | 0 | 0 | 0 | 3789500
Outside contractor | 139920 | 0 | 8745 | 34980 | 34980 | 34980 | 26235 | 0 | 0 | 0 | 0 | 0 | 139920
Plastic liner | 265000 | 0 | 16562.5 | 66250 | 66250 | 66250 | 49687.5 | 0 | 0 | 0 | 0 | 0 | 265000
Rock removal | 1060000 | 0 | 66250 | 265000 | 265000 | 265000 | 198750 | 0 | 0 | 0 | 0 | 0 | 1060000
Mining equipment | 5300000 | 0 | 5300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5300000
Chamber 2 |  | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | Total
Labor & benefits | 6423600 | 0 | 0 | 401475 | 1605900 | 1605900 | 1605900 | 1204425 | 0 | 0 | 0 | 0 | 6423600
Mining equipment operation | 1515800 | 0 | 0 | 94737.5 | 378950 | 378950 | 378950 | 284212.5 | 0 | 0 | 0 | 0 | 1515800
Supplies | 5258660 | 0 | 0 | 328666.25 | 1314665 | 1314665 | 1314665 | 985998.75 | 0 | 0 | 0 | 0 | 5258660
Precast concrete liner | 3789500 | 0 | 0 | 236843.75 | 947375 | 947375 | 947375 | 710531.25 | 0 | 0 | 0 | 0 | 3789500
Outside contractor | 139920 | 0 | 0 | 8745 | 34980 | 34980 | 34980 | 26235 | 0 | 0 | 0 | 0 | 139920
Plastic liner | 265000 | 0 | 0 | 16562.5 | 66250 | 66250 | 66250 | 49687.5 | 0 | 0 | 0 | 0 | 265000
Rock removal | 1060000 | 0 | 0 | 66250 | 265000 | 265000 | 265000 | 198750 | 0 | 0 | 0 | 0 | 1060000
Mining equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Chamber 3 |  | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | Total
Labor & benefits | 6423600 | 0 | 0 | 0 | 401475 | 1605900 | 1605900 | 1605900 | 1204425 | 0 | 0 | 0 | 6423600
Mining equipment operation | 1515800 | 0 | 0 | 0 | 94737.5 | 378950 | 378950 | 378950 | 284212.5 | 0 | 0 | 0 | 1515800
Supplies | 5258660 | 0 | 0 | 0 | 328666.25 | 1314665 | 1314665 | 1314665 | 985998.75 | 0 | 0 | 0 | 5258660
Precast concrete liner | 3789500 | 0 | 0 | 0 | 236843.75 | 947375 | 947375 | 947375 | 710531.25 | 0 | 0 | 0 | 3789500
Outside contractor | 139920 | 0 | 0 | 0 | 8745 | 34980 | 34980 | 34980 | 26235 | 0 | 0 | 0 | 139920
Plastic liner | 265000 | 0 | 0 | 0 | 16562.5 | 66250 | 66250 | 66250 | 49687.5 | 0 | 0 | 0 | 265000
Rock removal | 1060000 | 0 | 0 | 0 | 66250 | 265000 | 265000 | 265000 | 198750 | 0 | 0 | 0 | 1060000
Mining equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 modules total |  | FY07 | FY08 | FY09 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | Total
Labor & benefits | 19270800 | 0 | 401475 | 2007375 | 3613275 | 4817700 | 4416225 | 2810325 | 1204425 | 0 | 0 | 0 | 19270800
Mining equipment operation | 4547400 | 0 | 94737.5 | 473687.5 | 852637.5 | 1136850 | 1042112.5 | 663162.5 | 284212.5 | 0 | 0 | 0 | 4547400
Supplies | 15775980 | 0 | 328666.25 | 1643331.25 | 2957996.25 | 3943995 | 3615328.75 | 2300663.75 | 985998.75 | 0 | 0 | 0 | 15775980
Precast concrete liner | 11368500 | 0 | 236843.75 | 1184218.75 | 2131593.75 | 2842125 | 2605281.25 | 1657906.25 | 710531.25 | 0 | 0 | 0 | 11368500
Outside contractor | 419760 | 0 | 8745 | 43725 | 78705 | 104940 | 96195 | 61215 | 26235 | 0 | 0 | 0 | 419760
Plastic liner | 795000 | 0 | 16562.5 | 82812.5 | 149062.5 | 198750 | 182187.5 | 115937.5 | 49687.5 | 0 | 0 | 0 | 795000
Rock removal | 3180000 | 0 | 66250 | 331250 | 596250 | 795000 | 728750 | 463750 | 198750 | 0 | 0 | 0 | 3180000
Mining equipment | 5300000 | 0 | 5300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5300000
Total | 60657440 | 0 | 6453280 | 5766400 | 10379520 | 13839360 | 12686080 | 8072960 | 3459840 | 0 | 0 | 0 | 60657440
Contingency |  |  | 1935984 | 1729920 | 3113856 | 4151808 | 3805824 | 2421888 | 1037952 | 0 | 0 | 0 | 18197232
Grand Total |  |  | 8389264 | 7496320 | 13493376 | 17991168 | 16491904 | 10494848 | 4497792 | 0 | 0 | 0 | 78854672

## testing PMs
Testing of PMs (based on schedule 2)
| FY10 |  |  |  | FY11 |  |  |  | FY12 |  |  |  | FY13 |  |  |  | FY14 |  |  |  | FY15 |  |  |  | FY16
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
PMs
Vendor 1
FY Quantity |  |  |  |  | 10000 |  |  |  | 20000 |  |  |  | 20000 |  |  |  | 20000 |  |  |  | 5000
Vendor 2
FY Quantity |  |  |  |  | 10000 |  |  |  | 20000 |  |  |  | 20000 |  |  |  | 20000 |  |  |  | 5000
PM Testing
Test Facility
PM Testing
FY Quantity |  |  |  |  | 20000 |  |  |  | 40000 |  |  |  | 40000 |  |  |  | 40000 |  |  |  | 10000
tech's needed |  |  |  |  | 8 |  |  |  | 16 |  |  |  | 16 |  |  |  | 16 |  |  |  | 4
FY labor cost |  |  |  |  | 1000000 |  |  |  | 2000000 |  |  |  | 2000000 |  |  |  | 2000000 |  |  |  | 500000
CUM cost | [20 empty] | 7500000

## Installation Cost breakout
Installation schedule and costs (schedule 2)
| FY2013 | [10 empty] | FY2014
| nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct
Module 1 | [12 empty] | total
quantity per month | 4166 | 4166 | 4166 | 4166 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 50000
cost per month | 728633.4 | 728633.4 | 728633.4 | 728633.4 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 8745000
cost per FY | FY2013 nov: 8016191.7; FY2014 oct: 728808.3 | 8745000
| FY2014 | [10 empty] | FY2015
| nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct
Module 2 | [12 empty] | total
quantity per month | 4166 | 4166 | 4166 | 4166 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 50000
cost per month | 728633.4 | 728633.4 | 728633.4 | 728633.4 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 8745000
cost per FY | FY2014 nov: 8016191.7; FY2015 oct: 728808.3 | 8745000
| FY2015 | [10 empty] | FY2016
| nov | dec | jan | feb | mar | apr | may | jun | jul | aug | sep | oct
Module 3 | [12 empty] | total
quantity per month | 4166 | 4166 | 4166 | 4166 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 4167 | 50000
cost per month | 728633.4 | 728633.4 | 728633.4 | 728633.4 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 728808.3 | 8745000
cost per FY | FY2015 nov: 8016191.7; FY2016 oct: 728808.3 | 8745000
Grand Total Cost | [12 empty] | 26235000